## Slide 1
Migration Planning Activities

## Slide 2
Overall CalSAWS Planning Strategy Adjustments
  CalWIN/CalSAWS 58-County Requirements Planning: User Labs and Facilitated Requirements Gathering Sessions
  CalWIN Ancillary Systems Inventory and Analysis
  CalWIN Business Process Gap Analysis
CalSAWS Planning Strategy Adjustments
Original Scope
Workflow 1
  Continue Migration Planning and Joint Development Activities
Workflow 2
  Conduct CalACES Alternatives Analysis and Cost Benefit Analysis
Workflow 3
  Conduct CalSAWS Planning and Analysis
  CalWIN/CalSAWS Requirements Analysis 
  CalWIN Ancillary Systems Inventory & Analysis 
  CalWIN/CalSAWS Data Conversion Strategy 
  CalWIN Initial Data Mapping 
Revised Scope
Workflow 1
  Continue Migration Planning and Joint Development Activities
Workflow 2
  Conduct CalACES-CalSAWS Alternatives Analysis and Cost Benefit Analysis
Workflow 3
  Conduct CalSAWS Business Process Gap Analysis/Change Management

## Slide 3
CalSAWS Requirements Planning: Phase 0
Conduct Detailed Requirements Planning
  When: February 1 - March 7 (5 weeks)
  Participants: CalWIN and CalACES Existing Project Staff
  Tasks:
    Plan user labs and requirements sessions
    Document guiding principles and escalation process
    Identify skill-sets and secure resources
    Determine travel budget for county staff for PAPD Update
    Assist with communication processes with counties
  Output
    Work Plan/schedule
    Staff Loading Plan
    Travel Budget
    PAPD Update
    CRFI for CalWIN county recruitment

## Slide 4
CalSAWS Requirements Planning: Phase 1
Internal Initial Review of Existing System Requirements
  When: February 15 – March 16
  Participants: CalWIN and CalACES Existing Project Staff
  Task: Review existing 560 system requirements
  Output
    Confirm CalWIN impact on the existing requirements
    Determine requirements that have no CalWIN impact
    Determine requirements where specific CalWIN requirements will be needed (i.e. Conversion)

## Slide 5
CalACES Requirements Summary
Requirement Category | # of Requirements
Analytics | 1
Batch & Interface | 11
Call Center | 5
Central Print | 1
Change Management | 4
Conversion | 16
Correspondence | 69
Training Delivery | 11
Training Development | 76
Utilities/Journal/Resources | 6
Subtotal | 200
560 CalACES requirements resulted from the C-IV/LRS Side-by-Side process.
Note that some requirements correspond to the core application, others correspond to CalWIN ancillary systems

## Slide 6
CalACES Requirements Summary
Requirement Category | # of Requirements
Data Collection and Eligibility | 116
All Programs | 19
Application Registration | 7
Cal-Learn | 1
Change Reason | 3
Child Care | 1
CMSP | 1
File Clearance | 1
Financial Root Questions/Non-Financial Root Questions | 2
General Assistance/General Relief (GA/GR) | 5
General Requirements | 1
Home Page | 3
Homeless Assistance | 1
Inter-County Transfer (ICT) | 8
Medi-Cal/CalHEERS | 19
Non-compliance | 2
Periodic Reporting | 3
Renewals (CW, CF, MC) | 4
Supervisor Authorization - EDBC | 7
Time Limits | 7
Verifications | 3
Welfare To Work | 17
WINS | 1
Subtotal | 116

## Slide 7
CalACES Requirements Summary
Requirement Category | # of Requirements
* Enterprise Infrastructure | 1
* Equipment and Software | 19
Fiscal | 42
General Requirements | 8
Help Desk | 2
Imaging | 1
Implementation | 9
Lobby Management | 8
Manage Personnel | 31
Operations | 1
Project Management | 22
RDB | 5
Reports | 14
Site Preparation and Installation | 3
Special Investigations Units | 50
System Development | 3
Task Management | 9
Testing | 16
Subtotal | 244
Note that some requirements (*) will be impacted by the cloud strategy

## Slide 8
CalSAWS User Labs
  When: April 2 – May 11 (6 weeks)
  Participants: CalWIN County Staff, CalWIN Project Staff, LRS Project Staff, C-IV Project Staff, Migration Planning Staff
    Best and brightest County SMEs who understand CalWIN
    Recruiting Process: CalWIN CRFI
    Travel costs will be covered (but not staff time)
  Task: Understand and become familiar with LRS target system and 560 CalACES requirements to enable informed participation in subsequent requirements gathering sessions
  Sessions:
    20 participants per session, Monday - Thursday
    Concurrent sessions in North and South locations
    Participants will attend 1 or more weekly sessions
    Day 1 Sample Agenda follows
CalSAWS Requirements Planning: Phase 2

## Slide 9
CalSAWS User Labs: Day 1 Sample Agenda
  Welcome/Introduction
  Orientation PPT
    Overall CalSAWS plan/high level roadmap and schedule
    Message from Leadership Team
    Existing CalACES Requirements and how/where to find them
    Guiding Principles
    Goals for User Labs
    Next Steps
  Web-based Training (WBT)
    Basic Navigation
    Specific to User Lab, such as Medi-Cal Processing
    Will be provided to counties in advance to allow in-county preparation
  Group walk through of functionality
  Opportunities to use/test system with scenarios/test scripts
    Continues throughout the week
  Daily Debrief
    Goal: Q&A, potential requirements, additional case scenarios
CalSAWS Requirements Planning: Phase 2

## Slide 10
CalSAWS User Labs (Continued)
  Support for Participants:
    Faciliator: Welcome, orientation, Director’s message, CalSAWS Roadmap/Schedule (where we are and where we’re going), managing the daily debrief, consolidating feedback for requirements gathering sessions
    Roamers: LRS and CIV SMEs will provide instant help, navigation assistance, context for application organization, how various counties use the system
    Scribe: take notes/feedback and lessons learned, assist facilitator
    Tech Support: available to immediately address environment/access issues
  Environment:
    Active LRS test environment with pre-loaded data/test cases/scenarios
    Will allow for creation of new cases and manipulation of existing cases
    Batch support and time advancement available
  Outputs:
    Users will review and use the system
    Users will identify potential gaps and project staff will document the gaps
    The gaps will be reviewed in Phase 3, Requirements Gathering Sessions
CalSAWS Requirements Planning: Phase 2

## Slide 11
CalSAWS User Lab Proposed Weekly Schedule
  Week 1 – Eligibility, CalWORKs, CalFresh, ICT, eAPPs, CalHEERS
  Week 2 – Eligibility, Medi-Cal, CalFresh, CMSP, ICT, eAPPs, CalHEERS
  Week 3 – Welfare-to-Work, Child Care
  Week 4 – Miscellaneous (Security)
  Week 5 – Fiscal
  Week 6 – Foster Care, AAP, Kin-GAP, ARC
  Participants will attend 1 or more weekly sessions
CalSAWS Requirements Planning: Phase 2

## Slide 12
Guided Requirements Gathering Sessions
  When: May 14 – June 22 (6 weeks)
  Sessions scheduled by specific topic area
    Each topic expected to be no more than 1 week
    Number of sessions to be determined
  Participants: 58 County Representation, CalWIN Project Staff, LRS Project Staff, C-IV Project Staff, Migration Planning Staff
    County Staff should be able to make decisions for the counties they represent and ideally will have participated in the user lab sessions
    Recruiting Process: CalWIN CRFI
    Travel costs will be covered (but not staff time)
    Each participant would be expected to attend 1 or more sessions
  Output: Updated statement of requirements to be presented to the stakeholders
CalSAWS Requirements Planning: Phase 3

## Slide 13
Analyze CalWIN County Business Processes
  When: April 2 – June 29 (13 weeks) or Later
  Participants: CalWIN Counties, CalWIN Project Staff, Vendor TBD
  Output:
    Updated requirements to address business process gaps
CaWIN Business Process Gap Analysis

## Slide 14
Analyze CalWIN Ancillary Systems/External Tools
  When: April 2 – June 29 (13 weeks) or Later
  Participants: CalWIN Counties, CalWIN Project Staff, Vendor TBD
  Output:
    Updated requirements with Ancillary Systems/External Tool Results
CaWIN Ancillary Systems/External Tools Analysis