## Timeline
Project Timeline* - Key Policy Items (Critical, High or Volume Impact) *All items are targeted until approved by the SCRB/CCB process, and, therefore subject to change. |  |  | 2018-03-24 | 2018-04-01 | 2018-05-19 |  | 2018-06-03 |  | 2018-07-21 | TBD | 2017-09-03 |  | TBD
Request Control# | Program/Topic | Description | Release | Priority | Release | Priority | Release | Priority | Release | Priority | Release* | Priority | Release* | Priority | Release | Priority | Release | Priority | Release | Priority | Release | Priority | Release | Priority | Release | Priority | Release | Priority | Release | Priority | Release | Priority | Release
|  |  | 18.03 |  | 18.05 |  | 18.06 |  | 18.07 |  | 18.09 |  | 18.11
| YBN | Your Benefits Now (YBN) Change to reduce the EBT History from 90 days to 30 days. |  | 201716
| CalFresh | ACL 07-16 - Additional Zip Codes and Back-up Staff updates for an Active Local Educational Agency (LEA) in Direct Certification Program - EL SEGUNDO USD |  | 56049
| CalFresh | ACL 07-16 - Additional Zip Codes and Back-up Staff updates for an Active Local Educational Agency (LEA) in Direct Certification Program - Executive Preparatory Academy of Finance |  | 56051
| CalFresh | ACL 07-16 - Direct Certification Program (DC) for an New Local Educational Agency (LEA) - The Palmdale Aerospace Academy |  | 55586
| CalFresh | ACL 07-16 Addition of Zip Codes and Change of Staff update for an Active LEA in Direct Certification (DC) Program - Covina Valley Unified School District |  | 55688
| CalFresh | ACL 07-16 DIRECT CERTIFICATION (DC) FOR A NEW LOCAL EDUCATIONAL AGENCY (LEA) KEPPEL SCHOOL DISTRICT |  | 56208
| CalFresh | ACL 07-16 Direct Certification (DC) for a New Local Education Agency (LEA) Alliance College - Ready Public Schools |  | 58592
| CalFresh | ACL 07-16 Direct Certification (DC) for a new local Educational Agency (LEA) David and Margaret Home, Inc - Joan Macy School |  | 58315
| CalFresh | ACL 07-16 Update of School Provide Zip Codes and Change in the Direct Cert Staff for an Active Local Educational Agency (LEA) - East Whittier City School District |  | 58775
| Medi-Cal/MSP/CMSP | Direct Certification - Hillside Education center |  | 201750
| Medi-Cal/MSP/CMSP | Direct Certification - Long Beach Unified School district |  | 201751
| Medi-Cal/MSP/CMSP | Direct Certification - University Value High School |  | 201749
| N/A | Load file from DHCS to populate MBI number for existing applicants |  | 201555
| N/A | Scheduled DR Test Validation and Implementation |  | 201121
| Welfare-to-Work/Gain | < ITGC > ACL 13-59 - Workshare Form - Implement WTW 38 (6/13) in All Threshold Languages to LRS |  |  | 52395
| CalFresh | < ITGC > ACL 15-84 - Remove option from the Negative Action Detail Page - Didn't Sign SOF Drop-Down |  |  | 50556
| CalWORKs | < ITGC > ACL 17-58 - SB 1339: Automate the M40-195A and M40-195B Notices |  |  | 50794
| N/A | < ITGC > BI - BAR Reports - County Workshare |  |  | 52210
| Other | < ITGC > DHCS Renewal Master Request (RMR) Report Update V 2.3 |  |  | 54312
| Medi-Cal/MSP/CMSP | < ITGC > Inter-County Transfer (SB 1339) |  |  | 50461
| General Relief | < ITGC > MSUDRP Assessment Page Changes |  |  | 48356
| AAP, Foster Care, Kin-GAP, Medi-Cal/MSP/CMSP | < ITGC > Modify Manage Personnel logic to assign DCFS Medi-Cal cases appropriately (pre-paid placement & auto-test) |  |  | 51718
| Welfare-to-Work/Gain | < ITGC > Phase II - ACL 15-62 changes: Implement Workshare Static forms: WTW 26 and WTW 31 in all threshold languages. This is a split of SCR 50801. |  |  | 55130
| Fiscal | < ITGC > Update Auditor Controller files and Reports |  |  | 52214
| REP, Welfare-to-Work/Gain | < ITGC > WTW 24 MTC - Time Limit Extension Requests |  |  | 53782
| General Relief | <GR Premise> 12 ADA-related General Relief Forms Request to add GR Notices and Forms |  |  | 56756
| General Relief, GROW | <GR Premise> General Relief - End Date the Employable/Unemployable Status on the Work Registration Page After GR Denial/Termination - Add new EDBC batch to when GR Health Assessment is updated & create GROW Program when pt. Employable |  |  | 49018
| General Relief | <GR Premise> General Relief Needs Special Assistance Status Expiration reminder Text/Email |  |  | 51447
| General Relief | <GR Premise> Homeless Transition Age Youth and Disabled General Relief Population with New Invoice- upload the revised ABP 295 meals/lodging order and invoice to LRS |  |  | 47582
| General Relief | <GR Premise> L.A. County General Relief forms Phase III - Automate forms: ABP 23 (ABP 23-AU, ABP 23C-AU, ABP 23E-AU, and ABP 23B) and Add threshold language for the ABP 23 forms series |  |  | 56863
| General Relief | <GR Premise> Modify the Start Date logic for LAC General Relief Housing Subsidy on Money Management pages and Vendor recoupment changes for GR EDBC |  |  | 51959
| General Relief | <GR Premise> Report to Capture the Number of General Relief Willful Sanctions Imposed By Category |  |  | 54710
| Other | <R&A> Add Extract Capability to Eligibility Workload Inventory and Monthly Productivity Pages in LRS (based on C-IV SCR 7271) |  |  | 54524
| N/A | <R&A> Add New ADA Journal type - Special Circumstance. |  |  | 56221
| CalFresh | <R&A> CFL 15/16-64 - AB 2035 EBT Benefit Replacement due to Electronic Theft Update - SUAS |  |  | 50781
| CalLearn | <R&A> Cal-Learn Program - Add Zip Codes to Table |  |  | 53794
| WFP | <R&A> Modify LRS WFP&I Investigation Result Detail page to remove mandatory restriction on the Case Action field |  |  | 48753
| CAPI, General Relief | <R&A> Modify the IAR Detail page with a Generate Forms command button |  |  | 54015
| N/A | <R&A> Update DPSS ePolicy link at the LRS production Resources List Page with the new URL |  |  | 55695
| YBN | <R&A> YBN - Offline Mode Enhancement |  |  | 58162
| YBN | <R&A> YBN Security Assessment Findings - Group 3 (Password auto-complete is enabled, Insecure cookie attribute, Vulnerable to clickjacking & Missing Sub Resource Integrity support) |  |  | 58161
| YBN | <R&A> Your Benefits Now (YBN) to generate a pop-up or banner to alert participants when their Renewal, Recertification (RC), Redetermination (RD), Annual Agreement (AA), Quarterly Report (QR) 7 is due. |  |  | 55210
| CalFresh, CalWORKs | ACL XX-XX - Cost of Living Adjustment (COLA) for Minimum Basic Standard of Adequate Care (MBSAC) 2018-2019 |  |  | 54427
| Foster Care | ARC/FC Payments to Caretaker Prior to Home Approval |  |  | 201268
| CalLearn, REP, Welfare-to-Work/Gain | Adding the WTW Organization Level to All Existing Dashboards, Add Region and Region Group column in all Welfare-to-Work/REP/Cal-Learn BI Data Warehouse reports |  |  | 51697
| N/A | CalWIN Demo Support |  |  | 201019
| Medi-Cal/MSP/CMSP | DDCR 5072: < ITGC > MEDS Change Cycle Letter 390 - M3600 - MOVE PREGNANCY RELATED AID CODES and PREMIUM PAYMENT AID CODES TO SPECIAL SEGMENT |  |  | 49835
| N/A | LRS Production Operations support/coordination with Conduent (EBT) |  |  | 201220
| Medi-Cal/MSP/CMSP | Medi-Cal - Addition of Aid Codes 2H (FPL Blind), 6H (A&D FPL Disabled) and 6U (A & D FPL - Restricted) to the Non-MAGI Age 65 Batch Job |  |  | 200249
| CalWorks, CalFresh | No Cost SCR: CW/CF incorrectly passed for application month while the household status begin month was in later month |  |  | 201675
| CalFresh, CalWORKs, General Relief | Phase VII - Turn ON - Threshold Language NOAs - English versions are already in production |  |  | 200774
| General Relief | Run Batch EDBC for GR Active cases with a Money Management Record |  |  | 201880
| CalFresh, CalWORKs, General Relief, Medi-Cal/MSP/CMSP | SAR 7/QR 7-LA in all threshold languages on YBN |  |  | 57646
| CalWORKs, General Relief, RCA/RAM | SB 89 SFIS Repeal for CalWORKs/RCA and General Relief (GR) Programs |  |  | 200405
| N/A | ServiceNow - Tier 2 Reports and Transition to ServiceNow |  |  | 201073
| Training | Training Release 18.05 - LMS (County Materials) updates |  |  | 201978
| Training | Training Release 18.05 - Online Help (OLH) updates |  |  | 201242
| Training | Training Updates - ACL 15-84 - Remove option from the Negative Action Detail Page - Didn't Sign SOF Drop-Down (WBTs) |  |  | 201241
| Training | Training Updates - Add Admin U Reasons (WBTs) |  |  | 201175
| Training | Training Updates - Add Online functionality to group all GAIN Offices into GAIN Region Groups (WBTs) |  |  | 201205
| Training | Training Updates - Add Online functionality to group all GAIN Offices into GAIN Region Groups (JAs) |  |  | 201203
| Training | Training Updates - Appointment Schedule - Block Holidays, set daily threshold for RD appointments .... (WBTs) |  |  | 201179
| Training | Training Updates - CalFresh Application Processing Delay Reason with Manual EDBC (WBTs) |  |  | 201188
| Training | Training Updates - CalHEERS - Immigration Status Changes (WBTs) |  |  | 200351
| Training | Training Updates - DCFS: Add columns to the Foster Care License List page including License Type and License Number (WBTs) |  |  | 201199
| Training | Training Updates - DCFS: Add “Child/NMD is deceased” Placement End Reasons (WBTs) |  |  | 201172
| Training | Training Updates - Enhancement to Reports Search Page & Global Navigation Menu in LRS Application (WBTs) |  |  | 201186
| Training | Training Updates - Homeless Transition Age Youth and Disabled General Relief Population with New Invoice- upload the revised ABP 295 meals/lodging order and invoice to LRS (JAs) |  |  | 201239
| Training | Training Updates - Inter-County Transfer (SB 1339) (JAs) |  |  | 201232
| Training | Training Updates - Mandatory Substance Use Disorder Recovery Program (MSUDRP) Assessment Page Changes (JA) |  |  | 201233
| Training | Training Updates - Modification to Child Care Authorizations page (WBTs) |  |  | 200308
| Training | Training Updates - Modify CalHEERS Online Single Streamlined Application (WBTs) |  |  | 200350
| Training | Training Updates - Modify Manage Personnel logic to assign DCFS Medi-Cal cases appropriately (pre-paid placement & auto-test) (JAs) |  |  | 201229
| Training | Training Updates - Modify the Start Date logic for LAC General Relief Housing Subsidy on Money Management pages and Vendor recoupment changes for GR EDBC (JAs) |  |  | 201228
| Training | Training Updates - New Medicare Beneficiary Identifier (MBI) from Centers for Medicare & Medicaid Services (CMS) April 1, 2018 Go Live (WBTs) |  |  | 201737
| Training | Training Updates - SOCIAL SECURITY DENIAL DETAIL TAB ON STATE ABD 217 REPORT (WBTs) |  |  | 201190
| Training | Training Updates - Special Investigations - Add fields to Special Investigation pages (WBTs) |  |  | 201173
| Training | Training Updates - Training (DPSS) Updates - Master Assignment Queue (MAQ) Prioritization (WBTs) |  |  | 201181
| Training | Training Updates - WTW 24 MTC - item 5 - Time Limit Extension Requests (JAs) |  |  | 201227
| Training | Training Updates - “ACL 15-70 (AB 1930 – Educational Programs” (Student Eligibility as part of CalFresh E&T Program) ADDENDUM (WBTs) |  |  | 201174
| Medi-Cal/MSP/CMSP | Update Batch Trigger for MATURES 1 & 2 Form |  |  | 200910
| N/A | Update ICT Addresses for Contra Costa, Los Angeles, Riverside, Santa Barbara, and Yolo Counties |  |  | 55690
| N/A | Update Page Mapping Process |  |  | 201059
| Medi-Cal/MSP/CMSP | YBN Online Medi-Cal Renewal Process MC210RV/MC216 in threshold language except Eng/Span - Phase III |  |  | 54011
| Medi-Cal/MSP/CMSP | ACWDL 14-29 - Medi-Cal : Update rules to not allow CEC for persons failing MAGI due to Non-Payment of Premium |  |  |  |  | 55842
| Medi-Cal/MSP/CMSP | ACWDL 17-22: Update LRS with the 2017-2018 Family Member Base Allocation (FMBA) amount. |  |  |  |  | 55686
| Medi-Cal/MSP/CMSP | ACWDL 18-01 : Add Eligibility Evaluation Reasons from CalHEERS to Trigger MAGI Denial/Discontinuance Notices |  |  |  |  | 55295
| N/A | Build Cross Project Automated Scripts (CalHEERS) |  |  |  |  | 201060
|  | DDCR 3034, 3036: ACWDL 17-28 and 17-29: Inmate MC Aid Codes |  |  |  |  | 58841
| CalFresh, CalWORKs, CAPI, General Relief | Phase VIII - Information Only Request - Turn ON - Threshold Language NOAs - English versions are already in production |  |  |  |  | 200776
| N/A | Port SAWS-Initiated Automated Scripts (CalHEERS) |  |  |  |  | 201070
|  | Migrate Batch Scheduler from Control-M to BICSuite | [5 empty] | 59168
| CalFresh, CalLearn, CalWORKs, CAPI, General Relief, GROW, RCA/RAM, REP, Welfare-to-Work/Gain | Modify LRS to support new Vendor FIS Fidelity Information Services, LLC | [5 empty] | 59270
| REP, Welfare-to-Work/Gain | < ITGC > ACL 14-59 - Revision of GN6006B form (version 03/23/2015) | [6 empty] | 50296
| REP, Welfare-to-Work/Gain | < ITGC > ACL 14-65 - Automation of form WTW43 - 24 month time clock ending soon, all threshold languages- Update LRS to apply Welfare to Work exemptions | [6 empty] | 52406
| N/A | < ITGC > ACL 14-88 - Revise/Create 17 NOAs Messages for Deny, Discontinue, Change, and Partial Approval for Lack of Verification | [6 empty] | 50949
| CAPI, General Relief | < ITGC > ACL 99-11 Treatment of GR Interim Assistance Payment as a Recoupment Against CAPI Benefits | [6 empty] | 52413
| CalWORKs, Homeless Perm, Homeless Temp | < ITGC > ACLs 16-98 and 16-98E - Threshold language for the CalWORKs Homeless Assistance NOAs | [6 empty] | 50686
| CalFresh | < ITGC > CF 387 CalFresh Request for Information for Residency | [6 empty] | 49633
| Foster Care, Kin-GAP | < ITGC > DCFS: 2018 COLA | [6 empty] | 56670
| CalFresh | < ITGC > Phase II - ACL 17-34 - Add ESAP Indicator and Automate CF 377.2D | [6 empty] | 54952
| CalLearn, REP, Welfare-to-Work/Gain | < ITGC > Workshare WTW Forms -Update New Version of NA 822 (07/16), GN 6010.9B (07/17) and GN 6369 (07/17) in all Threshold Languages to LRS | [6 empty] | 49626
| CalFresh, CalWORKs, General Relief, Medi-Cal/MSP/CMSP | <ITGC> CSC LAGAN Tickets to create CSC Tasks by program to the correct worker ID | [6 empty] | 53793
| CalFresh | <R&A> ACL 17-05 - Expanded student eligibility criteria under CalFresh - AB 1930 | [6 empty] | 51457
| N/A | <R&A> Add to DPSS & SFV Mobile/Internal apps to allow document upload feature. | [6 empty] | 51489
| N/A | <R&A> Child Welfare Trust Changes | [6 empty] | 49832
| CalFresh, CalWORKs, General Relief, Medi-Cal/MSP/CMSP | <R&A> Customer Reporting Updates | [6 empty] | 52723
| N/A | <R&A> Enhancements to EBT Repayment Reports, Issuance Exception and Skipped Issuance Reports | [6 empty] | 48359
| General Relief | <R&A> Modify General Relief Work Registration Status of Employable/ Unemployable Tracking to Daily from Monthly | [6 empty] | 54711
| CalFresh | <R&A> YBN CF 37 in All Threshold Languages | [6 empty] | 201180
| CalWorks | ACL 03-20 - Count Income of Senior Parent not in CW Assistance Unit | [6 empty] | 56520
| CalFresh, CalWORKs, Medi-Cal/MSP/CMSP | ACL 17-58 - Electronic Inter-County Transfer (eICT) - Redetermination (RE) Date Alignment | [6 empty] | 49401
| Foster Care | Add Additional Foster Care Placement Types to the CA 237 FC Report | [6 empty] | 200718
| CalWORKs, RCA/RAM, REP, Welfare-to-Work/Gain | Changes in CW/RCA Adults by WTW Category (Global) Report | [6 empty] | 200371
| CalWORKs, RCA/RAM, REP, Welfare-to-Work/Gain | Changes in WTW/REP Activity Report (WAR) Report | [6 empty] | 200374
| Medi-Cal/MSP/CMSP | DDCR 3083: ACWDL 17-40: 2018 Medicare Catastrophic Coverage Act Spousal Impoverishment Caps - Community Spousal update | [6 empty] | 58593
| N/A | DDCR 4075: Update Exception Handling framework to log request details | [6 empty] | 200324
| N/A | DDCR 4084: Update online SQL query execution framework to log query details | [6 empty] | 200329
| N/A | Display Edit Button on Transaction Detail Page | [6 empty] | 201075
| CalFresh | Funding - <R&A> ACL 17-05 - Expanded student eligibility criteria under CalFresh - AB 1930 | [6 empty] | 201701
| N/A | Funding - <R&A> Add to DPSS & SFV Mobile/Internal apps to allow document upload feature. | [6 empty] | 201700
| N/A | Funding - <R&A> Child Welfare Trust Changes | [6 empty] | 201702
| CalFresh, CalWORKs, General Relief, Medi-Cal/MSP/CMSP | Funding - <R&A> Customer Reporting Updates | [6 empty] | 201699
| N/A | Funding - <R&A> Enhancements to EBT Repayment Reports, Issuance Exception and Skipped Issuance Reports | [6 empty] | 201703
| N/A | Funding - <R&A> Modify General Relief Work Registration Status of Employable/ Unemployable Tracking to Daily from Monthly | [6 empty] | 201698
| N/A | Funding - <R&A> YBN CF 37 in All Threshold Languages | [6 empty] | 201789
| N/A | Funding - Changes in CW/RCA Adults by WTW Category (Global) Report | [6 empty] | 201697
| N/A | Funding - Changes in WTW/REP Activity Report (WAR) Report | [6 empty] | 201687
| N/A | Implementation of C-IV SCR 12433 - Adding new a new security right for the Special Investigations Note page flow | [6 empty] | 59330
| N/A | Migrate Web Servers from OHS to Apache | [6 empty] | 200952
| CalWORKs | Remove Duplicate 'Mandatory/Optional Rules' Role Reasons for CalWORKs EDBC Override | [6 empty] | 201003
| N/A | Turn off default search execution for eApp search page | [6 empty] | 59010
| CalFresh | Update CalFresh School Attendance Employment Eligibility | [6 empty] | 200759
| Other | Updates to EBT Card Print List page and Reports | [6 empty] | 200738
| CalFresh | ACIN I-18-XX 2018 CalFresh COLA | [7 empty] | 56668
| CalWORKs | ACL XX-XXX - Update CalWORKs (CW) IRT Level 2018-2019 | [7 empty] | 56669
| N/A | BI Publisher upgrade | [7 empty] | 200909
| Welfare-to-Work/Gain | < ITGC > ACL 12-67 - Automation of the 319 – Meeting WPR WtW 24-Month Time Clock Stopper | [8 empty] | 53784
| CalFresh, CalWORKs, General Relief, GROW, Medi-Cal/MSP/CMSP, Welfare-to-Work/Gain | < ITGC > ACL 13-61 - YourBenefitsNow YBN and LEADER Replacement Systems LRS electronic notification and paperless option change and/ or Enhancements for NA1273, NA1274 & NA1275(e-NOTIFICATIONS). | [8 empty] | 49402
| CalWORKs, Welfare-to-Work/Gain | < ITGC > CalWORKs ACIN I-13-16 and ACL 16-90- Benefits for Deceased Child | [8 empty] | 47277
| AAP, Foster Care, Kin-GAP | < ITGC > DCFS: Modifications to the Work Order Detail and WorklList page are required to fully incorporate the functionality of the EW WORKS legacy system | [8 empty] | 51899
| N/A | <R&A> DPSS Mobile App, revise look and feel to align with the DPSS Communication Sections Design recommendation | [8 empty] | 53610
| CalWORKs, REP, Welfare-to-Work/Gain | ACIN I-01-07-Allow Exceptions to be Added for Tribal TANF and Out of State Months. | [8 empty] | 51485
| CalFresh | ACL 18-08: ABAWD Phase II - Design SCR | [8 empty] | 57971
| Foster Care | ACL 18-15 Last Date of Payment for Extended Foster Care | [8 empty] | 201036
| REP, Welfare-to-Work/Gain | ACL 18-38 - AB 480 (Gonzalez Fletcher) - Diapers | [8 empty] | 59192
| Medi-Cal/MSP/CMSP | ACWDL 18-XX :2018 Medicare Savings Program (MSP) Property Limits | [8 empty] | 200843
| N/A | ATS Security Assessment Findings - Group 1 | [8 empty] | 59074
| CalLearn, REP, Welfare-to-Work/Gain | Add Region and Region Group column in all Welfare-to-Work/REP/Cal-Learn detail reports (County Workshare) | [8 empty] | 52375
| N/A | Add Rescind reason of "Recertification Restoral" | [8 empty] | 200863
| CalFresh | Allow user to add ABAWD time limit month which already exists on the ABAWD Time Limit List page. | [8 empty] | 56917
| CalFresh, CalWORKs, CAPI, Foster Care, General Relief, Medi-Cal/MSP/CMSP, Refugee | Authorized Representative Information | [8 empty] | 47607
| Medi-Cal/MSP/CMSP | CalHEERS eHIT: Naturalized/Derived Citizenship updates (CH-109700) | [8 empty] | 200850
| Medi-Cal/MSP/CMSP | CalHEERS eHIT: SSA Title II Income and Disability Indicator Verifications (CH-92298) | [8 empty] | 201692
| CalHEERS | Creation of Master Test data for CalHEERS testing | [8 empty] | 201879
| Medi-Cal/MSP/CMSP | DDCR 3059: Add validation to prevent the same LRS person from being linked to multiple persons in a MAGI Referral | [8 empty] | 200630
| Medi-Cal/MSP/CMSP | DDCR 3104: Enhance Determination Response Handling - add Duplicate SSN validation | [8 empty] | 200636
|  | DDCR 3118: CalACES - Update Homeless Assistance Temporary (HT) and Homeless Assistance Permanent (HP) Benefits - Aid Code 35 to Count TANF Time Limit Clock | [8 empty] | 58824
| Medi-Cal/MSP/CMSP | DDCR 3135: Update Batch EDBC to skip cases when a person is closed on MC Program and the RE DER is MAGI Conditionally Eligible | [8 empty] | 200637
| CalWORKs, REP, Welfare-to-Work/Gain | DDCR 3161: CalACES - Add New Tribal TANF Provider "Tuolumne Band of Me-Wuk Indians" and additional new 6 Tribal TANF providers in LRS for CalACES | [8 empty] | 51484
| Medi-Cal/MSP/CMSP | DDCR 4022: Address same as Primary does not display on MAGI Person Detail page | [8 empty] | 200261
| Medi-Cal/MSP/CMSP | DDCR 4023: Validate unique MEDS Person Numbers for MAGI Request | [8 empty] | 200262
| Medi-Cal/MSP/CMSP | DDCR 4030: Remove the Age Requirement for the Caretaker Relative Field on Tax Household page | [8 empty] | 200266
| Medi-Cal/MSP/CMSP | DDCR 4034: MEDIL 13-03: Update MAGI Pending Eligible logic to treat retro months same as intake | [8 empty] | 200454
| N/A | DDCR 4047: ACL 17-125 - SB 570 VA Benefits Related to GI Bill | [8 empty] | 59263
| Medi-Cal/MSP/CMSP | DDCR 4049: Update Primary Applicant validations for MAGI Request | [8 empty] | 200274
| Medi-Cal/MSP/CMSP | DDCR 4061: Update system to save MAGI Determination to database for person without a Determination node | [8 empty] | 200280
| N/A | Documentation and transitioning of OID maintenance process from Tech Operations team to eGov team for YBN(CBO/FBO) and ATS user accounts | [8 empty] | 58022
| N/A | Enable field level auditing for Person Search, Journal, Tasks and Reminders | [8 empty] | 200949
| N/A | Enhance auditing framework to record old and new values of modified fields and user actions | [8 empty] | 200950
| N/A | Implement Work Managers to isolate EBT vendor issues impacting LRS application performance | [8 empty] | 200957
| N/A | Include additional Role Reason codes to be tracked by Time Limit Sanction job | [8 empty] | 201634
| N/A | Los Angeles County Auditor Controller file for Voucher Less Vendors | [8 empty] | 201082
| CalFresh | NO COST SCR - NOMI Denial batch shouldn't be denying the participant has attended the Intake Interview | [8 empty] | 56873
| CalFresh, CalWORKs, Medi-Cal/MSP/CMSP | Removal of Program-Specific Rescission Limits | [8 empty] | 52389
| N/A | Replace the PA 2012 (01/13) with Revised PA 2012 (07/15) Form and Add Referral Reason | [8 empty] | 49030
| CalWORKs | SB 380 - Remove Half-Sibling with Excessive Child Support from CW AU | [8 empty] | 200785
| N/A | Strategic Plan - Align active programs with the same primary applicant within the same district under a single Eligibility Worker | [8 empty] | 201379
| N/A | TTC Posted Collections on Recovery Account Transaction Date | [8 empty] | 201673
| N/A | Update Overpayment Adjustment Logic | [8 empty] | 200793
| N/A | Update Payment Request Detail page to have Payee Name link to Resource Detail page | [8 empty] | 200892
| N/A | Update the LRS Case Number Assignment | [8 empty] | 200861
| N/A | Update the Rescind Logic to accommodate for overlapping rescinded periods | [8 empty] | 200895
| YBN | YBN Security Assessment Findings - Group 2 (Improper error handling, Missing security headers & Missing HTTP strict-transport-security header) | [8 empty] | 58160
| YBN | YBN-Upgrade-Code Changes to Support WebLogic v12 and Java 8 | [8 empty] | 56603
| YBN | Your Benefits Now (YBN) Congratulations Page – Register To Vote section Update the Voter Hotline Number for Threshold Languages | [8 empty] | 201740
| CalWORKs, Refugee, Welfare-to-Work/Gain | [ITGC] ACL No. 13-70 - MEDS Interface - Safety Net & Drug/Fleeing Felon Aid Codes 3F and K1 | [8 empty] | 47284
| General Relief | [ITGC] CSSD General Relief (GR) File - LA County Only | [8 empty] | 48354
| N/A | [ITGC] Fix special characters in the IEVS (IFDS) and QCIS file | [8 empty] | 51445
| Medi-Cal/MSP/CMSP | 2019 MEDS Renewal and Recon Schedule | [10 empty] | 200897
|  | ACIN I-XX-18 - 2019 State Minimum Wage | [10 empty] | 58696
| CalFresh | ACL16-77 - YourBenefitsNow YBN New Application process and CW RE in all threshold language. | [10 empty] | 54521
| Medi-Cal/MSP/CMSP | ACWDL 03-49; ACWDL 11-33; ACL 03-46; ACL 04-22: Deemed Eligibility Functionality - Phase II | [10 empty] | 51741
| Medi-Cal/MSP/CMSP | ACWDL 18-XX Update LRS with the 2018-2019 Family Member Base Allocation (FMBA) amount. | [10 empty] | 200839
| CalFresh, CalWORKs, General Relief, RCA/RAM | ACWDL 18-XX, ACIN I-XX-18: 2019 Social Security Title II and Title XVI Cost of Living Adjustments (SSA COLA) | [10 empty] | 200729
| N/A | ATS Security Assessment Findings - Group 2 | [10 empty] | 59075
| YBN | Addendum - YBN to display the Participant Name and Program Type on the PA 1918, Verification of Benefits | [10 empty] | 57725
| Other | Business reply mail envelopes for the SAR 7 eligibility status report and the QR 7-LA eligibility status report | [10 empty] | 47290
| CalWorks | CalWORKs temporary Absence rule - Negative Action Reason "Visiting or Incarcerated" | [10 empty] | 49414
| Medi-Cal/MSP/CMSP | DDCR 3061: Add the 2K Aid Code for IHSS | [10 empty] | 200406
| N/A | DDCR 4028: Enhance Auditing framework to capture link text clicked by the user | [10 empty] | 200265
| N/A | DDCR 4032: Alert user about existing open Journal window while launching Journal | [10 empty] | 200268
| Medi-Cal/MSP/CMSP | DDCR 5009: Display Matching Bypass Indicator on MAGI Request and MAGI Person Detail pages | [10 empty] | 200629
| N/A | DDCR 5071: Placeholder - Audit: Update Audit framework to record User Login transaction | [10 empty] | 57133
| N/A | Enhance the existing EDMS Web Service to add application # as optional, open up the WSDL for all applications, allow case # as optional. | [10 empty] | 55961
| N/A | Enhance the reports architecture framework to remove dependencies on external software | [10 empty] | 200951
|  | ICT: Update ICT to send cases that have been flagged with Domestic Violence | [10 empty] | 200820
|  | Refactor CT73 for NOA Generation | [10 empty] | 201641
| Training | Training Support 2017-2018 | [10 empty] | 57054
| N/A | Update 2019 Batch Holiday | [10 empty] | 200896
| YBN | YBN Security Assessment Findings - Group 1 (Non-compliant authentication, Insufficient input validation (Cross Site Scripting), Server information disclosure & Insecure HTTP methods enabled) | [10 empty] | 58158