## Gantt
ACL 18-38 - AB 480 (Gonzalez Fletcher) - Diapers
C-IV SCR# 100305; CalACES SCR # 59192
Implementation Options |  | Target End Date |  | February |  |  |  | March |  |  |  | April |  |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | August
|  |  | 2018-02-05 | 2018-02-12 | 2018-02-19 | 2018-02-26 | 2018-03-05 | 2018-03-12 | 2018-03-19 | 2018-03-26 | 2018-04-02 | 2018-04-09 | 2018-04-16 | 2018-04-23 | 2018-04-30 | 2018-05-07 | 2018-05-14 | 2018-05-21 | 2018-05-28 | 2018-06-04 | 2018-06-11 | 2018-06-18 | 2018-06-25 | 2018-07-02 | 2018-07-09 | 2018-07-16 | 2018-07-23 | 2018-07-30 | 2018-08-06 | 2018-08-13 | 2018-08-20
Final ACL Received Date |  | 2018-03-30
ACL Effective Date |  | 2018-04-01 | 2018-04-09: TODAY
Release 18.05
| Build | 1/29/18 - 3/23/18 | bar: 2018-02-05 to 2018-02-19
| System Test | 3/23/18 - 5/11/18 | bar: 2018-03-26 to 2018-04-09
| Deployment (LRS) | Saturday 5/19/2018
| Deployment (C-IV) | Sunday 5/20/2018
Release 18.07
| Build | 3/26/18 - 5/24/18 | bar: 2018-03-26 to 2018-04-09
| System Test | 5/25/18 - 7/13/18
| Deployment (LRS) | Saturday 7/21/2018
| Deployment (C-IV) | Sunday 7/22/2018
Option 1: Diapers Bill Full Automation + Retro Effective Date 4/1/2018
| Design | 2018-05-04 | [29 empty] | TBD - State & Fiscal reporting | bar: 2018-04-02 to 2018-04-09
| Dep: Finalize NA 823 NOA Approval | 2018-04-25 | [29 empty] | Assuming Expedited Approved Build; Committee Approval
| Dep: Committee Decision on Retro | 2018-04-25 | [29 empty] | Assuming Expedited Approved Build; Committee Approval
| Dep: CRPC Response | 2018-04-25
| Committee Review | 2018-05-04 | [29 empty] | Option: Shorten review to one week
| Build | 2018-06-08 | [29 empty] | Option: Approve "Start Build" in parallel with Committee Review
| System Test | 2018-07-06 | [29 empty] | NOAs retro; Testing time included Retro.
| Deployment (LRS) - 18.07 | Saturday 7/21/2018 | [29 empty] | Unknown risk: EBT FIS testing/Go Live 6/23/18
| Deployment (C-IV) - 18.07 | Sunday 7/22/2018
Diapers Bill CTCR
(Need Type, Need Category, 14 Paycodes, Auditor Controller Testing)
| Design (2 weeks) | 2018-04-27 | [29 empty] | Decision PSC. To shift start Design Date | bar: 2018-04-02 to 2018-04-09
| Build & Auditor Controller Testing | 2018-05-11 | 2018-05-21: Shorten AC testing to one week
| System Test | 2018-05-18
| Deployment (LRS) - 18.05 | Saturday 5/19/2018
| Deployment (C-IV) - 18.05 | Sunday 5/20/2018
Full Automation | [31 empty] | TBD - Retro
| Design | 2018-05-18 | [29 empty] | TBD - State & Fiscal reporting | bar: 2018-04-02 to 2018-04-09
| Dep: Finalize NA 823 NOA Approval | 2018-04-25 | [29 empty] | Assuming Expedited Approved Build; Committee Approval
| Dep: Committee Decision on Retro | 2018-04-25 | [29 empty] | Assuming Expedited Approved Build; Committee Approval
| Dep: CRPC Response | 2018-04-25
| Committee Review | 2018-06-01 | [29 empty] | Option: Shorten review to one week
| Build | 2018-06-22 | [29 empty] | Option: Approve "Start Build" in parallel with Committee Review
| System Test | 2018-07-20 | [29 empty] | NOAs retro; Testing time included Retro.
| Deployment (LRS) - 18.07 | Saturday 7/21/2018 | [29 empty] | Unknown risk: EBT FIS testing/Go Live 6/23/18
| Deployment (C-IV) - 18.07 | Sunday 7/22/2018
?? CIT (Manual); Other considerations needed for Full Auto
Production Deployment Date
Critical Dependency
Create SCR for non-critical requirements (e.g., reportis, etc.)