## CalACES Change Management 2018-
SCR | Summary | Estimate | Funding Source | Change Type (SCR) | SPG Rating | Status | Fix Version/s | Minor Version | Team Responsible | Priority | Created | In Production | SPG Status | SPG Score | Other Agency Cross Reference | Committee / WorkGroup | Committee / WorkGroup | Committee / WorkGroup | Resolution
CA-202862 | Auto rescission for Medi-Cal programs where RE packet is received after 10-day cutoff | 2145 | LRS M&E | Enhancement | Critical | In Development | 18.11 |  | CalHEERS |  | 2018-05-30 13:23 |  | Approved |  | CIV-101405, CH-125364 | Medi-Cal/CMSP
CA-59192 | AB 480: ACL 18-38 / CFL 17/18-57 Add Additional Diaper Benefit Functionality - Phase II | 1420 | Premise | New Policy | Critical | In Production | 18.07 | 18.08.17 | Fiscal | 3-Normal/Low | 2018-01-19 11:41 | 2018-08-18 04:06 | Approved | N/A | CIV-100305 | Welfare to Work/WPR |  |  | Done
CA-51741 | Enhancement to Deemed Eligible Functionality | 1365 | LRS M&E | Policy Re-Design | Critical | System Test | 18.09 |  | CalHEERS | 3-Normal/Low | 2018-01-19 11:43 |  | Approved | N/A | CIV-11439 | Medi-Cal/CMSP |  |  | Done
CA-54027 | < ITGC > Modify the TCF recertification process for programs discontinued after the RE Due Month | 695 | Other | Enhancement | Critical | System Test | 18.09 |  | Online | 3-Normal/Low | 2018-01-19 11:45 |  | Approved |  | CIV-1073 | CalWORKs/CalFresh
CA-52879 | Update the EBT Repayment Process | 560 | LRS M&E | Enhancement | Critical | In Development | 18.11 |  | Fiscal | 3-Normal/Low | 2018-01-19 11:44 |  | Approved |  | CIV-101003 | Fiscal | Other
CA-51899 | <No Cost SCR> < ITGC > DCFS: Complete the Work Order Detail and Work Order List page modifications to fully incorporate the functionality of the EW WORKS legacy system originally slated for inclusion in LRS Phase I implementation | 545 | Other | Enhancement | Critical | System Test | 18.09 |  | Online | 3-Normal/Low | 2018-01-19 11:44 |  | Approved |  | LA County Specific | Usability
CA-50083 | Phase II - Add Threshold languages to existing RCA NOAs | 525 | LRS M&E | New Policy | Critical | System Test | 18.09 |  | Client Correspondence | 3-Normal/Low | 2018-01-19 11:45 |  | Approved | 0 | Per migration requirements CIV is adopting LRS NOA's | Correspondence
CA-52723 | Customer Reporting Updates | 500 | LRS M&E | Enhancement | Critical | In Production | 18.07 |  | Online | 3-Normal/Low | 2018-01-19 11:45 | 2018-07-22 16:07 | Approved |  | CIV-100710, CA-201699 | CalWORKs/CalFresh | Medi-Cal/CMSP |  | Done
CA-49832 | <R&A> Child Welfare Trust Changes | 360 | R&A - Fixed | Enhancement | Critical | In Production | 18.07 |  | Fiscal | 3-Normal/Low | 2018-01-19 11:43 | 2018-07-22 16:07 | Approved |  | CA-201702 | Fiscal |  |  | Done
CA-54342 | DDCR 5062: Update Child Support Member Transactions - Eligibility Status Date Functionality For Former MFG Children (C-IV SCR #7266) | 295 | LRS M&E | New Policy | Critical | System Test | 18.09 |  | Batch/Interfaces | 3-Normal/Low | 2018-01-19 11:44 |  | Approved |  | CIV-7266 | CalWORKs/CalFresh
CA-52874 | Applicant IEVS abstracts at Redetermination/Recertification. | 275 | LRS M&E | Enhancement | Critical | Approved | 18.11 |  | Batch/Interfaces | 3-Normal/Low | 2018-01-19 11:44 |  | Approved | N/A | CIV-10394 | IEVS
CA-203397 | ACL 18-89 Foster Care and Kin-GAP COLA Rate Increase - Batch EDBC | 270 | LRS M&E | New Policy | Critical | Approved | 18.07 | 18.09.14 | Eligibility |  | 2018-06-29 10:38 |  | Approved | 80 | CIV-101685 | Foster Care/Kin GAP/AAP
CA-56670 | ACL 18-89 Foster Care and Kin-GAP COLA Rate Increase | 220 | LRS M&E | New Policy | Critical | System Test | 18.07 | 18.09.14 | Eligibility | 3-Normal/Low | 2018-01-19 11:42 |  | Approved | 86 | CIV-9441 | Foster Care/Kin GAP/AAP
CA-202612 | CFL 17/18-32E: Update Foster Care (FC) Rate structure for RB-FFA rate level | 200 | LRS M&E | New Policy | Critical | Approved | 18.11 |  | Eligibility |  | 2018-05-10 13:45 |  | Approved | N/A |  | Foster Care/Kin GAP/AAP
CA-201634 | Update Time Limit Sanctions Batch | 195 | LRS M&E | Enhancement | Critical | System Test | 18.09 |  | Fiscal |  | 2018-03-21 11:54 |  | Approved |  | C-IV SCR 623 | Time Limits
CA-47284 | < ITGC > ACL No. 13-70 - MEDS Interface - Safety Net & Drug/Fleeing Felon Aid Codes 3F and K1 | 180 | LRS M&E | New Policy | Critical | System Test | 18.09 |  | Batch/Interfaces | 3-Normal/Low | 2018-01-19 11:44 |  | Approved |  | CIV-101257 | MEDS
CA-52389 | Removal of Program-Specific Rescission Limits | 140 | LRS M&E | Enhancement | Critical | System Test | 18.09 |  | Online | 3-Normal/Low | 2018-01-19 11:43 |  | Approved | N/A |  | CalWORKs/CalFresh
CA-203714 | Los Angeles Auditor Controller Trust Warrant Refund (TWR) Bank code change | 130 | LRS M&E | Operational Enhancement | Critical | System Test | 18.09 |  | Fiscal |  | 2018-07-25 10:11 |  | Approved
CA-200382 | DDCR 3109 and 4029: CW/RCA Income Reporting Threshold (IRT) Tiers | 130 | LRS M&E | Policy Re-Design | Critical | Approved | 18.11 |  | Eligibility |  | 2018-01-26 09:57 |  | Approved | 90 | CIV-55225 (DDCR 3109) & SCR 1017 (DDCR 4029) | CalWORKs/CalFresh
CA-203887 | ACIN I-54-18 - 2018 CalFresh COLA Run Batch EDBC | 118 | LRS M&O | New Policy | Critical | System Test | 18.07 | 18.09.07 | Eligibility |  | 2018-08-03 16:52 |  | Approved | n/a - Status was added prior to Priority requirement | CIV-101892 | CalWORKs/CalFresh
CA-203885 | ACL 18-93 Adoption Assistance Program (AAP) COLA Rate Increase - Batch EDBC | 110 | LRS M&E | New Policy | Critical | Approved | 18.07 | 18.09.14 | Eligibility |  | 2018-08-03 16:20 |  | Approved | 80 |  | Foster Care/Kin GAP/AAP
CA-201379 | Strategic Plan - Align active programs with the same primary applicant within the same district under a single Eligibility Worker | 110 | LRS M&E | Data Change | Critical | System Test | 18.09 |  | Online |  | 2018-03-12 17:44 |  | Approved | 90 | LA County Specific | Usability
CA-203884 | ACL 18-93 Adoption Assistance Program (AAP) COLA Rate Increase | 105 |  | New Policy | Critical | System Test | 18.07 | 18.09.14 | Eligibility |  | 2018-08-03 16:13 |  | Approved |  |  | Foster Care/Kin GAP/AAP
CA-203559 | CFL 17/18-32E: Update Foster Care (FC) Rate structure for RB-FFA rate level - Batch EDBC | 95 | LRS M&E | New Policy | Critical | Approved | 18.11 |  | Eligibility |  | 2018-07-11 15:23 |  | Approved | TBD |  | Foster Care/Kin GAP/AAP
CA-56668 | ACIN I-54-18 - 2018 CalFresh COLA | 78 | LRS M&E | New Policy | Critical | System Test | 18.07 | 18.09.07 | Eligibility | 3-Normal/Low | 2018-01-19 11:41 |  | Approved | 86 | CIV-100437 | CalWORKs/CalFresh
CA-200843 | ACWDL 18-04: 2018 Medicare Savings Program (MSP) Property Limits | 50 | LRS M&E | New Policy | Critical | Development Complete | 18.11 |  | CalHEERS | 3-Normal/Low | 2018-02-14 10:19 |  | Approved | 86 | CIV-100550 | Medi-Cal/CMSP
CA-200526 | GR Homelessness Account Update FY18-19 | 45 | LRS M&E | Enhancement | Critical | Test Complete | 18.09 |  | Fiscal |  | 2018-01-31 13:20 |  | Approved |  | LA County Specific | Fiscal |  |  | Done
CA-203571 | Initial List Prior to Implementation of SCR 58012 | 35 | LRS M&E | Operational Enhancement | Critical | In Production | 18.07 |  | Eligibility |  | 2018-07-12 10:25 | 2018-07-22 16:07 | Approved |  | None | Foster Care/Kin GAP/AAP |  |  | Done
CA-201740 | Your Benefits Now (YBN): Update the Voter Hotline Number for Threshold Languages | 20 | LRS M&E | Enhancement | Critical | Test Complete | 18.09 |  | Online |  | 2018-03-28 08:07 |  | Approved |  | CIV-100900 | C4Yourself |  |  | Done
CA-201673 | TTC Posted Collections on Recovery Account Transaction Date | 20 | LRS M&E | Enhancement | Critical | Test Complete | 18.09 |  | Fiscal |  | 2018-03-21 16:50 |  | Approved |  | LA County Specific | Collections |  |  | Done
CA-203900 | Training QA of Job Aids Impacted by SCR CA-51899 | 16 | LRS M&E | Enhancement | Critical | Approved | 18.09 |  | Training |  | 2018-08-06 15:27 |  | Approved
CA-203536 | Initial List Prior to Implementation of SCR 200592 | 15 | LRS M&E | Operational Enhancement | Critical | In Production | 18.07 |  | Eligibility |  | 2018-07-10 17:25 | 2018-07-22 16:07 | Approved |  | CIV-101715 | Foster Care/Kin GAP/AAP |  |  | Done
CA-204241 | Training QA of Job Aids Impacted by SCR CA-52389 | 8 | LRS M&E | Enhancement | Critical | Test Complete | 18.09 |  | Training |  | 2018-08-23 11:00 |  | Approved | N/A |  |  |  |  | Done
CA-203214 | Design for CalHEERS Change IV | 5120 | Premise | Operational Enhancement | High | Test Complete | 18.09 |  | CalHEERS |  | 2018-06-19 10:43 |  | Approved |  | CalHEERS CRs: CR 92295, CR 119408, CR 121151, CR 124708, CR 124914, CR 124918 |  |  |  | Done
CA-201310 | CalHEERS eHIT: Update VLP Interface to version 37 (CH-92295) | 2900 | Premise | New Policy | High | In Development | 19.02 |  | CalHEERS |  | 2018-03-09 08:59 |  | Approved |  | CH-92295; CH-121151; CIV-100608 | Medi-Cal/CMSP
CA-47607 | Authorized Representative Information | 2355 | LRS M&E | Enhancement | High | In Development | 18.11 |  | Online | 3-Normal/Low | 2018-01-19 11:45 |  | Approved |  | CIV-1383 | CalWORKs/CalFresh | Medi-Cal/CMSP
CA-52413 | < ITGC > ACL 99-11 Treatment of GR Interim Assistance Payment as a Recoupment Against CAPI Benefits | 1875 | LRS M&E | Policy Re-Design | High | In Production | 18.07 |  | Eligibility | 3-Normal/Low | 2018-01-19 11:44 | 2018-07-22 16:07 | Approved |  |  | CalWORKs/CalFresh | Other |  | Done
CA-51485 | ACIN I-01-07-Allow Exceptions to be Added for Tribal TANF and Out of State Months. | 1330 | LRS M&E | Policy Re-Design | High | In Development | 18.11 |  | Fiscal | 3-Normal/Low | 2018-01-19 11:47 |  | Approved | 0 | C-IV SCR 4815 | Time Limits
CA-59077 | ATS Security Assessment Findings - Group 3 | 754 | LRS M&E | Enhancement | High | Approved | 19.01 |  | Tech Arch | 3-Normal/Low | 2018-01-19 11:43 |  | Approved
CA-53784 | < ITGC > ACL 12-67 - Automation of the 319 â€“ Meeting WPR WtW 24-Month Time Clock Stopper | 725 | LRS M&E | Policy Re-Design | High | In Development | 18.11 |  | Fiscal | 3-Normal/Low | 2018-01-19 11:46 |  | Approved |  | C-IV SCR 632 | Welfare to Work/WPR
CA-58591 | Modifications to Logic of LRS REP Reports: AOGP Actuals (monthly), AOGP Goals and Actuals (annual), ASP, and RS 50 (trimester) | 485 | LRS M&E | Enhancement | High | Test Complete | 18.09 |  | Reports | 3-Normal/Low | 2018-01-19 11:44 |  | Approved | TBD | None | State/Fiscal Reports |  |  | Done
CA-58012 | ACL 17-75 Update the Kin-GAP rate schedule to use Case Dismissal Date | 425 | LRS M&E | New Policy | High | Test Complete | 18.09 |  | Imaging | 3-Normal/Low | 2018-01-19 11:41 |  | Approved | N/A | C-IV SCR 10978 | Foster Care/Kin GAP/AAP |  |  | Done
CA-203710 | AB 480: ACL 18-38 / CFL 17/18-57 Add Additional Diaper Benefit Functionality - Phase II - Testing | 385 | LRS M&E | New Policy | High | In Production | 18.07 | 18.08.17 | System Test |  | 2018-07-25 00:54 | 2018-08-18 04:06 | Approved |  | CA-59192, CA-202085 and CIV-100986 | Welfare to Work/WPR |  |  | Done
CA-58022 | Complete Documentation, Training and Transitioning of OID Maintenance Process from Tech Operations to eGov team for YBN(CBO/FBO) and ATS Accounts | 365 | LRS M&E | Operational Enhancement | High | Approved | 18.09 |  | Tech Ops | 3-Normal/Low | 2018-01-19 11:41 |  | Approved
CA-201125 | DPSS/DCFS Incident/DCR support SCR for 18.07 | 350 | LRS M&E | Operational Enhancement | High | Approved | 18.07 |  | Eligibility |  | 2018-03-01 11:39 |  | Approved | TBD
CA-48354 | < ITGC > CSSD General Relief (GR) File - LA County Only | 350 | LRS M&E | Enhancement | High | System Test | 18.09 |  | Batch/Interfaces | 3-Normal/Low | 2018-01-19 11:44 |  | Approved |  |  | Other
CA-56520 | ACL 03-20 - Count Income of Senior Parent not in CW Assistance Unit | 340 | LRS M&E | Policy Re-Design | High | In Production | 18.07 |  | Eligibility | 3-Normal/Low | 2018-01-19 11:41 | 2018-07-22 16:07 | Approved |  | C- IV SCR 458 | CalWORKs/CalFresh |  |  | Done
CA-51445 | < ITGC > Fix special characters in the IEVS (IFDS) and QCIS file | 325 | LRS M&E | Enhancement | High | System Test | 18.09 |  | Batch/Interfaces | 3-Normal/Low | 2018-01-19 11:44 |  | Approved |  | CIV-101304 | IEVS
CA-200850 | CalHEERS eHIT: Naturalized/Derived Citizenship updates (CH-109700) | 315 | Premise | New Policy | High | Test Complete | 18.09 |  | CalHEERS |  | 2018-02-14 11:03 |  | Approved | N/A | CH-109700; CH-113161; CIV-100538 | Medi-Cal/CMSP |  |  | Done
CA-201082 | Los Angeles County Auditor Controller file for Voucher Less Vendors | 305 | LRS M&E | Operational Enhancement | High | System Test | 18.09 |  | Fiscal |  | 2018-02-27 17:34 |  | Approved | N/A |  | Fiscal
CA-202861 | Receive AB 110 Pay Code through DataMart file | 270 | LRS M&E | New Policy | High | In Production | 18.07 | 18.08.17 | Fiscal |  | 2018-05-30 11:47 | 2018-08-18 04:06 | Approved |  | CA-202839 |  |  |  | Done
CA-200350 | Training Updates - Modify CalHEERS Online Single Streamlined Application (WBTs) | 250 | LRS M&E | Enhancement | High | In Production | 18.07 |  | Training | 4-Cosmetic | 2018-01-25 10:27 | 2018-07-22 16:07 | Approved | [5 empty] | Done
CA-201249 | Training Updates - WTW 24 MTC - item 5 - Time Limit Extension Requests | 200 | LRS M&E | Enhancement | High | In Production | 18.07 |  | Training |  | 2018-03-07 11:16 | 2018-07-22 16:07 | Approved | [5 empty] | Done
CA-58841 | DDCR 3034, 3036: ACWDL 17-28 and 17-29: Inmate MC Aid Codes | 195 | LRS M&E | New Policy | High | In Production | 18.06 |  | CalHEERS | 3-Normal/Low | 2018-01-19 11:44 | 2018-06-03 16:55 | Approved |  | CIV-50329, CIV-49867; CIV-8677 | Medi-Cal/CMSP |  |  | Done
CA-200592 | ACL 11-15E11 Update KG EDBC to Consider the SOC 369A Date | 195 | LRS M&E | Policy Re-Design | High | Test Complete | 18.09 |  | Eligibility |  | 2018-02-02 13:13 |  | Approved |  | CIV-503 | Foster Care/Kin GAP/AAP |  |  | Done
CA-59270 | Modify LRS to support new Vendor FIS Fidelity Information Services, LLC | 190 | LRS M&E | Enhancement | High | In Production | 18.06 | 18.06.24 | Tech Ops | 3-Normal/Low | 2018-01-19 11:42 | 2018-06-25 22:22 | Approved |  | C-IV 11727 | Fiscal |  |  | Done
CA-203260 | Update Office Boundaries table for CalHEERS and eICT Referrals | 190 | LRS M&E | Data Change | High | In Production | 18.07 | 18.07.28 | CalHEERS |  | 2018-06-21 10:55 | 2018-07-30 21:17 | Approved |  | N/A - This change impacts LRS Only. |  |  |  | Done
CA-200351 | Training Updates - CalHEERS - Immigration Status Changes (WBTs) | 180 | LRS M&E | Enhancement | High | In Production | 18.07 |  | Training | 4-Cosmetic | 2018-01-25 10:38 | 2018-08-07 20:52 | Approved | [5 empty] | Done
CA-203249 | AB 480: ACL 18-38 - Generate the NA 823 when manually issuing diaper allowance | 160 | LRS M&E | New Policy | High | In Development | 18.11 |  | Fiscal |  | 2018-06-20 14:13 |  | Approved |  | CIV-101674 | Welfare to Work/WPR
CA-203207 | ACL 18-75 : Phase II - Funding for Emergency Caregivers with Placements of Children prior to RFA Approval | 130 | LRS M&E | New Policy | High | In Production | 18.07 | 18.08.17 | Eligibility |  | 2018-06-19 08:06 | 2018-08-18 04:06 | Approved |  | CIV-101516 | Foster Care/Kin GAP/AAP |  |  | Done
CA-203553 | Training Updates - AB 480: ACL 18-38 / CFL 17/18-57 Add Additional Diaper Benefit Functionality - Phase II (WBTs) | 125 | LRS M&E | Enhancement | High | System Test | 18.09 |  | Training |  | 2018-07-11 14:56 |  | Approved
CA-203861 | Add the Pub 10 (02/17) Non-MAGI Medi-Cal Brochure and Revise DHCS 7077 in English and Spanish | 105 | LRS M&E | Enhancement | High | Approved | 18.09 | 18.10.XX | Client Correspondence |  | 2018-08-02 15:17 |  | Approved | N/A |  | Correspondence
CA-202379 | Workshare: Implement Revised MC-007 (Static Form) | 100 | LRS M&E | Policy Re-Design | High | System Test | 18.09 |  | Client Correspondence |  | 2018-04-27 08:53 |  | Approved | N/A | CIV-101645 | Correspondence
CA-200896 | Update 2019 Batch Holiday | 100 | LRS M&E | Operational Enhancement | High | Approved | 18.11 |  | Batch/Production Operations |  | 2018-02-15 15:17 |  | Approved | 70 | CIV-100492 | Usability
CA-204038 | Training Updates - Removal of LACO Seal/Logo from LRS WBTs | 100 | LRS M&E | Enhancement | High | Approved | 19.06 |  | Training |  | 2018-08-14 10:06 |  | Approved | TBD
CA-202875 | ACL 18-66 - Batch EDBC for Cost of Living Adjustment (COLA) for Income In-Kind (IIK) for 2018-2019 | 75 | LRS M&E | New Policy | High | In Production | 18.06 | 18.06.15 | Eligibility |  | 2018-05-31 09:03 | 2018-06-18 20:44 | Approved |  | CIV-101404 | CalWORKs/CalFresh |  |  | Done
CA-202677 | CalWIN Demo Environment Maintenance and Support For June 2018 | 75 | LRS M&E | Enhancement | High | In Production | 18.06 | 18.06.22 | Batch/Interfaces |  | 2018-05-16 07:40 | 2018-06-26 19:08 | Approved |  | CA-201019 | Other |  |  | Done
CA-56873 | NO COST SCR - NOMI Denial batch shouldn't be denying the participant has attended the Intake Interview | 70 | Other | Policy Re-Design | High | Test Complete | 18.09 |  | Batch/Interfaces | 3-Normal/Low | 2018-01-19 11:43 |  | Approved |  |  | CalWORKs/CalFresh |  |  | Done
CA-202497 | Training Updates - AB 480: ACL 18-38 / CFL 17/18-57 Add Diaper Benefit Functionality Phase I (JAs) | 61 | LRS M&E | New Policy | High | In Production | 18.06 |  | Training |  | 2018-05-03 13:30 | 2018-06-03 16:55 | Approved | [5 empty] | Done
CA-202501 | Training Updates - Customer Reporting Updates (JAs) | 60 | LRS M&E | Enhancement | High | In Production | 18.07 | 18.07.31 | Training |  | 2018-05-03 14:11 | 2018-07-31 18:54 | Approved | [5 empty] | Done
CA-200759 | Update CalFresh School Attendance Employment Eligibility | 60 | LRS M&E | Policy Re-Design | High | In Production | 18.07 |  | Eligibility |  | 2018-02-08 15:12 | 2018-07-22 16:07 | Approved |  | CIV-467 | CalWORKs/CalFresh |  |  | Done
CA-202402 | Design: Assess LRS Automated Regression Test Scripts for Conversion | 60 | LRS M&E | Enhancement | High | In Development | 18.07 | 18.09.XX | System Test |  | 2018-04-30 12:39 |  | Approved
CA-200861 | Update the LRS Case Number Assignment | 60 | LRS M&E | Enhancement | High | System Test | 18.09 |  | Online |  | 2018-02-14 14:13 |  | Approved |  |  | Usability
CA-200630 | DDCR 3059: Add validation to prevent the same LRS person from being linked to multiple persons in a MAGI Referral | 60 | LRS M&E | Enhancement | High | Test Complete | 18.09 |  | CalHEERS |  | 2018-02-05 13:21 |  | Approved |  | CIV 50910 | Medi-Cal/CMSP |  |  | Done
CA-56048 | Kin-GAP Program DCR | 60 | LRS M&O | Data Change | High | Development Complete | 18.09 |  | Online | 3-Normal/Low | 2018-01-19 11:41 |  | Approved | N/A |  | Foster Care/Kin GAP/AAP |  |  | Done
CA-200839 | ACWDL 18-13: 2018/2019 Family Member Base Allocation Amount | 50 | LRS M&E | New Policy | High | Approved | 18.11 |  | CalHEERS | 3-Normal/Low | 2018-02-14 10:00 |  | Approved | 84 | C-IV 100481 | Medi-Cal/CMSP
CA-200326 | DDCR 5057: Update ICT Detail page to navigate to ICT Program Person Detail (C-IV SCR#4479) | 50 | LRS M&E | Enhancement | High | Development Complete | 18.11 |  | Online | 2-Normal/Medium | 2018-01-25 07:34 |  | Approved |  | CIV-4479 | ICT
CA-58593 | DDCR 3083: ACWDL 17-40: 2018 Medicare Catastrophic Coverage Act Spousal Impoverishment Caps - Community Spousal update | 45 | LRS M&E | New Policy | High | In Production | 18.07 |  | CalHEERS | 3-Normal/Low | 2018-01-19 11:43 | 2018-07-22 16:07 | Approved |  | CIV-100272, CIV-53790 | Medi-Cal/CMSP |  |  | Done
CA-200892 | Update Payment Request Detail page to have Payee Name link to Resource Detail page | 45 | LRS M&E | Enhancement | High | System Test | 18.09 |  | Fiscal |  | 2018-02-15 13:46 |  | Approved | N/A | CIV-7551 | Fiscal
CA-203649 | ACWDL 17-40: Generate list of LTC programs to identify cases that may qualify for a lower share-of-cost | 30 | LRS M&E | New Policy | High | In Production | 18.07 | 18.07.27 | CalHEERS |  | 2018-07-18 18:42 | 2018-08-06 21:15 | Approved |  | CIV-101782 | Medi-Cal/CMSP |  |  | Done
CA-203567 | General Relief CalWIN Demo Support | 25 | LRS M&E | Operational Enhancement | High | In Production | 18.07 | 18.07.26 | System Test |  | 2018-07-11 17:56 | 2018-07-31 16:18 | Approved | [5 empty] | Done
CA-202506 | Training Updates - ACWDL 18-01 : Add Eligibility Evaluation Reasons from CalHEERS to Trigger MAGI Denial/Discontinuance Notices (JAs) | 24 | Premise | Enhancement | High | In Production | 18.07 |  | Training |  | 2018-05-03 14:41 | 2018-07-22 16:07 | Approved |  | CH-87156 |  |  |  | Done
CA-202514 | Training Updates - SB 89 SFIS Repeal for CalWORKs/RCA and General Relief (GR) Programs (WBTs) | 22 | LRS M&E | Enhancement | High | In Production | 18.07 |  | Training |  | 2018-05-03 15:34 | 2018-07-22 16:07 | Approved | [5 empty] | Done
CA-201169 | Training Updates - Update the manual EDBC process to allow run reasons to be used (WBTs) | 20 | LRS M&E | Enhancement | High | In Production | 18.07 |  | Training |  | 2018-03-05 12:41 | 2018-07-22 16:07 | Approved | [5 empty] | Done
CA-202840 | YBN: Enhancements to the EBT Account Balance and Transactions Page | 20 | LRS M&E | Enhancement | High | Test Complete | 18.09 |  | Online |  | 2018-05-29 15:45 |  | Approved |  |  | C4Yourself |  |  | Done
CA-200406 | DDCR 3061: Add the 2K Aid Code for IHSS | 20 | LRS M&E | Policy Re-Design | High | System Test | 18.11 |  | CalHEERS |  | 2018-01-28 12:24 |  | Approved |  | CIV-51180 | Medi-Cal/CMSP
CA-200259 | DDCR 4012: Update information available for print from Journal | 20 | LRS M&E | Enhancement | High | Approved | 19.01 |  | Online | 2-Normal/Medium | 2018-01-24 09:52 |  | Approved | N/A | CIV-557 | Usability
CA-203230 | ACL 18-66 - Identify Cases with an Income-In-Kind that Matches the Standard Amount | 15 | LRS M&O | New Policy | High | In Production | 18.06 | 18.07.18 | Eligibility |  | 2018-06-19 18:36 | 2018-07-31 18:52 | Approved |  | CIV-101561 | CalWORKs/CalFresh |  |  | Done
CA-203839 | Training QA of Job Aids Impacted by SCR CA-58841 | 13 | LRS M&E | Enhancement | High | Test Complete | 18.09 |  | Training |  | 2018-08-02 10:03 |  | Approved | [5 empty] | Done
CA-204111 | Training QA of Job Aids Impacted by SCR CA-53784 | 8 | LRS M&E | Enhancement | High | Approved | 18.11 |  | Training |  | 2018-08-16 14:28 |  | Approved | TBD
CA-202294 | Rename the Description for 'POI Recoupment' transaction type on Transaction Detail page | 5 | LRS M&E | Enhancement | High | In Development | 18.11 |  | Fiscal |  | 2018-04-24 14:46 |  | Approved |  |  | Collections
CA-202806 | ACL 18-82 - Elect Child Support Payment for Stepsibling or Half-Sibling in Lieu of Cash Aid - Phase 1 | 190 | Premise | New Policy | Low | System Test | 18.07 | 18.09.14 | Client Correspondence |  | 2018-05-25 10:51 |  | Approved |  | CIV-101374 | Correspondence
CA-203173 | Update Foster Care/Kin-GAP Income Exemption Logic to Handle Partial Income Exemptions | 170 | LRS M&E | Policy Re-Design | Low | Approved | 18.11 |  | Eligibility |  | 2018-06-15 10:05 |  | Approved |  | CIV-9914 | Foster Care/Kin GAP/AAP
CA-203342 | Update the layout for DPSS Daily eCAPS Postback Report | 160 | LRS M&E | Operational Enhancement | Low | In Development | 18.11 |  | Fiscal |  | 2018-06-26 09:42 |  | Approved | 32 | CIV-100258 | State/Fiscal Reports
CA-53124 | ACL 16-99 - Replace the PA 1725 Attendance/Enrollment Verification (02/05) form with the revised version (5/17) | 50 | LRS M&E | New Policy | Low | In Development | 18.11 |  | Client Correspondence | 3-Normal/Low | 2018-01-19 11:47 |  | Approved |  |  | Correspondence
CA-53610 | DPSS Mobile App, revise look and feel to align with the DPSS Communication Sections Design recommendation | 1030 | LRS M&E | Enhancement | Medium | System Test | 18.09 |  | Online | 3-Normal/Low | 2018-01-19 11:44 |  | Approved | N/A |  | C4Yourself
CA-59108 | DPSS/DCFS Support SCR to provide responses to Consortia queries | 800 | LRS M&E | Data Change | Medium | System Test | 18.09 |  | Batch/Interfaces | 3-Normal/Low | 2018-01-19 11:41 |  | Approved
CA-55961 | YBN/EDMS changes to add application/case level upload for CBOs and add telephone signature record viewing in LRS. Update/add webservice to post case #, sync YBN & LRS case tables | 785 |  | Enhancement | Medium | In Development | 18.11 |  | Batch/Interfaces | 3-Normal/Low | 2018-01-19 11:44 |  | Approved |  | LA County Specific | Imaging
CA-55295 | ACWDL 18-01 : Add Eligibility Evaluation Reasons from CalHEERS to Trigger MAGI Denial/Discontinuance Notices | 780 | Premise | New Policy | Medium | In Production | 18.06 |  | CalHEERS | 3-Normal/Low | 2018-01-19 11:43 | 2018-06-03 16:55 | Approved |  | CH-87156 , CIV-12029 | Medi-Cal/CMSP |  |  | Done
CA-56603 | YBN-Upgrade-Code Changes to Support WebLogic v12 and Java 8 | 740 | LRS M&E | Operational Enhancement | Medium | Approved | 18.11 |  | Tech Arch | 3-Normal/Low | 2018-01-19 11:42 |  | Approved |  |  | Tech
CA-202605 | County Ad-Hoc database - Technical Support | 640 | LRS M&E | Operational Enhancement | Medium | Approved | 19.01 |  | DBA |  | 2018-05-10 10:36 |  | Approved
CA-201879 | Create a Master Test Data Set for CalHEERS Integration Testing | 520 | Premise | Enhancement | Medium | In Production | 18.06 | 18.07.03 | CalHEERS |  | 2018-04-04 11:15 | 2018-07-10 17:42 | Approved |  | CH CR 116507 |  |  |  | Done
CA-50553 | ACL No. 17-01 TCVAP Aid Codes R1 and 1V to send Fed/State Only Indicator "S" to WDTIP & TRAC | 385 | LRS M&E | New Policy | Medium | In Development | 18.11 |  | Fiscal | 3-Normal/Low | 2018-01-19 11:44 |  | Approved | 66 | LA County Specific | Time Limits
CA-201126 | DPSS/DCFS Incident/DCR support SCR for 18.09 | 350 | LRS M&E | Operational Enhancement | Medium | Approved | 18.09 |  | Fiscal |  | 2018-03-01 11:42 |  | Approved | N/A
CA-59075 | ATS Security Assessment Findings - Group 2 | 331 | LRS M&E | Enhancement | Medium | Approved | 18.11 |  | Tech Arch | 3-Normal/Low | 2018-01-19 11:43 |  | Approved
CA-203193 | Build Automated Regression Test Coverage of Approved GAIN/GROW Scenarios | 300 | Other | Enhancement | Medium | In Production | 18.07 | 18.08.03 | System Test |  | 2018-06-18 12:18 | 2018-08-07 17:00 | Approved | [5 empty] | Done
CA-59074 | ATS Security Assessment Findings - Group 1 | 250 | LRS M&E | Enhancement | Medium | System Test | 18.09 |  | Tech Arch | 3-Normal/Low | 2018-01-19 11:43 |  | Approved |  |  | Tech
CA-203273 | Enhance recording of AMP and AUDIT to reduce database contention | 240 | LRS M&E | Operational Enhancement | Medium | Test Complete | 18.09 |  | DBA |  | 2018-06-21 14:32 |  | Approved | [5 empty] | Done
CA-202946 | Training Updates - < ITGC > Phase II - ACL 17-34 - Add Elderly Simplified Application Project (ESAP) Indicator and Automate CF 377.2D (WBTs) | 220 | LRS M&E | Enhancement | Medium | Approved | 18.09 |  | Training |  | 2018-06-04 16:52 |  | Approved
CA-203382 | Combine the WTW 25 and WTW 25A State and Detailed Reports Into One Template Per Report | 180 | LRS M&O | Enhancement | Medium | In Development | 18.11 |  | Reports |  | 2018-06-28 12:50 |  | Approved | 69 | CIV-100730 | State/Fiscal Reports
CA-55842 | ACWDL 14-29 - Medi-Cal : Update rules to not allow CEC for persons failing MAGI due to Non-Payment of Premium | 170 | LRS M&E | New Policy | Medium | In Production | 18.06 |  | CalHEERS | 3-Normal/Low | 2018-01-19 11:45 | 2018-06-03 16:55 | Approved |  | CIV-2831 | Medi-Cal/CMSP |  |  | Done
CA-203153 | Training Support - LRS Job Aids Transition to Consortium South | 165 | LRS M&E | Enhancement | Medium | Approved | 18.09 |  | Training |  | 2018-06-14 13:21 |  | Approved
CA-203917 | Training Updates - (DCFS Updates) - Modify CalHEERS Online Single Streamlined Application (DCFS WBTs) | 135 | LRS M&E | Enhancement | Medium | Approved | 18.09 |  | Training | 4-Cosmetic | 2018-08-07 12:07 | 2018-07-22 16:07 | Approved | TBD
CA-57784 | DEATH MATCH File - Change Excel Version to latest version - LA County Only | 130 | LRS M&E | Operational Enhancement | Medium | Approved | 18.11 |  | Batch/Interfaces | 3-Normal/Low | 2018-01-19 11:44 |  | Approved | 54 | LA County Specific | Other
CA-201070 | Port SAWS-Initiated Automated Scripts (CalHEERS) | 120 | LRS M&E | Enhancement | Medium | In Development | 18.06 | 18.09.xx | System Test |  | 2018-02-27 11:35 |  | Approved | N/A | CIV-100553
CA-202948 | Training Updates - Customer Reporting Updates (WBTs) | 120 | LRS M&E | Enhancement | Medium | Approved | 18.09 |  | Training |  | 2018-06-04 16:55 |  | Approved
CA-58059 | Modify Eligibility Status Action Code (ESAC) trigger condition for EW20 transaction | 120 | LRS M&E | Operational Enhancement | Medium | Approved | 18.11 |  | Batch/Interfaces | 3-Normal/Low | 2018-01-19 11:44 |  | Approved | N/A | CIV-101555 | MEDS
CA-200629 | DDCR 5009: Display Matching Bypass Indicator on MAGI Request and MAGI Person Detail pages | 115 | LRS M&E | Policy Re-Design | Medium | Development Complete | 18.11 |  | CalHEERS |  | 2018-02-05 13:14 |  | Approved |  | CIV-5591, CIV-2713, CIV-4421, CH-10021, CA-44706 | Medi-Cal/CMSP
CA-200741 | Update table column comments for missing category ID references | 104 | LRS M&E | Operational Enhancement | Medium | System Test | 18.09 |  | DBA |  | 2018-02-08 11:35 |  | Approved
CA-200742 | Clean up "LRS TABLE" and "LRS FIELD" comments. | 104 | LRS M&E | Operational Enhancement | Medium | Test Complete | 18.09 |  | DBA |  | 2018-02-08 11:36 |  | Approved | [5 empty] | Done
CA-200740 | Standardize existing records in the code_detl table | 104 | LRS M&E | Operational Enhancement | Medium | Test Complete | 18.09 |  | DBA |  | 2018-02-08 11:32 |  | Approved | [5 empty] | Done
CA-201255 | Training Updates - Homeless Transition Age Youth and Disabled General Relief Population with New Invoice- upload the revised ABP 295 meals/lodging order and invoice to LRS | 75 | LRS M&E | Enhancement | Medium | Test Complete | 18.09 |  | Training |  | 2018-03-07 12:03 |  | Approved | [5 empty] | Done
CA-202942 | Training Updates - Child Welfare Trust Changes (WBTs) | 65 | LRS M&E | Enhancement | Medium | In Development | 18.09 |  | Training |  | 2018-06-04 16:46 |  | Approved
CA-200274 | DDCR 4049: Update Primary Applicant validations for MAGI Request | 65 | LRS M&E | Enhancement | Medium | Test Complete | 18.09 |  | CalHEERS | 2-Normal/Medium | 2018-01-24 10:31 |  | Approved |  | CIV-1406 | Medi-Cal/CMSP |  |  | Done
CA-200261 | DDCR 4022: Address same as Primary does not display on MAGI Person Detail page | 65 | LRS M&E | Enhancement | Medium | Test Complete | 18.09 |  | CalHEERS | 2-Normal/Medium | 2018-01-24 09:58 |  | Approved |  | CIV-906 | Medi-Cal/CMSP |  |  | Done
CA-200454 | DDCR 4034: MEDIL 13-03: Update MAGI Pending Eligible logic to treat retro months same as intake | 60 | LRS M&E | New Policy | Medium | Test Complete | 18.09 |  | CalHEERS |  | 2018-01-30 09:23 |  | Approved |  | CIV-1107 | Medi-Cal/CMSP |  |  | Done
CA-200636 | DDCR 3104: Enhance Determination Response Handling - add Duplicate SSN validation | 55 | LRS M&E | Policy Re-Design | Medium | Test Complete | 18.09 |  | CalHEERS |  | 2018-02-05 13:41 |  | Approved |  | CIV-55074 | Medi-Cal/CMSP |  |  | Done
CA-200280 | DDCR 4061: Update system to save MAGI Determination to database for person without a Determination node | 55 | LRS M&E | Enhancement | Medium | Test Complete | 18.09 |  | CalHEERS | 1-High/Non-Cosmetic | 2018-01-24 11:05 |  | Approved |  | CIV-2583 | Medi-Cal/CMSP |  |  | Done
CA-55686 | ACWDL 17-22: Update LRS with the 2017-2018 Family Member Base Allocation (FMBA) amount. | 50 | LRS M&E | New Policy | Medium | In Production | 18.06 |  | CalHEERS | 3-Normal/Low | 2018-01-19 11:43 | 2018-06-03 16:55 | Approved |  | CIV-10102 | Medi-Cal/CMSP |  |  | Done
CA-200262 | DDCR 4023: Validate unique MEDS Person Numbers for MAGI Request | 50 | LRS M&E | Enhancement | Medium | Test Complete | 18.09 |  | CalHEERS | 2-Normal/Medium | 2018-01-24 10:01 |  | Approved |  | CIV-936 | Medi-Cal/CMSP |  |  | Done
CA-201246 | DCR to sync up Child Care program status and Child Care Request status | 45 | LRS M&E | Data Change | Medium | In Production | 18.06 | 18.06.17 | Online |  | 2018-03-07 11:10 | 2018-06-18 01:22 | Approved |  | SCR 53280 | Child Care |  |  | Done
CA-202949 | Training Updates - Add New ADA Journal type - Special Circumstance. (WBTs) | 45 | LRS M&E | Enhancement | Medium | Test Complete | 18.09 |  | Training |  | 2018-06-04 16:58 |  | Approved | [5 empty] | Done
CA-202503 | Training Updates - SB 89 SFIS Repeal for CalWORKs/RCA and General Relief (GR) Programs (JAs) | 44 | LRS M&E | Enhancement | Medium | In Production | 18.07 |  | Training |  | 2018-05-03 14:29 | 2018-07-22 16:07 | Approved | [5 empty] | Done
CA-203244 | Upgrade the Build Tool from Maven to Gradle Version 4 | 40 | LRS M&O | Operational Enhancement | Medium | System Test | 18.09 |  | Tech Arch |  | 2018-06-20 11:47 |  | Approved |  | CIV-9356
CA-54427 | ACL 18-66 - Cost of Living Adjustment (COLA) for Minimum Basic Standard of Adequate Care (MBSAC) and Income In-Kind (IIK) for 2018-2019 | 30 | LRS M&E | New Policy | Medium | In Production | 18.06 | 18.06.14 | Eligibility | 3-Normal/Low | 2018-01-19 11:41 | 2018-06-18 20:44 | Approved |  | CIV-100439 | CalWORKs/CalFresh |  |  | Done
CA-202938 | Training Updates - Add Extract Capability to Eligibility Workload Inventory and Monthly Productivity Pages in LRS (based on C-IV SCR 7271) (WBTs) | 30 | LRS M&E | Enhancement | Medium | In Production | 18.07 |  | Training |  | 2018-06-04 16:26 | 2018-07-22 16:07 | Approved | [5 empty] | Done
CA-202502 | Training Updates - Add Extract Capability to Eligibility Workload Inventory and Monthly Productivity Pages in LRS (JAs) | 30 | LRS M&E | Enhancement | Medium | In Production | 18.07 |  | Training |  | 2018-05-03 14:17 | 2018-07-22 16:07 | Approved | [5 empty] | Done
CA-201156 | Training Updates - GROW Program - 38055 - Update the Collaborator Access - allow a Single User to Log into Multiple Resources at one time (WBTs) | 30 | LRS M&E | Enhancement | Medium | Approved | 18.09 |  | Training |  | 2018-03-05 10:36 |  | Approved
CA-200266 | DDCR 4030: Remove the Age Requirement for the Caretaker Relative Field on Tax Household page | 30 | LRS M&E | Enhancement | Medium | System Test | 18.09 |  | CalHEERS | 2-Normal/Medium | 2018-01-24 10:11 |  | Approved |  | CIV 1046 | Medi-Cal/CMSP
CA-201178 | Training Updates - Trust Fund Activity Tracking Enhancements (WBTs) | 29 | LRS M&E | Enhancement | Medium | Approved | 18.09 |  | Training |  | 2018-03-05 14:56 |  | Approved
CA-203959 | Training Updates - (DCFS Updates) Add Extract Capability to Eligibility Workload Inventory and Monthly Productivity Pages in LRS (based on C-IV SCR 7271) (DCFS WBTs) | 25 | LRS M&E | Enhancement | Medium | System Test | 18.09 |  | Training |  | 2018-08-08 15:39 | 2018-07-22 16:07 | Approved | TBD
CA-202941 | Training Updates - Updates to EBT Card Print List page and Reports (WBTs) | 22 | LRS M&E | Enhancement | Medium | Approved | 18.09 |  | Training |  | 2018-06-04 16:32 |  | Approved
CA-201251 | Training Updates - Modify the Start Date logic for LAC General Relief Housing Subsidy on Money Management pages and Vendor recoupment changes for GR EDBC | 22 | LRS M&E | Enhancement | Medium | Test Complete | 18.09 |  | Training |  | 2018-03-07 11:43 |  | Approved | [5 empty] | Done
CA-202939 | Training Updates - AB 480: ACL 18-38 / CFL 17/18-57 Add Diaper Benefit Functionality Phase I (WBTs) | 20 | LRS M&E | Enhancement | Medium | Test Complete | 18.09 |  | Training |  | 2018-06-04 16:28 |  | Approved | [5 empty] | Done
CA-202940 | Training Updates - Remove "ALL" as the default option for Workload Reassignment Detail Page (WBT) | 20 | LRS M&E | Enhancement | Medium | Test Complete | 18.09 |  | Training |  | 2018-06-04 16:30 |  | Approved | [5 empty] | Done
CA-203574 | Training Updates - Rename "CalFresh - IHE" to "CalFresh - IHE (Customer Caused)" for CalFresh Overissuance (WBTs) | 18 | LRS M&E | Enhancement | Medium | Test Complete | 18.09 |  | Training |  | 2018-07-12 13:18 |  | Approved | [5 empty] | Done
CA-202936 | Training Updates - Modify the IAR Detail page with a Generate Forms command button (WBTs) | 15 | LRS M&E | Enhancement | Medium | In Production | 18.07 |  | Training |  | 2018-06-04 16:02 | 2018-07-22 16:07 | Approved | [5 empty] | Done
CA-55964 | Update YourBenefitsNow YBN zip code reference table | 15 | LRS M&E | Data Change | Medium | In Production | 18.07 |  | Online | 3-Normal/Low | 2018-01-19 11:43 | 2018-07-22 16:07 | Approved |  |  | C4Yourself |  |  | Done
CA-202935 | Training Updates - Modify LRS WFP&I Investigation Result Detail page to remove mandatory restriction on the Case Action field (WBTs) | 15 | LRS M&E | Enhancement | Medium | Test Complete | 18.09 |  | Training |  | 2018-06-04 15:58 |  | Approved | [5 empty] | Done
CA-201254 | Training Updates - MSUDRP Assessment Page Changes (WBTs) | 15 | LRS M&E | Enhancement | Medium | Test Complete | 18.09 |  | Training |  | 2018-03-07 12:00 |  | Approved | [5 empty] | Done
CA-202933 | Training Updates - CFL 15/16-64 - AB 2035 EBT Benefit Replacement due to Electronic Theft Update - SUAS (WBTs) | 15 | LRS M&E | Enhancement | Medium | In Development | 18.09 |  | Training |  | 2018-06-04 15:30 |  | Approved
CA-202510 | Training Updates - Update Job Aid 154 per QA Review Outstanding Comments (JAs) | 11 | LRS M&E | Enhancement | Medium | In Production | 18.07 | 18.07.31 | Training |  | 2018-05-03 15:08 | 2018-07-31 18:54 | Approved | [5 empty] | Done
CA-203667 | Training Release 18.09 - LMS Lite updates |  | LRS M&O | Enhancement | Medium | Development Complete | 18.09 |  | Training | 3-Normal/Low | 2018-07-20 11:48 |  | Approved
CA-57054 | Training Support 2017-2018 | 2250 | LRS M&E | Enhancement |  | In Development | 18.11 |  | Training | Low | 2018-01-19 16:12 |  | Approved
CA-50686 | < ITGC > ACLs 16-98 and 16-98E - Threshold language for the CalWORKs Homeless Assistance NOAs | 1210 | LRS M&E | Policy Re-Design |  | In Production | 18.07 |  | Client Correspondence | 3-Normal/Low | 2018-01-19 11:46 | 2018-07-22 16:07 | Approved |  |  | Correspondence |  |  | Done
CA-200374 | <R&A> Changes in WTW/REP Activity Report (WAR) Report | 1073 | R&A - Fixed | Enhancement |  | In Production | 18.06 | 18.07.05 | Reports | 1-High/Non-Cosmetic | 2018-01-25 15:50 | 2018-07-06 05:13 | Approved |  | CIV-100722, CA-201687 | Management Reports |  |  | Done
CA-54711 | <R&A> Modify General Relief Work Registration Status of Employable/ Unemployable Tracking to Daily from Monthly | 946 | R&A - Fixed | Enhancement |  | In Production | 18.07 |  | Eligibility | 3-Normal/Low | 2018-01-19 11:44 | 2018-07-22 16:07 | Approved |  | CA-201698 | CalWORKs/CalFresh |  |  | Done
CA-50949 | < ITGC > ACL 14-88 - Revise/Create 17 NOAs Messages for Deny, Discontinue, Change, and Partial Approval for Lack of Verification | 875 | LRS M&E | New Policy |  | Approved | 18.11 |  | Client Correspondence | 3-Normal/Low | 2018-01-19 11:43 |  | Approved |  |  | Correspondence
CA-59168 | Migrate Batch Scheduler from Control-M to BICSuite | 760 | LRS M&E | Operational Enhancement |  | In Production | 18.06 | 18.07.21 | Batch/Production Operations | 3-Normal/Low | 2018-01-19 11:41 | 2018-07-23 16:39 | Approved |  | CIV-7123 |  |  |  | Done
CA-49401 | ACL 17-58 - Electronic Inter-County Transfer (eICT) - Redetermination (RE) Date Alignment | 755 | LRS M&E | New Policy |  | In Production | 18.07 |  | Eligibility | 3-Normal/Low | 2018-01-19 11:43 | 2018-07-22 16:07 | Approved |  | CIV-100436 | CalWORKs/CalFresh | Medi-Cal/CMSP |  | Done
CA-52375 | Add Region and Region Group column in all Welfare-to-Work/REP/Cal-Learn detail reports (County Workshare) | 720 | LRS M&E | Enhancement |  | System Test | 18.09 |  | Reports | 3-Normal/Low | 2018-01-19 11:45 |  | Approved |  |  | Management Reports
CA-54521 | ACL16-77 - YourBenefitsNow YBN Application process and CW RE in all threshold language. | 682 | R&A - Fixed | Policy Re-Design |  | System Test | 18.09 |  | Batch/Production Operations | 3-Normal/Low | 2018-01-19 11:44 |  | Approved |  |  | C4Yourself | Usability
CA-201180 | <R&A> YBN CF 37 in All Threshold Languages. CF37, SAR7, QR7, MC210, MC216 and CW RD pdf version will be stored in threshold in EDMS. | 630 | R&A - Fixed | Enhancement |  | In Production | 18.07 |  | Online |  | 2018-03-05 15:03 | 2018-07-22 16:07 | Approved |  | CA-201789 | Other |  |  | Done
CA-49626 | < ITGC > Workshare WTW Forms -Update New Version of NA 822 (07/16), GN 6010.9B (07/17) and GN 6369 (07/17) in all Threshold Languages to LRS | 605 | LRS M&E | New Policy |  | In Production | 18.07 |  | Client Correspondence | 3-Normal/Low | 2018-01-19 11:46 | 2018-07-22 16:07 | Approved |  |  | Correspondence |  |  | Done
CA-58158 | YBN Security Assessment Findings - Group 1 (Non-compliant authentication, Insufficient input validation (Cross Site Scripting), Server information disclosure & Insecure HTTP methods enabled) | 546 | LRS M&E | Enhancement |  | Approved | 18.11 |  | Tech Arch | 3-Normal/Low | 2018-01-19 11:44 |  | Approved
CA-202274 | Enhance recording of Web Services transactions to reduce database contention | 529 | LRS M&E | Enhancement |  | In Production | 18.06 | 18.06.17 | DBA |  | 2018-04-23 17:28 | 2018-06-18 20:33 | Approved |  |  | Tech |  |  | Done
CA-54952 | < ITGC > Phase II - ACL 17-34 - Add Elderly Simplified Application Project (ESAP) Indicator and Automate CF 377.2D | 510 | LRS M&E | New Policy |  | In Production | 18.07 |  | Eligibility | 3-Normal/Low | 2018-01-19 11:45 | 2018-07-22 16:07 | Approved |  | CIV-12413 | CalWORKs/CalFresh |  |  | Done
CA-58160 | YBN Security Assessment Findings - Group 2 (Improper error handling, Missing security headers & Missing HTTP strict-transport-security header) | 432 | LRS M&E | Enhancement |  | Test Complete | 18.09 |  | Tech Arch | 3-Normal/Low | 2018-01-19 11:44 |  | Approved | [5 empty] | Done
CA-203396 | CLONE - Changes in CW/RCA Adults by WTW Category (Global) Report | 395 | R&A - Fixed | Enhancement |  | In Production | 18.06 | 18.07.05 | Reports | 1-High/Non-Cosmetic | 2018-06-29 09:26 | 2018-07-06 05:13 | Approved |  | CIV-100723, CA-201697 | Management Reports |  |  | Done
CA-200371 | Changes in CW/RCA Adults by WTW Category (Global) Report | 395 | R&A - Fixed | Enhancement |  | In Production | 18.06 | 18.07.05 | Reports | 1-High/Non-Cosmetic | 2018-01-25 15:09 | 2018-07-06 05:13 | Approved |  | CIV-100723, CA-201697 | Management Reports |  |  | Done
CA-201060 | Build Cross Project Automated Scripts (CalHEERS) | 350 | Premise | Enhancement |  | In Production | 18.06 |  | System Test |  | 2018-02-26 17:18 | 2018-06-03 16:55 | Approved |  | CH-117713, CIV-100552 |  |  |  | Done
CA-53793 | <ITGC> CSC LAGAN Tickets to create CSC Tasks by program to the correct worker ID | 315 | LRS M&E | Enhancement |  | In Production | 18.07 |  | Batch/Interfaces | 3-Normal/Low | 2018-01-19 11:46 | 2018-07-22 16:07 | Approved |  |  | IVR & Contact Center |  |  | Done
CA-202572 | funding: ACL16-77 - YourBenefitsNow YBN Application process and CW RE to track testing and deployment | 305 | LRS M&E | Policy Re-Design |  | System Test | 18.09 |  | Training | 3-Normal/Low | 2018-05-08 14:10 |  | Approved |  |  | C4Yourself
CA-51489 | <R&A> Add to DPSS & SFV Mobile/Internal apps to allow document upload feature. | 304 | R&A - Fixed | Enhancement |  | In Production | 18.07 |  | Online | 3-Normal/Low | 2018-01-19 11:45 | 2018-07-22 16:07 | Approved |  | CA-201700 | C4Yourself | Lobby Management |  | Done
CA-201789 | YBN CF 37 in All Threshold Languages | 260 | LRS M&E | Enhancement |  | In Production | 18.07 |  | System Test |  | 2018-03-29 18:28 | 2018-07-22 16:07 | Approved |  | CA-201180 | Other |  |  | Done
CA-202093 | Update Recon transactions to include the MBI | 255 | LRS M&E | New Policy |  | In Production | 18.06 | 18.06.17 | Batch/Interfaces |  | 2018-04-13 10:10 | 2018-06-18 20:35 | Approved |  | CIV-100988 | MEDS |  |  | Done
CA-201687 | Funding - Changes in WTW/REP Activity Report (WAR) Report | 253 | LRS M&E | Enhancement |  | In Production | 18.06 | 18.07.05 | Reports | 1-High/Non-Cosmetic | 2018-03-22 16:00 | 2018-07-15 16:41 | Approved |  | CIV-100722, CA-200374 |  |  |  | Done
CA-52406 | < ITGC > ACL 14-65 - Add WTW 43 and CW 2186A in Threshold Languages | 225 | LRS M&E | New Policy |  | In Production | 18.07 |  | Client Correspondence | 3-Normal/Low | 2018-01-19 11:44 | 2018-07-22 16:07 | Approved |  |  | Correspondence |  |  | Done
CA-201698 | Modify General Relief Work Registration Status of Employable/ Unemployable Tracking to Daily from Monthly | 224 | LRS M&E | Enhancement |  | In Production | 18.07 |  | Eligibility | 3-Normal/Low | 2018-03-23 13:10 | 2018-07-22 16:07 | Approved |  | CA-54711 | CalWORKs/CalFresh |  |  | Done
CA-201181 | Training Updates - Training (DPSS) Updates - Master Assignment Queue (MAQ) Prioritization (WBTs) | 210 | LRS M&E | Enhancement |  | In Production | 18.07 |  | Training |  | 2018-03-05 15:04 | 2018-07-22 16:07 | Approved | [5 empty] | Done
CA-201073 | ServiceNow - Tier 2 Reports and Transition to ServiceNow | 200 | LRS M&E | Operational Enhancement |  | System Test | 18.07 | TBD | Tech Ops |  | 2018-02-27 13:04 |  | Approved
CA-201258 | DDCR 3005: Add an Unverified E-Notification Request Report to the LRS System | 180 | LRS M&E | New Policy |  | System Test | 18.09 |  | Reports |  | 2018-03-07 15:28 |  | Approved |  | CIV-986 | Management Reports
CA-49840 | ACL 14-37 - CalFresh Replacement Benefits Status Reasons and Revised Form | 175 | LRS M&E | Policy Re-Design |  | Test Complete | 18.09 |  | Fiscal | 3-Normal/Low | 2018-01-19 11:47 |  | Approved |  |  | Fiscal |  |  | Done
CA-200738 | Updates to EBT Card Print List page and Reports | 160 | LRS M&E | Enhancement |  | In Production | 18.07 |  | Fiscal |  | 2018-02-08 11:16 | 2018-07-22 16:07 | Approved |  | CIV-1766 | Fiscal |  |  | Done
CA-48359 | <R&A> Enhancements to EBT Repayment Reports, Issuance Exception and Skipped Issuance Reports | 145 | R&A - Fixed | Enhancement |  | In Production | 18.07 |  | Fiscal | 3-Normal/Low | 2018-01-19 11:45 | 2018-07-22 16:07 | Approved |  | CIV-100543, CA-201703 | State/Fiscal Reports |  |  | Done
CA-201697 | Funding - Changes in CW/RCA Adults by WTW Category (Global) Report | 131 | LRS M&E | Enhancement |  | In Production | 18.06 | 18.07.05 | Reports | 1-High/Non-Cosmetic | 2018-03-23 12:19 | 2018-07-15 16:38 | Approved |  | CIV-100723, CA-200371 |  |  |  | Done
CA-203707 | Training Updates - Resource Databank Assessment Results (WBTs) | 130 | LRS M&E | Enhancement |  | System Test | 18.09 |  | Training |  | 2018-07-24 15:47 |  | Approved
CA-201702 | Child Welfare Trust Changes | 120 | LRS M&E | Enhancement |  | In Production | 18.07 |  | Fiscal | 3-Normal/Low | 2018-03-23 13:53 | 2018-07-22 16:07 | Approved |  | CA-49832 | Fiscal |  |  | Done
CA-201700 | Add to DPSS & SFV Mobile/Internal apps to allow document upload feature. | 102 | LRS M&E | Enhancement |  | In Production | 18.07 |  | Online | 3-Normal/Low | 2018-03-23 13:28 | 2018-07-22 16:07 | Approved |  | CA-51489 | C4Yourself |  |  | Done
CA-50296 | < ITGC > ACL 14-59 - Revision of GN6006B form (version 03/23/2015) | 100 | LRS M&E | New Policy |  | In Production | 18.07 |  | Client Correspondence | 3-Normal/Low | 2018-01-19 11:46 | 2018-07-22 16:07 | Approved |  |  | Correspondence |  |  | Done
CA-203160 | Support for DPSS Priority Focus Areas | 100 | LRS M&E | Operational Enhancement |  | Approved | 18.09 |  | Training |  | 2018-06-14 15:06 |  | Approved
CA-200324 | DDCR 4075: Update Exception Handling framework to log request details | 85 | LRS M&E | Enhancement |  | In Production | 18.07 |  | Tech Arch | 2-Normal/Medium | 2018-01-25 07:29 | 2018-07-22 16:07 | Approved |  | C-IV SCR 4267 |  |  |  | Done
CA-201075 | Display Edit Button on Transaction Detail Page | 80 | LRS M&E | Enhancement |  | In Production | 18.07 |  | Fiscal |  | 2018-02-27 13:42 | 2018-07-22 16:07 | Approved |  | C-IV SCR 6522 | Collections |  |  | Done
CA-200329 | DDCR 4084: Update online SQL query execution framework to log query details | 80 | LRS M&E | Enhancement |  | In Production | 18.07 |  | Tech Arch | 2-Normal/Medium | 2018-01-25 07:42 | 2018-07-22 16:07 | Approved |  | C-IV SCR 5230 |  |  |  | Done
CA-200637 | DDCR 3135: Update Batch EDBC to skip cases when a person is closed on MC Program and the RE DER is MAGI Conditionally Eligible | 75 | LRS M&E | Policy Re-Design |  | Test Complete | 18.09 |  | Batch/Interfaces |  | 2018-02-05 13:45 |  | Approved |  | CIV 55876 | Medi-Cal/CMSP |  |  | Done
CA-201703 | Enhancements to EBT Repayment Reports, Issuance Exception and Skipped Issuance Reports | 60 | LRS M&E | Enhancement |  | In Production | 18.07 |  | Fiscal | 3-Normal/Low | 2018-03-23 13:59 | 2018-07-22 16:07 | Approved |  | CIV-100543, CA-48359 | State/Fiscal Reports |  |  | Done
CA-202505 | Training Updates - ARC/FC Payments to Caretaker Prior to Home Approval (JAs) | 60 | LRS M&E | Enhancement |  | In Production | 18.07 |  | Training |  | 2018-05-03 14:36 | 2018-07-23 17:08 | Approved | [5 empty] | Done
CA-200776 | Phase VIII - Information Only Request - Turn ON - Threshold Language NOAs - English versions are already in production | 60 | Other | New Policy |  | In Production | 18.07 |  | Client Correspondence |  | 2018-02-09 15:17 | 2018-07-22 16:07 | Approved |  |  | Correspondence |  |  | Done
CA-200718 | Add Additional Foster Care Placement Types to the CA 237 FC Report | 60 | LRS M&E | Enhancement |  | In Production | 18.07 |  | Reports |  | 2018-02-07 16:26 | 2018-07-22 16:07 | Approved |  | CIV-933 | Fiscal | Foster Care/Kin GAP/AAP | State/Fiscal Reports | Done
CA-58824 | DDCR 3118: CalACES - Update Homeless Assistance Temporary (HT) and Homeless Assistance Permanent (HP) Benefits - Aid Code 35 to Count TANF Time Limit Clock | 55 | LRS M&E | Policy Re-Design |  | System Test | 18.09 |  | Lobby Mgmt | 3-Normal/Low | 2018-01-19 11:41 |  | Approved |  | C-IV SCR 55552 | Time Limits
CA-202519 | Training Updates - ARC/FC Payments to Caretaker Prior to Home Approval (WBTs) | 45 | LRS M&E | Enhancement |  | Test Complete | 18.09 |  | Training |  | 2018-05-03 15:50 |  | Approved | [5 empty] | Done
CA-59330 | Implementation of C-IV SCR 12433 - Adding new a new security right for the Special Investigations Note page flow | 40 | LRS M&E | Enhancement |  | In Production | 18.07 |  | Online | 3-Normal/Low | 2018-01-19 11:42 | 2018-07-22 16:07 | Approved |  | CIV-12433 | Fraud | Security | Security Usability | Done
CA-203676 | Training QA of Job Aids Impacted by SCR CA-51741 | 36 | LRS M&E | Enhancement |  | Test Complete | 18.09 |  | Training |  | 2018-07-23 11:30 |  | Approved | [5 empty] | Done
CA-203840 | Training QA of Job Aids Impacted by SCR CA-49401 | 22 | LRS M&E | Enhancement |  | Test Complete | 18.09 |  | Training |  | 2018-08-02 10:07 |  | Approved | [5 empty] | Done
CA-59010 | Turn off default search execution for eApp search page | 20 | LRS M&E | Enhancement |  | In Production | 18.07 |  | Online | 3-Normal/Low | 2018-01-19 11:42 | 2018-07-22 16:07 | Approved |  |  | C4Yourself |  |  | Done
CA-202500 | Training Updates - Phase II - ACL 17-34 - Add Elderly Simplified Application Project (ESAP) Indicator and Automate CF 377.2D (JAs) | 19 | LRS M&E | Enhancement |  | In Production | 18.07 |  | Training |  | 2018-05-03 14:05 | 2018-07-22 16:07 | Approved | [5 empty] | Done
CA-201200 | Training Updates - GR Policy 42-200 - Add Property Logic to LRS for GR Program (WBTs) | 15 | LRS M&E | Policy Re-Design |  | Test Complete | 18.09 |  | Training |  | 2018-03-05 17:34 |  | Approved | [5 empty] | Done
CA-49030 | Replace the PA 2012 (01/13) with Revised PA 2012 (07/15) Form | 15 | LRS M&E | Enhancement |  | Test Complete | 18.09 |  | Client Correspondence | 3-Normal/Low | 2018-01-19 11:45 |  | Approved |  |  | Correspondence |  |  | Done
CA-203843 | Training QA of Job Aids Impacted by SCR CA-201075 | 14 | LRS M&E | Enhancement |  | Test Complete | 18.09 |  | Training |  | 2018-08-02 10:10 |  | Approved | [5 empty] | Done
CA-201003 | Remove Duplicate 'Mandatory/Optional Rules' Role Reasons for CalWORKs EDBC Override | 10 | LRS M&E | Enhancement |  | In Production | 18.07 |  | Eligibility |  | 2018-02-22 13:42 | 2018-07-22 16:07 | Approved |  | CIV-75 | CalWORKs/CalFresh |  |  | Done
CA-203844 | Training QA of Job Aids Impacted by SCR CA-56221 | 10 | LRS M&E | Enhancement |  | Test Complete | 18.09 |  | Training |  | 2018-08-02 10:12 |  | Approved | [5 empty] | Done
CA-55375 | eICT: Update the E-ICT option for Source of the Application to ICT | 10 | LRS M&E | Enhancement |  | Test Complete | 18.09 |  | Online | 3-Normal/Low | 2018-01-19 11:43 |  | Approved |  | CIV-6871 | ICT |  |  | Done
CA-203842 | Training QA of Job Aids Impacted by SCR CA-48753 | 9 | LRS M&E | Enhancement |  | Test Complete | 18.09 |  | Training |  | 2018-08-02 10:09 |  | Approved | [5 empty] | Done
CA-202647 | Training Release 18.06 - Online Help (OLH) |  | LRS M&O | Enhancement |  | In Production | 18.06 |  | Training | 3-Normal/Low | 2018-05-14 09:56 | 2018-06-03 16:55 | Approved | [5 empty] | Done
CA-203490 | SB 1341 Phase II - Maintenance |  | Premise | Operational Enhancement |  | In Production | 18.07 |  | Batch/Production Operations |  | 2018-07-09 10:10 | 2018-08-08 21:09 | Approved | [5 empty] | Done
CA-202649 | Training Release 18.07 - Online Help (OLH) Updates |  | LRS M&O | Enhancement |  | In Production | 18.07 |  | Training | 3-Normal/Low | 2018-05-14 10:15 | 2018-07-22 16:07 | Approved | [5 empty] | Done
CA-202648 | Training Release 18.07 - LMS Lite updates |  | LRS M&E | Enhancement |  | In Production | 18.07 |  | Training | 3-Normal/Low | 2018-05-14 10:08 | 2018-07-23 19:31 | Approved | [5 empty] | Done
CA-203675 | Training Release 18.09 - Online Help (OLH) Updates |  | LRS M&O | Enhancement |  | In Assembly Test | 18.09 |  | Training | 3-Normal/Low | 2018-07-23 09:54 | 2018-07-22 16:07 | Approved