## C-IV Change Management 2018-09-
SCR | Summary | Estimate | Funding Source | Change Type (SCR) | SPG Rating | Status | Fix Version/s | Minor Version | Team Responsible | Priority | Created | In Production | SPG Status | SPG Score | Other Agency Cross Reference | Funding Source ID
CIV-10162 | MEDIL 17-09: Updated MAGI and Deductions Types Chart |  | Premise | New Policy | Low | Pending Rejection | TBD |  | CalHEERS | Medium | 2017-12-29 14:26 |  | Approved | 21 |  | CO-103
CIV-101748 | Reload WPR file | 10 | C-IV M&O | Operational Enhancement | Medium | In Production | 18.06 | 18.07.20 | Batch/Interfaces |  | 2018-07-16 13:00 | 2018-07-23 20:24 | Approved
CIV-101729 | DCR EBT Issuances from Submission Error to Issued status | 15 | C-IV M&O | Data Change | Medium | In Production | 18.06 | 18.07.17 | Fiscal |  | 2018-07-11 14:40 | 2018-07-18 00:10 | Approved
CIV-101706 | DCR Daily issuances for Monterey and Merced | 15 | C-IV M&O | Data Change | Medium | In Production | 18.06 | 18.07.10 | Fiscal |  | 2018-07-09 14:56 | 2018-07-11 00:53 | Approved
CIV-101661 | A data change to deny a pending event. |  | C-IV M&O | Individual Data Change | Medium | In Production | 18.06 | 18.07.11 | Online |  | 2018-06-29 10:32 | 2018-07-12 01:16 | Approved
CIV-101610 | DCR EBT WINS issuances to 'Issued' status | 15 | C-IV M&O | Data Change | Medium | In Production | 18.06 | 18.06.26 | Fiscal |  | 2018-06-25 15:43 | 2018-06-27 01:06 | Approved
CIV-101583 | Data Change : Unable to Deny pending app |  | C-IV M&O | Individual Data Change | Medium | In Production | 18.06 | 18.07.11 | Online |  | 2018-06-21 16:18 | 2018-07-12 01:16 | Approved
CIV-101561 | ACL 18-66 - Identify Cases with an Income-In-Kind that Matches the Standard Amount | 15 | C-IV M&O | New Policy | Medium | In Production | 18.06 | 18.07.18 | Eligibility |  | 2018-06-19 18:38 | 2018-07-18 22:18 | Approved |  | CA-203230
CIV-101549 | Remove Incorrect Voice Print | 5 | County Purchase | Individual Data Change | Medium | In Production | 18.06 | 18.06.26 | Contact Center |  | 2018-06-19 09:59 | 2018-06-27 01:06 | Approved |  |  | CSC Support
CIV-101528 | Update Mariposa IP address for outbound ftp transfers | 5 | C-IV M&O | Operational Enhancement | Medium | In Production | 18.06 | 18.06.15 | Batch/Interfaces |  | 2018-06-15 09:38 | 2018-06-21 16:52 | Approved
CIV-101457 | Unable to close the latest(5/18/2018) MC application and rescind the previous(4/10/2017) MC application |  | Change Order | Individual Data Change | Medium | In Production | 18.06 | 18.06.20 | CalHEERS |  | 2018-06-07 15:15 | 2018-06-21 19:50 | Approved |  |  | CO-103
CIV-101436 | Data Change : Unable to Deny pending months | 5 | C-IV M&O | Individual Data Change | Medium | In Production | 18.06 | 18.07.11 | Online |  | 2018-06-05 10:29 | 2018-07-12 01:16 | Approved
CIV-101404 | ACL 18-66 - Batch EDBC for Cost of Living Adjustment (COLA) for Income In-Kind (IIK) for 2018-2019 | 55 | C-IV M&O | New Policy | Medium | In Production | 18.06 | 18.06.15 | Eligibility |  | 2018-05-31 09:02 | 2018-06-18 21:03 | Approved |  | CA-202875
CIV-101373 | Data Change: Deny pending application |  | C-IV M&O | Individual Data Change | Medium | In Production | 18.06 | 18.07.11 | Online |  | 2018-05-25 10:18 | 2018-07-12 01:16 | Approved
CIV-101355 | Remove Incorrect Voice Print |  | County Purchase | Individual Data Change | Medium | In Production | 18.06 | 18.06.08 | Contact Center |  | 2018-05-24 10:07 | 2018-06-09 00:33 | Approved |  |  | CSC Support
CIV-101347 | Remove Incorrect Voice Print |  | County Purchase | Individual Data Change | Medium | In Production | 18.06 | 18.06.05 | Contact Center |  | 2018-05-23 15:33 | 2018-06-06 01:43 | Approved |  |  | CSC Support
CIV-101325 | Data Change: Modify BDA due to go live validation |  | C-IV M&O | Individual Data Change | Medium | In Production | 18.06 | 18.07.13 | Online |  | 2018-05-22 09:33 | 2018-07-14 00:37 | Approved
CIV-101275 | C4Y: Update Message on EBT Outage and Link to TEMP 2233 to C4Y | 10 | C-IV M&O | New Policy | High | In Production | 18.06 | 18.06.07 | Online |  | 2018-05-15 13:32 | 2018-06-08 00:31 | Approved
CIV-101197 | Incorrect BDA for Medi-Cal |  | C-IV M&O | Individual Data Change | Medium | In Production | 18.06 | 18.06.27 | Online |  | 2018-05-08 09:39 | 2018-06-28 00:38 | Approved
CIV-101188 | Update logic to process EBT End of Day files with timestamps | 100 | C-IV M&O | Enhancement | High | In Production | 18.06 | 18.06.24 | Fiscal |  | 2018-05-04 11:51 | 2018-06-25 03:45 | Approved
CIV-101183 | Add Voice Authentication to Non CSC counties IVR | 135 | C-IV M&O | Enhancement |  | In Production | 18.06 | 18.06.07 | Contact Center |  | 2018-05-03 14:57 | 2018-06-12 15:45 | Approved
CIV-101095 | Data Change: Remove Incorrect FC RE period |  | C-IV M&O | Individual Data Change | Medium | In Production | 18.06 | 18.06.14 | Eligibility |  | 2018-04-25 09:14 | 2018-06-15 00:20 | Approved
CIV-101039 | Unable to Deny Pending Program |  | C-IV M&O | Individual Data Change | Medium | In Production | 18.06 | 18.07.17 | Online |  | 2018-04-18 18:12 | 2018-07-18 00:18 | Approved
CIV-100988 | CO-103: MEDS: Update Recon transactions to include the MBI | 230 | Change Order | New Policy | Medium | In Production | 18.06 | 18.06.21 | Batch/Interfaces |  | 2018-04-13 10:09 | 2018-06-22 04:39 | Approved |  | CA-202093 | CO-103
CIV-100908 | C4Y Mobile App: Send Notification that EBT will be Unavailable | 25 | C-IV M&O | New Policy | Medium | In Production | 18.06 | 18.06.21 | Online |  | 2018-04-05 09:55 | 2018-06-22 04:39 | Approved
CIV-100840 | Update Sutter County Rush Warrant Stock | 50 | C-IV M&O | Operational Enhancement | High | In Production | 18.06 | 18.06.21 | Client Correspondence |  | 2018-03-28 13:13 | 2018-06-22 04:39 | Approved |  | Sutter
CIV-100828 | County Funded: Riverside County opt-in to General Assistance (Managed) | 80 | County Purchase | Enhancement | High | In Production | 18.06 | 18.06.27 | Fiscal |  | 2018-03-27 11:47 | 2018-06-28 00:38 | Approved |  | Riverside | GA-GR
CIV-100683 | Data Change: Disposition Pending Applications for Child Care |  | C-IV M&O | Individual Data Change | Medium | In Production | 18.06 | 18.06.07 | Online |  | 2018-03-13 11:37 | 2018-06-08 00:32 | Approved
CIV-100633 | Update ILTs for 18.05 Code - July Training Release | 60 | C-IV M&O | New Policy | Medium | In Production | 18.06 | 18.07.16 | Training | Medium | 2018-03-08 11:33 | 2018-08-08 23:06 | Approved |  | None
CIV-100439 | ACL 18-66 - Cost of Living Adjustment (COLA) for Minimum Basic Standard of Adequate Care (MBSAC) and Income In-Kind (IIK) for 2018-2019 | 25 | C-IV M&O | New Policy | High | In Production | 18.06 | 18.06.14 | Eligibility |  | 2018-02-13 08:49 | 2018-06-15 00:19 | Approved |  | CA-54427
CIV-100284 | Design: Build Cross Project Automation Scripts (CalHEERS) | 115 | Premise | Enhancement | High | In Production | 18.06 |  | System Test | Medium | 2018-01-30 11:52 | 2018-06-04 05:46 | Approved |  |  | CO-068
CIV-100194 | E2Lite: Turn off E2Lite Batch jobs for El Dorado County | 10 | C-IV M&O | Operational Enhancement | Medium | In Production | 18.06 | 18.06.13 | Batch/Interfaces | Low | 2018-01-19 10:24 | 2018-06-21 16:53 | Approved
CIV-100112 | Implement Nuance Voice Biometrics - San Bernardino | 240 | C-IV M&O | Enhancement | Critical | In Production | 18.06 | 18.06.28 | Contact Center | Medium | 2018-01-10 16:07 | 2018-06-29 00:42 | Approved
CIV-100038 | Case showing on pending app report | 1 | C-IV M&O | Individual Data Change | Medium | In Production | 18.06 | 18.07.16 | Online | Low | 2018-01-03 17:06 | 2018-07-18 00:17 | Approved
CIV-12173 | Suppress MAGI Determinations which represent No Change | 210 | Premise | Data Change |  | In Production | 18.06 | 18.06.21 | CalHEERS | High | 2017-12-29 14:26 | 2018-06-22 04:39 | Approved |  | CA-58749. This change is a result of a CalHEERS Defect introduced by CalHEERS CR 82949. | CO-103
CIV-10567 | Westat SNAP Barriers Study | 100 | C-IV M&O | New Policy |  | In Production | 18.06 | 18.06.22 | Eligibility | Critical | 2017-12-29 14:26 | 2018-06-25 21:54 | Approved |  | None
CIV-12029 | ACWDL 18-01: Add Eligibility Evaluation Reasons from CalHEERS to trigger MAGI Denial/Discontinuance Notices | 645 | Premise | New Policy | Critical | In Production | 18.06 |  | CalHEERS | High | 2017-12-29 14:26 | 2018-06-03 13:29 | Approved |  | CH-87156, CA-55295 | CO-068
CIV-11727 | CO-097: Enable new Electronic Benefit Transfer (EBT) Vendor Fidelity Information Services (FIS) | 185 | Premise | New Policy | Critical | In Production | 18.06 | 18.06.24 | Fiscal | Critical | 2017-12-29 14:26 | 2018-06-25 03:45 | Approved |  | LRS SCR CA-59270 | CO-097
CIV-10102 | ACWDL 17-22: 2017/2018 Family Member Base Allocation Amount | 40 | C-IV M&O | New Policy | High | In Production | 18.06 |  | CalHEERS | Medium | 2017-12-29 14:25 | 2018-06-03 13:29 | Approved |  | CA-55686
CIV-8677 | ACWDL 17-28 and 17-29: Inmate MC Aid Codes | 105 | Change Order | New Policy | Critical | In Production | 18.06 |  | CalHEERS | Medium | 2017-12-29 14:25 | 2018-06-03 13:29 | Approved |  | CA-58841 | CO-068
CIV-7123 | Migrate Batch Scheduler from CA Unicenter JMO to BICsuite | 670 | C-IV M&O | Operational Enhancement | High | In Production | 18.06 | 18.06.16 | Batch/Interfaces | Medium | 2017-12-29 14:25 | 2018-06-18 21:09 | Approved |  | None
CIV-11703 | CO-096 Upgrade the C4Y to ODI version 12.1.2 | 660 | Premise | Enhancement | Medium | In Production | 18.06 | 18.07.13 | Reports | Medium | 2017-12-29 14:26 | 2018-07-14 01:06 | Approved |  | LRS SIR 56375 | CO-096
CIV-101870 | Lobby Mgmt: RV-01-2018 & MR-01-2018 - Add lobby Kiosk records for new hardware for Riverside and Merced County | 50 | County Purchase | Operational Enhancement | Medium | In Production | 18.07 | 18.08.17 | Online |  | 2018-08-01 14:30 | 2018-08-18 00:10 | Approved |  | None | RV-01-2018 & MR-01-2018
CIV-101782 | ACWDL 17-40: Generate list of LTC programs to identify cases that may qualify for a lower share-of-cost | 15 | C-IV M&O | New Policy | High | In Production | 18.07 | 18.07.24 | CalHEERS |  | 2018-07-18 18:38 | 2018-07-24 19:24 | Approved |  | CA-203649
CIV-101774 | Update GEN 2000 - Passport to Services (Gross Income Calculation/Population) | 70 | C-IV M&O | Enhancement | High | In Production | 18.07 | 18.08.17 | Client Correspondence |  | 2018-07-18 14:00 | 2018-08-18 04:56 | Approved |  | N/A
CIV-101715 | Initial List Prior to Implementation of SCR 503 | 15 | C-IV M&O | Operational Enhancement | Critical | In Production | 18.07 | 18.07.23 | Eligibility |  | 2018-07-10 16:57 | 2018-07-23 20:25 | Approved |  | CA-203536
CIV-101673 | SIRFRA 3101 - SNAP Application Data Request - January-March 2018 | 40 | C-IV M&O | New Policy | High | In Production | 18.07 | 18.08.01 | Eligibility | Medium | 2018-07-02 11:03 | 2018-08-13 21:26 | Approved
CIV-101666 | Data Change - Case showing on pending application report | 5 | C-IV M&O | Individual Data Change | Medium | In Production | 18.07 | 18.08.07 | Online |  | 2018-06-29 16:50 | 2018-08-08 00:32 | Approved
CIV-101531 | Update Monterey County AAP Issuance Threshold | 20 | C-IV M&O | Enhancement | Medium | In Production | 18.07 |  | Fiscal |  | 2018-06-15 10:25 | 2018-07-22 15:48 | Approved |  | CA-201453
CIV-101516 | ACL 18-75: Phase II - Funding for Emergency Caregivers with Placements of Children prior to RFA Approval | 115 | C-IV M&O | New Policy | High | In Production | 18.07 | 18.08.17 | Eligibility |  | 2018-06-14 12:20 | 2018-08-18 00:09 | Approved |  | CA-203207
CIV-101407 | Add C-IV Functional Presentation for SCR 100436 - eICT RE Date Alignment - to Online Help | 35 | C-IV M&O | Enhancement |  | In Production | 18.07 |  | Training |  | 2018-05-31 13:57 | 2018-07-22 16:20 | Approved
CIV-101350 | Del Norte County Only: Update Warrants from Cancelled (Staledate) Status to Paid Status | 25 | C-IV M&O | Data Change | Medium | In Production | 18.07 |  | Fiscal |  | 2018-05-23 16:11 | 2018-07-22 15:55 | Approved
CIV-101186 | Data Change : Recreate Program and Person statuses for PN01 after IHSS linking. |  | C-IV M&O | Individual Data Change | Medium | In Production | 18.07 | 18.08.16 | Online |  | 2018-05-04 09:45 | 2018-08-17 00:17 | Approved
CIV-101160 | Data Change : Recreate Program statuses for PN09 after IHSS linking. |  | C-IV M&O | Individual Data Change | Medium | In Production | 18.07 | 18.08.16 | Online |  | 2018-05-02 10:30 | 2018-08-17 00:17 | Approved
CIV-101132 | Convert C-IV Baseline Automated Regression Test Scripts | 360 | C-IV M&O | Enhancement |  | In Development | 18.07 | 18.09.XX | System Test |  | 2018-04-30 12:25 |  | Approved
CIV-101070 | Online Help - Add Text Notification Report to Reports Overview | 5 | C-IV M&O | Enhancement | Medium | In Production | 18.07 |  | Training |  | 2018-04-23 09:57 | 2018-07-22 16:20 | Approved
CIV-101034 | Update Riverside County Rush Warrant Print and Positive Pay file | 120 | C-IV M&O | Operational Enhancement | Critical | In Production | 18.07 |  | Client Correspondence |  | 2018-04-18 14:34 | 2018-07-23 19:47 | Approved |  | CCM-180
CIV-100990 | Remove C-IV Functional Presentations from Online Help | 5 | C-IV M&O | Policy Re-Design | Medium | In Production | 18.07 |  | Training |  | 2018-04-13 10:37 | 2018-07-23 19:47 | Approved
CIV-100959 | Update Online Help for SCR 100645 ARC/FC Payments to Caretaker Prior to Home Approval | 5 | C-IV M&O | New Policy | Medium | In Production | 18.07 |  | Training |  | 2018-04-10 16:17 | 2018-07-23 19:47 | Approved
CIV-100775 | Allow Ad Hoc Administrators to Connect Directly to APEXDB | 100 | C-IV M&O | Operational Enhancement | Medium | In Production | 18.07 |  | DBA |  | 2018-03-22 07:55 | 2018-07-23 15:33 | Approved
CIV-100710 | Customer Reporting Updates | 45 | C-IV M&O | Enhancement | Low | In Production | 18.07 |  | Online |  | 2018-03-14 18:27 | 2018-07-23 19:47 | Approved |  | CA-52723
CIV-100691 | Add Program Start Date to Riverside County Clothing Allowance Batch job | 100 | C-IV M&O | Policy Re-Design | Medium | In Production | 18.07 |  | Fiscal |  | 2018-03-13 15:28 | 2018-07-22 15:53 | Approved
CIV-100685 | Update the Subscription Based Reports Job Aid | 5 | C-IV M&O | Enhancement | Medium | In Production | 18.07 |  | Training |  | 2018-03-13 11:53 | 2018-07-23 19:47 | Approved
CIV-100598 | Design: Enhance SQL Execution framework to capture long running SQL details | 320 | C-IV M&O | Enhancement | Medium | In Production | 18.07 |  | Performance |  | 2018-03-02 12:54 | 2018-07-23 19:47 | Approved
CIV-100543 | Enhancements to EBT Repayment Reports, Issuance Exception and Skipped Issuance Reports | 115 | C-IV M&O | Enhancement | High | In Production | 18.07 |  | Reports |  | 2018-02-26 12:46 | 2018-07-23 19:48 | Approved |  | CA-48359
CIV-100467 | Remove Automated Action: CalWORKs Child: Age 6, 16 or 17 Verify School Attendance | 15 | C-IV M&O | Enhancement | Medium | In Production | 18.07 |  | Batch/Interfaces |  | 2018-02-14 14:31 | 2018-07-22 15:50 | Approved
CIV-100436 | ACL 17-58 - Electronic Inter-County Transfer (eICT) - Redetermination (RE) Date Alignment | 605 | C-IV M&O | New Policy | Medium | In Production | 18.07 |  | Eligibility |  | 2018-02-12 15:57 | 2018-07-22 15:55 | Approved |  | CA-49401
CIV-100365 | Upgrade Cisco Unified Communications Manager 9.1 to version 10.5(2) | 60 | C-IV M&O | Operational Enhancement | Medium | In Production | 18.07 | 18.08.05 | Contact Center | Medium | 2018-02-02 16:22 | 2018-08-06 17:16 | Approved
CIV-100272 | ACWDL 17-40: 2018 Medicare Catastrophic Coverage Act Spousal Impoverishment Caps | 35 | Premise | New Policy | Critical | In Production | 18.07 |  | CalHEERS | Medium | 2018-01-29 15:21 | 2018-07-22 15:48 | Approved |  | CA-58593 | CO-103
CIV-12441 | Task Cleanup Request CRFI 17-016 | 40 | C-IV M&O | Data Change | Medium | In Production | 18.07 |  | Online | Medium | 2017-12-29 14:26 | 2018-07-22 15:53 | Approved |  | None
CIV-10668 | ACWDL 14-18: Batch Non-MAGI forms to MAGI Customer Turning 65 | 265 | Premise | Policy Re-Design | Medium | In Production | 18.07 |  | Client Correspondence | Medium | 2017-12-29 14:26 | 2018-07-22 15:55 | Approved |  | CA-203981 | CO-103
CIV-12270 | Remove Voice Prints | 150 | C-IV M&O | Enhancement | High | In Production | 18.07 |  | Online | Critical | 2017-12-29 14:26 | 2018-07-22 15:50 | Approved |  | CA-203995
CIV-12413 | Phase II - ACL 17-34 - Add Elderly Simplified Application Project (ESAP) Indicator and Automate CF 377.2D | 470 | C-IV M&O | New Policy | Low | In Production | 18.07 |  | Eligibility | Medium | 2017-12-29 14:26 | 2018-07-22 15:48 | Approved |  | CA-54952
CIV-10299 | C4Y: Create C4Yourself indicator in C-IV and display C-IV case number(s) in C4Yourself | 230 | C-IV M&O | Enhancement | Medium | In Production | 18.07 |  | Online | Medium | 2017-12-29 14:26 | 2018-07-23 19:48 | Approved |  | LRS SCR CA-201096
CIV-12524 | Update Individual Demographics Detail and Citizenship Status Detail with Republic of Palau | 25 | C-IV M&O | Operational Enhancement | Medium | In Production | 18.07 |  | Online | Low | 2017-12-29 14:26 | 2018-07-22 15:50 | Approved |  | CA-54717
CIV-11156 | San Bernardino Only: Change Accounting String for WTW TCVAP Fund Code V3 | 15 | C-IV M&O | Data Change | Medium | In Production | 18.07 |  | Fiscal | Medium | 2017-12-29 14:26 | 2018-07-22 15:50 | Approved |  | None
CIV-11950 | Lobby Management: Create "Hover" Feature on Reception Log List & Detail Pages | 60 | Premise | Enhancement | High | In Production | 18.07 |  | Online | Medium | 2017-12-29 14:26 | 2018-07-22 15:55 | Approved |  | LRS SCR 33690 | CO-070
CIV-12433 | Special Investigations Note Task Nav not visible to users that are assigned both Special Investigations and Hearings project security roles | 40 | C-IV M&O | Enhancement | Medium | In Production | 18.07 |  | Online | Medium | 2017-12-29 14:26 | 2018-07-22 15:55 | Approved |  | CA-59330
CIV-10914 | Synchronize WIS and C-IV Tax Intercept Balances 2018 | 90 | C-IV M&O | Enhancement | Medium | In Production | 18.07 | 18.07.27 | Fiscal | Medium | 2017-12-29 14:26 | 2018-07-30 15:45 | Approved |  | None
CIV-10782 | San Benito CFET Auto Registration Opt In | 15 | C-IV M&O | Operational Enhancement | Medium | In Production | 18.07 |  | Online | Medium | 2017-12-29 14:26 | 2018-07-22 15:53 | Approved |  | None
CIV-11033 | MEDS: Move Foster Care and Kin Gap aid codes into a special segment | 45 | C-IV M&O | Policy Re-Design | High | In Production | 18.07 |  | Batch/Interfaces | Medium | 2017-12-29 14:26 | 2018-07-22 15:53 | Approved |  | LRS SIR 32820
CIV-12006 | Update the Office for San Bernardino's Generic Worker | 10 | C-IV M&O | Operational Enhancement | Medium | In Production | 18.07 |  | Online | Medium | 2017-12-29 14:26 | 2018-07-22 15:53 | Approved |  | None
CIV-8453 | Create a new interface to send EBT Fraud information to CDSS | 380 | C-IV M&O | Enhancement | High | In Production | 18.07 |  | Batch/Interfaces | Medium | 2017-12-29 14:26 | 2018-07-22 15:48 | Approved |  | CA-52216
CIV-10687 | C4Y: Update My Documents and SAR 7 Instructions pages | 90 | C-IV M&O | Enhancement | High | In Production | 18.07 |  | Online | Low | 2017-12-29 14:26 | 2018-07-23 19:48 | Approved |  | None
CIV-8905 | Update GEN 2000 - Passport to Services (IVR Request, Central Print, Post to C4Y) | 520 | C-IV M&O | Enhancement | Medium | In Production | 18.07 |  | Contact Center | Medium | 2017-12-29 14:25 | 2018-07-22 15:50 | Approved |  | None
CIV-9785 | Update Job Aids Related to Sunset of Express Lane Enrollment Program | 10 | C-IV M&O | New Policy | Medium | In Production | 18.07 |  | Training | Low | 2017-12-29 14:25 | 2018-07-23 19:48 | Approved |  | None
CIV-6522 | Display Edit Button on Transaction Detail Page | 125 | C-IV M&O | Enhancement | Medium | In Production | 18.07 |  | Fiscal | Low | 2017-12-29 14:25 | 2018-07-23 19:48 | Approved |  | LRS SCR 201075
CIV-7477 | Call Log: Update Case Number when in Case Context on Call Log | 45 | Premise | Enhancement | Medium | In Production | 18.07 |  | Online | Medium | 2017-12-29 14:25 | 2018-07-23 19:48 | Approved |  | CA-201972 | CO-070
CIV-4493 | Implement RS 51-Refugee Resettlement Program Caseload Movement Report | 340 | C-IV M&O | New Policy | High | In Production | 18.07 |  | Reports | Medium | 2017-12-29 14:24 | 2018-07-22 15:55 | Approved |  | CA-57726
CIV-1766 | Updates to EBT Card Print List page and Reports | 170 | C-IV M&O | Enhancement | High | In Production | 18.07 |  | Fiscal | Medium | 2017-12-29 14:24 | 2018-07-22 15:53 | Approved |  | CA-200738
CIV-467 | Update CalFresh School Attendance Employment Eligibility (44387) | 50 | C-IV M&O | Policy Re-Design | High | In Production | 18.07 |  | Eligibility | Medium | 2017-12-29 14:22 | 2018-07-23 19:48 | Approved |  | CA-200759
CIV-458 | ACL 03-20 - Count Income of Senior Parent not in CW Assistance Unit (44283) | 285 | C-IV M&O | Policy Re-Design | High | In Production | 18.07 |  | Eligibility | Medium | 2017-12-29 14:22 | 2018-07-22 15:50 | Approved |  | CA-56520
CIV-75 | Remove Duplicate 'Mandatory/Optional Rules' Role Reasons for CalWORKs EDBC Override (32606) | 10 | C-IV M&O | Enhancement | Medium | In Production | 18.07 |  | Eligibility | Low | 2017-12-29 14:21 | 2018-07-22 15:48 | Approved |  | SCR CA-201003
CIV-933 | Add new THP+FC and THPP placements for Foster Care | 225 | C-IV M&O | Policy Re-Design |  | In Production | 18.07 |  | Eligibility | Medium | 2017-12-29 14:24 | 2018-07-22 15:48 | Approved |  | CA-55596, CA-200718
CIV-101102 | AB 480: ACL 18-38 / CFL 17/18-57 Add Additional Diaper Benefit Functionality - Phase III | 85 | C-IV M&O | New Policy | High | In Production | 18.07 | 18.08.27 | Fiscal |  | 2018-04-25 10:40 | 2018-08-28 15:35 | Approved | 80 | CA-202319
CIV-101846 | Data Change: Update the Incorrect program and person detail history |  | C-IV M&O | Individual Data Change | Medium | In Production | 18.07 | 18.08.15 | Eligibility |  | 2018-07-30 15:56 | 2018-08-16 00:42 | Approved | TBD
CIV-101995 | Issue Disaster CalFresh Supplements to Maximum Allotment for Shasta County | 60 | C-IV M&O | Data Change | Critical | In Production | 18.07 | 18.08.21 | Fiscal |  | 2018-08-15 08:35 | 2018-08-22 02:46 | Approved | TBD
CIV-101906 | Activate Disaster CalFresh Services for Shasta County | 55 | C-IV M&O | Enhancement | Critical | In Production | 18.07 | 18.08.21 | Fiscal |  | 2018-08-07 11:58 | 2018-08-22 02:46 | Approved | TBD
CIV-102045 | Activate Disaster CalFresh Services for Lake County | 40 | C-IV M&O | Data Change |  | In Production | 18.07 | 18.08.21 | Fiscal |  | 2018-08-20 10:36 | 2018-08-22 02:46 | Approved
CIV-100437 | ACIN I-54-18 - 2018 CalFresh COLA | 100 | C-IV M&O | New Policy | Critical | Test Complete | 18.07 | 18.09.07 | Eligibility |  | 2018-02-12 16:58 |  | Approved | 86 | CA-56668
CIV-102042 | Send Push Notification and C4Yourself Messages to Shasta and Lake users receiving additional CalFresh benefits up to maximum allotment | 30 | C-IV M&O | Data Change | Critical | In Production | 18.07 | 18.08.22 | Online |  | 2018-08-20 09:31 | 2018-08-23 00:20 | Approved | TBD
CIV-101871 | Task Management: Assign to Program Worker Default (Manual Tasks) | 15 | C-IV M&O | Enhancement | High | In Production | 18.07 | 18.08.09 | Online |  | 2018-08-01 15:01 | 2018-08-10 04:55 | Approved | TBD
CIV-102009 | Create C4Yourself Announcement for Shasta County Disaster CalFresh | 10 | C-IV M&O | Data Change | High | In Production | 18.07 | 18.08.17 | Online |  | 2018-08-16 09:25 | 2018-08-18 00:10 | Approved | TBD
CIV-101903 | Mass Replacement CalFresh Benefits for Lake, Mendocino and Shasta Counties | 30 | C-IV M&O | Enhancement | Critical | In Production | 18.07 | 18.08.13 | Fiscal |  | 2018-08-07 09:14 | 2018-08-14 01:05 | Approved | TBD
CIV-101976 | Mass Replacement CalFresh Benefits for Riverside County | 15 | C-IV M&O | Enhancement | Critical | In Production | 18.07 | 18.08.16 | Fiscal |  | 2018-08-13 13:52 | 2018-08-17 00:17 | Approved | TBD
CIV-102002 | Create Push Notification for Mass-Replacement Disaster CalFresh Benefits | 30 | C-IV M&O | Data Change | High | In Production | 18.07 | 18.08.20 | Online |  | 2018-08-15 14:09 | 2018-08-21 00:39 | Approved | TBD
CIV-100305 | AB 480: ACL 18-38 / CFL 17/18-57 Add Additional Diaper Benefit Functionality - Phase II | 1650 | Premise | New Policy | Critical | In Production | 18.07 | 18.08.17 | Fiscal | Medium | 2018-01-31 10:36 | 2018-08-18 00:10 | Approved | N/A | CA-59192 | CO-102
CIV-101685 | ACL 18-89 Foster Care and Kin-GAP COLA Rate Increase - Batch EDBC | 85 | C-IV M&O | New Policy | Critical | In Development | 18.07 | 18.09.14 | Eligibility |  | 2018-07-05 10:21 |  | Approved | 80 | CA-203397
CIV-101892 | ACIN I-54-18 - 2018 CalFresh COLA Run Batch EDBC | 65 | C-IV M&O | New Policy | Critical | Test Complete | 18.07 | 18.09.07 | Eligibility |  | 2018-08-03 16:47 |  | Approved | TBD | CA-203887
CIV-101014 | Update Instructor Led Trainings (ILTs) for 18.07 Code - September Training Release | 60 | C-IV M&O | Enhancement | Medium | System Test | 18.07 | 18.09.17 | Training |  | 2018-04-17 14:28 |  | Approved | N/A
CIV-12218 | Lobby Mgmt: FACT enhancement to support multiple operating systems | 7500 | County Purchase | Enhancement |  | In Production | 18.07 | 18.08.26 | Tech Arch | Medium | 2017-12-29 14:26 | 2018-08-26 14:40 | Approved |  | None | CSC Support
CIV-9441 | ACL 18-89 Foster Care and Kin-GAP COLA Rate Increase | 80 | C-IV M&O | New Policy | Critical | In Development | 18.07 | 18.09.14 | Eligibility | Low | 2017-12-29 14:25 |  | Approved | 86 | CA-56670
CIV-101374 | ACL 18-82 - Elect Child Support Payment for Stepsibling or Half-Sibling in Lieu of Cash Aid - Phase 1 | 160 | Premise | New Policy | High | Development Complete | 18.07 | 18.09.14 | Client Correspondence | Medium | 2018-05-25 10:46 |  | Approved | N/A | CA-202806 | CO-106
CIV-101819 | Update Online Help for SCR 101374 ACL 18-82 - Elect Child Support Payment for Stepsibling or Half-Sibling in Lieu of Cash Aid - Phase 1 | 5 | Premise | New Policy | Critical | Test Complete | 18.09 |  | Training |  | 2018-07-25 11:23 |  | Approved |  |  | CO-106
CIV-101730 | Update Forms Overview for SCR 101645 - Add MC-007 | 5 | C-IV M&O | Policy Re-Design |  | Test Complete | 18.09 |  | Training |  | 2018-07-11 15:02 |  | Approved
CIV-101688 | Update Online Help and Job Aids for SCR 11439 Enhancement to Deemed Eligible Functionality | 15 | Premise | Policy Re-Design | Critical | Test Complete | 18.09 |  | Training |  | 2018-07-05 13:33 |  | Approved |  |  | CO 103
CIV-101689 | Upgrade Calabrio One version 9.5 to version 10.3 | 400 | County Purchase | Operational Enhancement | Medium | In Development | 18.09 | 18.10.12 | Contact Center |  | 2018-07-05 14:11 |  | Approved |  |  | CSC Support
CIV-101677 | Add Job Aid - Medi-Cal CalHEERS â€“ MAGI Re-Evaluation (RE) Process | 10 | C-IV M&O | Enhancement | Medium | Test Complete | 18.09 |  | Training |  | 2018-07-03 10:40 |  | Approved | Approved by Karen and Dorothy 7/9/2018
CIV-101629 | Add EBT Printer for Kings County 16PRINTAVE | 10 | C-IV M&O | Operational Enhancement | High | Test Complete | 18.09 |  | Fiscal |  | 2018-06-26 14:04 |  | Approved
CIV-101618 | Update Job Aids for SCR 100710 | 10 | C-IV M&O | Enhancement | Medium | Test Complete | 18.09 |  | Training |  | 2018-06-26 08:04 |  | Approved
CIV-101545 | Add new Pay Codes for GA (Managed) for Monterey and Riverside Counties | 55 | C-IV M&O | Enhancement | High | Test Complete | 18.09 |  | Fiscal |  | 2018-06-19 08:20 |  | Approved
CIV-101486 | MobileWebservice: Renew Apple Push Notification Certificate | 10 | C-IV M&O | Operational Enhancement | High | Test Complete | 18.09 |  | Tech Arch |  | 2018-06-12 10:59 |  | Approved
CIV-101479 | Update Job Aid and Online Help for SCR 100305 AB 480: ACL 18-38 / CFL 17/18-57 Add Additional Diaper Benefit Functionality | 15 | C-IV M&O | New Policy | Critical | Test Complete | 18.09 |  | Training |  | 2018-06-11 16:31 |  | Approved
CIV-101482 | Update Batch Sweeps Job Aid | 5 | C-IV M&O | Enhancement | Medium | Test Complete | 18.09 |  | Training |  | 2018-06-12 08:26 |  | Approved
CIV-101381 | Update Post Call Survey Application | 30 | County Purchase | Enhancement | Medium | Test Complete | 18.09 |  | Contact Center |  | 2018-05-29 08:43 |  | Approved |  |  | CSC Support
CIV-101163 | Job Aid Update for SCR 1073 - Modify the TCF Recertification Process | 5 | C-IV M&O | Enhancement | Medium | Test Complete | 18.09 |  | Training |  | 2018-05-02 13:20 |  | Approved
CIV-101124 | Update Job Aids for SCR 10768 | 15 | C-IV M&O | Enhancement | High | Test Complete | 18.09 |  | Training |  | 2018-04-26 14:20 |  | Approved
CIV-100992 | Remove C-IV Functional Presentations from Online Help | 5 | C-IV M&O | Policy Re-Design | Medium | Test Complete | 18.09 |  | Training |  | 2018-04-13 12:08 |  | Approved
CIV-100900 | C4Y: Update the Voter Hotline Number for Threshold Languages | 20 | C-IV M&O | Enhancement | Critical | System Test | 18.09 |  | Online |  | 2018-04-04 11:27 |  | Approved |  | CA-201740
CIV-100726 | Deactivate Unnecessary PDF Format Scheduled Reports | 85 | C-IV M&O | Enhancement | High | Test Complete | 18.09 |  | Reports |  | 2018-03-16 10:02 |  | Approved |  | C-IV Specific
CIV-100168 | Add San Bernardino County District 28 to IVR and C4Yourself | 35 | C-IV M&O | Operational Enhancement | Medium | Test Complete | 18.09 |  | Lobby Mgmt | Medium | 2018-01-16 14:01 |  | Approved
CIV-11077 | Exceeding clock tasks are created for timed out persons. | 130 | C-IV M&O | Data Change | High | System Test | 18.09 |  | Batch/Interfaces | Low | 2017-12-29 14:26 |  | Approved
CIV-11928 | Modify Visual IVR queuing logic | 180 | County Purchase | Operational Enhancement | Medium | Test Complete | 18.09 |  | Contact Center | Medium | 2017-12-29 14:26 |  | Approved |  | None | CSC Support
CIV-6871 | eICT: Add ICT as Source of the Application | 85 | C-IV M&O | Enhancement | High | Test Complete | 18.09 |  | Online | Medium | 2017-12-29 14:25 |  | Approved |  | CA-55375
CIV-503 | ACL 11-15E11 Update the KG EDBC to Consider the SOC 369A Date | 65 | C-IV M&O | Policy Re-Design | Medium | Test Complete | 18.09 |  | Eligibility | Medium | 2017-12-29 14:23 |  | Approved |  | LRS SCR CA-200592
CIV-1073 | Modify the TCF recertification process for programs discontinued after the RE Due Month (56659) | 475 | C-IV M&O | Enhancement | Medium | System Test | 18.09 |  | Online | Medium | 2017-12-29 14:24 |  | Approved |  | CA-54027
CIV-101257 | MEDS Interface - Safety Net & Drug/Fleeing Felon Aid Codes 3F and K1 | 155 | C-IV M&O | New Policy | Critical | System Test | 18.09 |  | Batch/Interfaces |  | 2018-05-11 11:48 |  | Approved |  | CA-47284
CIV-101290 | Update Reports Overview for SCR 100726 | 5 | C-IV M&O | Enhancement | Medium | Test Complete | 18.09 |  | Training |  | 2018-05-16 13:15 |  | Approved
CIV-100364 | Upgrade Cisco Finesse from 10.5 to version 11.6 | 60 | County Purchase | Operational Enhancement | High | Test Complete | 18.09 |  | Contact Center | Medium | 2018-02-02 16:12 |  | Approved |  | C-IV Specific | CSC Support
CIV-101876 | Update the Non-MAGI packets with the updated forms | 65 |  | Enhancement | High | In Development | 18.09 | 18.10.XX | Client Correspondence |  | 2018-08-02 11:05 |  | Approved | N/A | 203981
CIV-623 | Update Time Limit Sanctions Batch | 85 | C-IV M&O | Enhancement | High | Test Complete | 18.09 |  | Batch/Interfaces | Medium | 2017-12-29 14:23 |  | Approved |  | CA-201634
CIV-101292 | Update C4Yourself Mobile App to be built with iOS 11.0 SDK or Later | 80 | C-IV M&O | Operational Enhancement | Medium | Test Complete | 18.09 |  | Tech Arch |  | 2018-05-16 16:36 |  | Approved
CIV-101406 | Update C4Yourself Android Mobile App to support API level 26 or higher | 100 | C-IV M&O | Operational Enhancement | Medium | Test Complete | 18.09 |  | Tech Arch |  | 2018-05-31 10:36 |  | Approved
CIV-100455 | CFL 15/16-64 - AB 2035 EBT Benefit Replacement due to Electronic Theft Update - SUAS | 260 | C-IV M&O | New Policy | Medium | System Test | 18.09 |  | Fiscal |  | 2018-02-14 09:41 |  | Approved |  | CA-50781
CIV-100681 | Update On-Request Reports with PDF format to Generate Only as a Spreadsheet | 145 | C-IV M&O | Enhancement | Medium | Test Complete | 18.09 |  | Reports |  | 2018-03-13 10:37 |  | Approved
CIV-101972 | Tehama County (Local Warrant Print) Update Warrant Mapping | 45 | C-IV M&O | Enhancement | High | System Test | 18.09 |  | Client Correspondence |  | 2018-08-13 11:59 |  | Approved | TBD | N/A
CIV-11439 | Enhancement to Deemed Eligible Functionality | 1400 | C-IV M&O | Policy Re-Design | Critical | System Test | 18.09 |  | CalHEERS | Medium | 2017-12-29 14:26 |  | Approved | N/A | CA-51741
CIV-8219 | CO-084: CalWORKs/CalFresh NOAs in Threshold languages Phase 4 of 5 | 1720 | Premise | New Policy | High | System Test | 18.09 |  | Client Correspondence | Medium | 2017-12-29 14:25 |  | Approved | N/A | None | CO-084/CO-104
CIV-101645 | Add Revised MC-007 (Static Form) | 30 | C-IV M&O | Policy Re-Design | High | Test Complete | 18.09 |  | Client Correspondence |  | 2018-06-28 10:09 |  | Approved | TBD | CA-202379
CIV-100538 | CalHEERS eHIT: Naturalized/Derived Citizenship updates (CH-109700) | 300 | Premise | New Policy | Critical | System Test | 18.09 | 18.09.23 | CalHEERS |  | 2018-02-23 13:26 |  | Approved | N/A | CH-109700; CH-113161; CA-200850 | CO-103
CIV-100550 | ACWDL 18-04: 2018 Medicare Savings Program (MSP) Property Limits | 40 | C-IV M&O | New Policy | Critical | Development Complete | 18.11 |  | CalHEERS |  | 2018-02-26 15:17 |  | Approved | 86 | CA-200843
CIV-100492 | Update 2019 Batch Holiday Calendar | 115 | C-IV M&O | Operational Enhancement | High | Approved | 18.11 |  | Batch/Interfaces |  | 2018-02-15 15:10 |  | Approved | 70 | CA-200896
CIV-12215 | C4Y: Update the image drop down for Uploading Documents | 25 | C-IV M&O | Enhancement | Medium | Approved | 18.11 |  | Online | Medium | 2017-12-29 14:26 |  | Approved |  | None
CIV-12387 | ACL 11-72E: Update Quality Control Sanction NOA fragments for 125 day period | 55 | C-IV M&O | Policy Re-Design | High | Approved | 18.11 |  | Client Correspondence | Medium | 2017-12-29 14:26 |  | Approved |  | None
CIV-8220 | CO-084: CalWORKs/CalFresh NOAs in Threshold languages Phase 5 of 5 | 1555 | Premise | New Policy | Medium | In Development | 18.11 |  | Client Correspondence | Medium | 2017-12-29 14:25 |  | Approved |  | None | CO-084
CIV-9914 | Update Foster Care/Kin-GAP Income Exemption Logic to Handle Partial Income Exemptions | 160 | C-IV M&O | Policy Re-Design | Low | In Development | 18.11 |  | Eligibility | Medium | 2017-12-29 14:25 |  | Approved |  | CA-203173
CIV-101674 | AB 480: ACL 18-38 - Generate the NA 823 when manually issuing diaper allowance | 105 | C-IV M&O | New Policy | High | In Development | 18.11 |  | Fiscal |  | 2018-07-02 15:37 |  | Approved |  | CA-203249
CIV-101515 | C4Y CO6935-2017 Remove Napa County Offices from C4Yourself | 45 | C-IV M&O | Data Change |  | Approved | 18.11 |  | Online |  | 2018-06-14 12:15 |  | Approved
CIV-100730 | DDCR 10001: Convert Remaining Scheduled PDF Reports into a Spreadsheet Format | 425 | C-IV M&O | Enhancement | Medium | In Development | 18.11 |  | Reports |  | 2018-03-16 10:39 |  | Approved | 69 | CA-203382
CIV-101173 | Implement Application for Monitoring Performance (AMP) Phase VI | 250 | C-IV M&O | Enhancement | Medium | In Assembly Test | 18.11 |  | Performance |  | 2018-05-02 21:42 |  | Approved |  | CA-202477
CIV-100379 | Update Outbound WIS Interface for 2019 STS Calendar Cycle Numbers | 15 | C-IV M&O | Enhancement | High | Approved | 18.11 |  | Fiscal | Medium | 2018-02-06 14:24 |  | Approved | 0
CIV-12096 | Update Issuance Detail page to have the Pay Code field read-only when issuance is in Cancelled status | 50 | C-IV M&O | Enhancement | Medium | In Development | 18.11 |  | Fiscal | Medium | 2017-12-29 14:26 |  | Approved | 48 | None
CIV-10394 | CES 2017-035 Request Applicant IEVS at Redetermination | 260 | C-IV M&O | Enhancement | Low | Approved | 18.11 |  | Batch/Interfaces | Low | 2017-12-29 14:26 |  | Approved | N/A | CA-52874
CIV-10638 | ACL 18-50 - Tracking of the Visually Impaired | 55 | C-IV M&O | Policy Re-Design | Medium | Approved | 18.11 |  | Online | Medium | 2017-12-29 14:26 |  | Approved | N/A
CIV-100258 | Create a new Daily Interface Payment Status Report | 600 | C-IV M&O | Enhancement | Low | In Development | 18.11 |  | Fiscal | Medium | 2018-01-26 10:07 |  | Approved | 32 | C-IV Specific (report changes CA-203342)
CIV-11700 | Upgrade to RoboHelp 2017 | 80 | C-IV M&O | Enhancement | Medium | Approved | 18.11 |  | Training | Medium | 2017-12-29 14:26 |  | Approved | Approved by Karen Rapponotti 8/28/2018 and Dorothy Avila 8/29/2018 | None
CIV-1383 | Authorized Representative Information | 2110 | C-IV M&O | Policy Re-Design | High | In Development | 18.11 |  | Online | Medium | 2017-12-29 14:24 |  | Approved | NA | LRS SCR 47607
CIV-101770 | Update Reports Overview for FNS 209 | 5 | C-IV M&O | Enhancement | High | Approved | 18.11 |  | Training |  | 2018-07-18 11:18 |  | Approved | Approved by Karen Rapponotti 8/28/2018 and Dorothy Avila 8/29/2018
CIV-101555 | Modify Eligibility Status Action Code (ESAC) trigger condition for EW20 transaction | 115 | C-IV M&O | Operational Enhancement | Medium | Approved | 18.11 |  | Batch/Interfaces |  | 2018-06-19 11:56 |  | Approved | TBD | CA-58059
CIV-102023 | Update Reports Overview for SCR CIV-100258 | 5 | C-IV M&O | Enhancement | Low | Approved | 18.11 |  | Training |  | 2018-08-16 14:40 |  | Approved | 32
CIV-101702 | Update Reports Overview in Online Help for WTW 25 and WTW 25A | 5 | C-IV M&O | Enhancement | Medium | Approved | 18.11 |  | Training |  | 2018-07-09 10:49 |  | Approved | 68
CIV-100987 | Remove C-IV Functional Presentations from Online Help | 5 | C-IV M&O | Policy Re-Design | High | Approved | 18.11 |  | Training |  | 2018-04-13 10:08 |  | Approved | Approved by Karen Rapponotti 8/28/2018 and Dorothy Avila 8/29/2018
CIV-100839 | Update Plumas County calendar for 2018 | 10 | C-IV M&O | Data Change | Medium | Approved | 18.11 |  | Batch/Interfaces |  | 2018-03-28 11:14 |  | Approved | TBD
CIV-100481 | ACWDL 18-13: 2018/2019 Family Member Base Allocation Amount | 40 | C-IV M&O | New Policy | High | Approved | 18.11 |  | CalHEERS | Medium | 2018-02-14 18:16 |  | Approved | 84 | CA-200839
CIV-8753 | Update CalFresh EDBC Logic to Correctly Evaluate PA Household Indicator | 135 | C-IV M&O | Policy Re-Design | High | Approved | 18.11 |  | Eligibility | Medium | 2017-12-29 14:25 |  | Approved | 79 | CA-53463
CIV-101405 | Auto rescission for Medi-Cal programs where RE packet is received after 10-day cutoff | 1765 | C-IV M&O | Enhancement | Critical | Approved | 18.11 |  | CalHEERS |  | 2018-05-31 09:43 |  | Approved |  | CA-202862
CIV-101532 | Job Aid Updates for SCR 100195 - Add Change Reason to Data Collection Pages | 50 | C-IV M&O | Enhancement | High | Approved | 19.01 |  | Training |  | 2018-06-15 11:04 |  | Approved
CIV-100195 | Add Change Reason to Data Collection Pages | 1960 | C-IV M&O | Enhancement | High | Approved | 19.01 |  | Eligibility | Medium | 2018-01-19 11:56 |  | Approved
CIV-100560 | Verify Adobe Reader Cloud (17.011.30099) Compatibility | 85 | C-IV M&O | Operational Enhancement | High | Approved | 19.01 |  | Client Correspondence | High | 2018-02-27 09:39 | 2018-01-23 00:11 | Approved | NA | 203469
CIV-101003 | Update the EBT Repayment Process | 570 | C-IV M&O | Enhancement | Medium | Approved | 19.01 |  | Fiscal |  | 2018-04-17 00:41 |  | Approved | TBD | CA-52879
CIV-100608 | CalHEERS eHIT: Update VLP Interface to version 37 (CH-92295) | 2920 | Premise | New Policy | High | In Development | 19.02 |  | CalHEERS |  | 2018-03-06 11:25 |  | Approved |  | CH-92295; CH-121151; CA-201310 | CO-103
CIV-1059 | Implement Additional Reports in the C-IV System (56590) |  | C-IV M&O | Enhancement | High | Approved | 19.03 |  | Reports | Medium | 2017-12-29 14:24 |  | Approved |  | CA-52210