## Sheet1
| 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025
| SFY 2018/19 | [5 empty] | SFY 2019/20 | [11 empty] | SFY 2020/21 | [11 empty] | SFY 2021/22 | [11 empty] | SFY 2022/23 | [11 empty] | SFY 2023/24 | [11 empty] | SFY 2024/25
 | time axis 2019-01-01 to 2025-03-01
Planning
Governance
CalSAWS DD&I | 2019-01-01: CalSAWS 58-County Design, Development, Test, Conversion and Implementation; 2022-11-01: CalSAWS Stabilization (6 Months)
[5 empty] | CalWIN OCM, Training & Imp Support Procurement | [11 empty] | CalWIN Business Process Alignment, Org Change Management, Training & Implementation Support
[5 empty] | Prepare & Approve RFP |  |  |  | Proposal Prep, Submit & Evaluate |  |  |  | Negotiate & Approve Contract
| QA Procurement (began 2018) |  |  |  | QA Support for CalSAWS 58-County DD&I | [47 empty] | QA Support for CalSAWS 58-County M&O
| CalSAWS Contact Center in the Cloud Procurement | [13 empty] | CalSAWS Contact Center Setup, Development, Test & Implementation | [31 empty] | CalSAWS Contact Center M&O
| Prepare & Approve RFP |  |  |  |  | Proposal Prep, Submit, Evaluate & Award |  |  |  |  | Negotiate & Approve Contract
CalSAWS M&O | 2020-04-01: Acquire & Contract with Procurement Vendor (9 months); 2021-01-01: CalSAWS 58-County M&O Procurement; 2023-05-01: M&O Vendor Transition Period (12 Months); 2024-05-01: Long Term CalSAWS M&O Period
[25 empty] | Requirements Analysis, Develop RFP & Draft Contract | [6 empty] | RFP Approvals |  |  | Proposal Prep, Submit, Evaluate & Prepare Vendor Selection Report(s) | [7 empty] | Negotiate Contract(s) |  |  |  | Contract Approvals |  |  |  | Con-tingency
Common Services | 2019-01-01: OCAT Procurement (began 2018); 2019-06-01: OCAT Design, Develop & Implement
|  |  | Consolidated Portal/Mobile App Planning & Procurement | [11 empty] | Consolidated Portal/Mobile App Design, Develop & Implement
|  |  | FCED Planning & Procurement | [11 empty] | FCED Design, Develop & Implement
C-IV | 2019-01-01: Base Contract End 10/31/2019
LRS | 2019-01-01: Base Contract End 11/7/2023
CalWIN | 2019-01-01: Base Contract End 1/31/2020
Single Portal/Mobile App Go-live
7/2021
39-County Go-live
7/2021
10/31/2020
Optional Extension Year 1
10/31/2021
Optional Extension Year 2
10/31/2022
Optional Extension Year 3
10/31/2023
Optional Extension Year 4
10/31/2024
Optional Extension Year 1
1/31/2023
Optional Extension 3 Years
1/31/2025
Optional Extension 2 Years
Last CalWIN Wave: CalSAWS
Migration Complete
10/2022
CalSAWS Planning Completed
12/31/2018
LRS ---> CalSAWS
11/2020
1st CalWIN Wave Go-live
10/2021
CalWIN OCM, Training, Imp Support End
11/2022
Long Term CalSAWS M&O Begins
5/2024
FCED Go-live
7/2021
39-County Go-live
7/2021
1st CalWIN Wave Go-live
10/2021
Last CalWIN Wave Go-live
10/2022
11/7/2023
LRS Base Contract End
CalSAWS JPA Approval
6/28/2019
CalSAWS OCAT Go-live
1/2021
LRS ---> AWS Cloud
7/2019