## SPG Approved - Design Confirmed
SCR | Summary | Estimate | Funding Source | Change Type (SCR) | SPG Rating | Status | Fix Version/s | Minor Version | Team Responsible | Priority | Created | SPG Status | SPG Score | Other Agency Cross Reference | Committee / WorkGroup
CA-205102 | ACL 18-75 Phase III - Sub Type Code Automation - Automated Test Scripting | 70 | LRS M&E | New Policy | Critical | Approved | 19.01 |  | System Test |  | 2018-10-11 11:50 | Approved | N/A - Approved by Dorothy Avila and Karen Rapponotti | CIV-102460 | Other
CA-205218 | Training Updates: Update the EBT Repayment Process (WBTs) | 164 | LRS M&E | Enhancement | Critical | Approved | 19.01 |  | Training |  | 2018-10-19 16:29 | Approved | NA â€“ Training LMS Related SCR
CA-203448 | Change of Post Office Boxes Due to FOD's Relocation - April 16, 2018 | 160 | LRS M&E | Data Change | Critical | System Test | 19.01 |  | Client Correspondence |  | 2018-07-05 10:27 | Approved | N/A |  | Correspondence
CA-54316 | YBN-New GR Forms | 485 | LRS M&E | Enhancement | Critical | System Test | 19.01 |  | Online | 3-Normal/Low | 2018-01-19 11:44 | Approved | N/A |  | C4Yourself Correspondence
CA-202814 | ACL 18-78 - CalWORKs: Implementation of AB 557 Victims of Domestic Abuse and Temporary Homeless Assistance Eligibility | 1020 | LRS M&E | New Policy | Critical | System Test | 19.01 |  | Eligibility |  | 2018-05-25 14:30 | Approved | N/A | CIV-101524 | CalWORKs/CalFresh
CA-204846 | Create LRS Automated Regression Scripts - Phase 1 | 185 | LRS M&E | Operational Enhancement | High | Approved | 19.01 |  | System Test |  | 2018-09-24 12:21 | Approved | N/A - Automated Test |  | Other
CA-200259 | DDCR 4012: Update information available for print from Journal | 20 | LRS M&E | Enhancement | High | Test Complete | 19.01 |  | Online | 2-Normal/Medium | 2018-01-24 09:52 | Approved | N/A | CIV-557 | Usability
CA-48648 | Adding Office Name column to Service Payment EBT Issuance Register Report | 70 | LRS M&E | Enhancement | High | System Test | 19.01 |  | Fiscal | 3-Normal/Low | 2018-01-19 11:47 | Approved | N/A |  | State/Fiscal Reports
CA-202731 | Your benefits Now (YBN) to add WIC mobile web link to resource panel SIRFRA 3439 | 50 | LRS M&E | Enhancement | High | System Test | 19.01 |  | Online |  | 2018-05-21 16:27 | Approved | N/A | CIV-101320 | C4Yourself
CA-59077 | ATS Security Assessment Findings - Group 3 | 754 | LRS M&E | Enhancement | High | System Test | 19.01 |  | Tech Arch | 3-Normal/Low | 2018-01-19 11:43 | Approved | N/A |  | Other
CA-205219 | Training Updates: ACWDL 17-12: Authorized Representative Information (Major Updates - WBTs) | 125 | LRS M&E | Enhancement | High | System Test | 19.01 |  | Training |  | 2018-10-19 16:35 | Approved | NA â€“ Training LMS Related SCR
CA-202349 | Update the Uncollectible Recovery Account Batch | 345 | LRS M&E | Policy Re-Design | High | System Test | 19.01 |  | Fiscal |  | 2018-04-26 10:45 | Approved | N/A | CIV-102218 | Collections
CA-56416 | ACL 17-53: ESAP Notice Automation | 790 | Premise | New Policy | High | System Test | 19.01 |  | Client Correspondence | 3-Normal/Low | 2018-01-19 11:42 | Approved | 81 | CIV-10181 | Correspondence
CA-200460 | DDCR 5019: MEDS Alerts for return mail for 1095B mailings from DHCS | 185 | LRS M&E | New Policy | High | System Test | 19.01 |  | Batch/Interfaces |  | 2018-01-30 09:57 | Approved | 73 | CIV-7098, CIV-102138 | MEDS
CA-205217 | Training Updates: ACL 12-67 - Automation of the 319 â€“ Meeting WPR WtW 24-Month Time Clock Stopper (WBTs) | 280 | LRS M&E | Enhancement | High | In Development | 19.01 |  | Training |  | 2018-10-19 16:16 | Approved | NA â€“ Training LMS Related SCR
CA-203469 | Inter County Transfer Address Updates | 165 | LRS M&E | Operational Enhancement | High | In Development | 19.01 |  | Client Correspondence |  | 2018-08-30 10:36 | Approved | 77 | CIV-102087 | Correspondence
CA-204383 | Update Overpayment Adjustment Logic | 565 | LRS M&E | Enhancement | High | In Development | 19.01 |  | Fiscal |  | 2018-02-12 10:36 | Approved | N/A | CIV-7716 | Fiscal