## Timeline
Review Date: | 2018-05-17
Project Timeline* - Key Policy Items (Critical, High or Volume Impact) *All items are targeted until approved by the SCRB/CCB process, and, therefore subject to change. |  | 2018-05-01 | 2018-06-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01
Program/Topic | C-IV RELEASES | Fixed | CalHEERS | Minor | Fixed | Minor | Fixed | Minor | Fixed | Minor | Fixed | Minor | Fixed | Minor | Fixed | Minor | Fixed | Minor | Fixed | Minor | Fixed | Minor | Fixed | Minor | Fixed | Minor | Fixed | Minor | Fixed | Minor | Fixed | Minor | Fixed | Minor | Fixed
|  | 18.05 / 18.06 |  |  | 18.07 |  | 18.09 |  | 18.11 |  | 19.01 |  | 19.03 |  | 19.05 |  | 19.07 |  | 19.09 |  | 19.11 |  | 20.01 |  | 20.03 |  | 20.05 |  | 20.07 |  | 20.09 |  | 20.11 |  | 21.01
Correspondence | CO-068: Add Eligibility Evaluation Reasons from CalHEERS to trigger MAGI Denial/Discontinuance Notices | 2018-06-01: 12029
Medi-Cal | ACWDL 17-28 and 17-29: Inmate MC Aid Codes | 2018-06-01: 8677
Medi-Cal | ACWDL 17-22: 2017/2018 Family Member Base Allocation Amount | 2018-06-01: 10102
C4Y | C4Y: Add Message About EBT Outage | 2018-06-01: 100711
C4Y | C4Y: Update Message on EBT Outage and Link to TEMP 2233 to C4Y | 2018-06-01: 101275
C4Y Mobile App | C4Y Mobile App: Send Notification that EBT will be Unavailable | 2018-06-01: 100908
CalFresh | Westat SNAP Barriers Study | 2018-06-01: 10567
CalWORKs | ACL 18-66 - Cost of Living Adjustment (COLA) for Minimum Basic Standard of Adequate Care (MBSAC) and Income In-Kind (IIK) for 2018-2019 | 2018-06-01: 100439
Fiscal | CO-097: Enable new Electronic Benefit Transfer (EBT) Vendor Fidelity Information Services (FIS) | 2018-06-01: 11727
Medi-Cal | CO-068: MEDS: Update Recon transactions to include the MBI | 2018-06-01: 100988
CalWORKs | Count Income of Senior Parent not in CW Assistance Unit (44283) | 2018-07-01: 458
Correspondence | Update GEN 2000 - Passport to Services (IVR Request, Central Print, Post to C4Y) | 2018-07-01: 8905
EBT | Create a new interface to send EBT Fraud information to CDSS | 2018-07-01: 8453
Foster Care | Add new THP+FC and THPP placements for Foster Care | 2018-07-01: 933
Medi-Cal | ACWDL 14-18: Batch Non-MAGI forms to MAGI Customer Turning 65 | 2018-07-01: 10668
Multiple | ACL 17-58 - Electronic Inter-County Transfer (eICT) - Redetermination (RE) Date Alignment | 2018-07-01: 100436
Reports | ACL 17-xx ESAP Reporting - Reporting Requirements for CalFresh Elderly Simplified Application Project (ESAP) | 2018-07-01: 12413
Reports | Implement RS 51-Refugee Resettlement Program Caseload Movement Report | 2018-07-01: 4493
CalFresh | ACIN I-18-XX 2018 CalFresh COLA | 2018-08-01: 100437
CalWORKs | ACL 18-XX - Elect Child Support Payment for Stepsibling or Half-Sibling in Lieu of Cash Aid - Phase 1 | 2018-08-01: 101374
CalWORKs | AB 480: ACL 18-38 / CFL 17/18-57 Add Additional Diaper Benefit Functionality - Phase II | 2018-08-01: 100305
CalWORKs | AB 480: ACL 18-38 / CFL 17/18-57 Add Additional Diaper Benefit Functionality - Phase III | 2018-08-01: 101102
CalWORKs | ACL 18-XX - Update CalWORKs (CW) IRT Level 2018-2019 | 2018-08-01: 100440
Foster Care | ACL 18-XX Foster Care Rate Increase | 2018-08-01: 9441
CalHEERS | CO-068: Automate EDR and Batch EDBC for MC Age Changes for Children Turning Ages 1 and 6 | 2018-09-01: 9433
Correspondence | CO-084: CalWORKs/CalFresh NOAs in Threshold languages Phase 4 of 5 | 2018-09-01: 8219
Fiscal | Update Overpayment Adjustment Logic | 2018-09-01: 7716
Fiscal | CFL 15/16-64 - AB 2035 EBT Benefit Replacement due to Electronic Theft Update - SUAS | 2018-09-01: 100455
Medi-Cal | Enhancement to Deemed Eligible Functionality | 2018-09-01: 11439
Multiple | Add Change Reason to Data Collection Pages (Migration Gap Reduction) | 2018-09-01: 100195
CalHEERS | CalHEERS eHIT: Naturalized/Derived Citizenship updates (CH-109700) | 2018-10-01: 100538
CalWORKs | ACL 18-XX - Elect Child Support Payment for Stepsibling or Half-Sibling in Lieu of Cash Aid | 2018-10-01: 100390
Child Care | ACL 18-XX - Update Child Care Regional Market Rate (RMR) Ceilings | 2018-10-01: 100474
Medi-Cal | ACWDL 18-XX: 2018 Medicare Premiums and Supplemental Security Income Standard and Parent Allocations and Property Limits for the Medicare Savings Programs and Other Programs | 2018-10-01: 100550
C4Yourself | C4Y: Update C4Yourself with latest SAWS 2 Plus form and appendices | 2018-11-01: 10690
CalFresh | Active $0 CF grants removed from Negative Univers File transfer to Suspend (S) | 2018-11-01: 8950
CalFresh | ACL 17-05 CalFresh Student Eligibility | 2018-11-01: 8054
CalHEERS | ACWDL 17-35: Add validation to prevent running EDBC against a DER with at least one Soft Pause individual | 2018-11-01: 10791
Correspondence | CO-084: CalWORKs/CalFresh NOAs in Threshold languages Phase 5 of 5 | 2018-11-01: 8220
Multiple | Update Event Logic when Moving the BDA or Logging a Rescind (41376) (Program App) | 2018-11-01: 331
Multiple | Authorized Representative Information | 2018-11-01: 1383
Multiple | ACIN I-XX-18 - 2019 State Minimum Wage | 2018-11-01: 100438
Multiple | ACWDL 18-XX, ACIN I-XX-18: 2019 Social Security Title II and Title XVI Cost of Living Adjustments (SSA COLA) | 2018-12-01: 100401
CalFresh | CO-091 - ABAWD Phase II | 2019-01-01: 7215

## Historical - 2018
Review Date: | 2018-04-12
Project Timeline* - Key Policy Items (Critical, High or Volume Impact) *All items are targeted until approved by the SCRB/CCB process, and, therefore subject to change. |  | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01
Program/Topic | C-IV RELEASES | Fixed | Minor | Fixed | Minor | Fixed | CalHEERS | Minor | Fixed | Minor | Fixed | Minor | Fixed | Minor | Fixed | Minor | Fixed | Minor | Fixed | Minor | Fixed | Minor | Fixed | Minor | Fixed | Minor | Fixed | Minor | Fixed | Minor | Fixed | Minor | Fixed | Minor | Fixed | Minor | Fixed | Minor | Fixed
|  | 18.01 / 18.02 |  | 18.03 |  | 18.05 / 18.06 |  |  | 18.07 |  | 18.09 |  | 18.11 |  | 19.01 |  | 19.03 |  | 19.05 |  | 19.07 |  | 19.09 |  | 19.11 |  | 20.01 |  | 20.03 |  | 20.05 |  | 20.07 |  | 20.09 |  | 20.11 |  | 21.01
CalFresh | SIRFRA 3101 - SNAP Application Data Request - July-September 2017 | 2018-02-01: 100182
CalFresh | Westat SNAP Barriers Study | 2018-02-01: 10567
CalHEERS | CO-068: Update MAGI Budget Detail page to support new Eligible Type Codes | 2018-02-01: 11067
Medi-Cal | ACWDL 17-20 2017 Medicare Premiums and Supplemental Security Income Standard and Parent Allocations and Property Limits for the Medicare Savings Programs and Other Programs | 2018-02-01: 9932
Medi-Cal | ACWDL 18-03 Add 2018 MC FPL Values to the System | 2018-02-01: 100176
Medi-Cal | ACWDL 18-03 Run Batch EDBC with 2018 MC FPL Values | 2018-02-01: 100192
Medi-Cal | MEDIL 18-03 Outreach Letter to Individuals on Home & Community-Based Services Waiver Waiting List | 2018-02-01: 100607
Reports | CAAL-Skills Pilot Data Exchange | 2018-02-01: 10576
CalFresh | CO-091 - Update ABAWD Time Limit Month List Page | 2018-03-01: 7357
Correspondence | CO-084: CalWorks/CalFresh NOAs in Threshold Languages Phase 3 of 5 | 2018-03-01: 8215
Correspondence | CO-084: Add Threshold for MC Fragments from SCR 776 | 2018-03-01: 11136
Correspondence | CO-084: ACWDL 17-32: Add threshold fragments for SCR 10892 | 2018-03-01: 11990
Fiscal | Update Payment Request Issuance Adjustment Claiming to not update the Pay Code for HSP & FSP issuances | 2018-03-01: 3769
Kin-GAP | CO-100: Update Kin-Gap Rate Schedule | 2018-03-01: 10978
Medi-Cal | MEDIL 17-15 Replace the HIC number in the C-IV system with the new Medicare Beneficiary Identifier (MBI) | 2018-03-01: 8965
Reports | Add New DSS 466 / FNS 366B Report to C-IV system | 2018-03-01: 10344
Reports | MEDIL 17-11: Update DHCS Renewals Master Request Report to the C-IV System | 2018-03-01: 9751
Medi-Cal | CO-068: Load file from DHCS to populate MBI number for existing applicants | 2018-04-01: 100678
CalWORKs | ACIN I-01-07 - Modify Cash Aid Time Limit Month Detail page for Tribal TANF and Out of State months (SCR 39526) | 2018-05-01: 4815
CalWORKs | AB 480: ACL 18-38 / CFL 17/18-57 Add Diaper Benefit Functionality Phase I | 2018-05-01: 100986
Foster Care | ACL 18-33 ARC/FC Payments to Caretaker Prior to Home Approval | 2018-05-01: 100645
Multiple | Add Money Management functionality for the General Assistance (Managed), RCA and CAPI Programs | 2018-05-01: 4398
Multiple | CO-101: eICT: ACL 17-58 SB 1339 Updates to the eICT Interface and Additional Documents Transfer | 2018-05-01: 9076
Multiple | CO-101: ACL 17-58 - SB 1339: Automate the M40-195A and M40-195B Notices | 2018-05-01: 100435
Multiple | SB 89 SFIS Repeal for CalWORKs/RCA and General Relief (GR) Programs | 2018-05-01: 100573
Reports | FNS 209 Quarterly State Report Enhancements | 2018-05-01: 11467
Task Management | Task Management: Add additional Automated Actions for Customer Status Report Packets | 2018-05-01: 9369
Welfare to Work | Update Cash Aid Time Limit Extender clock counts for Welfare to Work | 2018-05-01: 11266
Correspondence | CO-068: Add Eligibility Evaluation Reasons from CalHEERS to trigger MAGI Denial/Discontinuance Notices | 2018-06-01: 12029
Medi-Cal | ACWDL 17-28 and 17-29: Inmate MC Aid Codes | 2018-06-01: 8677
Medi-Cal | ACWDL 17-22: 2017/2018 Family Member Base Allocation Amount | 2018-06-01: 10102
C4Y | C4Y: Add Message About EBT Outage | 2018-06-01: 100711
C4Y | C4Y: Update Message on EBT Outage and Link to TEMP 2233 to C4Y | 2018-06-01: 101275
C4Y Mobile App | C4Y Mobile App: Send Notification that EBT will be Unavailable | 2018-06-01: 100908
CalFresh | Westat SNAP Barriers Study | 2018-06-01: 10567
CalWORKs | ACL 18-66 - Cost of Living Adjustment (COLA) for Minimum Basic Standard of Adequate Care (MBSAC) and Income In-Kind (IIK) for 2018-2019 | 2018-06-01: 100439
Fiscal | CO-097: Enable new Electronic Benefit Transfer (EBT) Vendor Fidelity Information Services (FIS) | 2018-06-01: 11727
Medi-Cal | CO-068: MEDS: Update Recon transactions to include the MBI | 2018-06-01: 100988
CalWORKs | Count Income of Senior Parent not in CW Assistance Unit (44283) | 2018-07-01: 458
Correspondence | Update GEN 2000 - Passport to Services (IVR Request, Central Print, Post to C4Y) | 2018-07-01: 8905
EBT | Create a new interface to send EBT Fraud information to CDSS | 2018-07-01: 8453
Foster Care | Add new THP+FC and THPP placements for Foster Care | 2018-07-01: 933
Medi-Cal | ACWDL 14-18: Batch Non-MAGI forms to MAGI Customer Turning 65 | 2018-07-01: 10668
Multiple | ACL 17-58 - Electronic Inter-County Transfer (eICT) - Redetermination (RE) Date Alignment | 2018-07-01: 100436
Reports | ACL 17-xx ESAP Reporting - Reporting Requirements for CalFresh Elderly Simplified Application Project (ESAP) | 2018-07-01: 12413
Reports | Implement RS 51-Refugee Resettlement Program Caseload Movement Report | 2018-07-01: 4493
CalFresh | ACIN I-18-XX 2018 CalFresh COLA | 2018-08-01: 100437
CalWORKs | ACL 18-XX - Elect Child Support Payment for Stepsibling or Half-Sibling in Lieu of Cash Aid - Phase 1 | 2018-08-01: 101374
CalWORKs | AB 480: ACL 18-38 / CFL 17/18-57 Add Additional Diaper Benefit Functionality - Phase II | 2018-08-01: 100305
CalWORKs | AB 480: ACL 18-38 / CFL 17/18-57 Add Additional Diaper Benefit Functionality - Phase III | 2018-08-01: 101102
CalWORKs | ACL 18-XX - Update CalWORKs (CW) IRT Level 2018-2019 | 2018-08-01: 100440
Foster Care | ACL 18-XX Foster Care Rate Increase | 2018-08-01: 9441
CalHEERS | CO-068: Automate EDR and Batch EDBC for MC Age Changes for Children Turning Ages 1 and 6 | 2018-09-01: 9433
Correspondence | CO-084: CalWORKs/CalFresh NOAs in Threshold languages Phase 4 of 5 | 2018-09-01: 8219
Fiscal | Update Overpayment Adjustment Logic | 2018-09-01: 7716
Fiscal | CFL 15/16-64 - AB 2035 EBT Benefit Replacement due to Electronic Theft Update - SUAS | 2018-09-01: 100455
Medi-Cal | Enhancement to Deemed Eligible Functionality | 2018-09-01: 11439
Multiple | Add Change Reason to Data Collection Pages (Migration Gap Reduction) | 2018-09-01: 100195
CalHEERS | CalHEERS eHIT: Naturalized/Derived Citizenship updates (CH-109700) | 2018-10-01: 100538
CalWORKs | ACL 18-XX - Elect Child Support Payment for Stepsibling or Half-Sibling in Lieu of Cash Aid | 2018-10-01: 100390
Child Care | ACL 18-XX - Update Child Care Regional Market Rate (RMR) Ceilings | 2018-10-01: 100474
Medi-Cal | ACWDL 18-XX: 2018 Medicare Premiums and Supplemental Security Income Standard and Parent Allocations and Property Limits for the Medicare Savings Programs and Other Programs | 2018-10-01: 100550
CalFresh | Active $0 CF grants removed from Negative Univers File transfer to Suspend (S) | 2018-11-01: 8950
CalFresh | ACL 17-05 CalFresh Student Eligibility | 2018-11-01: 8054
CalHEERS | ACWDL 17-35: Add validation to prevent running EDBC against a DER with at least one Soft Pause individual | 2018-11-01: 10791
Correspondence | CO-084: CalWORKs/CalFresh NOAs in Threshold languages Phase 5 of 5 | 2018-11-01: 8220
Multiple | Update Event Logic when Moving the BDA or Logging a Rescind (41376) (Program App) | 2018-11-01: 331
Multiple | Authorized Representative Information | 2018-11-01: 1383
Multiple | ACIN I-XX-18 - 2019 State Minimum Wage | 2018-11-01: 100438
Multiple | ACWDL 18-XX, ACIN I-XX-18: 2019 Social Security Title II and Title XVI Cost of Living Adjustments (SSA COLA) | 2018-12-01: 100401

## Historical - 2017
Project Timeline* - Key Policy Items (Critical, High or Volume Impact) *All items are targeted until approved by the SCRB/CCB process, and, therefore subject to change. |  | 2016-12-01 | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2017-12-01 | 2019-01-01
Program/Topic | C-IV RELEASES | Priority | Baseline | Priority | Baseline | Priority | Baseline | Priority | Baseline | Priority | Baseline | Priority | Baseline | Priority | Baseline | Priority | Baseline | Priority | Baseline | Priority | Baseline | Priority | Baseline | Priority | Baseline | Priority | Baseline
|  |  | 17.01 |  | 17.03 |  | 17.05 |  | 17.07 |  | 17.09 |  | 17.11 |  | 18.01 |  | 18.03 |  | 18.05 |  | 18.07 |  | 18.09 |  | 18.11 |  | 19.01
CalWORKs / CalFresh | Update CW/CF Redetermination Packet Contents and Functionality |  | 639
Medi-Cal | CO-068: ACWDL 14-35 - 2015 RE for Non MAGI LTC Mixed HH Programs (54693) |  | 888
Medi-Cal | CO-084: Add Medi-Cal NOAs in Threshold languages Phase 3 of 4 |  | 3894
Medi-Cal | CO-084: Update the MAGI Ineligible fragment language to differentiate between denial and discontinuance |  | 5467
Medi-Cal | CO-068: Update SAWS 2 PLUS logic for questions 6, 10, and 23F |  | 5749
Reports | CO-091: ACL 16-24 STAT 47 Report Updates |  | 6532
CalFresh | ACL 17-09: List of impacted cases for CalFresh (CF) Eligibility for SSI Suspend Status |  |  | 7866
CalHEERS | CO-068: Business Rules Exposure for SAWS (BREfS)- Phase A |  |  | 4561
CalHEERS | CO-068: Support CalHEERS System Changes for Other Health Care and Employer Sponsored Insurance (CR 29911) |  |  | 4597
CalHEERS | CO-068: Registered Domestic Partner Shared Income, American Indian/Alaskan Native Income |  |  | 4723
CalHEERS | CO-068: Update MAGI Determination List page to remove the primary applicant mismatch validation |  |  | 4725
CalHEERS | CO-068: County of Responsibility (COR) Electronic Inter-County Transfer (eICT) |  |  | 4730
CalHEERS | CO-068: Update eHIT Schema to Version 7.4 (CR 67666) |  |  | 5511
CalHEERS | CO-068: CalHEERS Interface - Matching Bypass Indicator |  |  | 5591
Medi-Cal | CO-068: ACWDL 16-25 2017 Medicare Catastrophic Coverage Act Spousal Impoverishment Caps |  |  | 7056
MEDS | CO-091: Update FX20 and CDB Recon to no longer suppress ABAWD data elements for waived counties |  |  | 7486
MEDS | CO-091: ACL 16-24: Operationally Trigger FX20 transactions for ABAWD recipients |  |  | 7569
Multiple | CO-068: ACWDL 17-02, ACIN I-92-16: Batch EDBC to apply 2017 SSA Cost of Living Adjustments (COLA) |  |  | 6970
C4Yourself | CO-088: ACL 17-04 - Add the HI01 CalHEERS Horizonal Integration Report to the C-IV System |  |  |  | 5019
CalFresh | Apply the CalFresh 20% earned income deduction to gross income in the net income test |  |  |  | 5081
Fiscal | Recovery Accounts - Update Uncollectible Batch for CF AEs under $35 (51070) |  |  |  | 763
Forms | CO-080: Add Forms in Threshold Languages |  |  |  | 2115
Forms | ACL 16-77 Revisions made to the CF 37 |  |  |  | 5827
General Assistance | Add Supportive Services functionality to the General Assistance (Managed) program. |  |  |  | 5041
Reports | CO-068: Add a Batch RE Mixed Household Exception Report to the C-IV System |  |  |  | 5711
Task Management | CO-086: Task Reassignment Enhancements |  |  |  | 5596
ARC | CO-081 - ACL 16-92 - ARC Program Change Notice to Caregivers |  |  |  |  | 3937
C4Yourself | CO-087 Implement C4Yourself Mobile App Phase-II, Release 3 |  |  |  |  | 5109
Fiscal | IRS Pub 1075, ACL 16-106: Remove references to FTI information from codes tables and convert Recovery Account Cause Reason types to an updated type code that does not contain a FTI Reference |  |  |  |  | 7567
Medi-Cal | Add 2017 Medi-Cal Federal Poverty Level (FPL) Values to the System |  |  |  |  | 7495
Medi-Cal | ACWDL 17-10: Run Batch EDBC with 2017 Federal Poverty Level (FPL) Values |  |  |  |  | 7497
CalWORKs/CalFresh | CO-095: Automate the creation of EBT Accounts | [5 empty] | 5878
Medi-Cal | CO-068: SIRFRA 1005 - Add a DHCS Renewals Master Request Report to the C-IV System | [5 empty] | 5651
Medi-Cal | CO-068: ACWDL 14-03: Update Medi-Cal Redetermination (MC RE) Signature Packets | [5 empty] | 7307
Medi-Cal | CO-084: ACWDL 15-33: Update MAGI Over Income NOA Regulations | [5 empty] | 7001
Medi-Cal | CO-084: SB 1341: MAGI 100 CIV in Threshold Languages | [5 empty] | 7021
Multiple | CO-094: SAR 7 Automated No Change EDBC Process | [5 empty] | 5741
Task Management | CO-086: My Tasks Page and Task Enhancements | [5 empty] | 6596
ARC | CO-081: Add/Update Approved Relative Caregiver (ARC) Forms | [6 empty] | 3915
ARC | CO-081: ACL 16-92 - Update Other Program Assistance (OPA) pages for ARC | [6 empty] | 3944
ARC | CO-081: ACL 16-92 - Update Child Support Interface with ARC Phase II | [6 empty] | 8872
CalHEERS | CO-068: Modify the online single streamline application (SSApp) to meet regulatory and statutory requirements, be consistent with the paper SSApp, and ensure accurate eligibility determinations | [6 empty] | 5715
CalHEERS | CO-068: Update eHIT Schema to Version 8.0 (CR 78444) | [6 empty] | 7162
CalWORKs | ACL 17-XX - MBSAC 2017 - Draft Letter | [6 empty] | 7951
Foster Care | ACL 17-XX Foster Care Rate Increase | [6 empty] | 5410
CalFresh | ACL 17-09 CalFresh (CF) Eligibility for SSI Suspend Status | [7 empty] | 6978
CalFresh | Elderly Simplified Application Project (ESAP) Waiver Approval | [7 empty] | 7292
CalFresh | Apply Standard Medical Deduction to CF households with an Elderly or Disabled Member | [7 empty] | 8183
General Assistance | County Funded: Update the Expungement reactivation functionality for GA EBT benefits | [7 empty] | 8474
Multiple | Capture Electronic Signatures within the C-IV System | [7 empty] | 6660
Multiple | CO-095 - Auto-Reactivate Expunged EBT Accounts | [7 empty] | 7285
Welfare to Work | CO-066: Automate the Good Cause WTW Status to the 24 Month Time clock | [7 empty] | 4784
CalFresh | ACIN I-xx-17 - CalFresh COLA Increase Effective 10/01/2017 | [8 empty] | 6356
CalFresh | ACL 17-35, ACIN I-XX-17 Run batch EDBC to apply the CalFresh (CF) COLA Values | [8 empty] | 9063
CalFresh | ACIN I-xx-17 - CalFresh COLA Increase to CalFresh Aged Property Limit 10/01/2017 | [8 empty] | 10617
CalFresh | Create Case Flag for Hurricane Evacuees | [8 empty] | 10934
CalWORKs | ACL 17-XX - Update CalWORKs (CW) IRT Level | [8 empty] | 10397
Correspondence | ACIN I-xx-17 - CalFresh COLA Benefit Change NOAs | [8 empty] | 10701
Foster Care | ACL 17-75 Foster Care Rate Increase | [8 empty] | 5410
Foster Care | ACL 17-75 Foster Care Rate Increase Batch | [8 empty] | 10135
Foster Care | CO-100: ACL 16-79 - Update the Kin-Gap Rate Determination Logic | [8 empty] | 10255
ARC | CO-081: ACL 16-92 - Update Fiscal and Reports jobs to pay ARC in arrears | [9 empty] | 3943
CalFresh | CO-091 - ACIN I-88-16 Update ABAWD and Work Registration Exemptions | [9 empty] | 6675
CalFresh | CO-091 - ACIN I-88-16 Update ABAWD Synchronization Batch Job | [9 empty] | 7274
CalFresh | CO-091 - ACIN I-88-16 Update Manual EDBC for ABAWD | [9 empty] | 7355
CalFresh | ACL 17-53 - ESAP Notices | [9 empty] | 9627
CalHEERS | CO-068: CalHEERS - Reasonable Opportunity Period | [9 empty] | 6645
CalHEERS | CO-068: Update EHIT Schema to Version 9.0 | [9 empty] | 9355
CalWORKs | ACL 16-90 - ACIN I-13-16 (AB 433) -CW - Deceased Child Continue Benefits for Month of Death of Child and the Month Following | [9 empty] | 3129
Correspondence | CO-084: CalWORKs/CalFresh NOAs in Threshold languages Phase 1 of 5 | [9 empty] | 7626
Fiscal | Update Mass Workload Reassignments on Recovery Accounts (36228) | [9 empty] | 154
Forms | CMSP ACL 16-02: Update CMSP Forms | [9 empty] | 6694
General Assistance | County Funded: Imperial, Madera, Plumas Counties opt-in to General Assistance (Managed) | [9 empty] | 9265
IEVS | CO-098: IEVS: Add IEVS Automation | [9 empty] | 6021
Medi-Cal | CO-084: SB 1341: Add Medi-Cal NOAs in Threshold languages Phase 4 of 4 | [9 empty] | 3895
Reports | CO-068: SIRFRAs - Add a DHCS CMS Performance Indicator Master Request Report to the C-IV System | [9 empty] | 8099
Task Management | Task Management: Task Reassignment Enhancements | [9 empty] | 8261
Task Management | Task Management: Task Reporting Enhancements | [9 empty] | 8326
WTW | CFL 16/17-23 - Add new Pay Codes and Fund Codes for HSP Housing Support Program Transportation and Child Care/Welfare to Work TCVAP | [9 empty] | 7329
CalFresh | Westat SNAP Barriers Study | [10 empty] | 10567
CalFresh | SIRFRA 3101 - SNAP Application Data Request - April-June 2017 | [10 empty] | 11389
CalFresh | Activate Disaster CalFresh Services for 6 C-IV Counties | [10 empty] | 11437
CalFresh | Issue Disaster CalFresh Supplements to Maximum Allotment for 6 C-IV Counties | [10 empty] | 11494
CalFresh | Butte County: Deactivate Disaster CalFresh Services in Butte County | [10 empty] | 11438
CalFresh | Lake County Only: Mass-Replacement of CalFresh Issuances | [10 empty] | 11367
CalFresh | Lake County: Deactivate Disaster CalFresh Services in Lake County | [10 empty] | 11756
CalFresh | Mendocino County Only: Mass-Replacement of CalFresh Issuances | [10 empty] | 11370
CalFresh | Mendocino County: Deactivate Disaster CalFresh Services in Mendocino County | [10 empty] | 11757
CalFresh | Napa County Only: Mass-Replacement of CalFresh Issuances (part 2) | [10 empty] | 11497
CalFresh | Napa County Only: Mass-Replacement of CalFresh Issuances | [10 empty] | 11369
CalFresh | Napa County: Deactivate Disaster CalFresh Services in Napa County | [10 empty] | 11758
CalFresh | Nevada County Only: Mass-Replacement of CalFresh Issuances | [10 empty] | 11410
CalFresh | Nevada County: Deactivate Disaster CalFresh Services in Nevada County | [10 empty] | 11759
CalFresh | Yuba County Only: Mass-Replacement of CalFresh Issuances | [10 empty] | 11411
CalFresh | Yuba County: Deactivate Disaster CalFresh Services in Yuba County | [10 empty] | 11760
CalFresh | Deactivate DSNAP Application on C4Yourself for All C-IV Counties | [10 empty] | 11685
CalFresh | Update C4Yourself office hours for Disaster Affected Counties for 11/01/2017 | [10 empty] | 11797
CalWORKs | ACL 17-108 - (CalWORKs) Changes To Asset Limits For Families That Include Elderly Or Disabled Household Members | [10 empty] | 11242
CalWORKs | ACWDL - Information about 2017 Wildfires | [10 empty] | 11449
Child Care | ACL 17-99 - Update Child Care Regional Market Rate(RMR) Ceilings | [10 empty] | 10359
Medi-Cal | CO-068: DACA Immigration Status Conversion and Lists | [10 empty] | 11436
Medi-Cal | CO-068: Support New CalHEERS Eligibility Evaluation Reason related to Reasonable Opportunity Period | [10 empty] | 6645
Medi-Cal | CO-068: Eligibility for IAP Based on Immigration Status | [10 empty] | 7145
Medi-Cal | CO-068: MCAP/CCHIP Transition to Medi-Cal | [10 empty] | 9117
Medi-Cal | CO-068: Update EHIT Schema to Version 9.0 | [10 empty] | 9355
CalWORKs/CalFresh | ACIN I-70-17 - Implementation of the New Statewide Minimum Wage 2018 | [11 empty] | 10270
Child Care | MB 17-08 / MB 17-09- Update Income Ceilings for Certification of Child Care | [11 empty] | 10024
Child Care | MB 17-11- Revised Family Fee Schedule | [11 empty] | 10622
Correspondence | CO-084: CalWORKs/CalFresh NOAs in Threshold languages Phase 2 of 5 | [11 empty] | 7674
Correspondence | CO-084: ACWDL 17-17: Adding Threshold Languages for MAGI Over Income Discontinuance NOAs | [11 empty] | 9673
Correspondence | CO-101: ACL 17-58 SB 1339 eICT Update M40-195A and Add M40-195B to Template Repository | [11 empty] | 10707
Fiscal | ACL 16-108: Update WIS Establishment Logic for CalFresh Recovery Accounts (Phase 2) | [11 empty] | 5503
Foster Care | CO-100: ACL 17-11 Long Term CCR Policy | [11 empty] | 3933
Foster Care | ACL 17-111: Update ITFC and multidimensional treatment effective 12/01/2017 | [11 empty] | 11911
Foster Care | Children of Foster Care or Kin-GAP Recipients Can be Found Eligible to CalWORKs Benefits (44280) | [11 empty] | 457
Task Management | Task Management: Add Priority Field to Task Types | [11 empty] | 8827
Task Management | Task Management: Collate C4Yourself / Mobile Document Uploads Into One Task | [11 empty] | 9368
CalWORKs | ACL 17-115 - CalWORKs Educational Oppurtunity and Attainment (EOA) - Informing Notice | [12 empty] | 12102
CalWORKs | ACL 17-115 - CalWORKs Educational Opportunity and Attainment (EOA) program | [12 empty] | 12070
Fiscal | ACL 16-108: Update FIN 107 Billing Statement | [12 empty] | 10582
Foster Care | CO 100: ACL 17-11- Run Batch EDBC to Populate Rate Structure | [12 empty] | 11227
Foster Care | CO 100: ACL 17-89 Foster Care Sharing Ratios Policy | [12 empty] | 11142
Foster Care | CO 100 - Add Run EDBC Validation for Foster Care Programs with no Intensive Services Foster Care (ISFC) State Program Number | [12 empty] | 11959
MEDS | 2018 MEDS Renewal and Recon Processing Schedule | [12 empty] | 11813
Multiple | CO-068: ACWDL 18-XX, ACIN I-81-17: 2018 Social Security Title II and Title XVI Cost of Living Adjustments (SSA COLA) Values | [12 empty] | 12147
Multiple | CO-068: ACWDL 18-XX, ACIN I-81-17: Batch EDBC to apply 2018 SSA Cost of Living Adjustments (COLA) | [12 empty] | 12162
Reports | ACL 17-07: Update the Foster Care Caseload Movement Report - CA 237 FC (49696) | [12 empty] | 696
Reports | CFL 16/17-41 16/17-41E Continuum of Care Reform (CCR) Fiscal Reports Updates | [12 empty] | 7338
Reports | ACL 17-XX Online page updates for DSS 466 | [12 empty] | 10511

## Historical - 2016
Project Timeline* - Key Policy Items (Critical, High or Volume Impact) *All items are targeted until approved by the SCRB/CCB process, and, therefore subject to change. Note: Items prior to R15.11x are listed with a Tracker SCR #; items from R15.11x or later have the CCM SCR# |  | 2016-01-01 | 2016-02-01 | 2016-03-01 | 2016-04-01 | 2016-05-01 | 2016-06-01 | 2016-07-01 | 2016-08-01 | 2016-09-01 | 2016-10-01 | 2016-11-01 | 2016-12-01 | 2017-01-01
Program/Topic | C-IV RELEASES | 2016-02-01: Priority; 2016-04-01: Priority; 2016-06-01: Priority; 2016-08-01: Priority; 2016-10-01: Priority; 2016-12-01: Priority
|  | 16.01 |  | 16.03 |  | 16.05 |  | 16.07 |  | 16.09 |  | 16.11 |  | 17.01
ARC | CO-081: ARC - Aid Codes, Manual EDBC & EBT Issuances - Phase 1 (55805) | 2016-01-01: 10
ARC | CO-081: ACL 15-XX Approved Relative Caregiver (ARC) NOAs | 2016-01-01: 1771
AAP | Add Recovery Account Status Reason ‘AAP – Do not collect’ for Status Uncollectible (57360) | 2016-01-01: 1145
CalFresh | Update the CF Determination of Categorically Eligible (CE) for GA/GR (57126) | 2016-01-01: 1389
CW/CF | CO-081: Update Mandatory Inclusion Logic (38747) | 2016-01-01: 1514
CW/CF | Threshold Languages - Add Translated CW/CF RE Packets - Phase 3 (55825) | 2016-01-01: 975
CW/CF | ACIN I-20-14 Revised SAR 7A Forms in Threshold Languages (55102) | 2016-01-01: 915
Multiple | Reports - Update the RE Date Report to Include Customer Report Information (57505) | 2016-01-01: 1162
Technical | eNotification - Add a Statistical Report to C-IV (55925) | 2016-01-01: 986
Technical | Threshold Languages - Adds Multiple Changes to C4Yourself for Threshold Languages | 2016-01-01: Multiple SCRs
WTW | CO-066 ACL 15-62: WTW 24 MTC Form Revisions (57799) | 2016-01-01: 1201
CalFresh | ACL 15-90: Elimination of Change Reporting Informing Notice - Phase 2 | 2016-02-01: 1268
CalWORKs/CalFresh | ACIN I-81-15 - Update Employment Detail Records per new Statewide Minimum Wage (57632) | 2016-02-01: 2423
eHIT | Update C-IV for eHIT Schema 4.0 changes (57394) | 2016-02-01: 1411
eHIT | CO-068: Add support for persons received without a Determination node | 2016-02-01: 2583
Medi-Cal | SB1341 - MAGI NOAs in SAWS (57310) | 2016-02-01: 1242
Medi-Cal | CO-068: Remove 90 Day Cure Language on Medi-Cal Denial NOAs | 2016-02-01: 2564
Medi-Cal | CO-068: Add 2016 Medi-Cal Federal Poverty Level (FPL) values to the system | 2016-02-01: 3112
Medi-Cal | CO-084: Update MAGI Footer to use Physical address and not Mailing Address | 2016-02-01: 3155
ARC | CO-081: Prevent a TANF MAP amount being used with ARC only Aid Code | 2016-03-01: 2418
CalFresh | CO-080: Forms - Adds 13 CF Forms to the Template Repository in Threshold Languages (57264) | 2016-03-01: 1138
CalFresh | Update Prorated Months to Not Close When Allotment Amount is $0 (55415) | 2016-03-01: 942
Medi-cal | CO-068: ACWDL #15-32: Add New Former Foster Youth NOAs (57807) | 2016-03-01: 1202
Medi-cal | CO-084: Add a MAGI RE Error Report to the C-IV System (57116) | 2016-03-01: 1117
Medi-cal | CO-084: Add a MAGI RE Discontinuance Report to C-IV system (57115) | 2016-03-01: 1116
Multiple | Forms - Updates 46 English & Spanish Forms to latest State Versions (57265) | 2016-03-01: 1139
ARC | CO-081: ACL 15-20 & 14-89 - Update Child Support Interfaces for ARC | 2016-04-01: 3317
CalFresh | SIRFRA 3101 - SNAP Application Data Request - Oct-Dec 2015 | 2016-04-01: 3663
CalHEERS | CO-068: Add Functionality to Enable Administrative Soft Pause Lift | 2016-04-01: 2713
CalHEERS | CO-068: Add Functionality to Support New MEC Check Options in CalHEERS | 2016-04-01: 2719
CalHEERS | CO-068: Enable the recently-implemented MAGI MEC and Soft Pause Lift Functionality | 2016-04-01: 2944
CalHEERS | CO-068: Modify Long Term Negative Action Enforcement During SB1341 Transition Period | 2016-04-01: 3316
CalWORKs | ACL 16-XX: COLA for Minimum Basic Standard of Adequate Care (MBSAC) | 2016-04-01: 3961
Medi-cal | CO-068: SB75 Full Scope Medi-Cal for All Children (57535) | 2016-04-01: 1164
Medi-cal | CO-068: SB75 Add new Restricted-Scope MAGI fragments | 2016-04-01: 2642
Medi-cal | CO-068: SB75 Automate EDR and Batch EDBC for Medi-Cal Children age changes | 2016-04-01: 2818
Medi-cal | CO-068: SB75 Reports Updates | 2016-04-01: 3113
Medi-cal | CO-068: SB75, One-Time Batch EDR and Batch EDBC Processing | 2016-04-01: 4024
Medi-cal | ACWDL 16-03 2016 Federal Poverty Levels - Batch Processing | 2016-04-01: 2924
CalFresh | Skip ES with missing postponed verificiations in Batch EDBC | 2016-05-01: 2695
CalFresh | CO-082: Elimination of Change Reporting (57615) Rules | 2016-05-01: 1176
CalFresh | CO-082: Update Periodic Report Due Month Calculation for a 2-year RE Period (49895) | 2016-05-01: 703
CalWORKs | Update EDBC IRT Rules for Mid Period Inc Incr When Only Income is Unearned (49005) | 2016-05-01: 665
Child Care | MB 13-01 - Trustline regulation changes for CAPP (47506) | 2016-05-01: 590
CMSP | CO-089: CMSP-ACL 14-04, 14-06 - Add CMSP 215 (51871) | 2016-05-01: 787
CMSP | CO-089: CMSP ACL 14-09 - Update CMSP Info Notice 1 & 2 (55014) | 2016-05-01: 908
CMSP | CO-089: CMSP: Modify AC 50/Asset Test (57139) | 2016-05-01: 1126
CMSP | CO-089: CMSP - Add new CMSP interface | 2016-05-01: 2834
Forms | Match State Revisions for CF 37 in Threshold Languages (57452) | 2016-05-01: 1158
Medi-Cal | CO-068: MC RE Packets: Suppress packet send if Mixed HH Packet has been sent | 2016-05-01: 1684
Medi-Cal | CO-068: Automate Non-MAGI Packet (56319) | 2016-05-01: 1024
Task Management | CO-086: Redesign Task Pages and Remove Reminders | 2016-05-01: 1568
Technical | Uprade ImageNow to 7.1 (42677) | 2016-05-01: 1455
C4Yourself | CO-088: Horizontal Integration between CalHEERS and C4Yourself | 2016-06-01: 1801
CalFresh | CO-082: Batch to Convert CF Cases From CR to SAR or Semi Annual Reporting Annually | 2016-06-01: 2002
CalFresh | CO 82: Provide a list of Change Reporting CF programs post 6/11/2016 | 2016-06-01: 2688
CalFresh | CO-082: ACL 15-90 - Provide a list of CalFresh Change Reporting Cases | 2016-06-01: 4562
Medi-Cal | CO-068: SIRFRA DHCS Tracking #1019 - 4M Disenrollment Data Search | 2016-06-01: 2342
Medi-Cal | CO-068: MEDIL I 16-04 Update 90-Day Cure Period Language on NOAs | 2016-06-01: 3283
Medi-Cal | Update EDBC Conditions Related to Obsolete MAGI Determinations | 2016-06-01: 4362
CalWORKs/CalFresh | Update Use of the Standard Deduction and Actual Expense for Self-Employment Income (56784) | 2016-07-01: 1083
CalFresh | Apply the CalFresh 20% earned income deduction to gross income (42616) | 2016-07-01: 385
CalHEERS | CO-068: Update the CalHEERS Interface to send Residency Verifications when 'No' and Verified (54104) | 2016-07-01: 871
CalHEERS | CalHEERS CR 3125: Add NQIs Benefit Plan | 2016-07-01: 2359
CalHEERS | NOA Snippets for Electronic Verification of Medicare Enrollment from SSA via the Federal Hub | 2016-07-01: 3946
General Assistance | County Funded: Add General Assistance as a Managed Program into C-IV (56959) | 2016-07-01: 1093
General Assistance | Allow Opt-In Group 2 Counties to utilize the General Assistance Managed program | 2016-07-01: 4016
Medi-Cal | CO-084: Add Functionality to generate NOAs in a recipient's Primary Language and in English (45316) | 2016-07-01: 506
Medi-Cal | CO-068: ACWDL 15-09 MC 216 Pre-Polulated Renewal Form in Threshold Languages | 2016-07-01: 1885
Medi-Cal | CO-068: Delete old OHC records of type “HF – Healthy Family” | 2016-07-01: 3190
Task Management | CO-086: Update Task Long Description Created by Customer Activities | 2016-07-01: 225
C4Yourself | CO-087: Mobile Application | 2016-08-01: 2557
CalFresh | SIRFRA 3101 - SNAP Application Data Request - Jan-March 2016 | 2016-08-01: 4923
CalFresh | ACL 16-XX - CalFresh COLA Increase Effective 10/01/2016 | 2016-08-01: 4935
CalFresh | Revert 20% Earned income deduction changes made through SCR 385 | 2016-08-01: 5062
CalWORKs | CalWORKs - COLA increase effective 10/01/2016 | 2016-08-01: 4719
CalWORKs | ACL 16-64 - Include TEMP 2250 in CW Benefit Increase NOA | 2016-08-01: 5509
CalWORKs / CalFresh | Run batch EDBC to apply the CalFresh (CF) and CalWORKs(CW) Cost Of Living Adjustment (COLA) values | 2016-08-01: 5324
Fiscal | Update the Direct Deposit File Effective Entry Date to handle Same-Day ACH before September 23, 2016 | 2016-08-01: 4957
Foster Care | ACL 16-57 Foster Care Rate Increase (CNI) | 2016-08-01: 1104
Medi-Cal | CO-084: ACWDL 16-14: Update MAGI NOAs with the newly updated MAGI Over Income reason (SB 1341) | 2016-08-01: 4668
MEDS | Update to MEDS Renewal/Recon Processing Schedule for August 2016 | 2016-08-01: 5064
C4Yourself | CO-088 C4Y: Add Upload Document Functionality through the C4Yourself Application (49077) | 2016-09-01: 671
C4Yourself | CO-088: C4Y: Add Appendix A and Health Coverage Questions to C4Yourself (56394) | 2016-09-01: 1031
CalFresh | Heathcock Lawsuit - Threshold Languages [49062 (XREF 43271)] | 2016-09-01: 669
CalFresh | Update the treatment of Veterans income (54393) | 2016-09-01: 1385
CalFresh | CF - Update allotment logic for restoration of aid waiver households (55415) | 2016-09-01: 1697
CalHEERS | CO-068: MC: Insurance Affordability Programs Transition Automation Enhancements (IAP Transition) | 2016-09-01: 4421
CalHEERS | CO-068: Projected Annual Income (PAI) Logic Updates | 2016-09-01: 4454
CalHEERS | CO-068: Support Changes to the CalHEERS System related to Qualified Health Plan (QHP) (CH 59947) | 2016-09-01: 4480
CalHEERS | CO-068: EHIT Schema Update (CR 61123) | 2016-09-01: 4516
Child Care | ACL 16-70: Update Child Care Regional Market Rate (RMR) Ceilings | 2016-09-01: 4911
Correspondence | ACL 14-37: Add 8 Static NOAs to the Template Repository in Threshold Languages | 2016-09-01: 3311
Diversion | Updates to Diversion processing (21976) | 2016-09-01: 18
Fiscal | Update the Transaction Detail page and Reports to support capturing and reporting the State Cycle Number | 2016-09-01: 2250
Fiscal | CFL 15/16-18: Add Recovery Account Transaction Types for new tax intercept percentages and update Tax Intercept Reports | 2016-09-01: 2685
Foster Care | Allow Higher Infant Supplemental Payment for Foster Family Agency Placements (44424) | 2016-09-01: 469
Medi-Cal | CO-084: Add Medi-Cal NOAs in Threshold languages Phase 1 of 4 | 2016-09-01: 3814
Medi-Cal | MC: Add Aid Code MCAP 0G to C-IV | 2016-09-01: 3976
Multiple | Update SAWS 2A SAR in Available Threshold Languages (57037) | 2016-09-01: 1103
Reports | ACL 16-39: Add the New CalFresh Monthly Caseload Movement Statistical Report (CF 296) | 2016-09-01: 3247
WINS | ACIN I-14-14E Work Incentive Nutritional Supplement (WINS) (52402) | 2016-09-01: 807
CalWORKs | ACL 16-XX - CWs - Repeal of MFG Rule - Mass Mailer | 2016-10-01: 4934
CalWORKs | ACL 16-XX - Update IRT levels | 2016-10-01: 6296
Foster Care | ACL 16-57 Foster Care Rate Increase Batch | 2016-10-01: 4955
CalFresh | ACL 15-70 - CF Student Eligibility (57530) | 2016-11-01: 1163
CalFresh | ACL 15-82 - Fleeing felons, probation or parole violators, and persons receiving CF benefits outside of the household are not eligible to TCF benefits | 2016-11-01: 1181
CalFresh / EBT | ACL 14-49, CRPC 2051 - Enable Restaurant Meals Program (RMP) Eligibility Determination and EBT Card Coding (57179) | 2016-11-01: 1129
CalWORKs | ACL 16-XX - REPEAL OF THE MAXIMUM FAMILY GRANT (MFG) RULE | 2016-11-01: 4715
Family Stabilization | CFL 14/15-60 - Add Additional Pay Codes and Fund Codes for Family Stabilization (57756) | 2016-11-01: 1196
Fiscal | Update Valuable Inventory Management | 2016-11-01: 2293
Fiscal | ACL 16-XX: Update WIS Establishment Logic for CalFresh Recovery Accounts | 2016-11-01: 5148
Foster Care | ACL 16-79 - Implement the Short Term Rate Increase for Continuum of Care Reform | 2016-11-01: 5750
Foster Care | CFL 16/17-07 - Add support for issuing and claiming Foster Care or KinGAP Infant Care Supplement Rate Supplement | 2016-11-01: 5179
Medi-Cal | CO-068: MEDIL - 13-03 Update MAGI Pending Eligible logic to treat retro months same as intake (57059) | 2016-11-01: 1107
Medi-Cal | CO-084: Add Medi-Cal NOAs in Threshold languages Phase 2 of 4 | 2016-11-01: 3892
Medi-Cal | CO-068: MEDIL 16-08 2016-2017 Family Member Base Allocation Amount | 2016-11-01: 4901
Reports | CFL 15/16-18: Update FNS 209 to Utilize the State Cycle Number | 2016-11-01: 3686
Task Management | CO-086: Task Management Phase 2 | 2016-11-01: 1569
C4Yourself | CO-087 C4Yourself Mobile App Release 2 | 2016-12-01: 5107
CalFresh | CO-0xx: ACL 16-24 ABAWD Time Limit | 2016-12-01: 3860
CalWORKs | ACIN I-67-16 - Implementation of the New Statewide Minimum Wage | 2016-12-01: 5802
CalWORKs | CO XX - ACL 16-66 - Apply mid-period logic to Child Support income for child who was previously a Maximum Family Grant (MFG) Child | 2016-12-01: 6735
Foster Care | CO-XX : ACL 16-79 Update the Foster Care Basic Rate on the ARC Manual EDBC to HBFC rate | 2016-12-01: 6508
Multiple | CO-091: ACL 16-24, 16-79, 16-66, 16-94: Batch EDBC for Continuum of Care Reform, Elimination of MFG and CalWORKS (CW) Tier 1 IRT cases, Batch ABAWD for CalFresh (CF) | 2016-12-01: 6372

## Historical - 2015
Project Timeline* - Key Policy Items (Critical, High or Volume Impact) *All items are targeted until approved by the SCRB/CCB process, and, therefore subject to change. Note: Items prior to R15.11x are listed with a Tracker SCR #; items from R15.11x or later have the CCM SCR# |  | 2015-02-01 | 2015-03-01 | 2015-04-01 | 2015-05-01 | 2015-06-01 | 2015-07-01 | 2015-08-01 | 2015-09-01 | 2015-10-01 | 2015-11-01 | 2015-12-01 | 2016-01-01
Program/Topic | C-IV RELEASES | 2015-03-01: Priority; 2015-05-01: Priority; 2015-08-01: Priority; 2015-10-01: Priority; 2015-12-01: Priority
|  | 15.02 |  | 15.04 |  |  | 15.07 |  | 15.09 |  | 15.11 |  | 16.01
Medi-Cal | CalHEERS - Update 'Req Disc-Written' Neg Actn Reason to Bypass MAGI Validation | 2015-04-01: 55895
Medi-Cal | CalHEERS - Update Citizenship Mapping | 2015-04-01: 55659
Medi-Cal | CalHEERS - Update Citizenship indicators and verification flags in EDR | 2015-04-01: 55685
Medi-Cal | CalHEERS - Update Outstanding EDR Report to Distinguish Between Batch or Online Generated | 2015-04-01: 55419
CW/CF | EBT - Replacement of Lost Benefits due to Electronic Theft | 2015-04-01: 48043
eICT | eICT - Update eICT Data Collection pages to include CH, WTW and CF data elements | 2015-04-01: 41203
CalWORKs | Family Stabilization - Add Additional Pay Codes | 2015-04-01: 54570
Medi-Cal | MAGI - Case Listing for MAGI Linkage Evaluation | 2015-04-01: 56172
CalWORKs | NOAs - Add CalWORKS Family Stabilization Program Notice and Forms | 2015-04-01: 54426
Medi-Cal | Reports - Add MAGI RE Packet Information to the Customer Reporting Progress Reports | 2015-04-01: 55210
CW/CF | SAWS 2 Plus - Update to match 12/2014 version and Root Questions | 2015-04-01: 51969
CalFresh | WINS - Monthly Caseload Report - WINS 2 | 2015-04-01: 55203
WTW | WPR - Long-Term WTW Sanction ON-GOING Monthly Batch Process to Move to K1/3F Aid Codes | 2015-04-01: 55940
Medi-Cal | Batch - 2015 FPL and SSA COLA Run for Medi-Cal | 2015-05-01: 53787
CalFresh | WINS - Update Monthly WINS Sweep to Remove 6-Month Check | 2015-05-01: 56482
CalWORKs | MBSAC - Update CalWORKs MBSAC Values for SFY 15-16 | 2015-06-01: 56727
CalFresh | ABAWDS - Update STAT 47, Discontinue STAT 48 and Add an Automated ABAWD Indicator | 2015-07-01: 55563
Child Care | Child Care - Updates to Pay Codes to Consolidate Expenditures | 2015-07-01: 50824
eICT | eICT - Update Interface for CH, WTW and CF data elements + CF Forms | 2015-07-01: 56258
eICT | eICT - Update Interface to include LRS | 2015-07-01: 55280
CalFresh | Forms - Adds 13 CF Forms/NOAs to TR & Updates 14 CF Forms/NOAs in the TR | 2015-07-01: 53413
CW/CF | Forms - Revise AR3, SAR3/7/7A, CW 8/8A/2211/2212 | 2015-07-01: 56068
CW/CF | Forms - Update CW/CF IRT Noticing - Phase 1 | 2015-07-01: 56091
CalWORKs | Income - Update Veteran's Disability to be Counted as CW Unearned Income + Lists | 2015-07-01: 50413
Medi-Cal | MAGI - Add a MAGI RE Packet for Mixed Households | 2015-07-01: 55186
Medi-Cal | Non-MAGI - Add a Non-MAGI Screening Packet to C-IV | 2015-07-01: 52065
CalWORKs | NOAs - CalWORKs Promissory Note Changes for OP Collection | 2015-07-01: 55983
WTW | WTW - Add 2 New Forms & 7 New Extension WDTIP TRAC Codes | 2015-07-01: 53986
WTW | WTW - Add WTW 38 to Template Repository | 2015-07-01: 56187
Technical | Technical - Upgrade C-IV System Platform Products (Includes JRules) | 2015-07-01: 55533
Medi-Cal | CalHEERS - Long Term Negative Action | 2015-07-01: 56121
Child Care | Child Care - Update Regional Market Rate (RMRs) | 2015-08-01: 57047
CalWORKs | Forms - Update VER 102 form School Attendance Requirements | 2015-08-01: 57046
Medi-Cal | MC - Update Disc & Denial NOAs and 90 day cure wording | 2015-08-01: 57079
CalFresh | FFY 2015 SUA, LUA, TUA, CalFresh COLA 2015-2016 | 2015-08-01: 57334
CalFresh | Activate Disaster Services in C-IV and C4Y for Lake County | 2015-08-01: 57538
CalFresh | Mass-Replace CalFresh Issuances for Counties affected by the wildfires | 2015-08-01: 57557
CalFresh | RE - Add New CalFresh RC Form CF37 | 2015-09-01: 55299
CalWORKs | CalWORKs - Updates to PWO and PSN | 2015-09-01: 50575
CalWORKs | Reports - Update CW Reports for K1/3F Aid Codes (XREF 57281) (K1/3F) | 2015-09-01: 56081
CW/CF | Forms - Update CW/CF IRT Noticing - Phase 2 | 2015-09-01: 56581
CW/CF | Threshold Languages - Add Translated CW/CF RE Packets - Phase 1 | 2015-09-01: 55823
eHIT | Remove multi-disposition logic from DERs | 2015-09-01: 57170
Family Stabilization | Family Stabilization - Add Pay Codes for Valuables | 2015-09-01: 55977
Medi-Cal | MC - Updates for FFCC Mandatory/Optional Coverage Groups | 2015-09-01: 55320
Medi-Cal | Reports - Add a Batch MAGI Skipped Report | 2015-09-01: 56464
Technical | C4Y - Allow Customers to Opt In/Out to Electronic and Text Notifications from C4Yourself | 2015-09-01: 55142
Technical | eNotification - Add a Check for C4Y Account Type | 2015-09-01: 56540
Technical | RE - Allow BDA to be Editable for Persons Added During RE Process | 2015-09-01: 50012
Technical | Texting - Roll out Functionality to 35 non-pilot counties | 2015-09-01: 56145
CalFresh | SIRFRA 3101 - SNAP Application Data Request - April - June 2015 | 2015-10-01: 57757
CalFresh | ACIN I-75-15- FFY 2016 SUA, LUA, TUA, CalFresh COLA 2015-2016 Batch | 2015-10-01: 57361
CalWORKs | ACIN 15-75 CalWORKs Federal Fiscal Year (FFY) 2016 Income Reporting Threshold (IRT) COLA | 2015-10-01: 57581
CalWORKs | Batch - Run EDBC for Active CW Cases with K1/3F Aid Codes (XREF 56081) w/Lists | 2015-10-01: 57281
CalWORKs | ACL 15-XX Definition of Fleeing Felon for the CalWORKs and CalFresh Programs - list | 2015-10-01: 57666
Medi-Cal | Limit Medi-Cal RE Batch EDBC to One Processing Attempt | 2015-10-01: 57190
Medi-Cal | MEDIL 15-21/ACWDL 15-27E: Update MC Neg Actn NOA Logic to Display Non-Cmplnc Reasons | 2015-10-01: 57417
Technical | Upgrade C-IV database to Oracle 12c | 2015-10-01: 54930
CalFresh | Heathcock Lawsuit - Update CalFresh OI Notices (XREF 49062) | 2015-11-01: 43271
CalWORKs | Add Housing Support Program Pay Codes | 2015-11-01: 57038
CalWORKs | CW - Updates the School Attendance Eligibility Requirements & Noticing | 2015-11-01: 55746
CalWORKs | Noticing - Adds 7 CalWORKs NOAs to the Template Repository | 2015-11-01: 44147
CalWORKs | Time Clocks - Add Perm and Temp HA Aid codes to count for TANF and CW | 2015-11-01: 55552
Child Care | Reports - ACL 15-35 Update CW 115 and CW 115A Reports | 2015-11-01: 53735
CW/CF | Forms - Update SAWS 2A SAR in English and Spanish | 2015-11-01: 56445
CW/CF | Threshold Languages - Add Translated CW/CF RE Packets - Phase 2 | 2015-11-01: 55824
Foster Care | ACL 12-43/15-58E AFDC -FC Increase Update FFA Intensive Treatment Rates | 2015-11-01: 45837
Multiple | CO-068: Add statuses to the Customer Reporting Progress Reports | 2015-11-01: 57454
Technical | MEDS - Update Interface EW Transaction Logic for ICTs | 2015-11-01: 46724
Technical | CO-068: Update Referral Linkage for C-IV eICT and CalHEERS | 2015-11-01: 56002
Technical | Technical - Add IE 11 as a Supported Browser Platform | 2015-11-01: 56710
Technical | Threshold Languages - Adds Multiple Changes to C4Yourself for Threshold Languages | 2015-11-01: Multiple SCRs
CalFresh | CO82: ACL 15-90: Elimination of Change Reporting Informing Notice - Phase 1 (57958) | 2015-12-01: 1279
CalWORKs | ACL 15-87: Earned Income Tax Credit (EITC) Notification through IVR & C4Y | 2015-12-01: 1507
Medi-Cal | CO68: ACWDL 16-XX Remove the Express Lane Program End Date | 2015-12-01: 2179
Medi-Cal | Batch: 2016 MEDS Renewal/RECON Calendar | 2015-12-01: 1607

## Historical - 2019
Project Timeline* - Key Policy Items (Critical, High or Volume Impact) *All items are targeted until approved by the SCRB/CCB process, and, therefore subject to change. |  | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01
Program/Topic | C-IV RELEASES | 2018-12-01: Priority; 2019-02-01: Priority; 2019-04-01: Priority; 2019-06-01: Priority; 2019-08-01: Priority; 2019-10-01: Priority; 2019-12-01: Priority; 2020-02-01: Priority; 2020-04-01: Priority; 2020-06-01: Priority; 2020-08-01: Priority; 2020-10-01: Priority; 2020-12-01: Priority
|  |  | 19.01 |  | 19.03 |  | 19.05 |  | 19.07 |  | 19.09 |  | 19.11 |  | 20.01 |  | 20.03 |  | 20.05 |  | 20.07 |  | 20.09 |  | 20.11 |  | 21.01