## North - CCB Approved
No. | SCR | Summary | Change Type (SCR) | SPG Priority | Status | Release | Minor Version | Other Agency Cross Reference | Committee
1 | CIV-106585 | ACL 19-24 Create list of cases aided on 5K-EA greater than 180 days | New Policy | High | New | TBD |  | CA-214133 | Foster Care/Kin GAP/AAP
2 | CIV-103675 | Migrate Monterey County IVR to Amazon Connect | Enhancement | High | Test Complete | 20.02 | 20.03.19 | CA-207026 | Contact Center Management
3 | CIV-103674 | Migrate Stanislaus County IVR to Amazon Connect | Enhancement | High | Test Complete | 20.02 | 20.03.12 | CA-207026 | Contact Center Management
4 | CIV-105458 | Automated Regression Test - Execution and Maintenance - 20.01 Release Cycle | Operational Enhancement | Medium | System Test | 20.02 | 20.03.XX | CA-211451 | Other
5 | CIV-106400 | ABAWD Clickthrough Support | Enhancement |  | Test Complete | 20.02 | 20.02.26 | CA-213548 | CalWORKs/CalFresh
6 | CIV-106533 | CCP Enhancements (Logging, Error Handling for failed Supervisor actions) | Enhancement |  | Test Complete | 20.02 | 20.03.09 |  | IVR & Contact Center
7 | CIV-106058 | Generate CF377.11C For Counties Losing ABAWD Waiver | New Policy | High | System Test | 20.02 | 20.03.19 | CA-212648 | CalWORKs/CalFresh, Correspondence
8 | CIV-105922 | Imaging: Create Imaging Script/Task to route back incorrectly indexed documents | Enhancement | Medium | Test Complete | 20.03 |  |  | Imaging
9 | CIV-105633 | Automated Regression Test - Execution and Maintenance - 20.03 Release Cycle | Operational Enhancement | Medium | In Development | 20.03 | 20.05.XX | CA-211827 | Other
10 | CIV-106069 | Update Tuolumne County GA Issuance Threshold | Enhancement | Medium | Test Complete | 20.03 |  |  | Fiscal
11 | CIV-104011 | ACL 19-34 Update Kin-GAP Beginning Date of Aid Rules to Accept Mid-Month Application Date | New Policy | High | System Test | 20.03 |  | CA-208184 | Foster Care/Kin GAP/AAP
12 | CIV-102442 | CO-1072-2018 -Update Address for Chico Office in IVR & C4Yourself | Operational Enhancement | Medium | Test Complete | 20.03 |  |  | IVR & Contact Center
13 | CIV-102600 | ACL 14-20 -CF 29A (2/14) - CalFresh Initial Appointment Letter | Policy Re-Design | High | Test Complete | 20.03 |  | CA-205414 | Correspondence
14 | CIV-105757 | CO12949-2019 Update Message of the Day Refresh Interval & Useful Links In Amazon CCP | Enhancement | Medium | Test Complete | 20.03 |  |  | IVR & Contact Center
15 | CIV-106577 | Update May Payroll dates for May 2020 and December 2020 for 37 Counties | Operational Enhancement | Medium | New | 20.03 | x |  | Fiscal
16 | CIV-103672 | Migrate San Bernardino County IVR to Amazon Connect | Enhancement | High | In Assembly Test | 20.03 | 20.04.23 | CA-207026 | IVR & Contact Center
17 | CIV-5165 | Add Medi-Cal Negative Action Reason 'Worker Initiated-Skip CalHEERS' | Enhancement | Medium | System Test | 20.03 |  | CA-209381 | Medi-Cal/CMSP
18 | CIV-9947 | Change Recovery Account Cause Code editing logic | Enhancement | High | Test Complete | 20.03 |  | CA-205652 | Collections
19 | CIV-789 | ACL 14-12, CFL 13/14-35 Family Stabilization Program for CalWORKs (51903) | Policy Re-Design | High | System Test | 20.03 |  | CA-51700, CA-57298 | Welfare to Work/WPR
20 | CIV-103666 | Migrate Riverside County IVR to Amazon Connect | Enhancement | High | System Test | 20.03 | 20.04.09
21 | CIV-105185 | Update CFWR Work Registration Exempt Status Reason Replace â€œPhysically/Mentally Incapacitatedâ€ with â€œUnfit For Employment-Medically Verifiedâ€ | Policy Re-Design | High | System Test | 20.03 |  | CA-210813 | CalWORKs/CalFresh
22 | CIV-105065 | NB Application Future Application Date | Enhancement | High | Test Complete | 20.03 |  | CA-210498 | CalWORKs/CalFresh
23 | CIV-104559 | ACL 19-67 - CalWORKs: Changes to Asset and Vehicle Value Limits | New Policy | High | Test Complete | 20.03 |  | CA-209360 | CalWORKs/CalFresh
24 | CIV-10075 | Add Need Categories for Family Stabilization and Housing Support to Needs Detail page | Enhancement | High | System Test | 20.03 |  | CA-205441 | Fiscal
25 | CIV-104040 | ACL 18-107, ACL 18-108 - SNB/TNB Forms and Notices - Threshold Languages Phase 3 | New Policy | Critical | System Test | 20.03 |  | CA-208261 | Correspondence
26 | CIV-103677 | Migrate Regional Contact Center IVR to Amazon Connect | Enhancement | High | System Test | 20.03 | 20.04.09 |  | IVR & Contact Center
27 | CIV-11725 | Add functionality to manage Conditionally Eligible status in MAGI Determinations | Enhancement | High | Test Complete | 20.03 |  | CA-203824, CA-211516 | Medi-Cal/CMSP
28 | CIV-104670 | Update NA 791 | Policy Re-Design | Medium | Test Complete | 20.03 |  | CA-203787 | Correspondence, Foster Care/Kin GAP/AAP
29 | CIV-102568 | ACL 18-92, ACL 18-107 Transitional Nutrition Benefit Program Recertification | New Policy | Critical | System Test | 20.03 |  | CA-205328 | CalWORKs/CalFresh
30 | CIV-104322 | New data elements to be added to the EICT Outbound file to indicate CalFresh SSI/SSP Reversal. | Enhancement | Critical | Test Complete | 20.03 |  | CA-208888 | ICT
31 | CIV-104383 | ACL 19-76 - CalWORKs Change in Earned Income Disregard (EID) and Income Reporting Thresholds Tiers (IRTs) | New Policy | High | In Development | 20.03 | 20.04.16 | CA-209033 | CalWORKs/CalFresh
32 | CIV-103676 | Migrate Kings County IVR to Amazon Connect | Enhancement | High | System Test | 20.03 | 20.03.26 | CA-207026 | Contact Center Management
33 | CIV-106597 | Update CF 377.11E Return Mailing Address to match BRM | New Policy |  | System Test | 20.03 | 20.03.10 |  | CalWORKs/CalFresh
34 | CIV-66 | Aligning Status Begin Date of Associated Programs With Primary Cash Aid Programs or EDBC Run Date, whichever is later | Enhancement | High | In Development | 20.05 |  | CA-58934 | Welfare to Work/WPR
35 | CIV-103679 | Migrate Non-Contact Center County IVRs to Amazon Connect | Enhancement | High | In Development | 20.05 |  |  | IVR & Contact Center
36 | CIV-104826 | Add threshold language translations for the newly added MAGI and Non-MAGI YAE fragments | New Policy | High | Design in Progress | 20.05 |  | CA-209956 | Correspondence
37 | CIV-105307 | Imaging: Update Imaging script to include Mobile, Kiosk, and Clerical Default Document Types | Enhancement | Low | System Test | 20.05 |  |  | Imaging
38 | CIV-7564 | Revised Medi-Cal Hierarchy | New Policy | Critical | In Development | 20.05 |  | CA-202778 | Medi-Cal/CMSP
39 | CIV-102191 | ACL 19-40 CalWORKs Outcome and Accountability Review (Cal-OAR) Phase II | New Policy | High | In Development | 20.05 |  | CA-204569 | Welfare to Work/WPR
40 | CIV-4108 | CO-113: Online CalWORKs Appraisal Tool (OCAT) Integration | Enhancement | High | In Assembly Test | 20.05 |  | CA-50302 | Welfare to Work/WPR
41 | CIV-104367 | ACWDL June 11, 2019; CFL NO. 18/19-26 Add Functionality for Housing Support Program (HSP) | New Policy | Critical | In Development | 20.05 |  | CA-208988 | CalWORKs/CalFresh
42 | CIV-103887 | Create State Agency Accounts for Designated DHCS and CDSS Staff | Enhancement | Low | In Development | 20.05 |  | CA-209032 | Other
43 | CIV-103989 | CFL 18/19-49 Create new Pay Codes for CalWORKs Home Visit Program (HVP) | New Policy | Medium | In Development | 20.05 |  | CA-208155 | Fiscal
44 | CIV-105913 | Updates to Generation of NA 823 and NA 820 for HSP and HVP | New Policy | High | Pending Approval | 20.05 |  | CA-212411 | Correspondence
45 | CIV-104671 | Update Previous Potential Benefit Calculation Logic | Enhancement | High | In Assembly Test | 20.05 |  | CA-209661 | Collections, State/Fiscal Reports
46 | CIV-106191 | Update Suspend logic for Tax Intercept Balancer | Enhancement | Medium | In Assembly Test | 20.05 |  |  | Tax Intercept
47 | CIV-104042 | ACL 19-42 Implement the Automation of CalWORKs Home Visiting Program (HVP) | New Policy | High | Approved | 20.05 |  | CA-208265 | CalWORKs/CalFresh, Welfare to Work/WPR
48 | CIV-103387 | Modify Existing Report | Enhancement | High | In Development | 20.05 |  | CA-211200 | State/Fiscal Reports
49 | CIV-105575 | CalHEERS eHIT: Update Interface Schema to version 15 | Enhancement | High | In Development | 20.06 |  | CA-211616; CH-154346 | Medi-Cal/CMSP
50 | CIV-106264 | Automated Regression Test - Execution and Maintenance - 20.05 Release Cycle | Operational Enhancement | Medium | New | 20.06 | 20.07.XX | CA-213283 | Other
51 | CIV-10791 | Prevent Advancing Medi-Cal Renewal with a Soft Pause Individual | New Policy | Critical | In Development | 20.06 |  | CA-58123 | Medi-Cal/CMSP
52 | CIV-1068 | CalHEERS eHIT: Married Filing Jointly and Out-of-State Address | Enhancement | High | In Development | 20.06 |  | CA-208863 ; CH-153970 | Medi-Cal/CMSP
53 | CIV-105722 | Update C4Yourself and C4Y mobile App downtime message page with external links and phone numbers | Operational Enhancement | High | Design in Progress | 20.07 |  | CA-212039
54 | CIV-103678 | Migrate Outbound Calling Campaigns to Amazon Connect | Enhancement | High | Design in Progress | 20.07 |  |  | IVR & Contact Center
55 | CIV-105460 | Enhance Replacement CalFresh Issuances to be replaceable up to Original Issuance Amount | Enhancement | High | Design in Progress | 20.07 |  |  | Fiscal
56 | CIV-102606 | Add State PINs to Integrated Service Payment / Valuable Detail Claiming Report | Enhancement | Medium | Approved | 20.07 |  | CA-209221 CA-208814 CIV-104015 | State/Fiscal Reports
57 | CIV-101447 | CF 387 CalFresh Request for Information for Residency | Enhancement | Medium | Approved | 20.07 |  | CA-49633 | CalWORKs/CalFresh
58 | CIV-104986 | Deactivating Pre-ACA Aid Codes | New Policy | High | Approved | 20.07 |  | CA-210307 | Medi-Cal/CMSP
59 | CIV-100845 | CF 296 - Changes in logic for Line 10 - Overdue Recertifications (CWD Caused) during the month | Policy Re-Design | Medium | Approved | 20.07 |  | CA-201742 | State/Fiscal Reports
60 | CIV-106126 | Imaging: Associate Doc Types to Views | Operational Enhancement | Low | Approved | 20.07 |  |  | Imaging
61 | CIV-106271 | Automated Regression Test - Execution and Maintenance - 20.07 Release Cycle | Operational Enhancement | Medium | New | 20.07 | 20.09.XX | CA-213304 | Other
62 | CIV-106135 | Update Riverside County Main Payroll date for December 2020 | Operational Enhancement | Medium | New | 20.09 |  |  | Fiscal

## North - SPG Approved
No. | SCR | Summary | Change Type (SCR) | SPG Priority | Status | Other Agency Cross Reference | Committee
1 | CIV-67 | Change Security to Allow all User Access to Release Note Report (31889) | Enhancement | Medium | New | CA-206709 | Security, Usability
2 | CIV-84 | IEVS: Review Findings Security Rights (32932) | Enhancement | Low | New |  | IEVS
3 | CIV-272 | Add additional field for known CIN (40067) | Enhancement | High | New |  | MEDS
4 | CIV-331 | Update Event Logic when Moving the BDA or Logging a Rescind | Enhancement | High | New | CIV-200895 | CalWORKs/CalFresh
5 | CIV-391 | Add Edit Functionality to a Service Arrangement | Enhancement | Critical | Design in Progress | CA-204582 | Welfare to Work/WPR
6 | CIV-430 | Count CalWORKs clock when Extender is added | Enhancement | High | New | CA-53782, CA-53784 | Time Limits
7 | CIV-533 | Update WEX/CS WorkSheet Detail Page | Enhancement | Medium | Design in Progress | CA-55200 and CIV-5340 | Welfare to Work/WPR
8 | CIV-580 | Update Application Detail to support View Mode (47286) | Enhancement | Medium | New | CA-206708 | Security, Usability
9 | CIV-661 | Automate the creation of months for Supportive Service recipients | Enhancement | Critical | Design in Progress | CA-210580 | Time Limits
10 | CIV-4400 | County Funded: Add General Assistance (Managed) Program NOAs and Forms | Enhancement | Critical | Ready for Committee |  | Other
11 | CIV-8583 | Time Limit Months for Immediate Need program | Enhancement | Critical | New | CA-204823 | Time Limits
12 | CIV-8786 | eICT: Add a Cancellation Reason Indicator to the eICT Interface | Enhancement | Medium | New | None | ICT
13 | CIV-9638 | eICT: Add validation to the 'Last Month of Aid' field while sending ICT. | Enhancement | Medium | New | None | ICT
14 | CIV-11907 | Flip ICT Status to Manually Complete | Enhancement | High | Design in Progress | 49021 | ICT
15 | CIV-12157 | Update logic to prevent UEID when changing the worker assigned to a Service | Enhancement | Medium | New | None | Security, Usability
16 | CIV-12446 | CA 812 Collection Reports Claim Adjustments | Enhancement | High | Committee Review | CA-52597 | State/Fiscal Reports
17 | CIV-100040 | Display Important County Dates Phase I | Enhancement | Medium | New | CA-201813 | Usability
18 | CIV-100260 | IEVS: Do not create tasks for IEVS abstracts that have been automatically closed. | Enhancement | High | New | CIV Specific | IEVS
19 | CIV-100400 | CES 2017-102 IEVS Income ending do not close abstract | Enhancement | Medium | Ready for Committee | CA-207572 | IEVS
20 | CIV-100504 | Update Bank Routing Information for Direct Deposit | Enhancement | High | Ready for Committee | CA-207344 | Fiscal
21 | CIV-101131 | CES 2018-035: Add Language to Text Notifications if appointments are in Person or by Telephone | Enhancement | Medium | New |  | IVR & Contact Center
22 | CIV-101174 | Update 206-Cal-Learn Time Limit Exemption to not apply to WTW time clock | Enhancement | High | New | CA-202482 | Welfare to Work/WPR
23 | CIV-101358 | ICT: Update the additional document type list to display alphabetically | Enhancement | Medium | New | CA-202781 | ICT
24 | CIV-101649 | Task Management: Update the Task Reassignment Detail page to include a Task Bundling option | Enhancement | Low | New
25 | CIV-102098 | Do not Create an Offset Transaction for Overpayment/Overissuances Adjustments | Enhancement | Critical | New | CA-204762 | Collections, State/Fiscal Reports
26 | CIV-102275 | Convert the Engagement and Longitudinal Analysis Reports in Business Intelligence to be On-Request Reports | Enhancement | Medium | Design in Progress |  | Management Reports
27 | CIV-102291 | WTW 24 MTC - Update WTW 24 MTC from Verified Actual Hours (Priority 10) | Enhancement | Critical | New | CA-53786 | Welfare to Work/WPR
28 | CIV-102292 | Convert the Caseload Inventory Report in Business Intelligence to be On-Request Reports | Enhancement | Medium | Design in Progress |  | Management Reports
29 | CIV-102305 | WTW 24 MTC - Update Tracking of Voc Ed (Priority 11) | Enhancement | Critical | New | CA-53787 | Welfare to Work/WPR
30 | CIV-102312 | Separate Penalties for "Assign Support Rights" Non-Compliance | Enhancement | High | New |  | CalWORKs/CalFresh
31 | CIV-102423 | Redesign FC Facility Ratios page ? Need to store historical ratio info based on the eff. date for Group Home and Foster Family Agency type | Enhancement | High | New | CA-55206 | RDB
32 | CIV-104299 | CalHEERS eHIT: Add SCAI to MAGI Medi-Cal Income Budget Periods | Enhancement | Critical | Design in Progress | CA-208864; CH-151332 | Medi-Cal/CMSP
33 | CIV-104321 | eICT: Updates for eICT Schema | Enhancement | High | Design in Progress | CA-208889; CH-106890; CH-109700; CH-109744; CH-109927; CH-113161; CH-121151; CH-131449; CH-136022; CH-137942; CH-139211; CH-139410; CH-139419; CH-92295; CH-92298 | ICT
34 | CIV-104665 | Add Threshold Languages for FC/KG CNI NOA Fragment | Enhancement | High | Design in Progress | CA-209638 | Correspondence
35 | CIV-104947 | Updates to reschedule the Restaurant Meals Batch EDBC Sweep | Enhancement | High | Design in Progress |  | CalWORKs/CalFresh
36 | CIV-105277 | Auto assign task to the MC Worker for the IEVS NHR combo (CF and MC) only case | Enhancement | High | Pending Approval | CA-210948 | Medi-Cal/CMSP
37 | CIV-105746 | Allow CalFresh Recovery Accounts to be set to active status | Enhancement | Medium | Committee Review | CA-212087 | Collections
38 | CIV-106351 | CalHEERS eHIT: BREfS: Enhance eHIT Verifications | Enhancement | High | Design in Progress | CA-213468; CH-158675 | Medi-Cal/CMSP
39 | CIV-106387 | Security to enable pages being added for the interface to OCAT | Enhancement | High | Design in Progress |  | Welfare to Work/WPR
40 | CIV-572 | Update MEDS to Send Prior FC / KG Aid Code to MEDS for NMD's Minor Infant Child (47096) | New Policy | High | Design in Progress | CA-203208 | MEDS
41 | CIV-632 | ACL 12-67, ACL 13-19, ACL 13-37, ACL 13-59 Welfare to Work (WTW) 24-Month Time Clock- Phase 3 (48176) | New Policy | High | New |  | Time Limits
42 | CIV-832 | ACL 14-64: Add CalWORKs Family Stabilization (FS) Program Quarterly Status Report - FSP 14 (53467) | New Policy | Critical | New | CA-56913 | State/Fiscal Reports
43 | CIV-966 | ACL 15-03: Transitioning from WTW 24 MTC Participation to Post WTW 24 MTC CW Federal Standards (55674) | New Policy | High | New |  | Welfare to Work/WPR
44 | CIV-1143 | ACL 16-14 - Expedited Service Entitlement and Application Processing for CalFresh (57327) | New Policy | Critical | New | CA 213349 | CalWORKs/CalFresh
45 | CIV-3094 | ACL 14-28 - Expansion of the Definition of Relative for the Kin-GAP Program | New Policy | High | New | None | Foster Care/Kin GAP/AAP
46 | CIV-7522 | Update EDBC to process mid-period TCF programs via eICT | New Policy | High | New | CA-200800 | CalWORKs/CalFresh, ICT
47 | CIV-7859 | ACL 16-98: Change HA Eligibility From 12-Month to 365-Day Period; Limit HA Manual and Override EDBC drop down values | New Policy | High | Design in Progress | CA-50686 and CA-51882 | CalWORKs/CalFresh
48 | CIV-8576 | Update special needs to issue current state amounts | New Policy | Medium | New | None | CalWORKs/CalFresh
49 | CIV-8633 | ACWDL 17-12: Changes to the Designation and Responsibilities of the Medi-Cal Authorized Representative | New Policy | Critical | New | CA-208191 | Medi-Cal/CMSP
50 | CIV-8975 | NFC 17-023: Update SAR 2 to latest state revision | New Policy | High | New | CA-202463 | Correspondence
51 | CIV-9259 | ACL 17-31 Application Procedures for CAPI | New Policy | Low | New | None | CalWORKs/CalFresh
52 | CIV-9741 | ACIN I-33-17 - Temporary absence in CalWORKs for hospital stay remains CWs eligible for duration of hospital stay | New Policy | Low | New | CA-49414 | CalWORKs/CalFresh
53 | CIV-10156 | CalFresh E&T Reporting | New Policy | High | New | CA-204858 | State/Fiscal Reports
54 | CIV-10179 | ACL 17-53: ESAP Notices Threshold Languages | New Policy | Medium | New | LRS 52758, 54952 | Correspondence
55 | CIV-10972 | ACL 17-87 -CalWORKs update to immunization penalty | New Policy | Medium | New | CA-201440 | CalWORKs/CalFresh
56 | CIV-12023 | ACWDL 17-36 - NOA snippets for Medi-Cal Inmate Program | New Policy | Medium | New | CA-200866 | Correspondence
57 | CIV-100213 | ACL 18-07 - SUSPENSION, REINSTATEMENT AND TERMINATION OF AND REAPPLICATION FOR CASH ASSISTANCE PROGRAM FOR IMMIGRANTS (CAPI) BENEFITS; TRANSMISSION OF UPDATED CAPI NOTICE OF CHANGE (NA 692) | New Policy | High | New |  | Correspondence
58 | CIV-100535 | ACL 18-16 - CalFresh Exclusion of Funeral Agreement from Resources | New Policy | Low | New |  | CalWORKs/CalFresh
59 | CIV-100580 | ACL 18-XX CW & CF: Partial Revision of State Automated Welfare Systems (SAWS) 2 PLUS Application Forms | New Policy | High | New | CA-202458 | Correspondence
60 | CIV-100774 | Updates to the GEN 1365 Form and Form Generation | New Policy | High | New | CA-202307 | Correspondence
61 | CIV-100878 | ACL 18-117: Implement CalFresh Churn Monthly Caseload Report - CF 18 | New Policy | High | Ready for Committee | CA-201836 | State/Fiscal Reports
62 | CIV-101796 | ACWDL 18-17: Translations â€“ MC 604 MDV Doctorâ€™s Verification (Reference All County Welfare Directors Letter No. 17-25) | New Policy | High | New | CA-203671 | Correspondence
63 | CIV-102263 | ACL 18-99 CF OI Collection Period | New Policy | Critical | New | CA-204863 | Collections
64 | CIV-102757 | ACL 18-75 Phase IV-Long Term Funding for Emergency Caregivers with Placements Prior to RFA Approval | New Policy | Critical | New | CA-205633 | Foster Care/Kin GAP/AAP
65 | CIV-102912 | ACL 18-75 Add 5L Aid Code for FC Emergency Assistance EC Ineligible Cases | New Policy | High | Design in Progress | CA-205913 | Foster Care/Kin GAP/AAP
66 | CIV-103015 | ACL 18-141 CF REVISED SUPPLEMENTAL FORM FOR EXCESS MEDICAL DEDUCTIONS (CF 31) | New Policy | High | New | CA-206080 | Correspondence
67 | CIV-103743 | ACL 18-08 - ABAWD - Phase III | New Policy | Critical | Design in Progress | CA-207637 | CalWORKs/CalFresh
68 | CIV-103934 | Cal-OAR - Phase I - Automation Alternative | New Policy | High | New | CA-208030 | Welfare to Work/WPR
69 | CIV-103983 | MEDIL I 19-12: Update on Asset Verification Reports | New Policy | High | Design in Progress | CA - 208130 | IEVS
70 | CIV-104019 | ACL 19-31and CFL 19/20-14 - Re-Entry into Extended Foster Care for Youth Receiving SSI | New Policy | High | New | CA-208203 | Foster Care/Kin GAP/AAP
71 | CIV-104043 | ACL 18-107, ACL 18-108 - SNB/TNB Forms and Notices - Threshold Languages Phase 4 | New Policy | Critical | Pending Approval | CA-208268 | Correspondence
72 | CIV-104574 | ACL 19-59 Revise DFA 358F and DFA 358S | New Policy | High | Committee Review | CA 209404 | State/Fiscal Reports
73 | CIV-104584 | Update Medi-Cal Auto-Discontinuance Batch for Failure to Complete RE to process at an Individual Level | New Policy | High | Design in Progress | CA-209422, CA-212697. | Medi-Cal/CMSP
74 | CIV-104703 | ACL 19-75 Revisions to ABCD 350 | New Policy | High | Committee Review | CA 209709 | State/Fiscal Reports
75 | CIV-104707 | Add NOAs and Forms for Electronic Theft | New Policy | High | Design in Progress | CA-209721 | Correspondence
76 | CIV-104848 | ACL 19-77 New and Revised Homeless Assistance Forms and Notices of Action | New Policy | High | New | CA-209996 | Correspondence
77 | CIV-104879 | ACIN I-44-19 Update State PINS to 8 digits | New Policy | High | New | CA-210119 | Fiscal
78 | CIV-105339 | Income Disregard for the Aged, Blind & Disabled Federal Poverty Level Program | New Policy | High | Pending Approval | CA-211216 | Medi-Cal/CMSP
79 | CIV-105343 | ACL 19-106, ACL-19-79 â€“ CalWORKs, CalFresh Income Exemptions | New Policy | Critical | Committee Review | CA-211229 | CalWORKs/CalFresh
80 | CIV-105562 | ACL-19-76: Batch EDBC Run to Apply 2020 Earned Income Disregard and Income Reporting Threshold Tiers | New Policy | High | Committee Review | CA-211596 | CalWORKs/CalFresh
81 | CIV-105835 | ACL 19-99 and 19-110 Online Summary Screen for Child Care Immediate and Continuous Eligibility | New Policy | Medium | New | CA-209408 | Child Care
82 | CIV-106099 | ACL 19-99 and 19-110 Monthly Report Immediate and Continuous Child Care Eligibility | New Policy | High | New | CA-212736 | Child Care
83 | CIV-106256 | ACIN I-XX-XX - 2021 State Minimum Wage CTCR | New Policy | High | New | CA-213269 | CalWORKs/CalFresh
84 | CIV-106257 | ACIN I-XX-XX- 2021 State Minimum Wage Run Batch EDBC | New Policy | High | New | CA-213270 | CalWORKs/CalFresh
85 | CIV-106258 | ACIN I-XX-20 - FFY 2021 CalFresh COLA | New Policy | High | New | CA-213273 | CalWORKs/CalFresh
86 | CIV-106259 | ACIN I-XX-XX- FFY 2021 CalFresh COLA Run Batch EDBC | New Policy | High | New | CA-213274 | CalWORKs/CalFresh
87 | CIV-106461 | ACL 19-76 - CalWORKs Change in Earned Income Disregard (EID) 2021 | New Policy | High | Design in Progress | CA-212912 | CalWORKs/CalFresh
88 | CIV-106529 | CalHEERS eHIT: Health4All â€“ Older Californians | New Policy | High | New | CA-213920; CH-159158 | Medi-Cal/CMSP
89 | CIV-443 | MEDS: Calculate CIN Check Digit (43880) | Operational Enhancement | Medium | New | CA-202312 | MEDS
90 | CIV-102290 | Quarterly release testing for EBT vendor FIS - May 2020 | Operational Enhancement | Medium | New | CA-213578 | Fiscal
91 | CIV-103841 | Update Primary Key IDs for Migration - Phase 1 | Operational Enhancement | Medium | Design in Progress | CA-202610 | Tech
92 | CIV-436 | NOA: Over Property NOA does not list property (43735) | Policy Re-Design | High | New |  | Correspondence
93 | CIV-644 | Update Incomplete CF Recertification Status (48318) | Policy Re-Design | High | New | CA-207798 | Correspondence
94 | CIV-676 | CW: Special Needs for Therapeutic Diets Returning Conflicting Values (49436) | Policy Re-Design | Low | New |  | CalWORKs/CalFresh
95 | CIV-818 | CalWORKs clock is ticking for parent who is under 18 years old (52832) | Policy Re-Design | High | Committee Review | CA-204747 | Time Limits
96 | CIV-960 | Update Child In Foster Care on 18th Birthday Check (55621) | Policy Re-Design | High | New |  | Foster Care/Kin GAP/AAP
97 | CIV-1131 | ACL 11-51: Update FC Education Travel Reimbursement NOAs (57200) | Policy Re-Design | Medium | New | CA-209231 | Correspondence
98 | CIV-1207 | CW Treatment of Unregistered Motor Vehicles | Policy Re-Design | Medium | Design in Progress | CA-213480 | CalWORKs/CalFresh
99 | CIV-3551 | Update Most Beneficial Logic for Add Person Mid-Period (SAR) | Policy Re-Design | High | New | None | CalWORKs/CalFresh
100 | CIV-5849 | ACL 18-50 - Implement Redesigned CalFresh Overissuance NOAs- Phase 1 | Policy Re-Design | High | Design in Progress | CA-202684 | Correspondence
101 | CIV-7278 | Apply Minimum Allotment Logic to CFAP Budget | Policy Re-Design | Low | New | None | CalWORKs/CalFresh
102 | CIV-7358 | CO-091: ACIN I-88-16 - Tracking Deleted Database Records for ABAWD Determination | Policy Re-Design | Medium | New | CA-56918 | CalWORKs/CalFresh
103 | CIV-8657 | Updates to CW Change NOA due to Overpayment Adjustment | Policy Re-Design | High | Design in Progress | CA-50293 | CalWORKs/CalFresh
104 | CIV-8850 | ACL 11-01, ACL 11-01E - Reimplement QNA File NA960X/NA960Y Reason Codes as Timed Out instead of Terminated | Policy Re-Design | High | New | LRS SCR 48771 | CalWORKs/CalFresh
105 | CIV-8950 | Active $0 CF grants removed from Negative Univers File transfer to Suspend (S) | Policy Re-Design | High | New | LRS SCR 48771 | CalWORKs/CalFresh
106 | CIV-10060 | Update CA1037 State report Revise line 8a logic | Policy Re-Design | High | New | CA-47600 | State/Fiscal Reports
107 | CIV-10385 | ACL 17-70 CAPI Clarification of the Indigence Exception Expiration Policy for Sponsor Immigrants | Policy Re-Design | Low | New | CA-51119 | CalWORKs/CalFresh
108 | CIV-11690 | Updates the DHCS CMS Performance Indicator Report | Policy Re-Design | Critical | Design in Progress | CA-55584 | State/Fiscal Reports
109 | CIV-100039 | ACL 17-70E CAPI Indigence Exception Expiration Policy | Policy Re-Design | Medium | New | CA-51119 | Correspondence
110 | CIV-100174 | Update Medicare Savings Program (MSP) NOAs | Policy Re-Design | High | Design in Progress | CA-202460 | Correspondence
111 | CIV-100432 | Update Cash Aid Time Limit Extender clock counts for Welfare to Work and CalWORKs | Policy Re-Design | High | New | CA-53782 CA-53784 | Time Limits
112 | CIV-100919 | Add Sample SAR7 to Template Respository and RE Packets | Policy Re-Design | High | New | CA-207892 | Correspondence
113 | CIV-101159 | Update Expedited Service Determination, Postponed Verification and Batch Discontinuance Process | Policy Re-Design | High | Committee Review | CA-53789 | CalWORKs/CalFresh
114 | CIV-101397 | Phase I - Change CalFresh Notice of Actions - New CF 286 Budget Cont. Page and Remove CF Text on CW NOA | Policy Re-Design | High | New | CA-50316 | Correspondence
115 | CIV-101513 | ACL 16-79 Add a drop down menu for out of state short-term residential therapeutic program (STRTP) placements | Policy Re-Design | High | New | CA-203392 | Foster Care/Kin GAP/AAP
116 | CIV-101570 | ACL 18-43 - CALIFORNIA WORK OPPORTUNITY AND RESPONSIBILITY TO KIDS (CalWORKs): REVISED NOTICE OF ACTION MESSAGES: M40-107(C), M40-107(D) AND M40-107(G) | Policy Re-Design | Medium | New | CA-204115 | Correspondence
117 | CIV-102306 | Time Limit should not be counted for Non-Cal-Learn 19 Year old Custodial Parents | Policy Re-Design | High | New | CA-54665 | Welfare to Work/WPR
118 | CIV-103104 | Include ARC When Determining if a Non Minor Dependent was in FC on their 18th Birthday | Policy Re-Design | Critical | New |  | Foster Care/Kin GAP/AAP
119 | CIV-103252 | Remove the HEAR 302 CIV and replace with the DPA 315 | Policy Re-Design | Medium | New |  | Correspondence
120 | CIV-103745 | NOMI - Interview Completion Due date to be 30 days from application date | Policy Re-Design | High | Design in Progress | CA-201756 | Correspondence
121 | CIV-105386 | ACL 19-118 Removal of the Consecutive Day rule for HA-Temp | Policy Re-Design | High | Design in Progress | CA-211293 | CalWORKs/CalFresh, Correspondence, RDB
122 | CIV-105397 | ACL 19-XXX Revise CalWORKs Stage Child Care NOAs | Policy Re-Design | Medium | New | CA-211332 | Correspondence
| CIV-105446 | Monthly Batch Job - Case Purge - Discontinued/Inactive Cases | Policy Re-Design | High | Design in Progress | CA-208415 | Other

## Key
SCR Status Key |  | SCR Change Type Key
System Change Request (SCR) Status | Definition | SCR Change Type | Definition
New | Default status when an Issue is created | Data Change | This change type is selected for data change that impacts high volume of cases
Design in Progress | Indicates that the Team/Consortium Staff are working on the Design | Enhancement | This change type is selected for changes to existing design that are not new policy or policy re design.
Ready for Committee | Indicates the Design is ready for Committee to review/approve | Individual Data Change | This change tyhpe is selected for data changes that impacts low volumne of cases (less than 20)
Committee Review | Indicates the Committee is reviewing for approval | New Policy | This change type is selected for SCRs that have references to regulations or state policy letters that have not yet been integrated in the system.
Pending Approval | Indicates that the Issue is pending the approval of CCB. | Operational Enhancement | This change type is selcted for changes to the system that are county specific, impact a specific technology upgrade (ie. New EBT Printer, New Warrant Stock, FTP changes, DB Upgrade, etc.), or are only operational in nature (IP address change, configurational file changes, etc.)
Approved | Indicates that the Issue has been Accepted by the CCB and/or has been given Expedited Approval and build may begin. | Policy Re-Design | This change type is selected of the SCRs is requesting a change to existing design with a regualtion or state policy letter reference.
In Development | Indicates that the Issue is in the development phase
Development Complete | Indicates that the development team has completed development of the Issue
In Assembly Test | Indicates the development team has completed development of the Issue and Assembly Test is in progress
System Test | Indicates that the Issue is currently in System Test and all Test Conditions are being validated in System Test
Test Complete | Indicates that the Issue has been validated in System Test and all Test Conditions have passed System Test