## North - CCB Approved
No. | SCR | Summary | Change Type (SCR) | SPG Priority | Status | Release | Minor Version | Other Agency Cross Reference | Committee
1 | CA-211586 | Tech Ops - Transition APP-CCRC file to go direct from CCRC to CalSAWS AWS | Operational Enhancement | Medium | New | TBD |  |  | Child Care
2 | CA-208817 | App Server storage issues, change temp file storage location | Operational Enhancement |  | Approved | 19.09 |  |  | Tech
3 | CA-214539 | Stop GR Discontinuance in EDBC and Generate GR, CAPI discontinued person list for April and May | Operational Enhancement | Critical | System Test | 20.03 | 20.04.16 |  | GA/GR
4 | CA-215275 | Issue April 2020 Disaster Supplement in accordance to HR 6201 Emergency Allotments | Enhancement | High | Design in Progress | 20.03 | 20.05.09 | CIV-106935 | Fiscal
5 | CA-214780 | CLONE - Update the Received Date on Vouchers for April Foster Care Benefit Month for LA County | Enhancement | High | New | 20.03 | 20.05.XX |  | Fiscal
6 | CA-211827 | Automated Regression Test - Execution and Maintenance - 20.03 Release Cycle | Operational Enhancement | Medium | In Development | 20.03 | 20.05.XX | CIV-105633 | Other
7 | CA-209033 | ACL 19-76 - CalWORKs Change in Earned Income Disregard (EID) and Income Reporting Thresholds Tiers (IRTs) | New Policy | High | System Test | 20.03 | 20.04.16 | CIV-104383 | CalWORKs/CalFresh
8 | CA-214426 | Implement Changes to Support Online Purchasing with EBT | Enhancement | High | In Development | 20.03 | 20.04.16 | CIV-106689 | Fiscal
9 | CA-214659 | Do not send SAR forms to central print and update Customer Report Status for May 2020 due month | New Policy | Critical | Design in Progress | 20.03 | 20.04.25 | CIV-106804 | CalWORKs/CalFresh,Correspondence
10 | CA-211596 | ACL-19-76: Batch EDBC Run to Apply 2020 Earned Income Disregard and Income Reporting Threshold Tiers | New Policy | High | Approved | 20.03 | 20.05.09 | CIV-105562 | CalWORKs/CalFresh
11 | CA-214881 | Hold TCF Issuances for Programs with overdue Recert | Operational Enhancement |  | In Development | 20.03 | 20.04.23 | CIV-106873 | Fiscal
12 | CA-207735 | Sending Outbound Images to EDMS as attachments | Operational Enhancement | Medium | Design in Progress | 20.03 | 20.04.16 |  | Imaging
13 | CA-214490 | Turn on the Time Limit Good Cause reason 407 Lack of Supportive Services | New Policy |  | In Development | 20.03 | 20.04.23 | CIV-106721 | Time Limits
14 | CA-215220 | List of DCFS Medi-Cal Discontinuances from Batch EDBC | New Policy | Critical | Approved | 20.03 | 20.04.xx | N/A | Medi-Cal/CMSP
15 | CA-214635 | Advance CW/CF RE Due Month for March - May 2020 | New Policy |  | In Development | 20.03 | 20.04.30 | CIV-106787 | CalWORKs/CalFresh
16 | CA-214678 | Do not send RE for May 2020 due month for CalWORKs and CalFresh | New Policy |  | Test Complete | 20.03 | 20.04.09 | CIV-106809 | CalWORKs/CalFresh, Correspondence
17 | CA-214784 | Advance CAPI RE and GR AA Due Month for March - May 2020. Update Customer reporting records for CAPI RE, GR QR7 and AA | New Policy | Critical | In Development | 20.03 | 20.04.30 |  | CalWORKs/CalFresh, GA/GR
18 | CA-214607 | Issue March 2020 Disaster Supplement in accordance to HR 6201 Emergency Allotments | Enhancement | High | System Test | 20.03 | 20.04.11 | CIV-106766 | Fiscal
19 | CA-212006 | Automated Regression Test (ART) - Transaction Coverage Reporting by Business Area | Operational Enhancement | Medium | In Development | 20.05 | 20.05.XX |  | Other
20 | CA-210926 | Add EDBC Validation to Force Completion of Customer Report | Enhancement | High | System Test | 20.05 |  |  | CalWORKs/CalFresh
21 | CA-208623 | Conduct Batch Eligibility Regression Testing Against the 20.05 Release | Operational Enhancement | High | System Test | 20.05 |  |  | Other
22 | CA-209661 | Update Previous Potential Benefit Calculation logic | Enhancement | High | System Test | 20.05 |  | CIV-104671 | Collections, State/Fiscal Reports
23 | CA-208988 | ACWDL June 11, 2019; CFL NO. 18/19-26 Add Functionality for Housing Support Program (HSP) | New Policy | Critical | System Test | 20.05 |  | CA-208109; CIV-104367 | CalWORKs/CalFresh
24 | CA-205454 | LRS only change: Remove DPSS-at-a-glance link from LRS Business Intelligence dashboard | Enhancement | High | System Test | 20.05 |  |  | Other
25 | CA-209032 | Create State Agency Accounts for Designated DHCS and CDSS Staff | Operational Enhancement | Low | System Test | 20.05 |  | CIV-103887 | Other
26 | CA-212411 | Updates to Generation of NA 823 and NA 820 for HSP and HVP | New Policy | High | System Test | 20.05 |  | CIV-105913 | Correspondence
27 | CA-208265 | ACL 19-42 Implement the Automation of CalWORKs Home Visiting Program (HVP) | New Policy | High | System Test | 20.05 |  | CIV-104042 | CalWORKs/CalFresh, Welfare to Work/WPR
28 | CA-214492 | Add new Document Type Value to YBN Verification Upload | Enhancement | Medium | System Test | 20.05 |  |  | CalWORKs/CalFresh, Self Service Portal
29 | CA-50800 | CalWORKs Denial NOA - correct the 30-day date inserted on the NOA | Policy Re-Design | High | System Test | 20.05 |  |  | Correspondence
30 | CA-208155 | CFL 18/19-49 Create new Pay Codes for CalWORKs Home Visit Program (HVP) | New Policy | Medium | System Test | 20.05 |  | CIV-103989 | Fiscal
31 | CA-211200 | Modify Existing Report | Enhancement | High | System Test | 20.05 |  | CIV-103387 | Internal Security
32 | CA-212924 | Modify DPSS Renewals Performance Measures Dashboard | Enhancement | Medium | In Development | 20.05 | 20.05.x |  | Management Reports
33 | CA-202778 | Revised Medi-Cal Hierarchy | New Policy | Critical | System Test | 20.05 |  | CIV-7564 | Medi-Cal/CMSP
34 | CA-204569 | ACL 19-40 CalWORKs Outcome and Accountability Review (Cal-OAR) Phase II | New Policy | High | System Test | 20.05 |  | CIV-102191 | Welfare to Work/WPR
35 | CA-50302 | OCAT - Upcoming Premise Item | Enhancement | High | System Test | 20.05 |  | CIV-4108 | Welfare to Work/WPR
36 | CA-213283 | Automated Regression Test - Execution and Maintenance - 20.05 Release Cycle | Operational Enhancement | Medium | In Development | 20.06 | 20.07.XX | CIV-106264 | Other
37 | CA-208386 | Content Development on CalSAWS.org | Operational Enhancement |  | Approved | 20.06 | 20.06.30 |  | Other
38 | CA-211616 | CalHEERS eHIT: Update Interface Schema to version 15 | Enhancement | High | Development Complete | 20.06 |  | CIV-105575; CH-154346 | Medi-Cal/CMSP
39 | CA-58123 | Prevent Advancing Medi-Cal Renewal with a Soft Pause Individual | New Policy | Critical | In Development | 20.06 |  | CIV-10791 | Medi-Cal/CMSP
40 | CA-208863 | CalHEERS eHIT: Married Filing Jointly and Out-of-State Address | Enhancement | High | In Development | 20.06 |  | CIV-1068; CH-153970 | Medi-Cal/CMSP
41 | CA-212828 | [Analytics] LRS CalFresh Dashboard Re-Platform | Enhancement | Medium | New | 20.07 | 20.06.30 |  | Management Reports
42 | CA-212185 | FC Case Assignment Logic Change | Enhancement | Low | In Development | 20.07 |  | N/A | Foster Care/Kin GAP/AAP
43 | CA-212039 | Update YBN/DPSS Mobile App downtime message page with external links and phone numbers | Operational Enhancement | Medium | Approved | 20.07 |  | CIV-105722 | Self Service Portal
44 | CA-213304 | Automated Regression Test - Execution and Maintenance - 20.07 Release Cycle | Operational Enhancement | Medium | New | 20.07 | 20.09.XX | CIV-106271 | Other
45 | CA-213106 | [Analytics] LRS SSI/SSP Dashboard Re-Platform | Enhancement | Medium | New | 20.07 | 20.06.30 |  | Management Reports
46 | CA-213105 | [Analytics] LRS Payments Dashboard Re-Platform | Enhancement | Medium | New | 20.07 | 20.06.30 |  | Management Reports
47 | CA-213102 | [Analytics] LRS CalFresh Meals Dashboard Re-Platform | Enhancement | Medium | New | 20.07 | 20.06.30 |  | Management Reports
48 | CA-209404 | ACL 19-59 Revise DFA 358F and DFA 358S | New Policy | High | Approved | 20.07 |  | CIV 104574 | State/Fiscal Reports
49 | CA-210307 | Deactivating Pre-ACA Aid Codes | New Policy | High | Approved | 20.07 |  | CIV-104986 | Medi-Cal/CMSP
50 | CA-209221 | Add State PINs to Integrated Service Payment / Valuable Detail Claiming Report | Enhancement | Medium | Approved | 20.07 |  | CIV-102606, CIV-104015, CA-208814 | State/Fiscal Reports
51 | CA-206347 | Update NOA logic for CW IRT to Generate the SAR 2 | Policy Re-Design | High | In Development | 20.07 |  |  | Correspondence
52 | CA-201742 | CF 296 - Changes in logic for Line 10 - Overdue Recertifications (CWD Caused) during the month. | Policy Re-Design | High | Approved | 20.07 |  | CIV-100845 | State/Fiscal Reports
53 | CA-202177 | Modifications to the Medi-Cal Renewal E-Hit Dashboard and DPSS Performance Measures Dashboard - Medi-Cal Renewals | Enhancement | High | Approved | 20.07 |  |  | Management Reports
54 | CA-200879 | ACL 19-95 Automate Disaster CalFresh | Policy Re-Design | Medium | In Development | 20.07 |  |  | CalWORKs/CalFresh
55 | CA-211216 | Income Disregard for the Aged, Blind & Disabled Federal Poverty Level Program | New Policy | High | Approved | 20.07 |  | CIV-105339 | Medi-Cal/CMSP
56 | CA-58455 | Data Change Request - Void Pending Approval Recovery Accounts | Enhancement | High | In Development | 20.07 |  |  | Collections
57 | CA-58579 | ACWDL 17-31 Revisions to the NA Back 9 for all Medi-Cal Notices of Action | New Policy | Critical | In Development | 20.07 |  | CIV-10665 | Correspondence
58 | CA-213087 | Convert to Stream Architecture - Batch Sweep for Deceased Date | Enhancement | High | In Development | 20.07 |  | N/A | Tech
59 | CA-213086 | Convert to Stream Architecture - MEDS EW10 Transaction | Enhancement | High | In Development | 20.07 |  | N/A | Tech
60 | CA-213103 | [Analytics] LRS Managed Personnel Dashboard Re-Platform | Enhancement | Medium | New | 20.07 | 20.06.30 |  | Management Reports
61 | CA-213170 | Add a Business Intelligence Search Page to CalSAWS | Enhancement | High | In Development | 20.07 |  |  | Management Reports
62 | CA-213988 | Replace Oracle IAM Security Stack | Enhancement |  | Approved | 20.07 | 20.08.08 |  | Tech
63 | CA-213672 | Standardize Account Number Format for Text Campaigns | Enhancement | Low | Development Complete | 20.07 |  | N/A | IVR & Contact Center
64 | CA-212087 | Allow CalFresh Recovery Accounts to be set to active status | Policy Re-Design | Medium | Development Complete | 20.07 |  | CIV-105746 | Collections
65 | CA-202055 | Separate Case & Issuance for CAPI Couple Case | Policy Re-Design | Critical | In Development | 20.07 |  |  | CalWORKs/CalFresh
66 | CA-208268 | ACL 18-107, ACL 18-108 - SNB/TNB Forms and Notices - Threshold Languages Phase 4 | New Policy | Critical | In Development | 20.07 |  | CIV-104043 | Correspondence
67 | CA-204496 | SB 1341 All County Solution Phase 2 - Updates to the flow of mixed Non-MAGI/MAGI NOAs | Enhancement | Medium | Approved | 20.09 |  | LRS Specific Change | Correspondence, Medi-Cal/CMSP
68 | CA-209956 | Add threshold language translations for MAGI and Non-MAGI YAE fragments | New Policy | High | Design in Progress | 20.09 |  | CIV-104826 | Correspondence
69 | CA-54659 | Update Repayment Term Summary and Detail Page | Operational Enhancement | High | Committee Review | 20.09 |  | CIV-5503 implemented Release 17.11 | Collections
70 | CA-52597 | CA 812 Collections Enhancement Report | Enhancement | High | Approved | 20.09 |  | CIV-12446 | Collections, State/Fiscal Reports
71 | CA-214600 | [Analytics] LRS Operational Reports Dashboard Re-Platform | Enhancement | Medium | New | 20.11 | 20.11.23 |  | Management Reports
72 | CA-211229 | ACL 19-106, ACL-19-79 â€“ CalWORKs, CalFresh Income Exemptions | New Policy | Critical | Approved | 20.11 |  | CIV-105343 | CalWORKs/CalFresh
73 | CA-49633 | CF 387 CalFresh Request for Information for Residency | Enhancement | Medium | Approved | 20.11 |  | CIV-101447 | CalWORKs/CalFresh, Correspondence
74 | CA-58934 | Aligning Status Begin Date of Associated Programs With Primary Cash Aid Programs or EDBC Run Date, whichever is later | Enhancement | High | In Development | 20.11 |  | CIV-66 | Welfare to Work/WPR
75 | CA-214213 | [Analytics] LRS Statistical Reports Dashboard Re-Platform | Enhancement | Medium | New | 21.11 | 21.09.30 |  | Management Reports

## North - SPG Approved
No. | SCR | Summary | Change Type (SCR) | SPG Priority | Status | Other Agency Cross Reference | Committee
1 | CA-214477 | Update eHIT to send MEC Admin Verification = N when Medi-Cal is auto-tested from CalWORKs | Enhancement | Medium | Design in Progress | CIV-12195 | Medi-Cal/CMSP
2 | CA-214445 | CalHEERS eHIT: Update Interface Schema to version 16 | Enhancement | High | Design in Progress | CH-157399, CIV-106700 | Medi-Cal/CMSP
3 | CA-214308 | Generate MC Restoration Notice after authorization instead of during run EDBC. | Enhancement | Medium | New |  | Correspondence
4 | CA-214104 | Inactivate Unnecessary Scheduled Reports | Enhancement | Low | Pending Approval |  | State/Fiscal Reports
5 | CA-213522 | Security to enable pages being added for the interface to OCAT | Enhancement | High | Pending Approval | CIV-106387 | Welfare to Work/WPR
6 | CA-213468 | CalHEERS eHIT: BREfS: Enhance eHIT Verifications | Enhancement | High | Design in Progress | CIV-106351; CH-158675 | Medi-Cal/CMSP
7 | CA-212911 | Update CalWORKs in Public Assistance CalFresh Budget at Initial Approval | Enhancement | Critical | Design in Progress |  | CalWORKs/CalFresh
8 | CA-211528 | Turn off Batch that triggers CBEST Appt for Participants with Temp U and Temp NSA Status | Enhancement | Medium | New |  | GA/GR
9 | CA-210948 | Auto assign task to the MC Worker for the IEVS NHR combo (CF and MC) only case | Enhancement | High | Design in Progress | CIV-105277 | Medi-Cal/CMSP
10 | CA-204582 | Add Edit Functionality to a Service Arrangement (42700) | Enhancement | Critical | Design in Progress | CIV-391 | Welfare to Work/WPR
11 | CA-204553 | CalWORKs/RCA Adults by Welfare-to-Work Category Report | Enhancement | High | New |  | Management Reports
12 | CA-204552 | WTW/REP Caseload Activity Report | Enhancement | Medium | New |  | Management Reports
13 | CA-204823 | Time Limit Months for Immediate Need program | Enhancement | Critical | New | CIV-8583 | CalWORKs/CalFresh
14 | CA-204494 | SB 1341 All County Solution Phase 4 - Letter Format Mixed Non-MAGI/MAGI NOAs | Enhancement | Medium | New |  | Correspondence, Medi-Cal/CMSP
15 | CA-204499 | SB 1341 All County Solution Phase 5 - Mixed Non-MAGI/MAGI Text updates and update to Skip Report | Enhancement | Medium | New |  | Correspondence, Medi-Cal/CMSP
16 | CA-204497 | SB 1341 All County Solution Phase 3 - Updates to the mixed Non-MAGI/MAGI NOAs to allow for mixed actions | Enhancement | Medium | Design in Progress |  | Correspondence, Medi-Cal/CMSP
17 | CA-203759 | PA 1672-1 - Employment verification form is generated erroneously | Enhancement | Critical | New |  | Correspondence
18 | CA-203447 | Change the Application Source to Other instead of ICT for Targeted Low Income linked program applications | Enhancement | High | New |  | ICT
19 | CA-207572 | CES 2017-102 IEVS Income ending do not close abstract | Enhancement | Medium | Committee Review | CIV-100400 | IEVS
20 | CA-203421 | Your Benefits Now (YBN) SAWS II Plus/GR SAWS II plus/CW RD form(also the SAWS II Plus) to remove all default mapping. | Enhancement | Medium | New |  | Self Service Portal, Tech
21 | CA-209798 | Enhance Functionality to Cancel MAGI Referrals and Determination Changes | Enhancement | High | Design in Progress | CIV-104735 | Medi-Cal/CMSP
22 | CA-209638 | Add Threshold Languages for FC/KG CNI NOA Fragment | Enhancement | High | Design in Progress | CIV-104665 | Correspondence
23 | CA-208864 | CalHEERS eHIT: Add SCAI to MAGI Medi-Cal Income Budget Periods | Enhancement | Critical | Design in Progress | CIV-104299; CH-151332 | Medi-Cal/CMSP
24 | CA-208889 | eICT: Updates for eHIT Schema | Enhancement | High | Design in Progress | CIV-104321; CH-106890; CH-109700; CH-109744; CH-109927; CH-113161; CH-121151; CH-131449; CH-136022; CH-137942; CH-139211; CH-139410; CH-139419; CH-92295; CH-92298 | ICT
25 | CA-208925 | Text to Opt out of Text Messages | Enhancement | Medium | Design in Progress |  | IVR & Contact Center
26 | CA-210580 | Automate the creation of months for Supportive Service recipients | Enhancement | Critical | Design in Progress | CIV-661
27 | CA-206709 | Change Security to Allow all User Access to Release Note Report | Enhancement | Medium | New | CIV-67 | Security
28 | CA-206708 | Update Application Detail to support View Mode | Enhancement | Medium | New | CIV-580 | Security
29 | CA-206394 | Add Threshold for MC RE/Restore Notice | Enhancement | Medium | Ready for Committee |  | Correspondence
30 | CA-205448 | ACL 14-20 - CalFresh Recertification Appointment Letter Revisions/Additions | Enhancement | Medium | New |  | Correspondence
31 | CA-205009 | Add additional Service Types to Resource Data Bank | Enhancement | Medium | New | CIV-3813 | RDB
32 | CA-206168 | Customer Reporting Page Updates | Enhancement | High | Design in Progress |  | CalWORKs/CalFresh
33 | CA-202920 | Strategic Plan -Case Alignment Phase III- All Active Eligibility Programs (GR/CF/MC) with multiple program blocks in all districts will be aligned under a single worker | Enhancement | High | New |  | Usability
34 | CA-202781 | ICT: Update the additional document type list to display alphabetically | Enhancement | Medium | New | CIV-101358 | ICT
35 | CA-200895 | Update the Rescind Logic to accommodate for overlapping rescinded periods | Enhancement | Medium | New | C-IV 450, C-IV 331 | CalWORKs/CalFresh
36 | CA-201813 | Display Important County Dates Phase I | Enhancement | Medium | New | CIV-100040 | Usability
37 | CA-201709 | Updates to Change Reason Mid-period addition of Individual | Enhancement | High | New |  | CalWORKs/CalFresh
38 | CA-202482 | Update 206-Cal-Learn Time Limit Exemption to apply to WTW time clock | Enhancement | High | New | CIV-101174 | Time Limits
39 | CA-201250 | YBN External Mobile App - add Analytics | Enhancement | Medium | New |  | Tech
40 | CA-54164 | Update Sanctions Dashboard Reports/Data in DPSSTATS Data Warehouse Homepage | Enhancement | Medium | Design in Progress |  | Management Reports
41 | CA-49410 | Allow Users to Authorize Multiple Transportation Types for Overlapping Periods | Enhancement | Medium | Design in Progress | CA-50300 | Welfare to Work/WPR
42 | CA-51491 | Modify LRS Functionality to Not Require Adding a Homeless Temp or Homeless Perm Program When Processing Supplemental Housing Assistance Programs. | Enhancement | High | New |  | CalWORKs/CalFresh
43 | CA-50091 | SB 1147 - Juvenile Probation Interface | Enhancement | Low | Design in Progress | LA County Specific | Medi-Cal/CMSP
44 | CA-52880 | Additions to Person, Vendor, Invoice Search Criteria; Modifications on the Money Management Resource Detail Page and On the on the Select Service and Provider Page | Enhancement | Medium | Design in Progress | LA County request for GA/GR program | Fiscal
45 | CA-49398 | Customer Reporting List page: Display by Name drop-down box | Enhancement | Medium | New |  | Usability
46 | CA-50782 | Enhance the Initial Search Screen of the Audit Tool | Enhancement | High | Design in Progress | Specific to LRS | Internal Security
47 | CA-50780 | Additional Detail for Audit Application Report | Enhancement | High | Committee Review | Specific to LRS | Internal Security
48 | CA-49411 | Document Detail page (GN 6070 Received Date) | Enhancement | Medium | New |  | Usability
49 | CA-51448 | Add Time Tracking Report to CalSAWS Audit Application | Enhancement | High | Design in Progress |  | Internal Security, Tech
50 | CA-48755 | Child care Task Assignment Addendum | Enhancement | High | New |  | Child Care
51 | CA-53607 | Add Form Trigger Reasons for the CL 3 and CL 4 / NA 290 - Cal-Learn and replace TEMP CL1 Spanish with CL1 Spanish | Enhancement | High | Design in Progress |  | Correspondence
52 | CA-52756 | Modify duplicate payment logic | Enhancement | High | New |  | Foster Care/Kin GAP/AAP
53 | CA-50300 | LRS Transportation types drop down | Enhancement | Medium | New | CA-49410 | Welfare to Work/WPR
54 | CA-47915 | DCFS: Send Medi-Cal to MEDS for AAP with $0 Authorized Amount 01/14/16 AA - Priority confirmed by RE | Enhancement | Medium | New |  | MEDS
55 | CA-56515 | Update Overpayment Adjustment Logic to stop Excess Recoupments | Enhancement | High | Ready for Committee | CIV-106691 | CalWORKs/CalFresh, Collections, Fiscal
56 | CA-47600 | Update CA1037 State report Revise line 8a logic | Enhancement | High | New | CIV-10060 | State/Fiscal Reports
57 | CA-51726 | Modifications to Benefit Recovery Management Report | Enhancement | Medium | Design in Progress |  | State/Fiscal Reports
58 | CA-55143 | Phase III - Modify and Add Validations to run EDBC for the Correct RE/SAR/QR Submit Month | Enhancement | High | New | CIV-702 | CalWORKs/CalFresh
59 | CA-55208 | Changes to the Child Care Requests page | Enhancement | High | New |  | Child Care
60 | CA-57452 | ACWDL 17-32 - NOA Requirements for Failure to Respond - Compliance with Settlement of Korean Community Center of the East Bay | Enhancement | High | Design in Progress | CIV-10892 | Correspondence
61 | CA-51876 | LRS Ancillary Pages: Modify the LRS Service Arrangement Detail Page, Service Type Description box to allow for the itemization of ancillary items requested under the Ancillary-Education category, instead of the current text box. | Enhancement | Medium | Design in Progress |  | Welfare to Work/WPR
62 | CA-55206 | Redesign FC Facility Ratios page ? Need to store historical ratio info based on the eff. date for Group Home and Foster Family Agency type | Enhancement | High | New | CIV-102423 | RDB
63 | CA-50978 | Add Reissue Logic for Incidental Payments | Enhancement | Medium | New |  | Fiscal
64 | CA-58963 | Revisions to the Medicare Savings Programs (MSP) Notices of Action (NOAs) 1 of 1 | Enhancement | High | Design in Progress |  | Correspondence
65 | CA-57104 | GR Self-Employment Expense Calculations | Enhancement | Medium | New |  | GA/GR
66 | CA-58006 | LRS mapping for domestic abuse/child abuse to LRS case from eapp screen. | Enhancement | Medium | New | LA County Specific | Self Service Portal, Usability
67 | CA-48412 | IHSS IPW Referrals/Auto Generate MEDI-CAL Application | Enhancement | Medium | Design in Progress |  | Medi-Cal/CMSP
68 | CA-52872 | Jail Match Interface for All Programs | Enhancement | Medium | Design in Progress | LA County Specific | Other
69 | CA-55200 | Update WEX/CS WorkSheet Detail Page | Enhancement | Medium | Design in Progress | CIV-533 | Welfare to Work/WPR
70 | CA-51492 | WTW Reports to include REP alongside of WTW for work registration type code. | Enhancement | Medium | New |  | Management Reports
71 | CA-47592 | SMART - CalWORKs Participants with 12 Months Disability and Potential Eligibility for SSI | Enhancement | Medium | New |  | Management Reports
72 | CA-48639 | Elimination of EBT Out-of-County/State Automated Appointments for General Relief and Cash Assistance Program for Immigrants (CAPI) participants | Enhancement | Medium | New | LA County Specific | GA/GR
73 | CA-57657 | C-IV-11229: Update Foster Care EDBC Sweeps to issue benefits for new applications received for past month | Enhancement | Critical | New | C-IV SCR 11229 | Fiscal
74 | CA-54527 | Modify the TTC Interface File | Enhancement | Medium | New | LA County Specific | Tax Intercept
75 | CA-53456 | DCFS: LRS to accommodate various licensing statuses per license number, instead of per vendor number. | Enhancement | High | New | CIV-102416 | RDB
76 | CA-214304 | Display the correct address validation message in the EDBC summary page | Enhancement | Medium | Design in Progress |  | Fiscal
77 | CA-53326 | Add process for all WebService Interfaces to queue up when partner's system is down, for both scheduled and unscheduled downtime. | Enhancement | High | New |  | ICT, Imaging
78 | CA-54848 | Phase III- Change CalFresh NOAs add ineligible person names in Term NOAs, Add TCF NOA for Fleeing Felon | Enhancement | High | New | LA County Specific-Transitional CF fleeing felon NOA already exist in CIV | Correspondence
79 | CA-213920 | CalHEERS eHIT: Health4All â€“ Older Californians | New Policy | High | Design in Progress | CIV-106529; CH-159158 | Medi-Cal/CMSP
80 | CA-213719 | ACL-19-76: Batch EDBC Run to Apply 2021 Earned Income Disregard | New Policy | High | Design in Progress | CIV 106463 | CalWORKs/CalFresh
81 | CA-213349 | ACL 16-14 - Expedited Service Entitlement and Application Processing for CalFresh (57327) | New Policy | Critical | New | CIV-1143 | CalWORKs/CalFresh
82 | CA-212912 | ACL 19-76 - CalWORKs Change in Earned Income Disregard (EID) 2021 | New Policy | High | Design in Progress | CIV-106461 | CalWORKs/CalFresh
83 | CA-213274 | ACIN I-XX-XX- FFY 2021 CalFresh COLA Run Batch EDBC | New Policy | High | New | CIV-106259 | CalWORKs/CalFresh
84 | CA-213273 | ACIN I-XX-20 - FFY 2021 CalFresh COLA | New Policy | High | New | CIV-106258 | CalWORKs/CalFresh
85 | CA-213270 | ACIN I-XX-XX - 2021 State Minimum Wage Run Batch EDBC | New Policy | High | New | CIV-106257 | CalWORKs/CalFresh
86 | CA-213269 | ACIN I-XX-XX- 2021 State Minimum Wage CTCR | New Policy | Medium | New | CIV-106256 | CalWORKs/CalFresh
87 | CA-203671 | ACWDL 18-17 and 17-25: Add MC 604 MDV Doctorâ€™s Verification to Template Repository | New Policy | High | New | CIV-101796 | Correspondence
88 | CA-208030 | ACL 19-40 Cal-OAR - Phase I - Automation Alternative | New Policy | High | New | CIV-103934 | Welfare to Work/WPR
89 | CA-208130 | MEDIL I 19-12: Update on Asset Verification Reports | New Policy | High | Design in Progress | CIV-103983 | IEVS
90 | CA-208191 | Changes to the Designation and Responsibilities of the Medi-Cal Authorized Representative | New Policy | High | New | CIV-8633 | Medi-Cal/CMSP
91 | CA-208203 | ACL 19-31and CFL 19/20-14- Re-Entry into Extended Foster Care for Youth Receiving SSI | New Policy | High | New | CIV-104019 | Foster Care/Kin GAP/AAP
92 | CA-207637 | ACL 18-08 - ABAWD - Phase III | New Policy | Critical | Design in Progress | CIV-103743 | CalWORKs/CalFresh
93 | CA-210119 | ACIN I-44-19 Update State PINS to 8 digits | New Policy | High | Committee Review | CIV-104879 | Fiscal
94 | CA-209996 | ACL 19-77 New and Revised Homeless Assistance Forms and Notice of Action | New Policy | High | New | CIV - 104848 | Correspondence
95 | CA-209721 | Add NOAs and Forms for Electronic Theft | New Policy | High | Design in Progress | CIV-104707 | Correspondence
96 | CA-209422 | Update Medi-Cal Auto-Discontinuance Batch for Failure to Complete RE to process at an Individual Level | New Policy | High | Ready for Committee | CIV-104584, CIV-106073 | Medi-Cal/CMSP
97 | CA-209408 | ACL 19-99 and 19-110 Online Summary Screen for Child Care Immediate and Continuous Eligibility | New Policy | Medium | New | CIV-105835 | Child Care
98 | CA-206080 | ACL 18-141 CF REVISED SUPPLEMENTAL FORM FOR EXCESS MEDICAL DEDUCTIONS (CF 31) | New Policy | High | New | CIV-103015 | Correspondence
99 | CA-205633 | ACL 18-75 Phase IV-Long Term Funding for Emergency Caregivers with Placements Prior to RFA Approval | New Policy | Critical | Design in Progress | CIV-102757 | Foster Care/Kin GAP/AAP
100 | CA-204863 | ACL 18-99 CF OI Collection Period | New Policy | Critical | New | CIV-102263 | Collections
101 | CA-204858 | ACWDL CalFresh Employment & Training (E&T) Compliance with New Federal Reporting Requirements | New Policy | High | New | CIV-10156 | State/Fiscal Reports
102 | CA-203208 | Update MEDS to Send Prior FC or KG Aid Code to MEDS for NMD's Minor Infant Child | New Policy | High | Design in Progress | CIV-572 | MEDS
103 | CA-202684 | ACL 18-50 - Implement Redesigned CalFresh Overissuance NOAs - Phase 1 | New Policy | High | Design in Progress | CIV-5849 | Correspondence
104 | CA-200866 | ACWDL 17-36 NOA snippets for Medi-Cal Inmate Program | New Policy | Medium | New | CIV-12023 | Correspondence
105 | CA-201836 | ACL 18-117: Implement CalFresh Churn Monthly Caseload Report - CF 18 | New Policy | High | Committee Review | CIV-100878 | State/Fiscal Reports
106 | CA-202463 | NFC 17-023 Update SAR 2 to the latest State version | New Policy | High | New | CIV-8975 | Correspondence
107 | CA-56913 | ACL 14-64: Add CalWORKs Family Stabilization (FS) Program Quarterly Status Report - FSP 14 (dependent on SCR CA-57298: Creating Family Stabilization Pages) | New Policy | Critical | New | CIV-832 | State/Fiscal Reports
108 | CA-49617 | ACL 16-45: Automate the CW 2219 for Non-Needy Caretaker application instead of the SAWS 2 Plus application | New Policy | Medium | Design in Progress | CIV-9772 | Correspondence
109 | CA-58236 | Add Translations of Revised Forms to LRS: ABP SSI 1, ABP SSI 3, and ABP SSI 4 | New Policy | Medium | New | LA County Forms for General Relief | Correspondence
110 | CA-50293 | ACL 11-80 - CalWORKs New & Revised Overpayment Notice of Action Messages Phase 1 | New Policy | High | Design in Progress | CIV-8657 | CalWORKs/CalFresh
111 | CA-53617 | ACWDL 17-14: Update the "Medi-Cal General Property Limitations" (MC 007) form in LRS and the LRS code tables with the Statewide Average Private Pay Rate (APPR) for 2019. | New Policy | High | New | CIV-104975 | Medi-Cal/CMSP
112 | CA-54311 | ACL 18-18 CalFresh Changes to Reporting Requirements | New Policy | Critical | New | CIV SCR# 100532 | CalWORKs/CalFresh
113 | CA-56916 | Modify the ABAWD super trigger functionality to detect deleted data to update the ABAWD status | New Policy | High | New |  | CalWORKs/CalFresh
114 | CA-50787 | ACL 16-120 - Create a Report that Identifies Overpayments that were created as a result of a Mandatory Mid-Period Change that was Reported Timely and the County was unable to provide a 10-Day Notice of Action. Addendum to SCR BPP-CWs-GPD-139 | New Policy | High | New |  | Management Reports
115 | CA-213185 | Add Generate Form button to generate for Ancillary (Work related and Education), Transportation, HSP, HVP, FS need categories | New Policy | High | Design in Progress |  | Correspondence
116 | CA-202054 | ACL-18-07 Suspend/Discontinue/Reinstate for CAPI case | New Policy | High | New | CIV-100213 | CalWORKs/CalFresh
117 | CA-205913 | ACL 18-75 Add 5L Aid Code for FC Emergency Assistance EC Ineligible Cases | New Policy | High | Committee Review | CIV-102912 | Foster Care/Kin GAP/AAP
118 | CA-212736 | ACL 19-99 and 19-110 Monthly Report Immediate and Continuous Child Care Eligibility | New Policy | High | New | CIV-106099 | Child Care
119 | CA-213578 | Quarterly release testing for EBT vendor FIS - May 2020 | Operational Enhancement | Medium | New | CIV-102290 | Fiscal
120 | CA-209492 | Refactor: Medi-Cal NOA Regulations | Operational Enhancement | Medium | New |  | Correspondence
121 | CA-206525 | Create CalSAWS mail server to change all YBN and IVR outbound related email to calSAWS email address | Operational Enhancement | Medium | New |  | IVR & Contact Center, Self Service Portal, Tech
122 | CA-202347 | LRS: Automate e-app status update from Data Transfer to Transfer to LRS once the case is processed (Active, Denied etc) and DCR to update Data transfer to Transfer to LRS status. | Operational Enhancement | Medium | New |  | Self Service Portal, Usability
123 | CA-201214 | Add Business Reply Mail (BRM) to MC 355 Form | Operational Enhancement | High | New |  | Correspondence
124 | CA-53434 | Selective Address Normalization (Tech) | Operational Enhancement | Medium | Design in Progress |  | Tech
125 | CA-54663 | Suppress WTW/REP/GROW forms when the Provider Resources are in house | Operational Enhancement | High | New | CIV-102421 | RDB
126 | CA-55990 | No Cost SCR: Update EDBC Run Date with latest Authorization Date | Operational Enhancement | High | New |  | CalWORKs/CalFresh, Foster Care/Kin GAP/AAP, Medi-Cal/CMSP
127 | CA-212374 | CalWORKS - Annual Redetermination - Income Increase and 10-Day NOA | Policy Re-Design | High | Design in Progress |  | CalWORKs/CalFresh
128 | CA-211293 | ACL 19-118 Removal of the Consecutive Day rule for HA-Temp | Policy Re-Design | High | Design in Progress | CIV-105386 | CalWORKs/CalFresh, Correspondence, RDB
129 | CA-204762 | Do not Create an Offset Transaction for Overpayment/Overissuances Adjustments | Policy Re-Design | Critical | New | CIV-102098 | Collections, State/Fiscal Reports
130 | CA-204747 | CalWORKs clock is ticking for parent who is under 18 years old | Policy Re-Design | High | Committee Review | CIV-818 | Time Limits
131 | CA-204115 | ACL 18-43 - Revise CalWORKs M40-107 Time Limit NOAs in the C, D, and G Series | Policy Re-Design | Medium | New | CIV 101570 | Correspondence
132 | CA-208415 | Monthly Batch Job - Case Purge - Discontinued/Inactive Cases | Policy Re-Design | High | Design in Progress | CIV-105446 | Other
133 | CA-203392 | ACL 16-79 Add a drop down menu for out of state short-term residential therapeutic program (STRTP) placements | Policy Re-Design | High | New | CIV-101513 | Foster Care/Kin GAP/AAP
134 | CA-210663 | Expedited Approval NOA and Recertification has incorrect message | Policy Re-Design | High | Design in Progress |  | Correspondence
135 | CA-209754 | Add Threshold Languages for GN 6050 RP and GN 6053-R | Policy Re-Design | Medium | New |  | Correspondence
136 | CA-206740 | YourBenefitsNow YBN and LEADER Replacement Systems LRS electronic notification and paperless option logic update. | Policy Re-Design | High | New |  | Usability
137 | CA-206415 | ACL 13-02 Good Cause Reason 407 - Lack of Supportive Services should not impact WTW 24 Month Clock. | Policy Re-Design | Critical | New | C-IV 12392 | Time Limits
138 | CA-209231 | ACL 11-51: FC Education Travel Reimbursement NOAs | Policy Re-Design | Medium | New | CIV-1131 | Correspondence
139 | CA-207798 | Update Incomplete CF Recertification Status (48318) | Policy Re-Design | High | New | CIV-644 | Correspondence
140 | CA-207892 | Add Sample SAR7 to Template Respository and RE Packets | Policy Re-Design | High | New | CIV-100919 | Correspondence
141 | CA-202307 | Updates to the GEN 1365 Form and Form Generation | Policy Re-Design | High | New | CIV-100774
142 | CA-200800 | Update EDBC to process mid-period TCF programs via eICT | Policy Re-Design | High | New | CIV-7522 | ICT
143 | CA-201756 | NOMI - Interview Completion Due date to be 30 days from application date | Policy Re-Design | High | Design in Progress | CIV-103745 | Correspondence
144 | CA-202460 | Update Verbiage for Medical Savings Program (MSP) NOAs | Policy Re-Design | High | Design in Progress | CIV-100174 | Correspondence
145 | CA-211332 | ACWDL 20-03 CalWORKs Stage Child Care NOAs | Policy Re-Design | Medium | New | CIV-105397 | Correspondence
146 | CA-49396 | ACL 15-96 â€“ Add and automate ARC Forms NA 1281, NA 1280, NA 1279, and NA 1278 | Policy Re-Design | High | Design in Progress |  | Correspondence
147 | CA-49395 | ACL: Update ARC1 and ARC1A Forms | Policy Re-Design | Medium | Design in Progress | C-IV SCR 3915 (CCM)
148 | CA-50801 | Phase I - ACL 15-62 changes: NA 816, NA 817 with the latest versions in all threshold languages. | Policy Re-Design | Critical | New |  | Correspondence
149 | CA-50316 | Phase I - Change CalFresh Notice of Actions - New CF 286 Budget Cont. Page | Policy Re-Design | High | New | CIV-101397 | Correspondence
150 | CA-51882 | Limit HA Manual and Override EDBC drop down values; OPA to consider in HA EDBC | Policy Re-Design | High | Design in Progress | CIV-7859 | CalWORKs/CalFresh
151 | CA-55584 | Updates to the DHCS CMS Performance Indicator Report | Policy Re-Design | Critical | Design in Progress | CIV-11690 | State/Fiscal Reports
152 | CA-54665 | Time Limit should not be counted for Non-Cal-Learn 19 Year old Custodial Parents | Policy Re-Design | High | New | CIV-102306 | Time Limits
153 | CA-50297 | Permit Concurrent Activity For Participants With Good Cause Status | Policy Re-Design | Critical | New |  | Welfare to Work/WPR
154 | CA-53789 | Update Expedited Service Determination, Postponed Verification and Batch Discontinuance Process | Policy Re-Design | High | Committee Review | CIV-101159 | CalWORKs/CalFresh
155 | CA-56887 | Phase III-B- Change CalFresh NOAs to include the name of the individuals on change and denial NOAs | Policy Re-Design | High | Design in Progress |  | Correspondence
156 | CA-213480 | CW Treatment of Unregistered Motor Vehicles | Policy Re-Design | Medium | Pending Approval | CIV-1207 | CalWORKs/CalFresh
157 | CA-55378 | Impose CW MAP Reduction within the allotted timeframe when Immunization Page is not updated for children in AU under age 6 | Policy Re-Design | Medium | Committee Review | CIV-Counties to adopt LRS Functionality | CalWORKs/CalFresh
158 | CA-48379 | Update AAP3 Form | Policy Re-Design | Medium | New |  | Foster Care/Kin GAP/AAP

## Key
SCR Status Key |  | SCR Change Type Key
System Change Request (SCR) Status | Definition | SCR Change Type | Definition
New | Default status when an Issue is created | Data Change | This change type is selected for data change that impacts high volume of cases
Design in Progress | Indicates that the Team/Consortium Staff are working on the Design | Enhancement | This change type is selected for changes to existing design that are not new policy or policy re design.
Ready for Committee | Indicates the Design is ready for Committee to review/approve | Individual Data Change | This change tyhpe is selected for data changes that impacts low volumne of cases (less than 20)
Committee Review | Indicates the Committee is reviewing for approval | New Policy | This change type is selected for SCRs that have references to regulations or state policy letters that have not yet been integrated in the system.
Pending Approval | Indicates that the Issue is pending the approval of CCB. | Operational Enhancement | This change type is selcted for changes to the system that are county specific, impact a specific technology upgrade (ie. New EBT Printer, New Warrant Stock, FTP changes, DB Upgrade, etc.), or are only operational in nature (IP address change, configurational file changes, etc.)
Approved | Indicates that the Issue has been Accepted by the CCB and/or has been given Expedited Approval and build may begin. | Policy Re-Design | This change type is selected of the SCRs is requesting a change to existing design with a regualtion or state policy letter reference.
In Development | Indicates that the Issue is in the development phase
Development Complete | Indicates that the development team has completed development of the Issue
In Assembly Test | Indicates the development team has completed development of the Issue and Assembly Test is in progress
System Test | Indicates that the Issue is currently in System Test and all Test Conditions are being validated in System Test
Test Complete | Indicates that the Issue has been validated in System Test and all Test Conditions have passed System Test