## Slide 1: Thursday, April 23, 2020
Contact Center Approach

## Slide 2: Schedule for a 58 County Contact Center Solution
2020
2023
Today
2020
2021
2022
2023
Definition / Approval
Mar 23 - Feb 8
Incorporate Requirements Needed for LA
Feb 8 - Apr 1
Incorporate Requirements Needed for CalWIN
Feb 5 - Oct 14
Move C-IV County Contact Center in CalSAWS
Jan 18 - Sep 24
C-IV
Go Live
Wave 1
Jan 14
Wave 2
Apr 15
Wave 3
Jul 15
Wave 4
Sep 16
Wave 5
Nov 18
Wave 6
Jan 13
Sep 24
*LA Go Live
Feb 18
Possible Project Start Date
Feb 1
Before diving into the 58-County Contact Center solution development and approval process, let’s look at the critical path deadlines
*Note: LA go live to be determined based on the timeline for requirements specific to LA gathered during the Functional Design Session

## Slide 3: In Progress Functional Design Contact Center Timeline
2020
2020
Today
Feb
Apr
Jun
Aug
Oct
Dec
Feb
Visit Contact Centers & Organize Approach
May 4 - Jun 5
Meet Reps from each County.
Jun 8 - Jun 12
Compile Counties & Advocates Feedback
Jun 15 - Jul 2
IVR/CC Committee Votes on Finalized Requirements
Jul 6 - Jul 10
Create and Review Solution/Estimate
Jul 13 - Sep 11
Review/Refine with Consortium & Clearbest
Sep 14 - Oct 2
State and Federal Approval
Oct 5 - Feb 5
Submit
CRFI
Mar 23
Functional Design Kickoff
Apr 27
Advocate Update
Sep 18
Advocate Session
May 27
PSC/JPA
PSC/JPA
PSC/JPA
Date | Governing Body | Material
July | PSC/JPA | JPA Board Asked to Approve Recommended Direction of Solution
August | PSC/JPA | Update on Solution/Estimate as Appropriate
September | PSC/JPA | Update on Solution/Estimate as Appropriate
October | PSC/JPA | JPA Board Asked for Approval to Send Out for State and Federal Approval
February | PSC/JPA | Final Board Approval

## Slide 4: Key Functional Design Topics
Discuss County vs. Project Managed
Discuss Telephonic Signature Solution
Understand Community-Based Organizations (CBO) Requirements
Understand Foster Care Requirements
CRM (Customer Relationship Management)
  Enhance Call Log
  Provide API’s for counties to call with their own CRM
Areas of Discussion for Local/Central Services
Services Best Done Centrally
Services
Best Done
Locally

## Slide 5: Key Criteria Used for Determining the Contact Center Solutions
As part of the process the Consortium will determine a solution that meets the criteria below:
  Meets all of the requirements from the Contact Center Functional Design process
  Platform as a Service with a pay only-for-what-you-use cost model
  Ability to procure the service through a leveraged government contract vehicle
  The solution needs to be performant (and there will be numerous performance checkpoints throughout the process)