EXHIBIT A, AMENDMENT NO. NINETY-SEVEN

I.	FINANCIAL MATTERS

A.	Maximum for Deliverables and Services

Consortium shall pay a maximum for Deliverables and Services described herein under this Agreement of $1,589,261,601.

B.	Equipment and Third Party Software Payments

Contractor may invoice the Consortium for Equipment and Third Party Software loaded on the Equipment following delivery thereof to Consortium in accordance with Sections 6.1.1 through 6.1.3 of the Agreement for the Equipment.  The preliminary costs for Equipment and Third Party payments are included in this Section and are based on the Equipment and Third Party Software, as defined in the Agreement and the Response.  The actual list of Equipment and Third Party Software and associated payments may differ based on the actual deliveries that are made by Contractor or Proquire in accordance with the Work Plan.

The Consortium shall pay the invoicing party, Proquire or Contractor as applicable, the charges for renting the Equipment set forth on the Schedule(s) that will be added to the Lease and $306.00 per month, beginning the first month in which Equipment is accepted under the Lease, for its Services in administering the list of Equipment to be installed on behalf of the Consortium, as provided in the Lease.  Commencing with the first month in which Equipment valued under $5,000.00 receives Acceptance under this Agreement and the Lease, the administrative fee will increase from $306.00 per month to $612.00 per month.  Contractor may invoice and collect rent on behalf of Proquire under the Lease.

The Consortium shall pay a maximum for Equipment and Third Party Software described herein under this Agreement of $101,581,548.  This amount shall be divided between development and implementation Equipment and Third Party Software of $57,945,547, and Maintenance and Operations Support Services Equipment and Third Party Software of $43,636,001.

C.	Maintenance and Operations Payments

Contractor will invoice the Consortium for actual Maintenance and Operations Support Services staff costs (hourly rates multiplied by actual hours worked) and C-IV Production Operations costs as identified in Schedule D-2 and in Schedule O-3.  Invoices will be issued monthly in arrears, beginning with the initial Maintenance and Operations Support Services, as identified in the Work Plan. The Consortium shall pay a maximum for Maintenance and Operations Payments described herein under this Agreement of $308,590,693.

D.	Facilities Payments

Facilities costs will be invoiced to the Consortium monthly in arrears, based on the amounts identified in Schedule E.  The Consortium shall pay a maximum for Facilities described herein under this Agreement of $26,600,106.

E.	Deliverables Payment Schedule

The following schedule contains the list of Project Deliverables in sequence by target invoice date.  The appropriate Work Plan task reference is provided to tie these Deliverables back to the Work Plan.  The Consortium will make payments for the Deliverables as noted in the schedule below.

F.	Migration

Contractor will invoice the Consortium in accordance with Appendix G of Change Order 027 ISAWS Migration.  The Consortium shall pay a maximum described herein under this Agreement of $99,978,373.

G.	Commodities Procurement

Contractor will invoice the Consortium in accordance commodities procurement costs as identified in Schedule CM.  The Consortium shall pay a maximum described herein under this Agreement of $12,912,462.

H. 	Initial Extension

From November 1, 2011 through October 31, 2013, Contractor will invoice the Consortium in accordance with the Extension Cost Pricing Schedules incorporated into Exhibit A, and the Consortium shall pay the maximum amount of $209,681,111.

I. 	Extension Two

From November 1, 2013 through October 31, 2019, Contractor will invoice the Consortium in accordance with the Extension Two Cost Pricing Schedules incorporated into Exhibit A, and the Consortium shall pay the maximum amount of $667,559,086.

| Num | Deliverable Description | Work Plan Reference | Due Date | Review Period | Target Invoice Date | Holdback Period | Price |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2 | Updated Project Work Plan | 1.1D2 | 3/21/2001 | 2 weeks | 4/4/2001 | R1 | $190,044 |
| 1 | Updated Project Organization Chart | 1.1D1 | 3/31/2001 | 1 week | 4/7/2001 | R1 | $47,511 |
| 52 | Site Preparation Plan – Development Facility | 4.B.1D1 | 3/31/2001 | 1 week | 4/7/2001 | R1 | $1,971,162 |
| 4 | Project Management PCD Update 1 | 1.3D1 | 4/4/2001 | 1 week | 4/7/2001 | R1 | $190,044 |
| 3 | Project Control Document (Final Format) | 1.2.2D1 | 4/30/2001 | 2 weeks | 5/14/2001 | R1 | $492,791 |
| 71 | Development Architecture Design | 4.3D1 | 5/2/2001 | 4 weeks | 5/30/2001 | R1 | $1,484,702 |
| 5 | Project Management PCD Update 2 | 1.3D2 | 5/7/2001 | 1 week | 5/14/2001 | R1 | $177,600 |
| 6 | Project Management PCD Update 3 | 1.3D3 | 6/7/2001 | 1 week | 6/14/2001 | R1 | $295,674 |
| 46 | Sponsor Goals and Expectations Report | 7.1D1 | 6/7/2001 | 1 week | 6/14/2001 | R1 | $492,791 |
| 48 | Communication and Involvement Plan | 7.2D1 | 6/30/2001 | 2 weeks | 7/14/2001 | R1 | $974,927 |
| 49 | Value Realization Plan | 1.5.7D1 | 6/30/2001 | 2 weeks | 7/14/2001 | R1 | $974,927 |
| 7 | Project Management PCD Update 4 | 1.3D4 | 7/10/2001 | 1 week | 7/17/2001 | R1 | $389,971 |
| 68 | High Level Data Model | 5.1.7D1 | 7/19/2001 | 2 weeks | 8/2/2001 | R1 | $1,470,884 |
| 70 | Execution Architecture Design | 4.2D1 | 7/31/2001 | 1 week | 8/7/2001 | R1 | $494,901 |
| 8 | Project Management PCD Update 5 | 1.3D5 | 8/7/2001 | 1 week | 8/14/2001 | R1 | $593,881 |
| 69 | Technical Infrastructure Requirements | 4.1D1 | 8/17/2001 | 1 week | 8/24/2001 | R1 | $1,481,196 |
| 9 | Project Management PCD Update 6 | 1.3D6 | 9/10/2001 | 1 week | 9/17/2001 | R1 | $588,353 |
| 53A | Site Installation Completed – Application Development Facility | 2.3D1 | 9/28/2001 | 1 week | 10/5/2001 | R1 | $1,979,602 |
| 10 | Project Management PCD Update 7 | 1.3D7 | 10/5/2001 | 1 week | 10/12/2001 | R1 | $592,478 |
| 73 | Computing Components Design | 4.5D1 | 10/12/2001 | 1 week | 10/19/2001 | R1 | $296,940 |
| 72 | Operations Architecture Design | 4.4D1 | 10/26/2001 | 4 weeks | 11/23/2001 | R1 | $980,589 |
| 82 | Release 1 General Design | 5.2.1D1 | 10/31/2001 | 4 weeks | 11/28/2001 | R1 | $2,976,949 |
| 116 | Overall Implementation Plan | 9.1D1 | 10/31/2001 | 4 weeks | 11/28/2001 | R1 | $1,488,475 |
| 11 | Project Management PCD Update 8 | 1.3D8 | 11/7/2001 | 1 week | 11/14/2001 | R1 | $595,390 |
| 74 | Technical Architecture Validation Report | 4.6D1 | 11/30/2001 | 1 week | 12/7/2001 | R1 | $493,732 |
| 85 | Release 2 General Design | 5.2.2D1 | 11/30/2001 | 4 weeks | 1/11/2002 | R2 | $4,961,582 |
| 88 | Release 3 General Design | 5.2.3D1 | 11/30/2001 | 4 weeks | 1/11/2002 | R3 | $2,506,603 |
| 12 | Project Management PCD Update 9 | 1.3D9 | 12/7/2001 | 1 week | 12/14/2001 | R1 | $522,396 |
| 75 | Technology Infrastructure Acquisition Rpt | 4.7D1 | 12/15/2001 | 1 week | 12/22/2001 | R1 | $197,493 |
| 77 | Development Architecture Build & Test | 4.9D1 | 12/31/2001 | 1 week | 1/7/2002 | R1 | $464,725 |
| 13 | Project Management PCD Update 10 | 1.3D10 | 1/8/2002 | 1 week | 1/15/2002 | R1 | $557,670 |
| 100 | Release 1 Conversion Plan - Merced | 6.3.6D1 | 1/15/2002 | 4 weeks | 2/12/2002 | R1 | $494,848 |
| 101 | Release 1 Conversion Plan - Riverside | 6.3.6D2 | 1/15/2002 | 4 weeks | 2/12/2002 | R1 | $989,697 |
| 102 | Release 1 Conversion Plan – Stanislaus | 6.3.6D3 | 1/15/2002 | 4 weeks | 2/12/2002 | R1 | $494,848 |
| 103 | Release 1 Conversion Plan - San Bernardino | 6.3.6D4 | 1/15/2002 | 4 weeks | 2/12/2002 | R1 | $989,697 |
| 91 | Training Plan | 8.1D1 | 1/31/2002 | 4 weeks | 2/28/2002 | R1 | $2,474,472 |
| 14 | Project Management PCD Update 11 | 1.3D11 | 2/7/2002 | 1 week | 2/14/2002 | R1 | $593,873 |
| 76 | Execution Architecture Build & Test | 4.8D1 | 2/28/2002 | 2 weeks | 3/14/2002 | R1 | $1,466,065 |
| 92 | Infrastructure Deployment Training Design | 8.2D1 | 2/28/2002 | 2 weeks | 3/14/2002 | R1 | $973,861 |
| 15 | Project Management PCD Update 12 | 1.3D12 | 3/7/2002 | 1 week | 3/14/2002 | R1 | $584,317 |
| 144 | System Operations and Support Plan | 10.1DP | 3/7/2002 | 4 weeks | 4/4/2002 | R1 | $1,947,722 |
| 79 | Computing Components Build & Test | 4.11D1 | 3/29/2002 | 2 weeks | 4/12/2002 | R1 | $486,930 |
| 16 | Project Management PCD Update 13 | 1.3D13 | 4/5/2002 | 1 week | 4/12/2002 | R1 | $521,598 |
| 145 | System Operations and Support Plan Update 1 | 10.1.D1 | 4/5/2002 | 1 week | 4/12/2002 | R1 | $47,418 |
| 47 | Change Plan | 7.1.6D1 | 4/30/2002 | 2 weeks | 5/14/2002 | R1 | $1,955,979 |
| 60 | Site Preparation Plan - Stanislaus | 2.8D1 | 4/30/2002 | 2 weeks | 5/14/2002 | R1 | $488,995 |
| 62 | Telecom Design | 3.1.3D1 | 4/30/2002 | 2 weeks | 5/14/2002 | R1 | $2,933,968 |
| 83 | Release 1 Detailed System Design | 5.3D1 | 4/30/2002 | 4 weeks | 5/28/2002 | R1 | $1,947,722 |
| 86A | Release 2 Detailed System Design (Part I) | 5.4D1 | 4/30/2002 | 4 weeks | 5/28/2002 | R2 | $4,615,148 |
| 84 | Release 1 System Test Plan | 5.9.1D1 | 5/1/2002 | 2 weeks | 5/15/2002 | R1 | $1,484,683 |
| 17 | Project Management PCD Update 14 | 1.3D14 | 5/7/2002 | 1 week | 5/14/2002 | R1 | $537,894 |
| 146 | System Operations and Support Plan Update 2 | 10.1.D2 | 5/7/2002 | 1 week | 5/14/2002 | R1 | $48,899 |
| 87 | Release 2 System Test Plan | 5.9.4D2 | 5/15/2002 | 2 weeks | 5/29/2002 | R2 | $1,896,719 |
| 90 | Release 3 System Test Plan | 5.9.7D3 | 5/15/2002 | 2 weeks | 5/29/2002 | R3 | $1,016,685 |
| PM 1 | Release 1 Detailed System Design Acceptance |  | 5/28/2002 |  |  |  |  |
| 58 | Site Preparation Plan - San Bernardino | 2.7D1 | 5/30/2002 | 2 weeks | 6/13/2002 | R1 | $1,389,299 |
| 78 | Operations Architecture Build & Test | 4.10D1 | 5/30/2002 | 2 weeks | 6/13/2002 | R1 | $1,466,065 |
| 93 | Infrastructure Deployment Training Developed | 8.2D2 | 5/30/2002 | 2 weeks | 6/13/2002 | R1 | $1,973,168 |
| 53B | Site Installation Completed – Development Facility | 2.3D2 | 5/31/2002 | 1 week | 6/7/2002 | R1 | $989,801 |
| 18 | Project Management PCD Update 15 | 1.3D15 | 6/6/2002 | 1 week | 6/13/2002 | R1 | $542,621 |
| 147 | System Operations and Support Plan Update 3 | 10.1D3 | 6/6/2002 | 1 week | 6/13/2002 | R1 | $49,329 |
| 50A | Site Preparation Plan – Production Data Center (Infrastructure Connectivity) | 2.2.3D1 | 6/6/2002 | 1 week | 6/13/2002 | R1 | $1,696,122 |
| 56 | Site Preparation Plan - Riverside | 2.6D1 | 6/28/2002 | 2 weeks | 7/12/2002 | R1 | $759,284 |
| 19 | Project Management PCD Update 16 | 1.3D16 | 7/9/2002 | 1 week | 7/16/2002 | R1 | $537,557 |
| 148 | System Operations and Support Plan Update 4 | 10.1.D4 | 7/9/2002 | 1 week | 7/16/2002 | R1 | $48,869 |
| 20 | Project Management PCD Update 17 | 1.3D17 | 8/7/2002 | 1 week | 8/14/2002 | R1 | $444,236 |
| 149 | System Operations and Support Plan Update 5 | 10.1.D5 | 8/7/2002 | 1 week | 8/14/2002 | R1 | $40,385 |
| 63 | Telecom Installation Plan | 3.2.1D1 | 8/7/2002 | 2 weeks | 8/21/2002 | R1 | $999,709 |
| 54 | Site Preparation Plan - Merced | 2.5D1 | 8/8/2002 | 2 weeks | 8/22/2002 | R1 | $514,939 |
| 117 | Release 1 Implementation Plan | 9.7D2 | 8/30/2002 | 4 weeks | 9/27/2002 | R1 | $927,888 |
| 86B | Release 2 Detailed System Design (Part II) | 5.4D2 | 8/30/2002 | 4 weeks | 9/27/2002 | R2 | $317,771 |
| 21 | Project Management PCD Update 18 | 1.3D18 | 9/9/2002 | 1 week | 9/16/2002 | R1 | $510,339 |
| 150 | System Operations and Support Plan Update 6 | 10.1D6 | 9/9/2002 | 1 week | 9/16/2002 | R1 | $46,394 |
| 108 | Release 2 Conversion Plan – Merced | 6.5.5.1D1 | 9/23/2002 | 4 weeks | 10/21/2002 | R2 | $507,723 |
| 109 | Release 2 Conversion Plan – Riverside | 6.5.5.2D2 | 9/23/2002 | 4 weeks | 10/21/2002 | R2 | $1,015,446 |
| 110 | Release 2 Conversion Plan – Stanislaus | 6.5.5.3D3 | 9/23/2002 | 4 weeks | 10/21/2002 | R2 | $507,723 |
| 111 | Release 2 Conversion Plan - San Bernardino | 6.5.5.4D4 | 9/23/2002 | 4 weeks | 10/21/2002 | R2 | $1,015,446 |
| CM1 | Release 2 Detailed System Design Acceptance | Agreement Milestone 1 | 9/27/2002 |  |  |  |  |
| 80 | Technical Infrastructure Product Test | 4.12.2D1 | 9/30/2002 | 2 weeks | 10/15/2002 | R1 | $1,954,754 |
| 22 | Project Management PCD Update 19 | 1.3D19 | 10/7/2002 | 1 week | 10/15/2002 | R1 | $537,557 |
| 151 | System Operations and Support Plan Update 7 | 10.1D7 | 10/7/2002 | 1 week | 10/15/2002 | R1 | $48,869 |
| 94 | Release 1 Training Design | 8.3D1 | 10/31/2002 | 2 weeks | 11/14/2002 | R1 | $945,058 |
| 176 | Imaging and IVR Architecture Design | 4.13D1 | 10/31/2002 | 2 weeks | 11/14/2002 | R2 | $472,529 |
| 23 | Project Management PCD Update 20 | 1.3D20 | 11/7/2002 | 1 week | 11/14/2002 | R1 | $519,782 |
| 152 | System Operations and Support Plan Update 8 | 10.1D8 | 11/7/2002 | 1 week | 11/14/2002 | R1 | $47,253 |
| 24 | Project Management PCD Update 21 | 1.3D21 | 12/6/2002 | 1 week | 12/13/2002 | R1 | $544,333 |
| 153 | System Operations and Support Plan Update 9 | 10.1D9 | 12/6/2002 | 1 week | 12/13/2002 | R1 | $49,485 |
| 25 | Project Management PCD Update 22 | 1.3D22 | 1/8/2003 | 1 week | 1/15/2003 | R1 | $551,453 |
| 154 | System Operations and Support Plan Update 10 | 10.1D10 | 1/8/2003 | 1 week | 1/15/2003 | R1 | $50,132 |
| PM 2 | Release 1 System Test Complete | Project Milestone | 1/31/2003 |  |  |  |  |
| 26 | Project Management PCD Update 23 | 1.3D23 | 2/7/2003 | 1 week | 2/14/2003 | R1 | $562,348 |
| 155 | System Operations and Support Plan Update 11 | 10.1D11 | 2/7/2003 | 1 week | 2/14/2003 | R1 | $51,123 |
| 95 | Release 1 Training Developed | 8.3D2 | 2/14/2003 | 2 weeks | 2/28/2003 | R1 | $1,022,197 |
| 96A | Release 2 Training Design (Part I) | 8.4D1 | 2/27/2003 | 2 weeks | 3/13/2003 | R2 | $1,738,533 |
| 27 | Project Management PCD Update 24 | 1.3D24 | 3/7/2003 | 1 week | 3/14/2003 | R1 | $559,177 |
| 156 | System Operations and Support Plan Update 12 | 10.1D12 | 3/7/2003 | 1 week | 3/14/2003 | R1 | $50,834 |
| 50B | Site Preparation Plan – Production Data Center (Application Deployment) | 2.2.5D1 | 3/17/2003 | 2 weeks | 3/31/2003 | R1 | $278,805 |
| PM 3 | Release 1 User Acceptance Test Acceptance | Project Milestone | 3/28/2003 |  |  |  |  |
| 158 | System Operations and Support Plan Implemented | 10.1DIM | 3/31/2003 | 2 weeks | 4/14/2003 | R1 | $1,022,197 |
| 89 | Release 3 Detailed System Design | 5.5D1 | 3/31/2003 | 4 weeks | 4/28/2003 | R3 | $2,044,394 |
| 28 | Project Management PCD Update 25 | 1.3D25 | 4/7/2003 | 1 week | 4/14/2003 | R1 | $562,208 |
| 157 | System Operations and Support Plan Update 13 | 10.1D13 | 4/7/2003 | 1 week | 4/14/2003 | R1 | $51,110 |
| 51A | Site Installation Completed – Production Data Center (Infrastructure Connectivity) | 2.2.4D1 | 4/28/2003 | 2 weeks | 5/12/2003 | R1 | $1,200,873 |
| 118 | Release 2 Implementation Plan | 9.7D3 | 4/28/2003 | 4 weeks | 5/27/2003 | R2 | $1,022,197 |
| 119 | Release 3 Implementation Plan | 9.7D4 | 4/28/2003 | 4 weeks | 5/27/2003 | R3 | $507,723 |
| 29 | Project Management PCD Update 26 | 1.3D26 | 5/7/2003 | 1 week | 5/14/2003 | R1 | $568,991 |
| 159 | System Operations and Support Plan Update 14 | 10.1D14 | 5/7/2003 | 1 week | 5/14/2003 | R1 | $51,726 |
| 96B | Release 2 Training Design (Part II) | 8.4D1 | 5/8/2003 | 2 weeks | 5/22/2003 | R2 | $579,510 |
| 89B | Release 3 Detailed System Design (Part II) |  | 5/16/2003 | 2 weeks | 5/30/2003 | R3 | $760,754 |
| 51B | Site Installation Completed – Production Data Center (Application Deployment) | 2.2.7D1 | 5/27/2003 | 2 weeks | 6/10/2003 | R1 | $1,860,371 |
| CM2 | Release 3 Detailed System Design Acceptance | Agreement Milestone 2 | 5/30/2003 |  |  |  |  |
| 30 | Project Management PCD Update 27 | 1.3D27 | 6/3/2003 | 1 week | 6/10/2003 | R1 | $588,089 |
| 160 | System Operations and Support Plan Update 15 | 10.1D15 | 6/3/2003 | 1 week | 6/10/2003 | R1 | $51,490 |
| 96C | Release 2 Training Design (Part III) | 8.4D1 | 6/5/2003 | 2 weeks | 6/16/2003 | R2 | $829,527 |
| 31 | Project Management PCD Update 28 | 1.3D28 | 7/8/2003 | 1 week | 7/15/2003 | R1 | $562,855 |
| 161 | System Operations and Support Plan Update 16 | 10.1D16 | 7/8/2003 | 1 week | 7/15/2003 | R1 | $51,169 |
| 32 | Project Management PCD Update 29 | 1.3D29 | 8/7/2003 | 1 week | 8/14/2003 | R1 | $566,426 |
| 162 | System Operations and Support Plan Update 17 | 10.1D17 | 8/7/2003 | 1 week | 8/14/2003 | R1 | $51,493 |
| PM 4 | Release 1 Pilot Acceptance | Project Milestone | 8/15/2003 |  |  |  |  |
| 33 | Project Management PCD Update 30 | 1.3D30 | 9/8/2003 | 1 week | 9/15/2003 | R1 | $563,483 |
| 163 | System Operations and Support Plan Update 18 | 10.1D18 | 9/8/2003 | 1 week | 9/15/2003 | R1 | $50,772 |
| 67 | Telecom Installation Completed - Stanislaus | 3.2.4D4 | 9/19/2003 | 2 weeks | 10/3/2003 | R1 | $1,992,515 |
| 181 | Quarterly Reporting System Test Complete | 5.9.10D1 | 9/30/2003 | 1 week | 10/7/2003 | R2 | $1,719,112 |
| CM3 | R2 System Test Acceptance | Agreement Milestone 3 | 9/30/2003 |  |  |  |  |
| 97 | Release 2 Training Developed | 8.8.8D | 10/2/2003 | 2 weeks | 10/16/2003 | R2 | $1,029,865 |
| 34 | Project Management PCD Update 31 | 1.3D31 | 10/7/2003 | 1 week | 10/14/2003 | R1 | $566,664 |
| 164 | System Operations and Support Plan Update 19 | 10.1D19 | 10/7/2003 | 1 week | 10/14/2003 | R1 | $51,515 |
| 64 | Telecom Installation Completed - Merced | 3.2.4D1 | 10/15/2003 | 2 weeks | 10/29/2003 | R1 | $1,959,034 |
| 98 | Release 3 Training Design | 8.11.3D | 10/16/2003 | 2 weeks | 10/30/2003 | R3 | $1,015,446 |
| 61 | Site Installation Completed- Stanislaus | 2.8D2 | 10/17/2003 | 2 weeks | 10/31/2003 | R1 | $2,044,653 |
| 35 | Project Management PCD Update 32 | 1.3D32 | 11/7/2003 | 1 week | 11/14/2003 | R1 | $554,851 |
| 165 | System Operations and Support Plan Update 20 | 10.1D20 | 11/7/2003 | 1 week | 11/14/2003 | R1 | $50,441 |
| 106 | Release 1 Conversion Plan Tasks Completed – Stanislaus | 6.12.8D3 | 11/10/2003 | 2 weeks | 11/24/2003 | R1 | $1,008,821 |
| 55A | Site Installation Completed - Merced (Infrastructure) | 2.5D2A | 11/12/2003 | 2 weeks | 11/26/2003 | R1 | $1,012,198 |
| 126 | Release 1 Implementation - Stanislaus | 9.3.4D1 | 11/17/2003 | 1 week | 11/24/2003 | R1 | $652,675 |
| CM5 | Release 2 User Acceptance Test Acceptance | Agreement Milestone 5 | 12/4/2003 |  |  |  |  |
| 36 | Project Management PCD Update 33 | 1.3D33 | 12/5/2003 | 1 week | 12/12/2003 | R2 | $273,285 |
| 122 | Release 1 Training Completed - Stanislaus | 8.15.13D | 12/5/2003 | 1 week | 12/12/2003 | R1 | $514,903 |
| 166 | System Operations and Support Plan Update 21 | 10.1D21 | 12/5/2003 | 1 week | 12/12/2003 | R2 | $54,657 |
| CM4 | Release 3 System Test Acceptance | Agreement Milestone 4 | 12/12/2003 |  |  |  |  |
| 104 | Release 1 Conversion Plan Tasks Completed – Merced | 6.10.9D1 | 12/15/2003 | 2 weeks | 12/29/2003 | R1 | $1,008,821 |
| 124 | Release 1 Implementation – Merced | 9.3.3D1 | 12/22/2003 | 1 week | 1/5/2004 | R1 | $504,410 |
| 37 | Project Management PCD Update 34 | 1.3D34 | 1/8/2004 | 1 week | 1/15/2004 | R2 | $262,792 |
| 167 | System Operations and Support Plan Update 22 | 10.1D22 | 1/8/2004 | 1 week | 1/15/2004 | R2 | $52,558 |
| 120 | Release 1 Training Completed – Merced | 8.15.16D | 1/9/2004 | 1 week | 1/16/2004 | R1 | $504,410 |
| 99 | Release 3 Training Developed | 8.11.4D | 2/5/2004 | 2 weeks | 2/19/2004 | R3 | $353,000 |
| 38 | Project Management PCD Update 35 | 1.3D35 | 2/6/2004 | 1 week | 2/13/2004 | R2 | $252,502 |
| 168 | System Operations and Support Plan Update 23 | 10.1D23 | 2/6/2004 | 1 week | 2/13/2004 | R2 | $50,500 |
| 130 | Release 2 Pilot Completed – Stanislaus | 9.4.5D1 | 2/13/2004 | 1 week | 2/20/2004 | R2 | $505,003 |
| CM7 | Release 3 User Acceptance Test Acceptance | Agreement Milestone 7 | 2/13/2004 |  |  |  |  |
| CM6 | Release 2 Pilot Acceptance | Agreement Milestone 6 | 2/23/2004 |  |  |  |  |
| 112 | Release 2 Conversion Plan Tasks Completed - Merced | 6.19.10D1 | 3/1/2004 | 2 weeks | 3/15/2004 | R2 | $459,267 |
| 39 | Project Management PCD Update 36 | 1.3D36 | 3/5/2004 | 1 week | 3/12/2004 | R2 | $191,118 |
| 169 | System Operations and Support Plan Update 24 | 10.1D24 | 3/9/2004 | 1 week | 3/16/2004 | R2 | $38,224 |
| 128 | Release 2 Training Completed - Merced | 8.15.19D | 3/12/2004 | 1 week | 3/17/2004 | R2 | $459,267 |
| 65 | Telecom Installation Completed - Riverside | 3.2.4D2 | 3/22/2004 | 2 weeks | 4/5/2004 | R1 | $3,227,603 |
| 132 | Release 2 Implementation - Merced | 9.5.3D1 | 4/2/2004 | 1 week | 4/9/2004 | R2 | $536,160 |
| 137 | Release 3 Implementation - Merced | 9.6.2D1 | 4/2/2004 | 1 week | 4/9/2004 | R3 | $250,000 |
| 114 | Release 2 Conversion Plan Tasks Completed - Stanislaus | 6.21.21D3 | 4/5/2004 | 2 weeks | 4/19/2004 | R2 | $459,267 |
| 40 | Project Management PCD Update 37 | 1.3D37 | 4/7/2004 | 1 week | 4/14/2004 | R2 | $202,441 |
| 134 | Release 2 Implementation – Stanislaus | 9.5.4D1 | 4/9/2004 | 1 week | 4/16/2004 | R2 | $418,396 |
| 136 | Release 3 Training Completed - Merced | 8.15.23D | 4/9/2004 | 1 week | 4/16/2004 | R3 | $250,000 |
| 141 | Release 3 Implementation – Stanislaus | 9.6.3D1 | 4/9/2004 | 1 week | 4/16/2004 | R3 | $202,441 |
| 170 | System Operations and Support Plan Update 25 | 10.1D25 | 4/9/2004 | 1 week | 4/16/2004 | R2 | $40,488 |
| 140 | Release 3 Training Completed – Stanislaus | 8.15.20D | 4/16/2004 | 1 week | 4/23/2004 | R3 | $191,118 |
| 57 | Site Installation Completed - Riverside | 2.6D2 | 4/26/2004 | 2 weeks | 5/10/2004 | R1 | $2,578,416 |
| 66A | Telecom Installation Completed - San Bernardino | 3.2.4D3A | 4/27/2004 | 2 weeks | 5/11/2004 | R1 | $604,207 |
| 41 | Project Management PCD Update 38 | 1.3D38 | 5/7/2004 | 1 week | 5/14/2004 | R2 | $128,179 |
| 171 | System Operations and Support Plan Update 26 | 10.1D26 | 5/11/2004 | 1 week | 5/18/2004 | R2 | $42,726 |
| 105 | Release 1 Conversion Plan Tasks Completed – Riverside | 6.11.8D2 | 5/24/2004 | 2 weeks | 6/7/2004 | R1 | $1,034,890 |
| 125 | Release 1 Implementation - Riverside | 9.3.5D1 | 6/1/2004 | 1 week | 6/8/2004 | R1 | $1,029,865 |
| 121 | Release 1 Training Completed - Riverside | 8.15.14D | 6/4/2004 | 1 week | 6/11/2004 | R1 | $1,029,865 |
| 42 | Project Management PCD Update 39 | 1.3D39 | 6/7/2004 | 1 week | 6/14/2004 | R2 | $115,591 |
| 172 | System Operations and Support Plan Update 27 | 10.1D27 | 6/9/2004 | 1 week | 6/16/2004 | R2 | $38,530 |
| 55B | Site Installation Completed - Merced (Workstations) | 2.5D2B | 6/9/2004 | 2 weeks | 6/23/2004 | R2 | $1,009,251 |
| 66B | Telecom Installation Completed - San Bernardino | 3.2.4D3B | 6/28/2004 | 2 weeks | 7/13/2004 | R1 | $4,991,811 |
| 43 | Project Management PCD Update 40 | 1.3D40 | 7/8/2004 | 1 week | 7/15/2004 | R2 | $267,013 |
| 173 | System Operations and Support Plan Update 28 | 10.1D28 | 7/12/2004 | 1 week | 7/19/2004 | R2 | $89,004 |
| 59 | Site Installation Completed - San Bernardino | 2.7D2 | 7/19/2004 | 2 weeks | 8/2/2004 | R1 | $4,677,013 |
| 107 | Release 1 Conversion Plan Tasks Completed - San Bernardino | 6.13.7D4 | 7/19/2004 | 2 weeks | 8/2/2004 | R1 | $2,021,725 |
| 123 | Release 1 Training Completed - San Bernardino | 8.15.15D | 7/26/2004 | 1 week | 8/2/2004 | R1 | $2,064,768 |
| 127 | Release 1 Implementation - San Bernardino | 9.3.6D1 | 7/26/2004 | 1 week | 8/2/2004 | R1 | $2,064,766 |
| 44 | Project Management PCD Update 41 | 1.3D41 | 8/6/2004 | 1 week | 8/13/2004 | R2 | $276,117 |
| 174 | System Operations and Support Plan Update 29 | 10.1D29 | 8/10/2004 | 1 week | 8/17/2004 | R2 | $92,040 |
| 113 | Release 2 Conversion Plan Tasks Completed - Riverside | 6.20.18D2 | 8/16/2004 | 2 weeks | 8/30/2004 | R2 | $920,393 |
| 129 | Release 2 Training Completed – Riverside | 8.15.17D | 8/20/2004 | 1 week | 8/27/2004 | R2 | $811,405 |
| 138 | Release 3 Training Completed – Riverside | 8.15.21D | 8/27/2004 | 1 week | 9/03/2004 | R3 | $405,701 |
| 133 | Release 2 Implementation – Riverside | 9.5.5D1 | 9/3/2004 | 1 week | 9/13/2004 | R2 | $3,047,044 |
| 139 | Release 3 Implementation – Riverside | 9.6.4D1 | 9/3/2004 | 1 week | 9/13/2004 | R3 | $386,082 |
| 45 | Project Management PCD Update 42 | 1.3D42 | 9/8/2004 | 1 week | 9/15/2004 | R2 | $300,607 |
| 175 | System Operations and Support Plan Update 30 | 10.1D30 | 9/10/2004 | 1 week | 9/17/2004 | R2 | $100,202 |
| 115 | Release 2 Conversion Plan Tasks Completed - San Bernardino | 6.22.19D4 | 9/28/2004 | 2 weeks | 10/12/2004 | R2 | $920,393 |
| 179 | Project Management PCD Update 43 | 1.3D43 | 10/7/2004 | 1 week | 10/14/2004 | R2 | $151,387 |
| 177 | System Operations and Support Plan Update 31 | 10.1D31 | 10/12/2004 | 1 week | 10/19/2004 | R2 | $151,387 |
| 131 | Release 2 Training Completed – San Bernardino | 8.15.18D | 10/15/2004 | 1 week | 10/22/2004 | R2 | $772,165 |
| 142 | Release 3 Training Completed - San Bernardino | 8.15.22D | 10/15/2004 | 1 week | 10/22/2004 | R3 | $445,481 |
| 135 | Release 2 Implementation - San Bernardino | 9.5.6D1 | 11/2/2004 | 2 weeks | 11/17/2004 | R2 | $3,452,757 |
| 143 | Release 3 Implementation - San Bernardino | 9.6.5D1 | 11/2/2004 | 1 week | 11/9/2004 | R3 | $460,195 |
| 180 | Project Management PCD Update 44 | 1.3D44 | 11/5/2004 | 1 week | 11/12/2004 | R2 | $151,387 |
| 178 | System Operations and Support Plan Update 32 | 10.1D32 | 11/9/2004 | 1 week | 11/17/2004 | R2 | $151,387 |
| 182 | Cash EBT Stanislaus Complete |  | 2/28/2005 | 1 week | 3/7/2005 | R3 | $109,460 |
| 183 | Transitional Food Stamps Complete |  | 4/18/2005 | 1 week | 4/25/2005 | N/A | $319,458 |
| 184 | San Bernardino County eFUNDs to Statewide EBT Transition |  | 5/20/2005 | 1 week | 5/27/2005 | N/A | $475,418 |
| CM8 | Consortium-wide Implementation Acceptance | Agreement Milestone 8 | 6/30/2005 |  |  |  |  |
| CM9 | Final Acceptance | Agreement Milestone 9 | 1/31/2006 |  |  |  |  |
|  | Total All Deliverables |  |  |  |  |  | $162,358,222 |