## Slide 1
CalACES/CalSAWS Planning

## Slide 2
CalACES-CalSAWS Progress
CalACES-CalSAWS Planning Timeline
CalSAWS User Labs Update
Requirements Gathering Status
CalSAWS Executive Leadership Team Update
Agenda

## Slide 3
The PAPDU has been updated to support a larger overall effort and additional concurrent activities in support of CalSAWS
CalWIN and CalACES have planned contract amendments/change orders to accommodate additional services by the 3rd Party Independent Contractor
Approval of the additional change order for CalACES is planned for the April 26, 2018 JPA meeting
Review and approval of the CalWIN change order is planned for April 13, 2018
CalACES-CalSAWS Progress
# | Key Task | Contract
1. | Conduct CalACES Alternatives Analysis and Cost Benefit Analysis | CalACES – First Data (Current)
2. | CalWIN/CalSAWS Requirements Analysis | CalACES – First Data
3. | CalWIN/CalSAWS Business Process Gap Analysis | CalWIN – Infosys
4. | CalWIN Ancillary Systems Analysis | CalWIN – Infosys
5. | CalWIN/CalSAWS Data Conversion Strategy | CalACES – First Data
6. | CalWIN Initial Data Mapping | CalWIN - Infosys

## Slide 4
CalACES-CalSAWS Planning Project Progress
Description
Conduct CalACES Alternatives Analysis and Cost Benefit Analysis
  Analyze options for CalACES hosting strategy
  Analyze options for CalACES datacenter consolidation
  Analyze options for CalACES database consolidation
  Analyze options for SAWS Shared Services e.g. Single SAWS Consolidated Portal
CalWIN/CalSAWS
Requirements Analysis
CalWIN/CalSAWS
Business Process Gap Analysis
  Plan Requirements Assessment
  Conduct CalSAWS User Labs
  Facilitate Requirements Sessions
  Assess Impact of Alternatives Analysis and Update Requirements (Existing & New)
  Document As-Is and To-Be Business Processes
  Compare CalWIN Functionality to CalACES/CalSAWS Functionality
  Document Gaps in Business Processes and Identify Requirements to Address Gaps
  Determine Impact of New Requirements
  Update Existing Requirements
Task
Status
1
2
3
  Hosting strategy identified as government cloud
  Additional analysis in progress
  User labs in progress
  Requirements sessions being planned
  Kick off meeting planned
  Information gathering in process

## Slide 5
CalACES-CalSAWS Planning Project Progress
Description
CalWIN Ancillary Systems Analysis
  Complete Inventory Request
  Complete Targeted Demonstrations
  Identify Essential Functionality & Gaps
  Update Requirements
CalWIN/CalSAWS Data Conversion Strategy
CalWIN Initial Data Mapping
  Gather CalWIN Database Information
  Analyze Preliminary Data Mapping
  Document Conversion Strategy Options
  Compare Database Table & Elements between CalWIN & CalACES
  Identify Required Core Tables & Elements
  Document Initial Data Mapping
Task
Status
4
5
6
  Kick off meeting planned
  Information gathering in process
  Kick off meeting planned
  Kick off meeting planned

## Slide 6
CalACES-CalSAWS Planning Timeline
1
2
3
4
5
6

## Slide 7
Challenges & Status
Technical Issues
  User Log Ins – Process change initiated
  Security Issues – Pending resolution for topic weeks
  Training Validations - Resolved
Operational Changes
  Additional Roamers needed in the North - Resolved
Documentation
  Capture all comment forms and debrief feedback in a central spreadsheet
  Parking lot forms have written response, shared with user lab participants and captured on the central spreadsheet
CalSAWS User Lab Updates Week 1 Eligibility CalWORKs/CalFresh Focus - (As of Wednesday EOB)

## Slide 8
Lessons Learned
Update process and validate that all security forms have been received and C Numbers so that everybody has a login in day one
More roamers in the North
Shortening the Project Logistics slide deck in the South
Reduce background information in Orientation Slide Deck and reduce overall detail to shorten the time
Do quicker and higher level demos
Hold questions during the demo until the end
Improvements
Week 2 - Log In issues were resolved within hours
Orientation overview was completed prior to User Lab by CalWIN Project Staff
Orientation and demonstrations were completed much quicker on day one
Additional staff available for roaming in the North
CalSAWS User Labs Week 1 (As of Wednesday EOB)

## Slide 9
CalSAWS User Labs Comment Form and Parking Lot Form Tracking
  All comment forms and parking lot forms will be documented in a tracking spreadsheet
  Staff will document all potential gaps and the gaps will be reviewed in Phase 3, Requirements Gathering Sessions
CalSAWS Tracking Spreadsheet
  Categorize all items into 4 categories:
  Design Difference Identified
  Existing CalACES Requirement
  Suggested Enhancement
  Duplicate
CalSAWS User Lab Overview

## Slide 10
CalSAWS User Labs Outcomes
User Lab Comments | North | South
Existing Requirements | 36 | 38
Design Difference Identified | 24 | 28
Suggest Enhancement | 14 | 26
N/A | 5 | 6
Totals | 79 | 98
Each comment was categorized into one of four categories:
Existing Requirements: Have an existing requirement and User Lab Participant is indicating a status change in the indicator as defined from the CalWIN Project Review
Design Difference Identified: A gap has been identified as a difference between LRS and CalWIN that affects efficiency or functionality
Suggest Enhancement: CalWIN Participants have identified a suggested enhancement* to the system *Note: Identified as an enhancement by Migration Planning Team and must be reviewed by CalWIN Project
N/A: These have been identified as Not Applicable due to being retracted by the User or an environment issue and it is not really a gap.
Note: There were 72 items across North/South that were determined to be duplicates of the items above.

## Slide 11
CalSAWS User Labs Outcomes
 | Explanation
Positive Comments | Immunizations functionality, Verifications List Page, Message Center, Address Pre-Population functionality during case creation, Task Navigation for easier access to specific pages, Codes on Citizenship page, Hide Person functionality, Universal Journal Template, Relationship Page, ICT process including images, Itemized Deductions in EDBC
Change Management Concerns | No Workflow, Display reasons for failing EDBC, Application Registration, Expedited Services/Immediate Need, FPL information not on EDBC, Medi-Cal behind the scenes evaluation for eligibility for other programs, Employment information in multiple places, Journal displays vertically

## Slide 12
  When
  May 14 – June 22 (6 weeks)
  Sessions scheduled by specific topic area
    Each topic expected to be no more than 1 week
    Number of sessions to be determined
  Participants
    Attendance 40 CalACES (5 per Region) and 40 CalWIN (2 per county) plus Project and State Staff
    County Staff should be able to make decisions for the counties they represent and ideally will have participated in the user lab sessions
    Recruiting Process: CalWIN-CalACES CRFI
    Travel costs will be covered (but not staff time)
    Each participant would be expected to attend 1 or more sessions
  Output
    Updated statement of requirements to be presented to the stakeholders
CalSAWS Guided Requirements Gathering Sessions

## Slide 13
  Agreed to form a JPA between CalWIN and CalACES
  Identified tasks to develop the JPA Agreement
  Working on Schedule
  Drafted a Memorandum of Understanding (See Attachment)
CalSAWS Executive Leadership Team Update
  Governance Planning – In Progress