## CalACES Chg Mgmt 2018 - North
SCR | Summary | Estimate | Funding Source | Change Type (SCR) | SPG Rating | Status | Fix Version/s | Minor Version | Team Responsible | Priority | Created | SPG Status | SPG Score | Other Agency Cross Reference | Committee / WorkGroup
SCR | Add C-IV Functional Presentation for SCR CIV-1383 Authorized Representative to Online Help | 35 | C-IV M&O | Policy Re-Design | High | Approved | 18.11 |  | Training |  | 2018-09-11 14:42 | Approved | NA
SCR | Update Plumas County calendar for 2018 | 10 | C-IV M&O | Data Change | Medium | Approved | 18.11 |  | Batch/Interfaces |  | 2018-03-28 11:14 | Approved | TBD |  | Fiscal
SCR | Update Outbound WIS Interface for 2019 STS Calendar Cycle Numbers | 15 | C-IV M&O | Enhancement | High | Approved | 18.11 | 18.11.xx | Fiscal | Medium | 2018-02-06 14:24 | Approved | 0 |  | Tax Intercept
SCR | Update Online Help for SCR 8219 Removal of 'Generate in Primary Language' Button | 10 | Premise | New Policy | High | Approved | 19.01 |  | Training |  | 2018-08-28 14:47 | Approved | TBD
SCR | Update Online Help for SCR 101003 - EBT Repayment | 5 | C-IV M&O | Enhancement | Medium | Approved | 19.01 |  | Training |  | 2018-08-07 15:41 | Approved | TBD
SCR | Add C-IV Functional Presentation for SCR 100195 - Add Change Reason to Data Collection Pages to Online Help | 35 | C-IV M&O | Enhancement | High | Approved | 19.01 |  | Training |  | 2018-06-28 16:51 | Approved | N/A
SCR | Job Aid Updates for SCR CIV-100195 - Add Change Reason to Data Collection Pages | 50 | C-IV M&O | Enhancement | High | Approved | 19.01 |  | Training |  | 2018-06-15 11:04 | Approved | N/A
SCR | Add WIC Mobile Site Link to C4Yourself | 45 | C-IV M&O | Enhancement | High | Approved | 19.01 |  | Online |  | 2018-05-21 16:26 | Approved | N/A | CA-202731 | C4Yourself
SCR | Create Administrative Kiosk Pages | 235 | C-IV M&O | Enhancement | Medium | Approved | 19.01 |  | Online |  | 2018-02-12 15:37 | Approved | N/A |  | Lobby Management
SCR | Add Change Reason to Data Collection Pages | 1960 | C-IV M&O | Enhancement | High | Approved | 19.01 |  | Eligibility | Medium | 2018-01-19 11:56 | Approved | N/A |  | CalWORKs/CalFresh Foster Care/Kin GAP/AAP Medi-Cal/CMSP
SCR | Implement Additional Reports in the C-IV System (56590) |  | C-IV M&O | Enhancement | High | Approved | 19.03 |  | Reports | Medium | 2017-12-29 14:24 | Approved | N/A | CA-52210
SCR | Tehama County (Local Warrant Print) Update Warrant Mapping | 45 | C-IV M&O | Enhancement | High | In Production | 18.09 |  | Client Correspondence |  | 2018-08-13 11:59 | Approved | TBD | N/A | Other
SCR | Update Online Help for SCR 101374 ACL 18-82 - Elect Child Support Payment for Stepsibling or Half-Sibling in Lieu of Cash Aid - Phase 1 | 5 | Premise | New Policy | Critical | In Production | 18.09 |  | Training |  | 2018-07-25 11:23 | Approved | N/A
SCR | Update Forms Overview for SCR 101645 - Add MC-007 | 5 | C-IV M&O | Policy Re-Design | Medium | In Production | 18.09 |  | Training |  | 2018-07-11 15:02 | Approved | N/A
SCR | Update Online Help and Job Aids for SCR 11439 Enhancement to Deemed Eligible Functionality | 15 | Premise | Policy Re-Design | Critical | In Production | 18.09 |  | Training |  | 2018-07-05 13:33 | Approved | N/A
SCR | Add Job Aid - Medi-Cal CalHEERS â€“ MAGI Re-Evaluation (RE) Process | 10 | C-IV M&O | Enhancement | Medium | In Production | 18.09 |  | Training |  | 2018-07-03 10:40 | Approved | Approved by Karen and Dorothy 7/9/2018
SCR | Add Revised MC-007 (Static Form) | 30 | C-IV M&O | Policy Re-Design | High | In Production | 18.09 |  | Client Correspondence |  | 2018-06-28 10:09 | Approved | TBD | CA-202379 | Correspondence
SCR | Add EBT Printer for Kings County 16PRINTAVE | 10 | C-IV M&O | Operational Enhancement | High | In Production | 18.09 |  | Fiscal |  | 2018-06-26 14:04 | Approved | N/A
SCR | Update Job Aids for SCR 100710 | 10 | C-IV M&O | Enhancement | Medium | In Production | 18.09 |  | Training |  | 2018-06-26 08:04 | Approved | N/A
SCR | Add new Pay Codes for GA (Managed) for Monterey and Riverside Counties | 55 | C-IV M&O | Enhancement | High | In Production | 18.09 |  | Fiscal |  | 2018-06-19 08:20 | Approved | NA
SCR | MobileWebservice: Renew Apple Push Notification Certificate | 10 | C-IV M&O | Operational Enhancement | High | In Production | 18.09 |  | Tech Arch |  | 2018-06-12 10:59 | Approved | N/A |  | Tech
SCR | Update Batch Sweeps Job Aid | 5 | C-IV M&O | Enhancement | Medium | In Production | 18.09 |  | Training |  | 2018-06-12 08:26 | Approved | N/A
SCR | Update Job Aid and Online Help for SCR 100305 AB 480: ACL 18-38 / CFL 17/18-57 Add Additional Diaper Benefit Functionality | 15 | C-IV M&O | New Policy | Critical | In Production | 18.09 |  | Training |  | 2018-06-11 16:31 | Approved | NA
SCR | Update C4Yourself Android Mobile App to support API level 26 or higher | 100 | C-IV M&O | Operational Enhancement | Medium | In Production | 18.09 |  | Tech Arch |  | 2018-05-31 10:36 | Approved | N/A |  | Tech
SCR | Update Post Call Survey Application | 30 | County Purchase | Enhancement | Medium | In Production | 18.09 |  | Contact Center |  | 2018-05-29 08:43 | Approved | N/A
SCR | Update C4Yourself Mobile App to be built with iOS 11.0 SDK or Later | 80 | C-IV M&O | Operational Enhancement | Medium | In Production | 18.09 |  | Tech Arch |  | 2018-05-16 16:36 | Approved | N/A |  | Tech
SCR | Update Reports Overview for SCR 100726 | 5 | C-IV M&O | Enhancement | Medium | In Production | 18.09 |  | Training |  | 2018-05-16 13:15 | Approved | N/A
SCR | MEDS Interface - Safety Net & Drug/Fleeing Felon Aid Codes 3F and K1 | 155 | C-IV M&O | New Policy | Critical | In Production | 18.09 |  | Batch/Interfaces |  | 2018-05-11 11:48 | Approved | N/A | CA-47284 | MEDS
SCR | Job Aid Update for SCR 1073 - Modify the TCF Recertification Process | 5 | C-IV M&O | Enhancement | Medium | In Production | 18.09 |  | Training |  | 2018-05-02 13:20 | Approved | N/A
SCR | Update Job Aids for SCR 10768 | 15 | C-IV M&O | Enhancement | High | In Production | 18.09 |  | Training |  | 2018-04-26 14:20 | Approved | N/A
SCR | Remove C-IV Functional Presentations from Online Help | 5 | C-IV M&O | Policy Re-Design | Medium | In Production | 18.09 |  | Training |  | 2018-04-13 12:08 | Approved | N/A
SCR | C4Y: Update the Voter Hotline Number for Threshold Languages | 20 | C-IV M&O | Enhancement | Critical | In Production | 18.09 |  | Online |  | 2018-04-04 11:27 | Approved | N/A | CA-201740 | C4Yourself
SCR | Deactivate Unnecessary PDF Format Scheduled Reports | 85 | C-IV M&O | Enhancement | High | In Production | 18.09 |  | Reports |  | 2018-03-16 10:02 | Approved | N/A | C-IV Specific | State/Fiscal Reports
SCR | Update On-Request Reports with PDF format to Generate Only as a Spreadsheet | 145 | C-IV M&O | Enhancement | Medium | In Production | 18.09 |  | Reports |  | 2018-03-13 10:37 | Approved | NA |  | Management Reports
SCR | CalHEERS eHIT: Naturalized/Derived Citizenship updates (CH-109700) | 300 | Premise | New Policy | Critical | In Production | 18.09 |  | CalHEERS |  | 2018-02-23 13:26 | Approved | N/A | CH-109700; CH-113161; CA-200850 | Medi-Cal/CMSP
SCR | CFL 15/16-64 - AB 2035 EBT Benefit Replacement due to Electronic Theft Update - SUAS | 260 | C-IV M&O | New Policy | Medium | In Production | 18.09 |  | Fiscal |  | 2018-02-14 09:41 | Approved | NA | CA-50781 | Fiscal
SCR | Upgrade Cisco Finesse from 10.5 to version 11.6 | 60 | County Purchase | Operational Enhancement | High | In Production | 18.09 |  | Contact Center | Medium | 2018-02-02 16:12 | Approved | N/A | C-IV Specific | Contact Center Management
SCR | Add San Bernardino County District 28 to IVR and C4Yourself | 35 | C-IV M&O | Operational Enhancement | Medium | In Production | 18.09 |  | Lobby Mgmt | Medium | 2018-01-16 14:01 | Approved | N/A |  | Other
SCR | Exceeding clock tasks are created for timed out persons. | 130 | C-IV M&O | Data Change | High | In Production | 18.09 |  | Batch/Interfaces | Low | 2017-12-29 14:26 | Approved | N/A |  | Time Limits
SCR | Modify Visual IVR queuing logic | 180 | County Purchase | Operational Enhancement | Medium | In Production | 18.09 |  | Contact Center | Medium | 2017-12-29 14:26 | Approved | N/A | None | Contact Center Management
SCR | Enhancement to Deemed Eligible Functionality | 1400 | C-IV M&O | Policy Re-Design | Critical | In Production | 18.09 |  | CalHEERS | Medium | 2017-12-29 14:26 | Approved | N/A | CA-51741 | Medi-Cal/CMSP
SCR | CO-084: CalWORKs/CalFresh NOAs in Threshold languages Phase 4 of 5 | 1720 | Premise | New Policy | High | In Production | 18.09 |  | Client Correspondence | Medium | 2017-12-29 14:25 | Approved | N/A | None | Correspondence
SCR | eICT: Add ICT as Source of the Application | 85 | C-IV M&O | Enhancement | High | In Production | 18.09 |  | Online | Medium | 2017-12-29 14:25 | Approved | N/A | CA-55375 | ICT
SCR | Modify the TCF recertification process for programs discontinued after the RE Due Month (56659) | 475 | C-IV M&O | Enhancement | Medium | In Production | 18.09 |  | Online | Medium | 2017-12-29 14:24 | Approved | N/A | CA-54027 | CalWORKs/CalFresh
SCR | Update Time Limit Sanctions Batch | 85 | C-IV M&O | Enhancement | High | In Production | 18.09 |  | Batch/Interfaces | Medium | 2017-12-29 14:23 | Approved | N/A | CA-201634 | Time Limits
SCR | ACL 11-15E11 Update the KG EDBC to Consider the SOC 369A Date | 65 | C-IV M&O | Policy Re-Design | Medium | In Production | 18.09 |  | Eligibility | Medium | 2017-12-29 14:23 | Approved | N/A | LRS SCR CA-200592 | Foster Care/Kin GAP/AAP
SCR | Update Cash Aid Time Limit Month Detail Page to allow 'Repay' reasons 700 and 701 for Tribal TANF or Out of State Months | 75 | C-IV M&O | Enhancement | High | Test Complete | 18.11 |  | Fiscal |  | 2018-08-07 10:45 | Approved | TBD | CA-51485 | Time Limits
SCR | Remove C-IV Functional Presentations from Online Help | 5 | C-IV M&O | Policy Re-Design | High | Test Complete | 18.11 |  | Training |  | 2018-04-13 10:08 | Approved | Approved by Karen Rapponotti 8/28/2018 and Dorothy Avila 8/29/2018
SCR | ACWDL 18-04: 2018 Medicare Savings Program (MSP) Property Limits | 40 | C-IV M&O | New Policy | Critical | Test Complete | 18.11 |  | CalHEERS |  | 2018-02-26 15:17 | Approved | 86 | CA-200843 | Medi-Cal/CMSP
SCR | Update Issuance Detail page to have the Pay Code field read-only when issuance is in Cancelled status | 50 | C-IV M&O | Enhancement | Medium | Test Complete | 18.11 |  | Fiscal | Medium | 2017-12-29 14:26 | Approved | 48 | None | Fiscal
SCR | ACL 18-50 - Tracking of the Visually Impaired | 55 | C-IV M&O | Policy Re-Design | Medium | Test Complete | 18.11 |  | Online | Medium | 2017-12-29 14:26 | Approved | N/A |  | Correspondence
SCR | ACL 11-72E: Update Quality Control Sanction NOA fragments for 125 day period | 55 | C-IV M&O | Policy Re-Design | High | Test Complete | 18.11 |  | Client Correspondence | Medium | 2017-12-29 14:26 | Approved | N/A | None | CalWORKs/CalFresh
SCR | AB 480: ACL 18-38 - Generate the NA 823 when manually issuing diaper allowance | 105 | C-IV M&O | New Policy | High | Test Complete | 18.11 |  | Fiscal |  | 2018-07-02 15:37 | Approved | N/A | CA-203249 | Welfare to Work/WPR
SCR | Update Reports Overview for SCR CIV-100258 | 5 | C-IV M&O | Enhancement | Low | System Test | 18.11 |  | Training |  | 2018-08-16 14:40 | Approved | 32
SCR | Online Help Updates for SCR CIV-1383 Authorized Representative | 25 | C-IV M&O | Policy Re-Design | High | System Test | 18.11 |  | Training |  | 2018-08-09 16:48 | Approved | N/A
SCR | NOA update for ACL 17-108 - (CalWORKs) Changes To Asset Limits For Families That Include Elderly Or Disabled Household Members | 60 | C-IV M&O | New Policy | High | System Test | 18.11 |  | Client Correspondence |  | 2018-07-18 14:38 | Approved | 81 | CIV-11242 and CA-56799 | Correspondence
SCR | Update Reports Overview for FNS 209 | 5 | C-IV M&O | Enhancement | High | System Test | 18.11 |  | Training |  | 2018-07-18 11:18 | Approved | Approved by Karen Rapponotti 8/28/2018 and Dorothy Avila 8/29/2018
SCR | Update Reports Overview in Online Help for WTW 25 and WTW 25A | 5 | C-IV M&O | Enhancement | Medium | System Test | 18.11 |  | Training |  | 2018-07-09 10:49 | Approved | 68
SCR | Modify Eligibility Status Action Code (ESAC) trigger condition for EW20 transaction | 115 | C-IV M&O | Operational Enhancement | Medium | System Test | 18.11 |  | Batch/Interfaces |  | 2018-06-19 11:56 | Approved | TBD | CA-58059 | MEDS
SCR | C4Y CO6935-2017 Remove Napa County Offices from C4Yourself | 45 | C-IV M&O | Data Change | Medium | System Test | 18.11 |  | Online |  | 2018-06-14 12:15 | Approved |  |  | C4Yourself
SCR | ACWDL 18-13: 2018/2019 Family Member Base Allocation Amount | 40 | C-IV M&O | New Policy | High | System Test | 18.11 |  | CalHEERS | Medium | 2018-02-14 18:16 | Approved | 84 | CA-200839 | Medi-Cal/CMSP
SCR | C4Y: Update the image drop down for Uploading Documents | 25 | C-IV M&O | Enhancement | Medium | System Test | 18.11 |  | Online | Medium | 2017-12-29 14:26 | Approved | N/A | None | C4Yourself
SCR | CES 2017-035 Request Applicant IEVS at Redetermination | 260 | C-IV M&O | Enhancement | Low | System Test | 18.11 |  | Batch/Interfaces | Low | 2017-12-29 14:26 | Approved | N/A | CA-52874 | IEVS
SCR | Upgrade to RoboHelp 2017 | 80 | C-IV M&O | Enhancement | Medium | System Test | 18.11 |  | Training | Medium | 2017-12-29 14:26 | Approved | Approved by Karen Rapponotti 8/28/2018 and Dorothy Avila 8/29/2018 | None
SCR | Update CalFresh EDBC Logic to Correctly Evaluate PA Household Indicator | 135 | C-IV M&O | Policy Re-Design | High | System Test | 18.11 |  | Eligibility | Medium | 2017-12-29 14:25 | Approved | 79 | CA-53463 | CalWORKs/CalFresh
SCR | CO-084: CalWORKs/CalFresh NOAs in Threshold languages Phase 5 of 5 | 1555 | Premise | New Policy | Medium | System Test | 18.11 |  | Client Correspondence | Medium | 2017-12-29 14:25 | Approved | TBD | None | Correspondence
SCR | Update Foster Care/Kin-GAP Income Exemption Logic to Handle Partial Income Exemptions | 160 | C-IV M&O | Policy Re-Design | Low | System Test | 18.11 |  | Eligibility | Medium | 2017-12-29 14:25 | Approved | TBD | CA-203173 | Foster Care/Kin GAP/AAP
SCR | Create a new Daily Interface Payment Status Report | 605 | C-IV M&O | Enhancement | Low | System Test | 18.11 |  | Fiscal | Medium | 2018-01-26 10:07 | Approved | 32 | C-IV Specific (report changes CA-203342) | State/Fiscal Reports
SCR | Auto rescission for Medi-Cal programs where RE packet is received after 10-day cutoff | 1815 | C-IV M&O | Enhancement | Critical | System Test | 18.11 |  | CalHEERS |  | 2018-05-31 09:43 | Approved | N/A | CA-202862 | Medi-Cal/CMSP
SCR | DDCR 10001: Convert Remaining Scheduled PDF Reports into a Spreadsheet Format | 425 | C-IV M&O | Enhancement | Medium | System Test | 18.11 |  | Reports |  | 2018-03-16 10:39 | Approved | 69 | CA-203382 | State/Fiscal Reports
SCR | Implement Application for Monitoring Performance (AMP) Phase VI | 250 | C-IV M&O | Enhancement | Medium | System Test | 18.11 |  | Performance |  | 2018-05-02 21:42 | Approved | N/A | CA-202477
SCR | ACWDL 17-12: Authorized Representative Information | 2110 | C-IV M&O | New Policy | High | System Test | 18.11 |  | Online | Medium | 2017-12-29 14:24 | Approved | NA | CA-47607 | CalWORKs/CalFresh Medi-Cal/CMSP
SCR | Upgrade Calabrio One version 9.5 to version 10.3 | 400 | County Purchase | Operational Enhancement | Medium | In Development | 18.09 | 18.10.29 | Contact Center |  | 2018-07-05 14:11 | Approved | N/A
SCR | Move Voice Prints between Counties | 280 | County Purchase | Enhancement | Medium | In Development | 18.11 | 18.12.XX | Contact Center |  | 2018-07-11 17:21 | Approved | TBD |  | IVR & Contact Center
SCR | Design - Architecture for MicroServices | 350 | C-IV M&O | Enhancement | Medium | In Development | 18.11 |  | Tech Arch |  | 2018-06-20 10:00 | Approved | N/A |  | Tech
SCR | Lobby Mgmt - Reception Zebra printer driver refactor | 215 | C-IV M&O | Enhancement | Medium | In Development | 19.01 |  | Online |  | 2018-03-27 11:03 | Approved | TBD | CA-204065 | Lobby Management
SCR | Update the EBT Repayment Process | 575 | C-IV M&O | Enhancement | Medium | In Development | 19.01 |  | Fiscal |  | 2018-04-17 00:41 | Approved | TBD | CA-52879 | Fiscal
SCR | ACL 17-53: ESAP Notice Automation | 650 | Premise | New Policy | High | In Development | 19.01 |  | Client Correspondence | Medium | 2017-12-29 14:26 | Approved | 81 | CA-56416 | Correspondence
SCR | CalHEERS eHIT: SSA Title II Income and Disability Indicator Verifications (CH-92298) | 330 | Premise | Enhancement | Critical | In Development | 19.02 |  | CalHEERS |  | 2018-03-23 10:49 | Approved | N/A | CA-201692; CH-92298 | Medi-Cal/CMSP