## CalACES Chg Mgmt 2018 - South
SCR | Summary | Estimate | Funding Source | Change Type (SCR) | SPG Rating | Status | Fix Version/s | Minor Version | Team Responsible | Priority | Created | SPG Status | SPG Score | Other Agency Cross Reference | Committee / WorkGroup
SCR | YBN Security Assessment Findings - Insecure File Upload | 100 | LRS M&E | Enhancement | Medium | Approved | 18.09 | 18.10.xx | Tech Arch |  | 2018-09-18 18:29 | Approved | N/A - Technical SCR Only
SCR | Training QA of Job Aids Impacted by SCR CA-47607 | 16 | LRS M&E | Enhancement | High | Approved | 18.11 |  | Training |  | 2018-09-14 15:33 | Approved | TBD
SCR | Training QA of Job Aids Impacted by SCR CA-51485 | 30 | LRS M&E | Enhancement | High | Approved | 18.11 |  | Training |  | 2018-08-29 09:16 | Approved | N/A
SCR | Training QA of Job Aids Impacted by SCR CA-54027 | 20 | LRS M&E | Enhancement | Critical | Approved | 18.11 |  | Training |  | 2018-08-23 10:51 | Approved | N/A
SCR | Training Support - LRS Job Aids Transition to Consortium South | 165 | LRS M&E | Enhancement | Medium | Approved | 18.11 |  | Training |  | 2018-06-14 13:21 | Approved | N/A
SCR | YBN-Upgrade-Code Changes to Support WebLogic v12 and Java 8 | 740 | LRS M&E | Operational Enhancement | Medium | Approved | 18.11 |  | Tech Arch | 3-Normal/Low | 2018-01-19 11:42 | Approved | N/A |  | Tech
SCR | County Ad-Hoc database - Technical Support | 640 | LRS M&E | Operational Enhancement | Medium | Approved | 19.01 |  | DBA |  | 2018-05-10 10:36 | Approved | N/A
SCR | Adding Office Name column to Service Payment EBT Issuance Register Report | 70 | LRS M&E | Enhancement | High | Approved | 19.01 |  | Fiscal | 3-Normal/Low | 2018-01-19 11:47 | Approved | N/A |  | State/Fiscal Reports
SCR | ATS Security Assessment Findings - Group 3 | 754 | LRS M&E | Enhancement | High | Approved | 19.01 |  | Tech Arch | 3-Normal/Low | 2018-01-19 11:43 | Approved | N/A
SCR | CalHEERS eHIT: SSA Title II Income and Disability Indicator Verifications (CH-92298) | 385 | Premise | Enhancement | Critical | Approved | 19.02 |  | CalHEERS |  | 2018-03-23 10:52 | Approved | N/A | CIV-100810; CH-92298 | Medi-Cal/CMSP
SCR | Training Updates - Removal of LACO Seal/Logo from LRS WBTs | 100 | LRS M&E | Enhancement | High | Approved | 19.06 |  | Training |  | 2018-08-14 10:06 | Approved | TBD
SCR | Training QA of Job Aids Impacted by SCR CA-52389 | 8 | LRS M&E | Enhancement | Critical | In Production | 18.09 |  | Training |  | 2018-08-23 11:00 | Approved | N/A
SCR | Training Updates - (DCFS Updates) Add Extract Capability to Eligibility Workload Inventory and Monthly Productivity Pages in LRS (based on C-IV SCR 7271) (DCFS WBTs) | 25 | LRS M&E | Enhancement | Medium | In Production | 18.09 |  | Training |  | 2018-08-08 15:39 | Approved | TBD
SCR | Training Updates - (DCFS Updates) - Modify CalHEERS Online Single Streamlined Application (DCFS WBTs) | 135 | LRS M&E | Enhancement | Medium | In Production | 18.09 |  | Training | 4-Cosmetic | 2018-08-07 12:07 | Approved | TBD
SCR | Training QA of Job Aids Impacted by SCR CA-51899 | 16 | LRS M&E | Enhancement | Critical | In Production | 18.09 |  | Training |  | 2018-08-06 15:27 | Approved | TBD
SCR | YBN: Enhancements to the EBT Account Balance and Transactions Page | 20 | LRS M&E | Enhancement | High | In Production | 18.09 |  | Online |  | 2018-05-29 15:45 | Approved | N/A |  | C4Yourself
SCR | funding: ACL16-77 - YourBenefitsNow YBN Application process and CW RE to track testing and deployment | 305 | LRS M&E | Policy Re-Design | Medium | In Production | 18.09 |  | System Test | 3-Normal/Low | 2018-05-08 14:10 | Approved | N/A |  | C4Yourself
SCR | Training QA of Job Aids Impacted by SCR CA-58841 | 13 | LRS M&E | Enhancement | High | In Production | 18.09 |  | Training |  | 2018-08-02 10:03 | Approved | TBD
SCR | Training QA of Job Aids Impacted by SCR CA-49401 | 22 | LRS M&E | Enhancement | Medium | In Production | 18.09 |  | Training |  | 2018-08-02 10:07 | Approved | TBD
SCR | Training QA of Job Aids Impacted by SCR CA-48753 | 9 | LRS M&E | Enhancement | Medium | In Production | 18.09 |  | Training |  | 2018-08-02 10:09 | Approved | TBD
SCR | Training Updates - AB 480: ACL 18-38 / CFL 17/18-57 Add Additional Diaper Benefit Functionality - Phase II (WBTs) | 125 | LRS M&E | Enhancement | High | In Production | 18.09 |  | Training |  | 2018-07-11 14:56 | Approved | N/A
SCR | Training Updates - Resource Databank Assessment Results (WBTs) | 130 | LRS M&E | Enhancement | Medium | In Production | 18.09 |  | Training |  | 2018-07-24 15:47 | Approved | TBD
SCR | Training Release 18.09 - Online Help (OLH) Updates |  | LRS M&O | Enhancement | Medium | In Production | 18.09 |  | Training | 3-Normal/Low | 2018-07-23 09:54 | Approved | N/A
SCR | Training QA of Job Aids Impacted by SCR CA-51741 | 36 | LRS M&E | Enhancement | Medium | In Production | 18.09 |  | Training |  | 2018-07-23 11:30 | Approved | N/A
SCR | Training Updates - Rename "CalFresh - IHE" to "CalFresh - IHE (Customer Caused)" for CalFresh Overissuance (WBTs) | 18 | LRS M&E | Enhancement | Medium | In Production | 18.09 |  | Training |  | 2018-07-12 13:18 | Approved | N/A
SCR | Upgrade the Build Tool from Maven to Gradle Version 4 | 40 | LRS M&O | Operational Enhancement | Medium | In Production | 18.09 |  | Tech Arch |  | 2018-06-20 11:47 | Approved | N/A | CIV-9356
SCR | Training QA of Job Aids Impacted by SCR CA-56221 | 10 | LRS M&E | Enhancement | Medium | In Production | 18.09 |  | Training |  | 2018-08-02 10:12 | Approved | TBD
SCR | Training QA of Job Aids Impacted by SCR CA-201075 | 14 | LRS M&E | Enhancement | Medium | In Production | 18.09 |  | Training |  | 2018-08-02 10:10 | Approved | TBD
SCR | Los Angeles Auditor Controller Trust Warrant Refund (TWR) Bank code change | 130 | LRS M&E | Operational Enhancement | Critical | In Production | 18.09 |  | Fiscal |  | 2018-07-25 10:11 | Approved | TBD
SCR | Training Release 18.09 - LMS Lite updates |  | LRS M&O | Enhancement | Medium | In Production | 18.09 |  | Training | 3-Normal/Low | 2018-07-20 11:48 | Approved | N/A
SCR | Enhance recording of AMP and AUDIT to reduce database contention | 240 | LRS M&E | Operational Enhancement | Medium | In Production | 18.09 |  | DBA |  | 2018-06-21 14:32 | Approved | N/A
SCR | Design for CalHEERS Change IV | 5120 | Premise | Operational Enhancement | High | In Production | 18.09 |  | CalHEERS |  | 2018-06-19 10:43 | Approved | N/A | CalHEERS CRs: CR 92295, CR 119408, CR 121151, CR 124708, CR 124914, CR 124918, CR 106890, CR 109744, CR 122183
SCR | Support for DPSS Priority Focus Areas | 100 | LRS M&E | Operational Enhancement | Medium | In Production | 18.09 |  | Training |  | 2018-06-14 15:06 | Approved | N/A
SCR | Training Updates - Customer Reporting Updates (WBTs) | 120 | LRS M&E | Enhancement | Medium | In Production | 18.09 |  | Training |  | 2018-06-04 16:55 | Approved | N/A
SCR | Training Updates - Add New ADA Journal type - Special Circumstance. (WBTs) | 45 | LRS M&E | Enhancement | Medium | In Production | 18.09 |  | Training |  | 2018-06-04 16:58 | Approved | N/A
SCR | Training Updates - < ITGC > Phase II - ACL 17-34 - Add Elderly Simplified Application Project (ESAP) Indicator and Automate CF 377.2D (WBTs) | 220 | LRS M&E | Enhancement | Medium | In Production | 18.09 |  | Training |  | 2018-06-04 16:52 | Approved | N/A
SCR | Training Updates - Child Welfare Trust Changes (WBTs) | 65 | LRS M&E | Enhancement | Medium | In Production | 18.09 |  | Training |  | 2018-06-04 16:46 | Approved | TBD
SCR | Training Updates - Remove "ALL" as the default option for Workload Reassignment Detail Page (WBT) | 20 | LRS M&E | Enhancement | Medium | In Production | 18.09 |  | Training |  | 2018-06-04 16:30 | Approved | N/A
SCR | Training Updates - Modify LRS WFP&I Investigation Result Detail page to remove mandatory restriction on the Case Action field (WBTs) | 15 | LRS M&E | Enhancement | Medium | In Production | 18.09 |  | Training |  | 2018-06-04 15:58 | Approved | N/A
SCR | Training Updates - CFL 15/16-64 - AB 2035 EBT Benefit Replacement due to Electronic Theft Update - SUAS (WBTs) | 15 | LRS M&E | Enhancement | Medium | In Production | 18.09 |  | Training |  | 2018-06-04 15:30 | Approved | N/A
SCR | Training Updates - AB 480: ACL 18-38 / CFL 17/18-57 Add Diaper Benefit Functionality Phase I (WBTs) | 20 | LRS M&E | Enhancement | Medium | In Production | 18.09 |  | Training |  | 2018-06-04 16:28 | Approved | N/A
SCR | Training Updates - ARC/FC Payments to Caretaker Prior to Home Approval (WBTs) | 45 | LRS M&E | Enhancement | Medium | In Production | 18.09 |  | Training |  | 2018-05-03 15:50 | Approved | N/A
SCR | Workshare: Implement Revised MC-007 (Static Form) | 100 | LRS M&E | Policy Re-Design | High | In Production | 18.09 |  | Client Correspondence |  | 2018-04-27 08:53 | Approved | N/A | CIV-101645 | Correspondence
SCR | Training Updates - Modify the Start Date logic for LAC General Relief Housing Subsidy on Money Management pages and Vendor recoupment changes for GR EDBC | 22 | LRS M&E | Enhancement | Medium | In Production | 18.09 |  | Training |  | 2018-03-07 11:43 | Approved | N/A
SCR | Training Updates - GR Policy 42-200 - Add Property Logic to LRS for GR Program (WBTs) | 15 | LRS M&E | Policy Re-Design | Medium | In Production | 18.09 |  | Training |  | 2018-03-05 17:34 | Approved | N/A
SCR | Training Updates - GROW Program - 38055 - Update the Collaborator Access - allow a Single User to Log into Multiple Resources at one time (WBTs) | 30 | LRS M&E | Enhancement | Medium | In Production | 18.09 |  | Training |  | 2018-03-05 10:36 | Approved | .
SCR | Your Benefits Now (YBN): Update the Voter Hotline Number for Threshold Languages | 20 | LRS M&E | Enhancement | Critical | In Production | 18.09 |  | Online |  | 2018-03-28 08:07 | Approved | N/A | CIV-100900 | C4Yourself
SCR | Update Time Limit Sanctions Batch | 195 | LRS M&E | Enhancement | Critical | In Production | 18.09 |  | Fiscal |  | 2018-03-21 11:54 | Approved | N/A | C-IV SCR 623 | Time Limits
SCR | DDCR 3005: Add an Unverified E-Notification Request Report to the LRS System | 180 | LRS M&E | New Policy | Medium | In Production | 18.09 |  | Reports |  | 2018-03-07 15:28 | Approved | N/A | CIV-986 | Management Reports
SCR | Training Updates - Homeless Transition Age Youth and Disabled General Relief Population with New Invoice- upload the revised ABP 295 meals/lodging order and invoice to LRS | 75 | LRS M&E | Enhancement | Medium | In Production | 18.09 |  | Training |  | 2018-03-07 12:03 | Approved | N/A
SCR | Training Updates - MSUDRP Assessment Page Changes (WBTs) | 15 | LRS M&E | Enhancement | Medium | In Production | 18.09 |  | Training |  | 2018-03-07 12:00 | Approved | N/A
SCR | TTC Posted Collections on Recovery Account Transaction Date | 20 | LRS M&E | Enhancement | Critical | In Production | 18.09 |  | Fiscal |  | 2018-03-21 16:50 | Approved | N/A | LA County Specific | Collections
SCR | Training Updates - Trust Fund Activity Tracking Enhancements (WBTs) | 29 | LRS M&E | Enhancement | Medium | In Production | 18.09 |  | Training |  | 2018-03-05 14:56 | Approved | N/A
SCR | DPSS/DCFS Incident/DCR support SCR for 18.09 | 350 | LRS M&E | Operational Enhancement | Medium | In Production | 18.09 |  | Fiscal |  | 2018-03-01 11:42 | Approved | N/A
SCR | Update Payment Request Detail page to have Payee Name link to Resource Detail page | 45 | LRS M&E | Enhancement | High | In Production | 18.09 |  | Fiscal |  | 2018-02-15 13:46 | Approved | N/A | CIV-7551 | Fiscal
SCR | Update the LRS Case Number Assignment | 60 | LRS M&E | Enhancement | High | In Production | 18.09 |  | Online |  | 2018-02-14 14:13 | Approved | N/A |  | Usability
SCR | DDCR 3135: Update Batch EDBC to skip cases when a person is closed on MC Program and the RE DER is MAGI Conditionally Eligible | 75 | LRS M&E | Policy Re-Design | Medium | In Production | 18.09 |  | Batch/Interfaces |  | 2018-02-05 13:45 | Approved | N/A | CIV 55876 | Medi-Cal/CMSP
SCR | DDCR 3059: Add validation to prevent the same LRS person from being linked to multiple persons in a MAGI Referral | 60 | LRS M&E | Enhancement | High | In Production | 18.09 |  | CalHEERS |  | 2018-02-05 13:21 | Approved | N/A | CIV 50910 | Medi-Cal/CMSP
SCR | DDCR 3104: Enhance Determination Response Handling - add Duplicate SSN validation | 55 | LRS M&E | Policy Re-Design | Medium | In Production | 18.09 |  | CalHEERS |  | 2018-02-05 13:41 | Approved | N/A | CIV-55074 | Medi-Cal/CMSP
SCR | Los Angeles County Auditor Controller file for Voucher Less Vendors | 305 | LRS M&E | Operational Enhancement | High | In Production | 18.09 |  | Fiscal |  | 2018-02-27 17:34 | Approved | N/A |  | Fiscal
SCR | CalHEERS eHIT: Naturalized/Derived Citizenship updates (CH-109700) | 315 | Premise | New Policy | High | In Production | 18.09 |  | CalHEERS |  | 2018-02-14 11:03 | Approved | N/A | CH-109700; CH-113161; CIV-100538 | Medi-Cal/CMSP
SCR | Standardize existing records in the code_detl table | 104 | LRS M&E | Operational Enhancement | Medium | In Production | 18.09 |  | DBA |  | 2018-02-08 11:32 | Approved | N/A
SCR | Update table column comments for missing category ID references | 104 | LRS M&E | Operational Enhancement | Medium | In Production | 18.09 |  | DBA |  | 2018-02-08 11:35 | Approved | N/A
SCR | Clean up "LRS TABLE" and "LRS FIELD" comments. | 104 | LRS M&E | Operational Enhancement | Medium | In Production | 18.09 |  | DBA |  | 2018-02-08 11:36 | Approved | N/A
SCR | ACL 11-15E11 Update KG EDBC to Consider the SOC 369A Date | 195 | LRS M&E | Policy Re-Design | High | In Production | 18.09 |  | Eligibility |  | 2018-02-02 13:13 | Approved | N/A | CIV-503 | Foster Care/Kin GAP/AAP
SCR | DDCR 4034: MEDIL 13-03: Update MAGI Pending Eligible logic to treat retro months same as intake | 60 | LRS M&E | New Policy | Medium | In Production | 18.09 |  | CalHEERS |  | 2018-01-30 09:23 | Approved | N/A | CIV-1107 | Medi-Cal/CMSP
SCR | DDCR 4061: Update system to save MAGI Determination to database for person without a Determination node | 55 | LRS M&E | Enhancement | Medium | In Production | 18.09 |  | CalHEERS | 1-High/Non-Cosmetic | 2018-01-24 11:05 | Approved | N/A | CIV-2583 | Medi-Cal/CMSP
SCR | DDCR 4049: Update Primary Applicant validations for MAGI Request | 65 | LRS M&E | Enhancement | Medium | In Production | 18.09 |  | CalHEERS | 2-Normal/Medium | 2018-01-24 10:31 | Approved | N/A | CIV-1406 | Medi-Cal/CMSP
SCR | DDCR 4023: Validate unique MEDS Person Numbers for MAGI Request | 50 | LRS M&E | Enhancement | Medium | In Production | 18.09 |  | CalHEERS | 2-Normal/Medium | 2018-01-24 10:01 | Approved | N/A | CIV-936 | Medi-Cal/CMSP
SCR | DDCR 4022: Address same as Primary does not display on MAGI Person Detail page | 65 | LRS M&E | Enhancement | Medium | In Production | 18.09 |  | CalHEERS | 2-Normal/Medium | 2018-01-24 09:58 | Approved | N/A | CIV-906 | Medi-Cal/CMSP
SCR | DDCR 4030: Remove the Age Requirement for the Caretaker Relative Field on Tax Household page | 30 | LRS M&E | Enhancement | Medium | In Production | 18.09 |  | CalHEERS | 2-Normal/Medium | 2018-01-24 10:11 | Approved | N/A | CIV 1046 | Medi-Cal/CMSP
SCR | YBN Security Assessment Findings - Group 2 (Improper error handling, Missing security headers & Missing HTTP strict-transport-security header) | 432 | LRS M&E | Enhancement | Medium | In Production | 18.09 |  | Tech Arch | 3-Normal/Low | 2018-01-19 11:44 | Approved | N/A
SCR | eICT: Update the E-ICT option for Source of the Application to ICT | 10 | LRS M&E | Enhancement | Medium | In Production | 18.09 |  | Online | 3-Normal/Low | 2018-01-19 11:43 | Approved | N/A | CIV-6871 | ICT
SCR | ACL 17-75 Update the Kin-GAP rate schedule to use Case Dismissal Date | 425 | LRS M&E | New Policy | High | In Production | 18.09 |  | Imaging | 3-Normal/Low | 2018-01-19 11:41 | Approved | N/A | C-IV SCR 10978 | Foster Care/Kin GAP/AAP
SCR | Modifications to Logic of LRS REP Reports: AOGP Actuals (monthly), AOGP Goals and Actuals (annual), ASP, and RS 50 (trimester) | 485 | LRS M&E | Enhancement | High | In Production | 18.09 |  | Reports | 3-Normal/Low | 2018-01-19 11:44 | Approved | TBD | None | State/Fiscal Reports
SCR | <No Cost SCR> < ITGC > DCFS: Complete the Work Order Detail and Work Order List page modifications to fully incorporate the functionality of the EW WORKS legacy system originally slated for inclusion in LRS Phase I implementation | 545 | Other | Enhancement | Critical | In Production | 18.09 |  | Online | 3-Normal/Low | 2018-01-19 11:44 | Approved | N/A | LA County Specific | Usability
SCR | NO COST SCR - NOMI Denial batch shouldn't be denying the participant has attended the Intake Interview | 70 | Other | Policy Re-Design | High | In Production | 18.09 |  | Batch/Interfaces | 3-Normal/Low | 2018-01-19 11:43 | Approved | N/A |  | CalWORKs/CalFresh
SCR | Removal of Program-Specific Rescission Limits | 140 | LRS M&E | Enhancement | Critical | In Production | 18.09 |  | Online | 3-Normal/Low | 2018-01-19 11:43 | Approved | N/A |  | CalWORKs/CalFresh
SCR | Add Region and Region Group column in all Welfare-to-Work/REP/Cal-Learn detail reports (County Workshare) | 720 | LRS M&E | Enhancement | Medium | In Production | 18.09 |  | Reports | 3-Normal/Low | 2018-01-19 11:45 | Approved | N/A |  | Management Reports
SCR | < ITGC > Modify the TCF recertification process for programs discontinued after the RE Due Month | 695 | Other | Enhancement | Critical | In Production | 18.09 |  | Online | 3-Normal/Low | 2018-01-19 11:45 | Approved | N/A | CIV-1073 | CalWORKs/CalFresh
SCR | Replace the PA 2012 (01/13) with Revised PA 2012 (07/15) Form | 15 | LRS M&E | Enhancement | Medium | In Production | 18.09 |  | Client Correspondence | 3-Normal/Low | 2018-01-19 11:45 | Approved | N/A |  | Correspondence
SCR | < ITGC > Fix special characters in the IEVS (IFDS) and QCIS file | 325 | LRS M&E | Enhancement | High | In Production | 18.09 |  | Batch/Interfaces | 3-Normal/Low | 2018-01-19 11:44 | Approved | N/A | CIV-101304 | IEVS
SCR | DDCR 5062: Update Child Support Member Transactions - Eligibility Status Date Functionality For Former MFG Children (C-IV SCR #7266) | 295 | LRS M&E | New Policy | Critical | In Production | 18.09 |  | Batch/Interfaces | 3-Normal/Low | 2018-01-19 11:44 | Approved | N/A | CIV-7266 | CalWORKs/CalFresh
SCR | Enhancement to Deemed Eligible Functionality | 1365 | LRS M&E | Policy Re-Design | Critical | In Production | 18.09 |  | CalHEERS | 3-Normal/Low | 2018-01-19 11:43 | Approved | N/A | CIV-11439 | Medi-Cal/CMSP
SCR | ACL 14-37 - CalFresh Replacement Benefits Status Reasons and Revised Form | 175 | LRS M&E | Policy Re-Design | Medium | In Production | 18.09 |  | Fiscal | 3-Normal/Low | 2018-01-19 11:47 | Approved | N/A |  | Fiscal
SCR | Phase II - Add Threshold languages to existing RCA NOAs | 525 | LRS M&E | New Policy | Critical | In Production | 18.09 |  | Client Correspondence | 3-Normal/Low | 2018-01-19 11:45 | Approved | 0 | Per migration requirements CIV is adopting LRS NOA's | Correspondence
SCR | DPSS Mobile App, revise look and feel to align with the DPSS Communication Sections Design recommendation | 1030 | LRS M&E | Enhancement | Medium | In Production | 18.09 |  | Online | 3-Normal/Low | 2018-01-19 11:44 | Approved | N/A |  | C4Yourself
SCR | ACL16-77 - YourBenefitsNow YBN Application process and CW RE in all threshold language. | 682 | R&A - Fixed | Policy Re-Design | Medium | In Production | 18.09 |  | Batch/Interfaces | 3-Normal/Low | 2018-01-19 11:44 | Approved | N/A |  | C4Yourself
SCR | < ITGC > CSSD General Relief (GR) File - LA County Only | 350 | LRS M&E | Enhancement | High | In Production | 18.09 |  | Batch/Interfaces | 3-Normal/Low | 2018-01-19 11:44 | Approved | N/A |  | Other
SCR | DDCR 3139: < ITGC > ACL No. 13-70 - MEDS Interface - Safety Net & Drug/Fleeing Felon Aid Codes 3F and K1 | 180 | LRS M&E | New Policy | Critical | In Production | 18.09 |  | Batch/Interfaces | 3-Normal/Low | 2018-01-19 11:44 | Approved | N/A | CIV-101257 | MEDS
SCR | ATS Security Assessment Findings - Group 1 | 250 | LRS M&E | Enhancement | Medium | In Production | 18.09 |  | Tech Arch | 3-Normal/Low | 2018-01-19 11:43 | Approved | N/A |  | Tech
SCR | Complete Documentation, Training and Transitioning of OID Maintenance Process from Tech Operations to eGov team for YBN(CBO/FBO) and ATS Accounts | 365 | LRS M&E | Operational Enhancement | High | In Production | 18.09 | 18.08.03 | Tech Ops | 3-Normal/Low | 2018-01-19 11:41 | Approved | N/A
SCR | DPSS/DCFS Support SCR to provide responses to Consortia queries | 916 | LRS M&E | Data Change | Medium | In Production | 18.09 |  | Batch/Interfaces | 3-Normal/Low | 2018-01-19 11:41 | Approved | N/A
SCR | Kin-GAP Program DCR | 60 | LRS M&O | Data Change | High | In Production | 18.09 |  | Online | 3-Normal/Low | 2018-01-19 11:41 | Approved | N/A |  | Foster Care/Kin GAP/AAP
SCR | DDCR 3118: CalACES - Update Homeless Assistance Temporary (HT) and Homeless Assistance Permanent (HP) Benefits - Aid Code 35 to Count TANF Time Limit Clock | 55 | LRS M&E | Policy Re-Design | Medium | In Production | 18.09 |  | Fiscal | 3-Normal/Low | 2018-01-19 11:41 | Approved | N/A | C-IV SCR 55552 | Time Limits
SCR | GR Homelessness Account Update FY18-19 | 45 | LRS M&E | Enhancement | Critical | In Production | 18.09 |  | Fiscal |  | 2018-01-31 13:20 | Approved | N/A | LA County Specific | Fiscal
SCR | Training QA of Job Aids Impacted by SCR CA-203249 | 22 | LRS M&E | Enhancement | High | Test Complete | 18.11 |  | Training |  | 2018-08-29 09:20 | Approved | N/A
SCR | Training QA of Job Aids Impacted by SCR CA-53784 | 8 | LRS M&E | Enhancement | High | Test Complete | 18.11 |  | Training |  | 2018-08-16 14:28 | Approved | TBD
SCR | Training Updates - Updates to EBT Card Print List page and Reports (WBTs) | 22 | LRS M&E | Enhancement | Medium | Test Complete | 18.11 |  | Training |  | 2018-06-04 16:32 | Approved | N/A
SCR | Training Support 2017-2018 | 2250 | LRS M&E | Enhancement | Medium | Test Complete | 18.11 |  | Training | Low | 2018-01-19 16:12 | Approved | N/A
SCR | DEATH MATCH File - Change Excel Version to latest version - LA County Only | 130 | LRS M&E | Operational Enhancement | Medium | Test Complete | 18.11 |  | Batch/Interfaces | 3-Normal/Low | 2018-01-19 11:44 | Approved | 54 | LA County Specific | Other
SCR | Strategic Plan - Align active programs with the same primary applicant within the same district under a single Eligibility Worker | 110 | LRS M&E | Data Change | Critical | System Test | TBD |  | Online |  | 2018-03-12 17:44 | Approved | 90 | LA County Specific | Usability
SCR | Update the layout for DPSS Daily eCAPS Postback Report | 160 | LRS M&E | Operational Enhancement | Low | System Test | 18.11 |  | Fiscal |  | 2018-06-26 09:42 | Approved | 32 | CIV-100258 | State/Fiscal Reports
SCR | Update Foster Care/Kin-GAP Income Exemption Logic to Handle Partial Income Exemptions | 170 | LRS M&E | Policy Re-Design | Low | System Test | 18.11 |  | Eligibility |  | 2018-06-15 10:05 | Approved | N/A | CIV-9914 | Foster Care/Kin GAP/AAP
SCR | Rename the Description for 'POI Recoupment' transaction type on Transaction Detail page | 5 | LRS M&E | Enhancement | High | System Test | 18.11 |  | Fiscal |  | 2018-04-24 14:46 | Approved | N/A |  | Collections
SCR | DDCR 3061: Add the 2K Aid Code for IHSS | 20 | LRS M&E | Policy Re-Design | High | System Test | 18.11 |  | CalHEERS |  | 2018-01-28 12:24 | Approved | N/A | CIV-51180 | Medi-Cal/CMSP
SCR | DDCR 3109 and 4029: CW/RCA Income Reporting Threshold (IRT) Tiers | 130 | LRS M&E | Policy Re-Design | Critical | System Test | 18.11 |  | Eligibility |  | 2018-01-26 09:57 | Approved | 90 | CIV-55225 (DDCR 3109) & SCR 1017 (DDCR 4029) | CalWORKs/CalFresh
SCR | DDCR 5057: Update ICT Detail page to navigate to ICT Program Person Detail (C-IV SCR#4479) | 50 | LRS M&E | Enhancement | High | System Test | 18.11 |  | Online | 2-Normal/Medium | 2018-01-25 07:34 | Approved | N/A | CIV-4479 | ICT
SCR | ACL 16-99 - Replace the PA 1725 Attendance/Enrollment Verification (02/05) form with the revised version (5/17) | 50 | LRS M&E | New Policy | Low | System Test | 18.11 |  | Client Correspondence | 3-Normal/Low | 2018-01-19 11:47 | Approved | N/A |  | Correspondence
SCR | ACIN I-01-07-Allow Exceptions to be Added for Tribal TANF and Out of State Months. | 1330 | LRS M&E | Policy Re-Design | High | System Test | 18.11 |  | Fiscal | 3-Normal/Low | 2018-01-19 11:47 | Approved | 0 | CIV-4815 , CIV-101905 | Time Limits
SCR | DDCR 5088: ACL 17-108 - (CalWORKs) Changes To Asset Limits For Families That Include Elderly Or Disabled Household Members | 110 | LRS M&E | New Policy | High | System Test | 18.11 |  | Eligibility | 3-Normal/Low | 2018-01-19 11:44 | Approved | 81 | CIV-11242, CIV-101777 | CalWORKs/CalFresh
SCR | Applicant IEVS abstracts at Redetermination/Recertification. | 275 | LRS M&E | Enhancement | Critical | System Test | 18.11 |  | Batch/Interfaces | 3-Normal/Low | 2018-01-19 11:44 | Approved | N/A | CIV-10394 | IEVS
SCR | ACL No. 17-01 TCVAP Aid Codes R1 and 1V to send Fed/State Only Indicator "S" to WDTIP & TRAC | 385 | LRS M&E | New Policy | Medium | System Test | 18.11 |  | Fiscal | 3-Normal/Low | 2018-01-19 11:44 | Approved | 66 | LA County Specific | Time Limits
SCR | Update CalFresh EDBC Logic to Correctly Evaluate PA Household Indicator | 160 | LRS M&E | Policy Re-Design | High | System Test | 18.11 |  | Eligibility | 3-Normal/Low | 2018-01-19 11:42 | Approved | 79 | CIV-8753 | CalWORKs/CalFresh
SCR | DDCR 3079: Modify Eligibility Status Action Code (ESAC) trigger condition for EW20 transaction | 120 | LRS M&E | Operational Enhancement | Medium | System Test | 18.11 |  | Batch/Interfaces | 3-Normal/Low | 2018-01-19 11:44 | Approved | N/A | CIV-101555 | MEDS
SCR | Combine the WTW 25 and WTW 25A State and Detailed Reports Into One Template Per Report | 180 | LRS M&O | Enhancement | Medium | System Test | 18.11 |  | Reports |  | 2018-06-28 12:50 | Approved | 69 | CIV-100730 | State/Fiscal Reports
SCR | Auto rescission for Medi-Cal programs where RE packet is received after 10-day cutoff | 2145 | LRS M&E | Enhancement | Critical | System Test | 18.11 |  | CalHEERS |  | 2018-05-30 13:23 | Approved | N/A | CIV-101405, CH-125364 | Medi-Cal/CMSP
SCR | AB 480: ACL 18-38 - Generate the NA 823 when manually issuing diaper allowance | 160 | LRS M&E | New Policy | High | System Test | 18.11 |  | Fiscal |  | 2018-06-20 14:13 | Approved | N/A | CIV-101674 | Welfare to Work/WPR
SCR | ACWDL 17-12: Authorized Representative Information | 2355 | LRS M&E | New Policy | High | System Test | 18.11 |  | Online | 3-Normal/Low | 2018-01-19 11:45 | Approved | N/A | CIV-1383 | CalWORKs/CalFresh
SCR | < ITGC > ACL 14-88 - Revise/Create 17 NOAs Messages for Deny, Discontinue, Change, and Partial Approval for Lack of Verification | 875 | LRS M&E | New Policy | Medium | System Test | 18.11 |  | Client Correspondence | 3-Normal/Low | 2018-01-19 11:43 | Approved | N/A |  | Correspondence
SCR | ACWDL 18-13: 2018/2019 Family Member Base Allocation Amount | 50 | LRS M&E | New Policy | High | Development Complete | 18.11 |  | CalHEERS | 3-Normal/Low | 2018-02-14 10:00 | Approved | 84 | C-IV 100481 | Medi-Cal/CMSP
SCR | DDCR 5009: Display Matching Bypass Indicator on MAGI Request and MAGI Person Detail pages | 115 | LRS M&E | Policy Re-Design | Medium | Development Complete | 18.11 |  | CalHEERS |  | 2018-02-05 13:14 | Approved | N/A | CIV-5591, CIV-2713, CIV-4421, CH-10021, CA-44706 | Medi-Cal/CMSP
SCR | Add ON_DELETE triggers for 54 tables | 120 | LRS M&E | Enhancement | Medium | Development Complete | 18.11 |  | DBA |  | 2018-03-06 14:37 | Approved | N/A | C-IV SCR 55284 (from Tracker) and C-IV SCR 2066 (from RTC)
SCR | ACWDL 18-04: 2018 Medicare Savings Program (MSP) Property Limits | 50 | LRS M&E | New Policy | Critical | Development Complete | 18.11 |  | CalHEERS | 3-Normal/Low | 2018-02-14 10:19 | Approved | 86 | CIV-100550 | Medi-Cal/CMSP
SCR | < ITGC > ACL 12-67 - Automation of the 319 â€“ Meeting WPR WtW 24-Month Time Clock Stopper | 725 | LRS M&E | Policy Re-Design | High | Development Complete | 18.11 |  | Fiscal | 3-Normal/Low | 2018-01-19 11:46 | Approved | N/A | C-IV SCR 632 | Welfare to Work/WPR
SCR | CFL 17/18-32E: Update Foster Care (FC) Rate structure for RB-FFA rate level | 215 | LRS M&E | New Policy | Critical | In Development | 18.11 |  | Eligibility |  | 2018-05-10 13:45 | Approved | N/A |  | Foster Care/Kin GAP/AAP
SCR | CFL 17/18-32E: Update Foster Care (FC) Rate structure for RB-FFA rate level - Batch EDBC | 95 | LRS M&E | New Policy | Critical | In Development | 18.11 |  | Eligibility |  | 2018-07-11 15:23 | Approved | TBD |  | Foster Care/Kin GAP/AAP
SCR | Update 2019 Batch Holiday | 100 | LRS M&E | Operational Enhancement | High | In Development | 18.11 |  | Batch/Production Operations |  | 2018-02-15 15:17 | Approved | 70 | CIV-100492 | Usability
SCR | DDCR 4032: Alert user about existing open Journal window while launching Journal | 50 | LRS M&E | Enhancement | High | In Development | 18.11 |  | Tech Arch | 2-Normal/Medium | 2018-01-24 10:15 | Approved | N/A | C-IV RTC-1089 | Usability
SCR | ATS Security Assessment Findings - Group 2 | 331 | LRS M&E | Enhancement | Medium | In Development | 18.11 |  | Tech Arch | 3-Normal/Low | 2018-01-19 11:43 | Approved | N/A
SCR | YBN Security Assessment Findings - Group 1 (Non-compliant authentication, Insufficient input validation (Cross Site Scripting), Server information disclosure & Insecure HTTP methods enabled) | 546 | LRS M&E | Enhancement | High | In Development | 18.11 |  | Tech Arch | 3-Normal/Low | 2018-01-19 11:44 | Approved | n/a
SCR | DPSS/DCFS Support SCR to provide responses to Consortia queries | 1175 | LRS M&E | Data Change | Medium | In Development | 18.11 |  | Batch/Interfaces |  | 2018-09-18 10:53 | Approved | N/A - Support SCR
SCR | Update the EBT Repayment Process | 560 | LRS M&E | Enhancement | Critical | In Development | 18.11 |  | Fiscal | 3-Normal/Low | 2018-01-19 11:44 | Approved | N/A | CIV-101003 | Fiscal
SCR | Your benefits Now (YBN) to add WIC mobile web link to resource panel SIRFRA 3439 | 50 | LRS M&E | Enhancement | High | In Development | 19.01 |  | Online |  | 2018-05-21 16:27 | Approved | N/A | CIV-101320 | C4Yourself
SCR | DDCR 4012: Update information available for print from Journal | 20 | LRS M&E | Enhancement | High | In Development | 19.01 |  | Online | 2-Normal/Medium | 2018-01-24 09:52 | Approved | N/A | CIV-557 | Usability
SCR | ACL 17-53: ESAP Notice Automation | 790 | Premise | New Policy | High | In Development | 19.01 |  | Client Correspondence | 3-Normal/Low | 2018-01-19 11:42 | Approved | 81 | CIV-10181 | Correspondence