## SPG Approved - Design Confirmed
SCR | Summary | Estimate | Funding Source | Change Type (SCR) | SPG Rating | Status | Fix Version/s | Minor Version | Team Responsible | Priority | Created | SPG Status | SPG Score | Other Agency Cross Reference | Committee / WorkGroup
CIV-102460 | ACL 18-75 Phase III - Sub Type Code Automation - Automated Test Scripting | 50 | C-IV M&O | New Policy | Critical | Approved | 19.01 |  | System Test |  | 2018-10-11 11:50 | Approved | N/A - Approved by Dorothy Avila and Karen Rapponotti | CA-205102 | Other
CIV-102505 | Update Job Aid Homeless Assistance - Process and Issue Benefits for SCR 101524 | 5 | C-IV M&O | New Policy | Critical | System Test | 19.01 |  | Training |  | 2018-10-17 16:09 | Approved | TBD
CIV-102543 | Update Job Aid - Customer Option Detail for Diaper Assistance for SCR 100305 | 5 | Premise | New Policy | Critical | System Test | 19.01 |  | Training |  | 2018-10-23 11:26 | Approved | TBD
CIV-101524 | ACL 18-78 - CalWORKs: Implementation of AB 557 Victims of Domestic Abuse and Temporary Homeless Assistance Eligibility | 35 | C-IV M&O | New Policy | Critical | System Test | 19.01 |  | Eligibility |  | 2018-06-14 15:35 | Approved | TBD | CA-202814 | CalWORKs/CalFresh
CIV-10181 | ACL 17-53: ESAP Notice Automation | 650 | Premise | New Policy | High | In Assembly Test | 19.01 |  | Client Correspondence | Medium | 2017-12-29 14:26 | Approved | 81 | CA-56416 | Correspondence
CIV-102471 | Automated Regression Test - Execution and Maintenance - 19.01 Release Cycle | 250 | C-IV M&O | Operational Enhancement | High | Approved | 19.01 | 19.03.XX | System Test |  | 2018-10-12 08:08 | Approved | N/A - Automated Test | CA-205108 | Other
CIV-102087 | Inter County Transfer Address Updates | 55 | C-IV M&O | Operational Enhancement | High | System Test | 19.01 |  | Client Correspondence | Medium | 2018-08-23 09:20 | Approved | 77 | CA-204383 | Correspondence
CIV-101320 | Add WIC Mobile Site Link to C4Yourself | 45 | C-IV M&O | Enhancement | High | System Test | 19.01 |  | Online |  | 2018-05-21 16:26 | Approved | N/A | CA-202731 | C4Yourself
CIV-102341 | Job Aid update for SCR CIV-101905 | 5 | C-IV M&O | Enhancement | High | System Test | 19.01 |  | Training |  | 2018-09-27 09:40 | Approved | N/A
CIV-102274 | Update the Forms Overview in Online Help for SCR CIV-101876 | 5 | C-IV M&O | Enhancement | High | System Test | 19.01 |  | Training |  | 2018-09-19 08:44 | Approved | N/A |  | Correspondence
CIV-102138 | MEDS Alerts for return mail for 1095B mailings from DHCS | 160 | C-IV M&O | New Policy | High | System Test | 19.01 |  | Batch/Interfaces |  | 2018-08-29 09:30 | Approved | TBD | CA-200460 | MEDS
CIV-102136 | Update Online Help for SCR 8219 Removal of 'Generate in Primary Language' Button | 10 | Premise | New Policy | High | System Test | 19.01 |  | Training |  | 2018-08-28 14:47 | Approved | TBD
CIV-102082 | Update Job Aids for SCR 100390 ACL 18-82 - Elect Child Support Payment for Stepsibling or Half-Sibling in Lieu of Cash Aid | 5 | Premise | New Policy | High | System Test | 19.01 |  | Training |  | 2018-08-22 13:10 | Approved | N/A
CIV-100560 | Verify Adobe Reader Cloud (17.011.30105) Compatibility | 75 | C-IV M&O | Operational Enhancement | High | System Test | 19.01 |  | Client Correspondence | High | 2018-02-27 09:39 | Approved | NA | CA-203469