## SPG Approved - Design Confirmed
SCR | Summary | Estimate | Funding Source | Change Type (SCR) | SPG Rating | Status | Fix Version/s | Minor Version | Team Responsible | Priority | Created | SPG Status | SPG Score | Other Agency Cross Reference | Committee / WorkGroup
CA-205943 | Training: Update WBTs per SCR CA-202814 | 14 | LRS M&E | Enhancement | Critical | Test Complete | 19.03 |  | Training |  | 2018-12-10 14:45 | Approved | NA â€“ Training LMS Related SCR |  | Training
CA-205949 | Training: Update WBTs per SCR CA-201692 | 15 | Premise | Enhancement | Critical | System Test | 19.03 |  | Training |  | 2018-12-10 16:00 | Approved | NA â€“ Training LMS Related SCR | CH-92298 | Training
CA-200976 | MEDS: Make the Citizenship Indicator required / (CIV-100064) | 720 | LRS M&E | New Policy | Critical | System Test | 19.03 |  | Batch/Interfaces |  | 2018-02-21 09:54 | Approved | N/A | CIV-100064 | MEDS
CA-205795 | ACL 18-90: Add ability to differentiate SSI and SSP Payments on the Other Program Assistance page | 196 | Premise | New Policy | Critical | System Test | 19.03 |  | Online |  | 2018-11-29 17:01 | Approved | 85 | CIV-102860 | CalWORKs/CalFresh
CA-201379 | Strategic Plan - Align active programs with the same primary applicant within the same district under a single Eligibility Worker | 110 | LRS M&E | Data Change | Critical | Development Complete | 19.03 |  | Online |  | 2018-03-12 17:44 | Approved | 90 |  | Usability
CA-205102 | ACL 18-75 Phase III - Sub Type Code Automation - Automated Test Scripting | 70 | LRS M&E | New Policy | Critical | In Development | 19.03 | 19.02.XX | System Test |  | 2018-10-11 11:50 | Approved | N/A - Approved by Dorothy Avila and Karen Rapponotti | CIV-102460 | Other
CA-205976 | Training QA of Job Aids Impacted by SCR CA-205795 | 5 | Premise | Enhancement | Critical | Approved | 19.03 |  | Training |  | 2018-12-11 13:17 | Approved | 85 | CIV-102860 | Training
CA-200265 | DDCR 4028: Enhance Auditing framework to capture link text clicked by the user | 52 | LRS M&E | Enhancement | High | Test Complete | 19.03 |  | Tech Arch | 2-Normal/Medium | 2018-01-24 10:09 | Approved | N/A | C-IV CCM-1013 | Other
CA-205060 | Reports Modifications - Phase III Long Term Funding for Emergency Caregiver | 285 | LRS M&E | New Policy | High | Test Complete | 19.03 |  | Reports |  | 2018-10-09 12:11 | Approved | 53 | CIV-102435 | Foster Care/Kin GAP/AAP Management Reports
CA-51444 | IEVS Security Access | 110 | LRS M&E | Enhancement | High | Test Complete | 19.03 |  | Online | 3-Normal/Low | 2018-01-19 11:43 | Approved | N/A |  | IEVS
CA-200949 | Enable field level auditing for Person Search, Journal, Tasks and Reminders | 80 | LRS M&E | Enhancement | High | Test Complete | 19.03 |  | Tech Arch | 2-Normal/Medium | 2018-02-19 16:22 | Approved | N/A | C-IV Tracker-56151 | Other
CA-200950 | Enhance auditing framework to record old and new values of modified fields and user actions | 40 | LRS M&E | Enhancement | High | Test Complete | 19.03 |  | Tech Arch | 2-Normal/Medium | 2018-02-19 16:28 | Approved | N/A | C-IV Tracker-46040 | Other
CA-205941 | Training: Update WBTs per SCR CA-202349 | 18 | LRS M&E | Enhancement | High | System Test | 19.03 |  | Training |  | 2018-12-10 14:36 | Approved | NA â€“ Training LMS Related SCR |  | Training
CA-202392 | Update Disaster CalFresh Application and Reporting | 805 | LRS M&E | Enhancement | High | System Test | 19.03 |  | Online |  | 2018-04-27 16:36 | Approved | N/A | CIV-100253 | C4Yourself CalWORKs Fiscal State/Fiscal Reports
CA-203722 | Display prior Change Reason Information in View Mode | 1655 | LRS M&E | Enhancement | High | System Test | 19.03 |  | Online |  | 2018-07-25 14:39 | Approved | N/A - Approved By Dorothy Avila and Michelle Peterson 7/26/2018 | CIV-100195 | CalWORKs/CalFresh
CA-206079 | Automated Regression Test - Execution and Maintenance - 19.03 Release Cycle | 280 | LRS M&E | Operational Enhancement | High | In Development | 19.03 | 19.05.XX | System Test |  | 2018-12-18 08:00 | Approved | N/A - Automated Test | CIV-103006 | Other
CA-205940 | Training: Update WBTs per SCR CA-200785 | 26 | Premise | New Policy | High | Approved | 19.03 |  | Training |  | 2018-12-10 14:28 | Approved | NA â€“ Training LMS Related SCR | CIV-100390 | Training
CA-205946 | Training: Update WBTs per SCR CA-201310 | 100 | Premise | Enhancement | High | Approved | 19.03 |  | Training |  | 2018-12-10 15:46 | Approved | NA â€“ Training LMS Related SCR | CH-92295; CH-121151 | Training
CA-205948 | Training: Update WBTs per SCR CA-200852 | 25 | Premise | Enhancement | High | Approved | 19.03 |  | Training |  | 2018-12-10 15:55 | Approved | NA â€“ Training LMS Related SCR | CH-109927 | Training
CA-205627 | Training QA of Job Aids Impacted by SCR CA-202749 | 2 | LRS M&E | Enhancement | High | Approved | 19.03 |  | Training |  | 2018-11-15 15:04 | Approved | N/A |  | Training