## South - CCB Approved
No. | SCR | Summary | Change Type (SCR) | Priority | Status | Release | Minor Version | Other Agency Cross Reference | Committee / WorkGroup
1 | CA-209290 | Mobile App Issue Due to iOS 13 Release in Fall 2019 | Operational Enhancement | High | New | RWR
2 | CA-209661 | Update Previous Potential Benefit Calculation Logic | Enhancement | High | New | TBD |  | CIV-104671 | Collections, State/Fiscal Reports
3 | CA-206317 | ACL 19-70 Foster Care, Kin-GAP COLA Rate Increase for Year 2019 - Batch EDBC | New Policy | High | System Test | 19.07 | 19.09.07 | CIV-103141 | Foster Care/Kin GAP/AAP
4 | CA-206229 | ACL 19-73: CalWORKs MAP Increase COLA ; ACL 19-85 - CW IRT Increase; ACIN I-54-19 - FFY 2020 CalFresh COLA; Effective 10/2019- Run Batch EDBC | New Policy | Critical | System Test | 19.07 | 19.09.14 | CIV-103090 | CalWORKs/CalFresh
5 | CA-208931 | ACL 19-58 AAP COLA Rate Increase for Year 2019 - Batch EDBC | New Policy | High | System Test | 19.07 | 19.09.07 |  | Foster Care/Kin GAP/AAP
6 | CA-208817 | App Server storage issues, change temp file storage location | Operational Enhancement |  | In Development | 19.07 | 19.XX.XX |  | Tech
7 | CA-206310 | ACL 19-70 Foster Care and Kin-GAP COLA Rate Increase for Year 2019 | New Policy | High | System Test | 19.07 | 19.09.07 | CIV-100485 | Foster Care/Kin GAP/AAP
8 | CA-208921 | ACL 19-58 Adoptions Assistance Program (AAP) COLA Rate Increase for Year 2019 | New Policy | High | System Test | 19.07 | 19.09.07 |  | Foster Care/Kin GAP/AAP
9 | CA-208385 | Transition CalACES.org to CalSAWS.org - New website and content | Enhancement |  | Pending Approval | 19.07 | 19.08.26
10 | CA-208339 | Update SNB NOA for the "No CF" closure reason and Requested Discontinuance Regulations | Policy Re-Design | Critical | Test Complete | 19.09 |  | CIV-104075 | Correspondence
11 | CA-208241 | CalHEERS eHIT: One-time Batches to Transition Young Adults from Restricted to Full Scope Medi-Cal | Enhancement | High | In Development | 19.09 | 19.11.22 | CIV-104022; CH-139211 | Medi-Cal/CMSP
12 | CA-207587 | CalHEERS eHIT: Update Aid Code Descriptions for New CA Subsidy to 600% FPL (CH-137942) | Enhancement | Medium | System Test | 19.09 |  | CIV-103711; CH-137942 | Medi-Cal/CMSP
13 | CA-207581 | CalHEERS eHIT: Update Interface Schema to version 13 (CH-139410) | Enhancement | High | System Test | 19.09 | 19.09.CH | CIV-103707; CH-139410 | Medi-Cal/CMSP
14 | CA-207515 | CalHEERS eHIT: Add 'Covered CA Change' to MAGI Referral (CH-136022) | Enhancement | Medium | System Test | 19.09 | 19.09.CH | CIV-103652; CH-136022 | Medi-Cal/CMSP
15 | CA-206941 | CalHEERS eHIT: Medi-Cal Eligibility Rules Update for Young Adult Expansion (CH-139211) | New Policy | High | System Test | 19.09 |  | CIV-103662; CH-139211 | Medi-Cal/CMSP
16 | CA-206854 | Add and Update Staff Classification Titles | Enhancement | Medium | Test Complete | 19.09 |  | CIV-8470 | Usability
17 | CA-209162 | SB 1341 Phase 1 & 2 - Maintenance | Operational Enhancement |  | New | 19.09
18 | CA-208834 | Changes due to New Refugee Employment and Acculturation Services (REAS) Contract implementation effective November 1, 2019. | Policy Re-Design | Medium | In Development | 19.09 | 19.10.31 | N/A | Welfare to Work/WPR
19 | CA-208681 | Add a Journal Entry once the Recovery Account status is updated to Terminated | Enhancement | High | System Test | 19.09 |  | CIV-102218 | Collections
20 | CA-208525 | County Ad-Hoc database - Technical Support - August and September 2019 | Operational Enhancement | Medium | System Test | 19.09 |  |  | Tech
21 | CA-208526 | Automated Regression Test - Transaction Backlog - Phase 1 | Operational Enhancement | Medium | In Development | 19.09 |  |  | Other
22 | CA-200844 | 2019 Medicare Savings Program (MSP) Property Limits | New Policy | Critical | Test Complete | 19.09 |  | CIV-100484 | Medi-Cal/CMSP
23 | CA-202477 | Implement Application for Monitoring Performance (AMP) Phase VI | Enhancement | Medium | System Test | 19.09 | 19.10.13 | CIV-101173 | Tech
24 | CA-203039 | YourBenefitsNow (YBN): Update SAR7 Threshold Language Questions to match form in LRS | Enhancement | Medium | Test Complete | 19.09 |  |  | C4Yourself
25 | CA-52394 | Modify Outbound Call Inbound Result File Processing Program to recognize new result code value '00'. | Enhancement | Medium | Test Complete | 19.09 |  | N/A | IVR & Contact Center
26 | CA-50982 | Link PVS, NHR, IFDS, IEVS Applicant tasks to automatically close when the report is completed by the Worker | Enhancement | High | System Test | 19.09 |  | CIV-102097 | IEVS
27 | CA-52237 | Child Welfare Programs: Provide Work Order Monthly Reports via Oracle Business Intelligence | Enhancement | Low | System Test | 19.09 |  |  | Management Reports
28 | CA-202724 | ACWDL 19-03: NOA Requirements at Annual RE and Change of Circumstances | New Policy | High | System Test | 19.09 |  | CIV-100708 | Correspondence
29 | CA-209109 | Add Full/Restricted Scope verbiage for Young Adult Expansion MAGI NOAs(CH-139211) | New Policy | High | In Development | 19.09 | 19.11.14 | CIV-104415; CH-139211 | Correspondence, Medi-Cal/CMSP
30 | CA-57971 | DDCR 5012 / ACL 18-08 and ACL 18-94 ABAWD - Phase II | New Policy | Critical | System Test | 19.09 |  | CIV-7215, CIV-7486 | CalWORKs/CalFresh
31 | CA-210134 | Redeliver: EDMS: LRS update - Image and View Image button URL security updates. | Operational Enhancement | Critical | Approved | 19.09 |  |  | Imaging
32 | CA-208374 | CFL 18/19-79 Update Electronic Theft replacement and reporting | New Policy | High | In Development | 19.11 |  | CIV-104094 | Fiscal, State/Fiscal Reports
33 | CA-205319 | ACL 18-107, ACL 18-108 - SNB/TNB Forms and Notices - Threshold Languages Phase 1 | New Policy | Critical | In Development | 19.11 |  | CIV-102560 | Correspondence, Medi-Cal/CMSP
34 | CA-204599 | ABAWD: Update MEDS Transactions for the 36-month rollover process | New Policy | Critical | In Development | 19.11 |  | CIV-102209 | MEDS
35 | CA-204420 | SAR 7 Texting Campaign | Enhancement | Critical | In Development | 19.11 |  | N/A | IVR & Contact Center
36 | CA-203981 | Add/Update Non-MAGI Screening Packets | New Policy | High | In Development | 19.11 |  | CIV-10668, CIV-101876, CIV-102151 | Correspondence
37 | CA-209540 | County Ad-Hoc database - Technical Support - October and November 2019 | Operational Enhancement | Medium | Approved | 19.11 |  |  | Tech
38 | CA-209407 | Update Issuance Thresholds for 2020 (CRFI 19-026) | Enhancement | Medium | In Development | 19.11 |  | CIV-104577 | Fiscal
39 | CA-209151 | Enforce Data Integrity during Accept EDBC | Enhancement | Medium | In Development | 19.11 |  |  | Medi-Cal/CMSP
40 | CA-208840 | Automated Regression Test - Transaction Backlog - Phase 2 | Operational Enhancement | Medium | Approved | 19.11 |  |  | Other
41 | CA-208841 | Automated Regression Test - Transaction Backlog - Phase 3 | Operational Enhancement | Medium | Approved | 19.11 |  |  | Other
42 | CA-208685 | ACL 19-50 - Increase Threshold For CalFresh Overissuances | New Policy | High | Committee Review | 19.11 |  | CIV-104217 | Collections, State/Fiscal Reports
43 | CA-201021 | DDCR:Update Targeted Low-Income search page to default 'Type' and 'Status' fields to â€œBlankâ€ | Enhancement | Low | In Development | 19.11 |  | Tracker-54924 | Medi-Cal/CMSP
44 | CA-200547 | YBN MC Renewal Process MC604 IPS Packet & Mixed HH RE Packet in all Threshold Language Phase IV | Enhancement | High | In Development | 19.11 |  |  | C4Yourself
45 | CA-201641 | Refactor CT73 for NOA Generation | Enhancement | High | In Development | 19.11 |  |  | Correspondence
46 | CA-202330 | Stop benefit offsets on CalFresh Administrative Error Recovery Accounts | Policy Re-Design | Critical | In Development | 19.11 |  | CIV-104159 | Collections
47 | CA-51971 | Modify the GR Termination Date When LRS/MEDS Interface Updates the SSl/SSP Approval Information | Enhancement | Medium | In Development | 19.11 |  |  | GA/GR
48 | CA-51457 | ACL 17-05 & 18-27 CalFresh Student Eligibility | New Policy | Critical | In Development | 19.11 |  | CIV-8054 | CalWORKs/CalFresh
49 | CA-53457 | ACL 17-30 CalFresh Eligibility for Victims of Domestic Violence | New Policy | High | In Development | 19.11 |  | CIV-8775 | CalWORKs/CalFresh
50 | CA-50808 | Child Welfare Program: BI: Vendor Dashboard report | Enhancement | Medium | In Development | 19.11 |  |  | Management Reports
51 | CA-49736 | Clean-up of MC Program Block for Individuals Active on CW | Enhancement | Critical | In Development | 19.11 |  | CIV-102308 | Medi-Cal/CMSP
52 | CA-56680 | SB 1341 All County Solution Phase 1 - Separate MSP NOAs | Enhancement | Medium | In Development | 19.11 |  |  | Correspondence, Medi-Cal/CMSP
53 | CA-58588 | ACL 18-121 Changes to Income and Eligibility Verification System (IEVS) Management Report (DPA 482) | New Policy | High | In Development | 19.11 |  | CIV-12021 | State/Fiscal Reports
54 | CA-52219 | Supervisor's Approval for Refunds | Enhancement | High | In Development | 19.11 |  |  | Collections
55 | CA-205441 | Add Need Category of Family Stabilization to Needs Detail page | Enhancement | High | Design in Progress | 20.01 |  | CIV-10075 | Fiscal
56 | CA-206994 | CalHEERS eHIT: Add Spousal Support Agreement/Modification Date | Enhancement | Medium | Approved | 20.02 |  | CH-138728; CIV-103599 | Medi-Cal/CMSP

## South - SPG Approved
No. | SCR | Summary | Change Type (SCR) | SPG Priority | Status | Other Agency Cross Reference | Committee / WorkGroup
1 | CA-207950 | CalHEERS eHIT: Young Adult Expansion â€“ Age Reevaluation Updates | Enhancement | High | Committee Review | CIV-103874; CH-139211 | Medi-Cal/CMSP
2 | CA-207080 | Eliminate EDD Registration Requirements for General Relief Program | Enhancement | High | Design in Progress |  | GA/GR
3 | CA-205652 | Change Recovery Account Cause Code editing logic | Enhancement | High | Design in Progress | CIV-9947 | Collections
4 | CA-205642 | CalHEERS eHIT: BREfS Phase C, Part 2 Override Eligibility Determination Functionality | Enhancement | High | Design in Progress | CIV-102761, CH-109747 | Medi-Cal/CMSP
5 | CA-205512 | Update Office Location on system generated Benefit Reductions and Offset Transactions | Enhancement | High | Committee Review | CIV-101423 | Collections
6 | CA-205499 | Update Name Drop Down on Deemed Eligibility List Page to Update Age Restriction | Enhancement | High | Design in Progress | CIV-102654 | Medi-Cal/CMSP
7 | CA-204952 | CalHEERS eHIT: Add Medi-Cal Deemed Infant and Medi-Cal Access Infant Program Functionality | Enhancement | High | New | CH-122183, CIV-102360 | Medi-Cal/CMSP
8 | CA-204823 | Time Limit Months for Immediate Need program | Enhancement | Critical | New | CIV-8583 | CalWORKs/CalFresh
9 | CA-204582 | Add Edit Functionality to a Service Arrangement (42700) | Enhancement | Critical | Design in Progress | CIV-391 | Welfare to Work/WPR
10 | CA-204553 | CalWORKs/RCA Adults by Welfare-to-Work Category Report | Enhancement | High | New |  | Management Reports
11 | CA-204497 | SB 1341 All County Solution Phase 3 - Updates to the mixed Non-MAGI/MAGI NOAs to allow for mixed actions | Enhancement | Medium | Design in Progress |  | Correspondence, Medi-Cal/CMSP
12 | CA-204499 | SB 1341 All County Solution Phase 5 - Mixed Non-MAGI/MAGI Text updates and update to Skip Report | Enhancement | Medium | New |  | Correspondence, Medi-Cal/CMSP
13 | CA-204496 | SB 1341 All County Solution Phase 2 - Updates to the flow of mixed Non-MAGI/MAGI NOAs | Enhancement | Medium | Design in Progress |  | Correspondence, Medi-Cal/CMSP
14 | CA-204494 | SB 1341 All County Solution Phase 4 - Letter Format Mixed Non-MAGI/MAGI NOAs | Enhancement | Medium | New |  | Correspondence, Medi-Cal/CMSP
15 | CA-204326 | Transitional CalFresh Eligibility Updates | Enhancement | Medium | Pending Approval | CIV-102404 | CalWORKs/CalFresh
16 | CA-206805 | Add Family Size 11 and 12 to FPL Code Table | Enhancement | Medium | New | CIV-103498 | Medi-Cal/CMSP
17 | CA-206692 | Update YBN url for Text and Email Campaigns | Enhancement | High | New |  | IVR & Contact Center
18 | CA-206598 | Your Benefits Now Online Medi-Cal Renewal Process form MC 262LTC in all Threshold Language | Enhancement | High | New |  | C4Yourself
19 | CA-206602 | Your Benefits Now Online Medi-Cal Renewal Process form MC14A MSP in all Threshold Language | Enhancement | High | New |  | C4Yourself
20 | CA-206561 | Modify Color Range on Performance Measures Dashboards | Enhancement | Low | New |  | Management Reports
21 | CA-206520 | Automate SAWS 30 - IEVS Employment and Income Verification Form | Enhancement | High | Ready for Committee | CIV-103772 | IEVS
22 | CA-206394 | Add Threshold for MC RE/Restore Notice | Enhancement | Medium | Design in Progress |  | Correspondence
23 | CA-204030 | CalHEERS eHIT: IAP Transition Enhancement | Enhancement | Medium | Design in Progress | CIV-101980; CH-124914 | Medi-Cal/CMSP
24 | CA-203824 | Add functionality to manage Conditionally Eligible status in MAGI determinations | Enhancement | High | Design in Progress | CIV-11725 | Medi-Cal/CMSP
25 | CA-203757 | SSP 14 to prepopulate County IA Agency name | Enhancement | Medium | New |  | Correspondence
26 | CA-210148 | Update income mapping to CalHEERS for 'Educational, Student' income category | Enhancement | High | Design in Progress | CIV-104902 | Medi-Cal/CMSP
27 | CA-209638 | Add Threshold Languages for FC/KG CNI NOA Fragment | Enhancement | High | Design in Progress | CIV-104665 | Correspondence
28 | CA-209381 | Add new Negative Action Reasons for Medi-Cal to close the program bypassing the MAGI process. | Enhancement | Medium | Design in Progress | CIV-5165 | Medi-Cal/CMSP
29 | CA-209221 | Add State PINs to Integrated Service Payment / Valuable Detail Claiming Report | Enhancement | Medium | Design in Progress | CIV-102606, CIV-104015, CA-208814 | State/Fiscal Reports
30 | CA-209076 | Enhance Refused Verification functionality to send failed Admin Verif | Enhancement | Medium | Committee Review | CIV-104268 | Medi-Cal/CMSP
31 | CA-209050 | Add MC Annual Renewal NOA Variable Threshold Population | Enhancement | High | Design in Progress |  | Correspondence
32 | CA-208888 | New data elements to be added to the eICT Outbound file to indicate CalFresh SSI/SSP Reversal. | Enhancement | Critical | Design in Progress | CIV-104322 | ICT
33 | CA-208863 | CalHEERS eHIT: Married Filing Jointly and Out-of-State Residence Address | Enhancement | High | Design in Progress | CIV-1068; CH-142899 | Medi-Cal/CMSP
34 | CA-208864 | CalHEERS eHIT: Income Data Quality Enhancements Phase III | Enhancement | Critical | Design in Progress | CIV-104299; CH- | Medi-Cal/CMSP
35 | CA-200895 | Update the Rescind Logic to accommodate for overlapping rescinded periods | Enhancement | Medium | New | C-IV 450, C-IV 331 | CalWORKs/CalFresh
36 | CA-58455 | Data Change Request - Void Pending Approval Recovery Accounts | Enhancement | High | New |  | Fiscal
37 | CA-201656 | OBIEE: Caseload Inventory Report Program Persons | Enhancement | High | New | CIV-675 | Management Reports
38 | CA-201569 | Place Holder SCR to update the Imprest Cash functionality in Issued Valuable Inventory Report | Enhancement | High | New | CIV-11257 | State/Fiscal Reports
39 | CA-201250 | YBN External Mobile App - add Analytics | Enhancement | Medium | New |  | Tech
40 | CA-50782 | Enhance the Initial Search Screen of the Audit Tool | Enhancement | High | Design in Progress | Specific to LRS
41 | CA-202482 | Update 206-Cal-Learn Time Limit Exemption to apply to WTW time clock | Enhancement | High | New | CIV-101174 | Time Limits
42 | CA-202177 | Modifications to the Medi-Cal Renewal E-Hit Dashboard and DPSS Performance Measure Dashboard - Medi-Cal Renewals | Enhancement | High | New |  | Management Reports
43 | CA-202110 | WTW 25/25A State Reports - Modifications | Enhancement | Critical | New | CIV-102056 | State/Fiscal Reports
44 | CA-201742 | CF 296 - Changes in logic for Line 10 - Overdue Recertifications (CWD Caused) during the month. | Enhancement | High | New | CIV-100845 | State/Fiscal Reports
45 | CA-201709 | Updates to Change Reason Mid-period addition of Individual | Enhancement | High | New |  | CalWORKs/CalFresh
46 | CA-202920 | Strategic Plan -Case Alignment Phase III- All Active Eligibility Programs (GR/CF/MC) with multiple program blocks in all districts will be aligned under a single worker | Enhancement | High | New |  | Usability
47 | CA-203485 | Update to LRS database for intake applications source/program history | Enhancement | Low | New |  | Usability
48 | CA-203421 | Your Benefits Now (YBN) SAWS II Plus/GR SAWS II plus/CW RD form(also the SAWS II Plus) to remove all default mapping. | Enhancement | Medium | New |  | C4Yourself, Tech
49 | CA-55591 | Add table ORG_DETL to outbound DCFS extracts | Enhancement | Low | New | LA County Specific | Foster Care/Kin GAP/AAP
50 | CA-53607 | Add Form Trigger Reasons for the CL 3 and CL 4 / NA 290 - Cal-Learn and replace TEMP CL1 Spanish with CL1 Spanish | Enhancement | High | Design in Progress
51 | CA-52756 | Modify duplicate payment logic | Enhancement | High | New |  | Foster Care/Kin GAP/AAP
52 | CA-54164 | Update Sanctions Dashboard Reports/Data in DPSSTATS Data Warehouse Homepage | Enhancement | Medium | New |  | Management Reports
53 | CA-49842 | Change all outbound calls data file format to accommodate participant appointment date/time. | Enhancement | Medium | Committee Review | IVR-LA County Specific | IVR & Contact Center
54 | CA-53326 | Add process for all WebService Interfaces to queue up when partner's system is down, for both scheduled and unscheduled downtime. | Enhancement | High | New |  | C4Yourself, ICT, Imaging
55 | CA-52880 | Additions to Person, Vendor, Invoice Search Criteria; Modifications on the Money Management Resource Detail Page and On the on the Select Service and Provider Page | Enhancement | Medium | Design in Progress | LA County request for GA/GR program | Fiscal
56 | CA-55693 | Create an additional CalHEERs column for the Medi-Cal Pending Applications Report in Business Intelligence/DPSSTATS | Enhancement | High | New | CIV-100785 | Management Reports
57 | CA-55962 | MEDS: Add new logic to MEDS transaction AP18 to send the System Date for any future Application Date | Enhancement | Medium | Design in Progress |  | MEDS
58 | CA-54848 | Phase III- Change CalFresh NOAs add ineligible person names in Term NOAs, Add TCF NOA for Fleeing Felon | Enhancement | High | New | LA County Specific-Transitional CF fleeing felon NOA already exist in CIV
59 | CA-47600 | Update CA1037 State report Revise line 8a logic | Enhancement | High | New | CIV-10060 | State/Fiscal Reports
60 | CA-51884 | Reports - Resource Data Bank - Service Providers with a Status of Close or an end date within the next 6 months. | Enhancement | Medium | New |  | RDB
61 | CA-54527 | Modify the File Layout of TTC Collection Data for the Weekly Mass Upload and Reports and Modify the File Layout of TTC Data Forwarded to the Accounts Receivable System | Enhancement | Low | New | LA County Specific | Tax Intercept
62 | CA-57647 | Monthly CalFresh New Applications District Office, Your Benefits Now (YBN) and Customer Service Center | Enhancement | High | New |  | Management Reports
63 | CA-51876 | LRS Ancillary Pages: Modify the LRS Service Arrangement Detail Page, Service Type Description box to allow for the itemization of ancillary items requested under the Ancillary-Education category, instead of the current text box. | Enhancement | Medium | New |  | Welfare to Work/WPR
64 | CA-50780 | Additional Detail for Audit Application Report | Enhancement | High | Ready for Committee | Specific to LRS
65 | CA-48755 | Child care Task Assignment Addendum | Enhancement | High | New |  | Child Care
66 | CA-51448 | Add Time Tracking Report to CalACES Audit Application | Enhancement | High | Design in Progress |  | Tech
67 | CA-50800 | CalWORKs Denial NOA - correct the 30-day date inserted on the NOA | Enhancement | High | Design in Progress |  | Correspondence
68 | CA-53786 | WTW 24 MTC - Update WTW 24 MTC from Verified Actual Hours (Priority 10) | Enhancement | Critical | New | CIV-102291
69 | CA-50091 | SB 1147 - Juvenile Probation Interface | Enhancement | Low | New | LA County Specific | Medi-Cal/CMSP
70 | CA-48412 | IHSS IPW Referrals/Auto Generate MEDI-CAL Application | Enhancement | Medium | Design in Progress |  | Medi-Cal/CMSP
71 | CA-49841 | Automate Medi-Cal Discontinuance for Individual turning age 65 for failure to return MC 604 IPS | Enhancement | High | New | CIV-11988 | Correspondence, Medi-Cal/CMSP
72 | CA-51726 | Modifications to Benefit Recovery Management Report | Enhancement | Medium | New |  | State/Fiscal Reports
73 | CA-52597 | CA 812 Collections Enhancement Report | Enhancement | High | Design in Progress | CIV-12446 | Collections, State/Fiscal Reports
74 | CA-52073 | < ITGC > DCFS: Modify CCSAS file layout to send ARC referral to child support for a $50 disregard | Enhancement | Medium | Design in Progress | LA County Specific | Foster Care/Kin GAP/AAP
75 | CA-55208 | Changes to the Child Care Requests page | Enhancement | High | New |  | Child Care
76 | CA-55206 | Redesign FC Facility Ratios page ? Need to store historical ratio info based on the eff. date for Group Home and Foster Family Agency type | Enhancement | High | New | CIV-102423 | RDB
77 | CA-49410 | Allow Users to Authorize Multiple Transportation Types for Overlapping Periods | Enhancement | Medium | Design in Progress | CA-50300 | Welfare to Work/WPR
78 | CA-49308 | DCFS: Create a task when child goes from AAP to FC | Enhancement | Medium | Design in Progress |  | Foster Care/Kin GAP/AAP, Task Management
79 | CA-53787 | WTW 24 MTC - Update Tracking of Voc Ed (Priority 11) | Enhancement | Critical | New
80 | CA-48348 | Extension of Time-Period for Dropping the Worker on Discontinued Eligibility Programs | Enhancement | Critical | Design in Progress |  | CalWORKs/CalFresh
81 | CA-52751 | Create a daily outbound file for Families and Children's Index (FCI) | Enhancement | Medium | Design in Progress |  | CalWORKs/CalFresh, Medi-Cal/CMSP
82 | CA-52872 | Jail Match Interface for All Programs | Enhancement | Medium | Design in Progress | LA County Specific | Other
83 | CA-57044 | Add IHSS income to the IFDS (IFD115) Quarterly Outbound file, (C-IV SIR #9156) | Enhancement | Medium | Design in Progress | CIV-9156 | IEVS
84 | CA-50543 | IEVS Criminal Assignment and processing | Enhancement | High | Design in Progress | CIV-102716 | IEVS
85 | CA-47915 | DCFS: Send Medi-Cal to MEDS for AAP with $0 Authorized Amount 01/14/16 AA - Priority confirmed by RE | Enhancement | Medium | New |  | MEDS
86 | CA-58124 | LRS Dashboard Applications Report to include (CBO) Agency code for each DPSS program | Enhancement | Medium | New | CIV-100782 | Management Reports
87 | CA-56515 | Stop Benefit Reductions/Offsets on Zero or Negative Recovery Accounts | Enhancement | High | New |  | CalWORKs/CalFresh, Collections
88 | CA-49633 | < ITGC > CF 387 CalFresh Request for Information for Residency | Enhancement | High | Ready for Committee | CIV-101447 | CalWORKs/CalFresh, Correspondence
89 | CA-55143 | Phase III - Modify and Add Validations to run EDBC for the Correct RE/SAR/QR Submit Month | Enhancement | High | Design in Progress | CIV-702 | CalWORKs/CalFresh
90 | CA-56693 | DCFS - Enhance the MEDS Journal Detail Exception Report | Enhancement | Medium | New | LA County Specific | Management Reports
91 | CA-54520 | CIV-100748 CalFresh Churn Trends Report for District Offices | Enhancement | High | New | CIV-100748 | Management Reports
92 | CA-53789 | Update Expedited Service Determination, Pending Verification and Batch Discontinuance Process | Enhancement | High | Design in Progress | CIV-101159 | CalWORKs/CalFresh
93 | CA-57104 | GR Self-Employment Expense Calculations | Enhancement | Medium | Design in Progress |  | GA/GR
94 | CA-58006 | LRS mapping for domestic abuse/child abuse to LRS case from eapp screen. | Enhancement | Medium | New | LA County Specific | C4Yourself, Usability
95 | CA-53456 | DCFS: LRS to accommodate various licensing statuses per license number, instead of per vendor number. | Enhancement | High | New | CIV-102416 | RDB
96 | CA-58963 | Revisions to the Medicare Savings Programs (MSP) Notices of Action (NOAs) 1 of 1 | Enhancement | High | New |  | Correspondence
97 | CA-58777 | Create BI Dashboard that identifies entry source for SAR 7, QR-7, Recertification/Redetermination/Renewal/Reevaluation (RC/RD/RN/RE) | Enhancement | Medium | New | CIV-100783 | Management Reports
98 | CA-208925 | SAR7 - Text to Opt out of Text Messages | Enhancement | Medium | New |  | IVR & Contact Center
99 | CA-57452 | ACWDL 17-32 - NOA Requirements for Failure to Respond - Compliance with Settlement of Korean Community Center of the East Bay | Enhancement | High | Design in Progress | CIV-10892 | Correspondence
100 | CA-55200 | Update WEX/CS WorkSheet Detail Page | Enhancement | Medium | Design in Progress | CIV-533 | Welfare to Work/WPR
101 | CA-51491 | Modify LRS Functionality to Not Require Adding a Homeless Temp or Homeless Perm Program When Processing Supplemental Housing Assistance Programs. | Enhancement | High | New |  | CalWORKs/CalFresh
102 | CA-208268 | ACL 18-107, ACL 18-108 - SNB/TNB Forms and Notices - Threshold Languages Phase 4 | New Policy | Critical | Committee Review | CIV-104043 | Correspondence
103 | CA-208261 | ACL 18-107, ACL 18-108 - SNB/TNB Forms and Notices - Threshold Languages Phase 3 | New Policy | Critical | Committee Review | CIV-104040 | Correspondence
104 | CA-208258 | ACL 18-107, ACL 18-108 - SNB/TNB Forms and Notices - Threshold Languages Phase 2 | New Policy | Critical | Pending Approval | CIV-104036 | Correspondence
105 | CA-208203 | ACL 19-31 Re-Entry into Extended Foster Care for Youth Receiving SSI | New Policy | High | New | CIV-104019 | Foster Care/Kin GAP/AAP
106 | CA-208191 | ACWDL 17-12: Changes to the Designation and Responsibilities of the Medi-Cal Authorized Representative | New Policy | High | New | CIV-8633 | Medi-Cal/CMSP
107 | CA-208184 | ACL 19-34 Update Kin-GAP Beginning Date of Aid Rules to Accept Mid-Month Application Date | New Policy | High | Design in Progress | CIV 104011 | Foster Care/Kin GAP/AAP
108 | CA-205633 | ACL 18-75 Phase IV-Long Term Funding for Emergency Caregivers with Placements Prior to RFA Approval | New Policy | Critical | Design in Progress | CIV-102757 | Foster Care/Kin GAP/AAP
109 | CA-205328 | ACL 18-92, ACL 18-107 Transitional Nutrition Benefit Program Recertification | New Policy | Critical | Design in Progress | CIV-102568 | CalWORKs/CalFresh
110 | CA-205286 | Update the MEDS Alerts ZZZ Reports to include Alert 9068 | New Policy | High | Design in Progress
111 | CA-204863 | ACL 18-99 CF OI Collection Period | New Policy | Critical | New | CIV-102263 | Collections
112 | CA-204858 | ACWDL CalFresh Employment & Training (E&T) Compliance with New Federal Reporting Requirements | New Policy | High | Design in Progress | CIV-10156 | State/Fiscal Reports
113 | CA-204417 | ACL 07-16 Direct Certification (DC) for a New Local Education Agency (LEA) Snowline Joint Unified School District | New Policy | High | New |  | CalWORKs/CalFresh
114 | CA-206223 | ACIN I-XX-19 - 2020 State Minimum Wage | New Policy | Medium | Ready for Committee | CIV-103087 | CalWORKs/CalFresh
115 | CA-206080 | ACL 18-141 CF REVISED SUPPLEMENTAL FORM FOR EXCESS MEDICAL DEDUCTIONS (CF 31) | New Policy | High | New | CIV-103015 | Correspondence
116 | CA-205913 | Add 5L Aid Code for FC Emergency Assistance EC Ineligible Cases | New Policy | High | Design in Progress | CIV-102912 | Foster Care/Kin GAP/AAP
117 | CA-203671 | ACWDL 18-17 and 17-25: Add MC 604 MDV Doctorâ€™s Verification to Template Repository | New Policy | High | New | CIV-101796 | Correspondence
118 | CA-209721 | Add NOAs and Forms for Electronic Theft | New Policy | High | Design in Progress | CIV-104707 | Correspondence
119 | CA-209709 | ACL 19-75 Revisions to ABCD 350 | New Policy | High | Design in Progress | CIV 104703 | State/Fiscal Reports
120 | CA-209498 | ACIN I-41-19 STAT 47 - Exclude CFAP Recipients | New Policy | High | Design in Progress | CIV 104608 | State/Fiscal Reports
121 | CA-209488 | ACL XX-XX Child Care Immediate and Continuous Eligibility to Stage One | New Policy | Medium | Design in Progress | CIV-104597 | Child Care
122 | CA-209422 | Update Medi-Cal Auto-Discontinuance Batch for Failure to Complete RE to process at an Individual Level | New Policy | High | Design in Progress | CIV-104584 | Medi-Cal/CMSP
123 | CA-209404 | ACL 19-59 Revise DFA 358F and DFA 358S | New Policy | High | New | CIV 104574 | State/Fiscal Reports
124 | CA-200866 | ACWDL 17-36 NOA snippets for Medi-Cal Inmate Program | New Policy | Medium | New | CIV-12023 | Correspondence
125 | CA-200840 | 2019/2020 Family Member Base Allocation Amount | New Policy | High | Committee Review | CIV-100482 | Medi-Cal/CMSP
126 | CA-200824 | ACWDL 19-XX, ACIN I-XX-19: 2020 Social Security Title II and Title XVI Cost of Living Adjustments (SSA COLA) | New Policy | High | New |  | CalWORKs/CalFresh, Foster Care/Kin GAP/AAP, Medi-Cal/CMSP
127 | CA-202778 | Revised Medi-Cal Hierarchy | New Policy | Critical | Design in Progress | CIV-7564 | Medi-Cal/CMSP
128 | CA-202682 | AB2718 TMC 12 month eligibility changes. | New Policy | Critical | New | CIV-101282 | Medi-Cal/CMSP
129 | CA-202684 | ACL 18-50 - Implement Redesigned CalFresh Overissuance NOAs | New Policy | High | New | CIV-5849
130 | CA-202463 | NFC 17-023 Update SAR 2 to the latest State version | New Policy | High | New | CIV-8975 | Correspondence
131 | CA-202054 | Suspend/Discontinue/Reinstate for CAPI case | New Policy | High | New | CIV-100213
132 | CA-201836 | ACL 18-117: Implement CalFresh Churn Report - CF 18 | New Policy | High | Design in Progress | CIV-100878 | State/Fiscal Reports
133 | CA-203208 | Update MEDS to Send Prior FC or KG Aid Code to MEDS for NMD's Minor Infant Child | New Policy | High | Design in Progress | CIV-572 | MEDS
134 | CA-56341 | ACL 17-34 - CFR 273.2 Create monthly/annual report for Non-Assistance CalFresh Elderly Simplified Application Project (ESAP) Waiver Approval for Elderly/Disabled (E/D) Households (HHs) with no earned income | New Policy | Medium | New | CIV-100752 | Management Reports
135 | CA-56913 | ACL 14-64: Add CalWORKs Family Stabilization (FS) Program Quarterly Status Report - FSP 14 (dependent on SCR CA-57298: Creating Family Stabilization Pages) | New Policy | Critical | New | CIV-832 | State/Fiscal Reports
136 | CA-58236 | Add Translations of Revised Forms to LRS: ABP SSI 1, ABP SSI 3, and ABP SSI 4 | New Policy | Medium | New | LA County Forms for General Relief | Correspondence
137 | CA-50293 | ACL 11-80 - CalWORKs New & Revised Overpayment Notice of Action Messages | New Policy | High | Design in Progress | C-IV SCR 8657
138 | CA-50787 | ACL 16-120 - Create a Report that Identifies Overpayments that were created as a result of a Mandatory Mid-Period Change that was Reported Timely and the County was unable to provide a 10-Day Notice of Action. Addendum to SCR BPP-CWs-GPD-139 | New Policy | High | New |  | Management Reports
139 | CA-57298 | ACL 14-12 - New Family Stabilization List Page and Detail Page | New Policy | High | Design in Progress | CIV-789 and CIV-10075 | Welfare to Work/WPR
140 | CA-48513 | Change EDBC logic to auto-test for 4M when youth 18 years or older exits FC | New Policy | Medium | New | LA County Specific | Foster Care/Kin GAP/AAP
141 | CA-51987 | ACL 14-91 - Track Workfare and 15% Exemptions on Stat 47 Quarterly Report (see SCR CA-50766) | New Policy | Medium | New | CIV-9009 | State/Fiscal Reports
142 | CA-51451 | Automate Discontinuance of OTLICP for NPP | New Policy | Critical | New | CIV-870 | Medi-Cal/CMSP
143 | CA-58123 | Add Validation to Prevent Advancing Medi-Cal Renewal with a Soft Pause Individual | New Policy | Critical | Design in Progress | CIV-10791 | Medi-Cal/CMSP
144 | CA-53617 | ACWDL 17-14: Update the "Medi-Cal General Property Limitations" (MC 007) form in LRS and the LRS code tables with the Statewide Average Private Pay Rate (APPR) for 2017. | New Policy | High | New |  | Medi-Cal/CMSP
145 | CA-58579 | ACWDL 17-31 Revisions to the NA Back 9 for all Medi-Cal Notices of Action | New Policy | Critical | New | CIV-10665 | Correspondence
146 | CA-56916 | Modify the ABAWD super trigger functionality to detect deleted data to update the ABAWD status | New Policy | High | New |  | CalWORKs/CalFresh
147 | CA-54311 | ACL 18-18 CalFresh Changes to Reporting Requirements | New Policy | Critical | New | CIV SCR# 100532 | CalWORKs/CalFresh
148 | CA-206224 | ACIN I-XX-19 - 2020 State Minimum Wage Run Batch EDBC | New Policy | High | Ready for Committee | CIV-103088 | CalWORKs/CalFresh
149 | CA-49617 | ACL 16-45: Automate the CW 2219 for Non-Needy Caretaker application instead of the SAWS 2 Plus application | New Policy | Medium | Design in Progress | CIV-9772 | Correspondence
150 | CA-203060 | ACL 17-61 - Achieving a Better Life Experience (ABLE) Accounts | New Policy | Medium | In Development | CIV-9838 | CalWORKs/CalFresh
151 | CA-201036 | ACL 18-15 Last Date of Payment for Extended Foster Care | New Policy | High | Design in Progress | CIV -100500 | Foster Care/Kin GAP/AAP
152 | CA-205562 | 2019 Bicsuite Batch Schedule Calendar Update | Operational Enhancement | Critical | New |  | Other
153 | CA-205535 | Add Monthly Report to Track Non-Federal Cases from CWS/CMS Special Project Page and ID Num Page | Operational Enhancement | Medium | New |  | Management Reports
154 | CA-205523 | Add Scheduled Report to Track FC/KG/AAP Minors Aging Out at 18 or 21 Years of Age | Operational Enhancement | Medium | New |  | Management Reports
155 | CA-205454 | LRS only change: remove DPSS-at-a-glance link from LRS Business Intelligence dashboard. | Operational Enhancement | High | New |  | Management Reports
156 | CA-206525 | YBN - Create CalSAWS mail server to change all YBN and outbound related email to calSAWS email address | Operational Enhancement | Medium | New |  | C4Yourself
157 | CA-203787 | Auto Discontinue of AAP When Youth Turn 18/21 | Operational Enhancement | Medium | Design in Progress | CIV-104670 | Foster Care/Kin GAP/AAP
158 | CA-209492 | Refactor: Medi-Cal NOA Regulations | Operational Enhancement | Medium | New |  | Correspondence
159 | CA-201657 | OBIEE: Apply Oracle Patch to OBIEE | Operational Enhancement | Medium | New | CIV-593 | IVR & Contact Center
160 | CA-201226 | Provide Internal Services Department (ISD) LMRS/SFV lobby app, lobby monitor and lobby check in app web services & database for SFV office. Removing SFV self service/check in/lobby monitor coding from YBN | Operational Enhancement | High | New |  | Lobby Management
161 | CA-54663 | Suppress WTW/REP/GROW forms when the Provider Resources are in house | Operational Enhancement | High | New | CIV-102421 | RDB
162 | CA-202347 | LRS: Automate e-app status update from Data Transfer to Transfer to LRS once the case is processed (Active, Denied etc) and DCR to update Data transfer to Transfer to LRS status. | Operational Enhancement | Medium | New |  | C4Yourself
163 | CA-202312 | MEDS: Calculate CIN Check Digit | Operational Enhancement | Medium | New | CIV-443 | MEDS
164 | CA-51131 | Enhance the Employment Summation and Employment Summation Detail Reports | Operational Enhancement | Medium | Design in Progress | CIV-100733 | Management Reports
165 | CA-58934 | WTW Program is created Before the CW Program Approval Date. | Operational Enhancement | High | Design in Progress | CIV-66 | Welfare to Work/WPR
166 | CA-55990 | No Cost SCR: Update EDBC Run Date with latest Authorization Date | Operational Enhancement | High | New |  | CalWORKs/CalFresh, Foster Care/Kin GAP/AAP, Medi-Cal/CMSP
167 | CA-53434 | Selective Address Normalization (Tech) | Operational Enhancement | Medium | Design in Progress |  | Tech
168 | CA-207892 | Add Sample SAR7 to Template Respository and RE Packets | Policy Re-Design | High | New | CIV-100919 | Correspondence
169 | CA-207798 | Update Incomplete CF Recertification Status (48318) | Policy Re-Design | High | New | CIV-644 | Correspondence
170 | CA-204762 | Do not Create an Offset Transaction for Overpayment/Overissuances Adjustments | Policy Re-Design | Critical | Design in Progress | CIV-102098 | Collections, State/Fiscal Reports
171 | CA-204747 | CalWORKs clock is ticking for parent who is under 18 years old | Policy Re-Design | High | Design in Progress | CIV-818 | Time Limits
172 | CA-206740 | YourBenefitsNow YBN and LEADER Replacement Systems LRS electronic notification and paperless option logic update. | Policy Re-Design | High | New |  | Usability
173 | CA-206415 | ACL 13-02 Good Cause Reason 407 - Lack of Supportive Services should not impact WTW 24 Month Clock. | Policy Re-Design | Critical | New | C-IV 12392 | Time Limits
174 | CA-205982 | Update CW EDBC to Remove Stepsibling or Half-Sibling Excluded from CalWORKs in the CalFresh Budget | Policy Re-Design | Critical | Ready for Committee | CIV-102946 | CalWORKs/CalFresh
175 | CA-204115 | ACL 18-43 - Revise CalWORKs M40-107 Time Limit NOAs in the C, D, and G Series | Policy Re-Design | Medium | New | CIV 101570
176 | CA-209754 | Add Threshold Languages for GN 6050 RP and GN 6053-R | Policy Re-Design | Medium | New |  | Correspondence
177 | CA-209231 | ACL 11-51: FC Education Travel Reimbursement NOAs | Policy Re-Design | Medium | New | CIV-1131 | Correspondence
178 | CA-200879 | Automate Disaster CalFresh | Policy Re-Design | Medium | Design in Progress |  | CalWORKs/CalFresh
179 | CA-200800 | Update EDBC to process mid-period TCF programs via eICT | Policy Re-Design | High | New | CIV-7522 | ICT
180 | CA-201575 | CF - FTP INS Document, Income of FRE should be prorated | Policy Re-Design | High | Ready for Committee | CIV-101430 | CalWORKs/CalFresh
181 | CA-202460 | Update Verbiage for Medical Savings Program (MSP) NOAs | Policy Re-Design | High | Design in Progress | CIV-100174 | Correspondence
182 | CA-202055 | Separate Case & Issuance for CAPI Couple Case | Policy Re-Design | Critical | Design in Progress | CIV-103281 | CalWORKs/CalFresh
183 | CA-201756 | NOMI - Interview Completion Due date to be 30 days from application date | Policy Re-Design | High | Ready for Committee | CIV-103745
184 | CA-203392 | ACL 16-79 Add a drop down menu for out of state short-term residential therapeutic program (STRTP) placements | Policy Re-Design | High | New | CIV-101513 | Foster Care/Kin GAP/AAP
185 | CA-50303 | Update LRS to have WTW/REP/Cal-Learn sanctions, GR sanction and GR Time Limit at a person level instead of the program level, so the sanction will follow the person if they are moved to another case. | Policy Re-Design | High | New |  | Time Limits
186 | CA-50316 | Phase I - Change CalFresh Notice of Actions - New CF 286 Budget Cont. Page | Policy Re-Design | High | New | CIV-101397 | Correspondence
187 | CA-50776 | CalFresh Work Requirement Changes | Policy Re-Design | Medium | New |  | CalWORKs/CalFresh
188 | CA-49396 | ACL 15-96 â€“ Add and automate ARC Forms NA 1281, NA 1280, NA 1279, and NA 1278 | Policy Re-Design | High | New |  | Correspondence
189 | CA-49395 | ACL: Update ARC1 and ARC1A Forms | Policy Re-Design | Medium | Design in Progress | C-IV SCR 3915 (CCM)
190 | CA-50801 | Phase I - ACL 15-62 changes: NA 816, NA 817 with the latest versions in all threshold languages. | Policy Re-Design | Medium | New |  | Correspondence
191 | CA-51882 | ACL 16-98: Change HA Eligibility From 12-Month to 365-Day Period; Limit HA Manual and Override EDBC drop down values | Policy Re-Design | High | Committee Review | CIV-7859 | CalWORKs/CalFresh
192 | CA-54665 | Time Limit should not be counted for Non-Cal-Learn 19 Year old Custodial Parents | Policy Re-Design | High | New | CIV-102306 | Time Limits
193 | CA-56887 | Phase III-B- Change CalFresh NOAs to include the name of the individuals on change and denial NOAs | Policy Re-Design | High | New |  | Correspondence
194 | CA-55378 | Require the Immunizations page is updated when a child in the Assistance Unit is under age 6 and not in school | Policy Re-Design | Medium | New | CIV-Counties to adopt LRS Functionality | CalWORKs/CalFresh
195 | CA-55584 | DHCS CMS PI Update V 1.6 | Policy Re-Design | Critical | New | CIV-11690 | State/Fiscal Reports
196 | CA-50297 | Permit Concurrent Activity For Participants With Good Cause Status | Policy Re-Design | Critical | New |  | Welfare to Work/WPR
197 | CA-204814 | Update WDTIP Outbound file writer to not allow LD02 transactions to be generated for WTW supportive services participation records | Policy Re-Design | Critical | Design in Progress | CIV-541 | Welfare to Work/WPR
198 | CA-202307 | Updates to the GEN 1365 Form and Form Generation | Policy Re-Design | High | Design in Progress | CIV-100774

## Key
SCR Status Key |  | SCR Change Type Key
System Change Request (SCR) Status | Definition | SCR Change Type | Definition
New | Default status when an Issue is created | Data Change | This change type is selected for data change that impacts high volume of cases
Design in Progress | Indicates that the Team/Consortium Staff are working on the Design | Enhancement | This change type is selected for changes to existing design that are not new policy or policy re design.
Ready for Committee | Indicates the Design is ready for Committee to review/approve | Individual Data Change | This change tyhpe is selected for data changes that impacts low volumne of cases (less than 20)
Committee Review | Indicates the Committee is reviewing for approval | New Policy | This change type is selected for SCRs that have references to regulations or state policy letters that have not yet been integrated in the system.
Pending Approval | Indicates that the Issue is pending the approval of CCB. | Operational Enhancement | This change type is selcted for changes to the system that are county specific, impact a specific technology upgrade (ie. New EBT Printer, New Warrant Stock, FTP changes, DB Upgrade, etc.), or are only operational in nature (IP address change, configurational file changes, etc.)
Approved | Indicates that the Issue has been Accepted by the CCB and/or has been given Expedited Approval and build may begin. | Policy Re-Design | This change type is selected of the SCRs is requesting a change to existing design with a regualtion or state policy letter reference.
In Development | Indicates that the Issue is in the development phase
Development Complete | Indicates that the development team has completed development of the Issue
In Assembly Test | Indicates the development team has completed development of the Issue and Assembly Test is in progress
System Test | Indicates that the Issue is currently in System Test and all Test Conditions are being validated in System Test
Test Complete | Indicates that the Issue has been validated in System Test and all Test Conditions have passed System Test