## MCK- Consortium Ramp-up (hidden)
Consortium DD&I Staffing Levels by Activity and Function |  |  |  | FTEs by Quarter
Activity | Consortium Function | Sub-function/ Role | Projected FTE | 2018Q3 | 2018Q4 | 2019Q1 |  |  | 2019Q2 |  |  | 2019Q3 |  |  | 2019Q4 |  |  | 2020Q1 |  |  | 2020Q2 |  |  | 2020Q3 |  |  | 2020Q4 |  |  | 2021Q1 |  |  | 2021Q2 |  |  | 2021Q3 |  |  | 2021Q4 |  |  | 2022Q1 |  |  | 2022Q2 |  |  | 2022Q3 |  |  | 2022Q4 |  |  | 2023Q1 |  |  | 2023Q2 |  |  |  |  | 2023Q3
Infra Set-Up | Technical Operations | Director | 1 | 0 | 1 | 1 |  |  | 1 |  |  | 1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | 0
| Technical Operations | Cloud Manager | 1 | 0 | 1 | 1 |  |  | 1 |  |  | 1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | 0
| Technical Operations | Technical Operations Manager | 1 | 0 | 1 | 1 |  |  | 1 |  |  | 1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | 0
| Technical Operations | System Admin/ Tech Support | 7 | 0 | 4 | 7 |  |  | 7 |  |  | 4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | 0
Application Design | Policy/ Design/ Governance | Director | 1 | 0 | 0 | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | 0
| Policy/ Design/ Governance | Policy Manager | 1 | 0 | 0 | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | 0
| Policy/ Design/ Governance | Policy Analyst | 4 | 0 | 0 | 2 |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | 0
| Policy/ Design/ Governance | Design Manager | 1 | 0 | 0 | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | 0
| Policy/ Design/ Governance | Product Owner | 30 | 0 | 0 | 8 |  |  | 15 |  |  | 30 |  |  | 15 |  |  | 8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | 0
Application Dev & Unit Test | Application Development & Test | Director | 1 | 0 | 0 | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | 0
| Application Development & Test | Development Manager | 1 | 0 | 0 | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | 0
| Application Development & Test | Development Analysts | 16 | 0 | 0 | 4 |  |  | 8 |  |  | 16 |  |  | 16 |  |  | 16 |  |  | 16 |  |  | 16 |  |  | 16 |  |  | 8 |  |  | 4 |  |  | 4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | 0
| Application Development & Test | Release Manager | 1 | 0 | 0 | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | 0
| Application Development & Test | Release Management Analyst | 2 | 0 | 0 | 1 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | 0
System Testing | Application Development & Test | Test Manager | 1 | 0 | 0 | 0 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | 0
| Application Development & Test | Tester | 12 | 0 | 0 | 0 |  |  | 3 |  |  | 6 |  |  | 12 |  |  | 12 |  |  | 12 |  |  | 6 |  |  | 6 |  |  | 3 |  |  | 3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | 0
Portal & Mobile | N/A - considered within Application Dev & Unit Test |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | 0
Data - Common & CalACES | N/A - considered within Application Dev & Unit Test |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | 0
Data - CalWIN specific | N/A - considered within Application Dev & Unit Test |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | 0
Implementation Support | Technical Operations | Help Desk Manager | 1 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  |  |  | 1
| Technical Operations | System Admin/ Tech Support | 8 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 2 |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 8 |  |  | 8 |  |  | 8 |  |  | 8 |  |  | 4 |  |  | 4 |  |  | 4 |  |  |  |  | 4
| Technical Operations | System Performance Manager | 1 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  |  |  | 1
Change Management | Customer Engagement | Director | 1 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  |  |  | 1
| Customer Engagement | Customer Engagement Manager | 2 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  |  |  | 2
| Customer Engagement | Regional Manager | 20 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 10 |  |  | 10 |  |  | 10 |  |  | 20 |  |  | 20 |  |  | 10 |  |  | 10 |  |  | 10 |  |  | 10 |  |  | 10 |  |  |  |  | 10
Training |  |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | 0
PMO | PMO | PMO Director | 1 | 0 | 1 | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  |  |  | 1
| PMO | PMO Lead | 1 | 0 | 1 | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  |  |  | 1
| PMO | PMO Analyst | 5 | 0 | 1 | 2 |  |  | 3 |  |  | 4 |  |  | 5 |  |  | 5 |  |  | 5 |  |  | 5 |  |  | 5 |  |  | 5 |  |  | 5 |  |  | 5 |  |  | 5 |  |  | 5 |  |  | 5 |  |  | 5 |  |  | 5 |  |  | 5 |  |  | 5 |  |  |  |  | 5
| PMO | Fiscal and Contract Manager | 1 | 0 | 1 | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  |  |  | 1
| PMO | Fiscal and Contract Analyst | 10 | 0 | 2 | 2 |  |  | 2 |  |  | 2 |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 6 |  |  | 6 |  |  | 6 |  |  | 6 |  |  | 6 |  |  | 10 |  |  | 10 |  |  | 10 |  |  | 10 |  |  | 10 |  |  | 10 |  |  |  |  | 10
| PMO | Procurement Manager | 1 | 0 | 1 | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  |  |  | 1
| PMO | Procurement Analyst | 2 | 0 | 2 | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  |  |  | 2
| Technical Operations | Project IT Manager | 1 | 0 | 1 | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  |  |  | 1
Management & Administration | Management & Administration | Executive Director, Executive Assistance (2), Chief Deputy Director, Legal Counsel | 5 | 0 | 5 | 5 |  |  | 5 |  |  | 5 |  |  | 5 |  |  | 5 |  |  | 5 |  |  | 5 |  |  | 5 |  |  | 5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | 0
Total |  |  | 141 | 0 | 22 | 47 |  |  | 66 |  |  | 90 |  |  | 77 |  |  | 68 |  |  | 55 |  |  | 44 |  |  | 52 |  |  | 53 |  |  | 44 |  |  | 40 |  |  | 50 |  |  | 55 |  |  | 45 |  |  | 45 |  |  | 41 |  |  | 41 |  |  | 41 |  |  |  |  | 41
Consortium DD&I staff loading assumptions |  |  |  | Staff levels by quarter
Activity | Consortium Function | Sub-function/ Role | Projected FTE |  | 2018Q4 | 2019Q1 | 2019Q1 | 2019Q1 | 2019Q2 | 2019Q2 | 2019Q2 | 2019Q3 | 2019Q3 | 2019Q3 | 2019Q4 | 2019Q4 | 2019Q4 | 2020Q1 | 2020Q1 | 2020Q1 | 2020Q2 | 2020Q2 | 2020Q2 | 2020Q3 | 2020Q3 | 2020Q3 | 2020Q4 | 2020Q4 | 2020Q4 | 2021Q1 | 2021Q1 | 2021Q1 | 2021Q2 | 2021Q2 | 2021Q2 | 2021Q3 | 2021Q3 | 2021Q3 | 2021Q4 | 2021Q4 | 2021Q4 | 2022Q1 | 2022Q1 | 2022Q1 | 2022Q2 | 2022Q2 | 2022Q2 | 2022Q3 | 2022Q3 | 2022Q3 | 2022Q4 | 2022Q4 | 2022Q4 | 2023Q1 | 2023Q1 | 2023Q1 | 2023Q2 | 2023Q2 | 2023Q2 | 2023Q3 | 2023Q3 | 2023Q3
Infra Set-Up | Technical Operations | Director | 1 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Technical Operations | Cloud Manager | 1 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Technical Operations | Technical Operations Manager | 1 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Technical Operations | System Admin/ Tech Support | 7 |  | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 50% | 50% | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Application Design | Policy/ Design/ Governance | Director | 1 |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Policy/ Design/ Governance | Policy Manager | 1 |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Policy/ Design/ Governance | Policy Analyst | 4 |  |  | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50% | 50% | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Policy/ Design/ Governance | Design Manager | 1 |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Policy/ Design/ Governance | Product Owner | 30 |  |  | 25% | 25% | 25% | 50% | 50% | 50% | 100% | 100% | 100% | 50% | 50% | 50% | 25% | 25% | 25% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Application Dev & Unit Test | Application Development & Test | Director | 1 |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Application Development & Test | Development Manager | 1 |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Application Development & Test | Development Analysts | 16 |  |  | 25% | 25% | 25% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50% | 50% | 50% | 25% | 25% | 25% | 25% | 25% | 25% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Application Development & Test | Release Manager | 1 |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Application Development & Test | Release Management Analyst | 2 |  |  | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
System Testing | Application Development & Test | Test Manager | 1 | [5 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Application Development & Test | Tester | 12 | [5 empty] | 25% | 25% | 25% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50% | 50% | 50% | 50% | 50% | 50% | 25% | 25% | 25% | 25% | 25% | 25% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Portal & Mobile | N/A - considered within Application Dev & Unit Test
Data - Common & CalACES | N/A - considered within Application Dev & Unit Test
Data - CalWIN specific | N/A - considered within Application Dev & Unit Test
Implementation Support | Technical Operations | Help Desk Manager | 1 | [23 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Technical Operations | System Admin/ Tech Support | 8 | [23 empty] | 25% | 25% | 25% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
| Technical Operations | System Performance Manager | 1 | [23 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Change Management | Customer Engagement | Director | 1 | [23 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Customer Engagement | Customer Engagement Manager | 2 | [23 empty] | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Customer Engagement | Regional Manager | 20 | [26 empty] | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
Training
PMO | PMO | PMO Director | 1 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| PMO | PMO Lead | 1 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| PMO | PMO Analyst | 5 |  | 20% | 40% | 40% | 40% | 60% | 60% | 60% | 80% | 80% | 80% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| PMO | Fiscal and Contract Manager | 1 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| PMO | Fiscal and Contract Analyst | 10 |  | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| PMO | Procurement Manager | 1 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| PMO | Procurement Analyst | 2 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Technical Operations | Project IT Manager | 1 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Management & Administration | Management & Administration | Executive Director, Executive Assistance (2), Chief Deputy Director, Legal Counsel | 5 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Total |  |  | 141 |  | 14.54% | 32.27% | 32.27% | 32.27% | 46.1% | 46.1% | 46.1% | 62.77% | 62.77% | 62.77% | 54.61% | 54.61% | 54.61% | 47.87% | 47.87% | 47.87% | 39.01% | 39.01% | 39.01% | 31.21% | 31.21% | 31.21% | 36.88% | 36.88% | 36.88% | 37.59% | 37.59% | 37.59% | 31.21% | 31.21% | 31.21% | 28.37% | 28.37% | 28.37% | 35.46% | 35.46% | 35.46% | 39.01% | 39.01% | 39.01% | 31.91% | 31.91% | 31.91% | 31.91% | 31.91% | 31.91% | 29.08% | 29.08% | 29.08% | 29.08% | 29.08% | 29.08% | 29.08% | 29.08% | 29.08% | 29.08% | 29.08% | 29.08%
Expected rate at which Consortium Staff roll from DD&I to M&O, these roles are expected to be leveraged out of current LRS M&O until baseline FTEs (83) are reached
Consortium M&O Staffing Levels by Activity and Function |  |  |  | FTEs by Quarter
Activity | Consortium Function | Sub-function/ Role | Projected FTE | 2018Q3 | 2018Q4 | 2019Q1 |  |  | 2019Q2 |  |  | 2019Q3 |  |  | 2019Q4 |  |  | 2020Q1 |  |  | 2020Q2 |  |  | 2020Q3 |  |  | 2020Q4 |  |  | 2021Q1 |  |  | 2021Q2 |  |  | 2021Q3 |  |  | 2021Q4 |  |  | 2022Q1 |  |  | 2022Q2 |  |  | 2022Q3 |  |  | 2022Q4 |  |  | 2023Q1 |  |  | 2023Q2 |  |  |  |  | 2023Q3
Infra Set-Up | Technical Operations | Director | 1 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | Linear scale up to steady-state Consortium M&O projections
| Technical Operations | Cloud Manager | 1 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| Technical Operations | Technical Operations Manager | 1 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| Technical Operations | System Admin/ Tech Support | 7 | 0 | 0 | 0 |  |  | 0 |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 4
Application Design | Policy/ Design/ Governance | Director | 1 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1
| Policy/ Design/ Governance | Policy Manager | 1 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1
| Policy/ Design/ Governance | Policy Analyst | 4 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 4
| Policy/ Design/ Governance | Design Manager | 1 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1
| Policy/ Design/ Governance | Product Owner | 30 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 30 |  |  | 30 |  |  | 30 |  |  | 30 |  |  | 30 |  |  | 30 |  |  | 30 |  |  | 30 |  |  | 30 |  |  | 30 |  |  | 30
Application Dev & Unit Test | Application Development & Test | Director | 1 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1
| Application Development & Test | Development Manager | 1 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1
| Application Development & Test | Development Analysts | 16 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| Application Development & Test | Release Manager | 1 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1
| Application Development & Test | Release Management Analyst | 2 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2
System Testing | Application Development & Test | Test Manager | 1 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1
| Application Development & Test | Tester | 12 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 6 |  |  | 6 |  |  | 9 |  |  | 9 |  |  | 12 |  |  | 12 |  |  | 12 |  |  | 12 |  |  | 12 |  |  | 12
Portal & Mobile | N/A - considered within Application Dev & Unit Test |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
Data - Common & CalACES | N/A - considered within Application Dev & Unit Test |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
Data - CalWIN specific | N/A - considered within Application Dev & Unit Test |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
Implementation Support | Technical Operations | Help Desk Manager | 1 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| Technical Operations | System Admin/ Tech Support | 8 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 4
| Technical Operations | System Performance Manager | 1 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
Change Management | Customer Engagement | Director | 1 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| Customer Engagement | Customer Engagement Manager | 2 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| Customer Engagement | Regional Manager | 20 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 10 |  |  | 10 |  |  | 10
Training |  |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
PMO | PMO | PMO Director | 1 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| PMO | PMO Lead | 1 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| PMO | PMO Analyst | 5 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| PMO | Fiscal and Contract Manager | 1 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| PMO | Fiscal and Contract Analyst | 10 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| PMO | Procurement Manager | 1 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| PMO | Procurement Analyst | 2 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| Technical Operations | Project IT Manager | 1 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
Management & Administration | Management & Administration | Executive Director, Executive Assistance (2), Chief Deputy Director, Legal Counsel | 5 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 5 |  |  | 5 |  |  | 5 |  |  | 5 |  |  | 5 |  |  | 5 |  |  | 5
Total |  |  | 141 | 0 | 0 | 0 |  |  | 0 |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 41 |  |  | 52 |  |  | 52 |  |  | 55 |  |  | 60 |  |  | 64 |  |  | 64 |  |  | 64 |  |  | 74 |  |  | 74 |  |  | 78
Consortium M&O staff loading assumptions |  |  |  | Staff load by quarter
Activity | Consortium Function | Sub-function/ Role | Projected FTE |  | 2018Q4 | 2019Q1 |  |  | 2019Q2 |  |  | 2019Q3 |  |  | 2019Q4 |  |  | 2020Q1 |  |  | 2020Q2 |  |  | 2020Q3 |  |  | 2020Q4 |  |  | 2021Q1 |  |  | 2021Q2 |  |  | 2021Q3 |  |  | 2021Q4 |  |  | 2022Q1 |  |  | 2022Q2 |  |  | 2022Q3 |  |  | 2022Q4 |  |  | 2023Q1 |  |  | 2023Q2 |  |  |  |  | 2023Q3
Infra Set-Up | Technical Operations | Director | 1 |  | 0% | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | Linear scale up to steady-state Consortium M&O projections
| Technical Operations | Cloud Manager | 1 |  | 0% | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0%
| Technical Operations | Technical Operations Manager | 1 |  | 0% | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0%
| Technical Operations | System Admin/ Tech Support | 7 |  | 0% | 0% |  |  | 0% |  |  | 50% |  |  | 50% |  |  | 50% |  |  | 50% |  |  | 50% |  |  | 50% |  |  | 50% |  |  | 50% |  |  | 50% |  |  | 50% |  |  | 50% |  |  | 50% |  |  | 50% |  |  | 50%
Application Design | Policy/ Design/ Governance | Director | 1 |  | 0% | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100%
| Policy/ Design/ Governance | Policy Manager | 1 |  | 0% | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100%
| Policy/ Design/ Governance | Policy Analyst | 4 |  | 0% | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100%
| Policy/ Design/ Governance | Design Manager | 1 |  | 0% | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100%
| Policy/ Design/ Governance | Product Owner | 30 |  | 0% | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100%
Application Dev & Unit Test | Application Development & Test | Director | 1 |  | 0% | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100%
| Application Development & Test | Development Manager | 1 |  | 0% | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100%
| Application Development & Test | Development Analysts | 16 |  | 0% | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0%
| Application Development & Test | Release Manager | 1 |  | 0% | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100%
| Application Development & Test | Release Management Analyst | 2 |  | 0% | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100%
System Testing | Application Development & Test | Test Manager | 1 |  | 0% | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100%
| Application Development & Test | Tester | 12 |  | 0% | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 50% |  |  | 50% |  |  | 75% |  |  | 75% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100%
Portal & Mobile | N/A - considered within Application Dev & Unit Test
Data - Common & CalACES | N/A - considered within Application Dev & Unit Test
Data - CalWIN specific | N/A - considered within Application Dev & Unit Test
Implementation Support | Technical Operations | Help Desk Manager | 1 | [38 empty] | 0% |  |  | 0% |  |  | 0% |  |  | 0%
| Technical Operations | System Admin/ Tech Support | 8 | [38 empty] | 0% |  |  | 0% |  |  | 0% |  |  | 50%
| Technical Operations | System Performance Manager | 1 | [38 empty] | 0% |  |  | 0% |  |  | 0% |  |  | 0%
Change Management | Customer Engagement | Director | 1 | [38 empty] | 0% |  |  | 0% |  |  | 0% |  |  | 0%
| Customer Engagement | Customer Engagement Manager | 2 | [38 empty] | 0% |  |  | 0% |  |  | 0% |  |  | 0%
| Customer Engagement | Regional Manager | 20 | [38 empty] | 0% |  |  | 50% |  |  | 50% |  |  | 50%
PMO | PMO | PMO Director | 1 |  | 0% | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0%
| PMO | PMO Lead | 1 |  | 0% | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0%
| PMO | PMO Analyst | 5 |  | 0% | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0%
| PMO | Fiscal and Contract Manager | 1 |  | 0% | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0%
| PMO | Fiscal and Contract Analyst | 10 |  | 0% | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0%
| PMO | Procurement Manager | 1 |  | 0% | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0%
| PMO | Procurement Analyst | 2 |  | 0% | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0%
| Technical Operations | Project IT Manager | 1 |  | 0% | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0%
Management & Administration | Management & Administration | Executive Director, Executive Assistance (2), Chief Deputy Director, Legal Counsel | 5 |  | 0% | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100%
Total |  |  | 141 |  | 0% | 0% |  |  | 0% |  |  | 2.482% |  |  | 2.482% |  |  | 2.482% |  |  | 28.72% |  |  | 36.52% |  |  | 36.52% |  |  | 38.65% |  |  | 42.2% |  |  | 45.04% |  |  | 45.04% |  |  | 45.04% |  |  | 52.13% |  |  | 52.13% |  |  | 54.96%

## 1-McKinsey Estimate (DD&I) (hidden)
MCKINSEY ESTIMATES (DD&I PHASE - Excluding Pilot/POC) | [93 empty] | Return to Navigation
[13 empty] | 47 | 47 | 47 | 66 | 66 | 66 | 90 | 90 | 90 | 77 | 77 | 77 | 68 | 68 | 68 | 55 | 55 | 55 | 44 | 44 | 44 | 52 | 52 | 52 | 53 | 53 | 53 | 44 | 44 | 44 | 40 | 40 | 40 | 50 | 50 | 50 | 55 | 55 | 55 | 45 | 45 | 45 | 45 | 45 | 45 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 0 | 0 | 0
| Nominal Month | [11 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9
| FFY | [11 empty] | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 24 | 24 | 24 |  | SFY | SFY | SFY | SFY | SFY | SFY | SFY | SFY | SFY |  | FFY | FFY | FFY | FFY | FFY | FFY | FFY | FFY | FFY
| SFY | [11 empty] | 18/19 | 18/19 | 18/19 | 18/19 | 18/19 | 18/19 | 19/20 | 19/20 | 19/20 | 19/20 | 19/20 | 19/20 | 19/20 | 19/20 | 19/20 | 19/20 | 19/20 | 19/20 | 20/21 | 20/21 | 20/21 | 20/21 | 20/21 | 20/21 | 20/21 | 20/21 | 20/21 | 20/21 | 20/21 | 20/21 | 21/22 | 21/22 | 21/22 | 21/22 | 21/22 | 21/22 | 21/22 | 21/22 | 21/22 | 21/22 | 21/22 | 21/22 | 22/23 | 22/23 | 22/23 | 22/23 | 22/23 | 22/23 | 22/23 | 22/23 | 22/23 | 22/23 | 22/23 | 22/23 | 23/24 | 23/24 | 23/24 | 23/24 | 23/24 | 23/24 |  | 18/19 | 19/20 | 20/21 | 21/22 | 22/23 | 23/24 | 24/25 | 25/26 | 26/27 |  | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
| Month | [71 empty] | Total | Total | Total | Total | Total | Total | Total | Total | Total | Total | Total | Total | Total | Total | Total | Total | Total | Total | Total | Total | Total | time axis 2019-01-01 to 2023-12-01
ALLOCATION |  | SUB-FUNCTION/ ROLE | NAME | SALARY | BENEFITS | DURATION (MONTHS) | HOURS / MONTH | RATE PER HOUR | TOTAL COST | TOTAL COST PER FTE | TOTAL MONTHLY COST (PER FTE) | [61 empty] | TOTAL
DDI |  | Management & Administration |  |  |  |  | 176 | 150 | 26400 | 26400 | 26400 |  | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 3564000 | 792000 | 1584000 | 1188000 | 0 | 0 | 0 | 0 | 0 | 0 | 3564000 | 1188000 | 1584000 | 792000 | 0 | 0 | 0 | 0 | 0 | 0 | 3564000
DDI |  | Application Development & Test |  |  |  |  | 176 | 150 | 26400 | 26400 | 26400 |  | 211200 | 211200 | 211200 | 448800 | 448800 | 448800 | 739200 | 739200 | 739200 | 897600 | 897600 | 897600 | 897600 | 897600 | 897600 | 897600 | 897600 | 897600 | 607200 | 607200 | 607200 | 607200 | 607200 | 607200 | 316800 | 316800 | 316800 | 211200 | 211200 | 211200 | 105600 | 105600 | 105600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 17820000 | 1980000 | 10296000 | 5227200 | 316800 | 0 | 0 | 0 | 0 | 0 | 17820000 | 4197600 | 9900000 | 3722400 | 0 | 0 | 0 | 0 | 0 | 0 | 17820000
DDI |  | Policy/ Design/ Governance |  |  |  |  | 176 | 150 | 26400 | 26400 | 26400 |  | 343200 | 343200 | 343200 | 580800 | 580800 | 580800 | 976800 | 976800 | 976800 | 580800 | 580800 | 580800 | 343200 | 343200 | 343200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 8474400 | 2772000 | 5702400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8474400 | 5702400 | 2772000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8474400
DDI |  | Technical Operations |  |  |  |  | 176 | 150 | 26400 | 26400 | 26400 |  | 290400 | 290400 | 290400 | 290400 | 290400 | 290400 | 211200 | 211200 | 211200 | 26400 | 26400 | 26400 | 26400 | 26400 | 26400 | 26400 | 26400 | 26400 | 26400 | 26400 | 26400 | 132000 | 132000 | 132000 | 184800 | 184800 | 184800 | 184800 | 184800 | 184800 | 184800 | 184800 | 184800 | 290400 | 290400 | 290400 | 290400 | 290400 | 290400 | 290400 | 290400 | 290400 | 290400 | 290400 | 290400 | 184800 | 184800 | 184800 | 184800 | 184800 | 184800 | 184800 | 184800 | 184800 | 184800 | 184800 | 184800 |  |  |  | 10454400 | 1742400 | 871200 | 1584000 | 3168000 | 2534400 | 554400 | 0 | 0 | 0 | 10454400 | 2376000 | 316800 | 2059200 | 3484800 | 2217600 | 0 | 0 | 0 | 0 | 10454400
DDI |  | PMO |  |  |  |  | 176 | 150 | 26400 | 26400 | 26400 |  | 264000 | 264000 | 264000 | 290400 | 290400 | 290400 | 316800 | 316800 | 316800 | 396000 | 396000 | 396000 | 396000 | 396000 | 396000 | 396000 | 396000 | 396000 | 396000 | 396000 | 396000 | 448800 | 448800 | 448800 | 448800 | 448800 | 448800 | 448800 | 448800 | 448800 | 448800 | 448800 | 448800 | 448800 | 448800 | 448800 | 554400 | 554400 | 554400 | 554400 | 554400 | 554400 | 554400 | 554400 | 554400 | 554400 | 554400 | 554400 | 554400 | 554400 | 554400 | 554400 | 554400 | 554400 | 554400 | 554400 | 554400 |  |  |  | 25740000 | 1663200 | 4514400 | 5227200 | 6019200 | 6652800 | 1663200 | 0 | 0 | 0 | 25740000 | 2613600 | 4752000 | 5385600 | 6336000 | 6652800 | 0 | 0 | 0 | 0 | 25740000
DDI |  | Customer Engagement |  |  |  |  | 176 | 150 | 26400 | 26400 | 26400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52800 | 52800 | 52800 | 316800 | 316800 | 316800 | 316800 | 316800 | 316800 | 316800 | 316800 | 316800 | 580800 | 580800 | 580800 | 607200 | 607200 | 607200 | 343200 | 343200 | 343200 | 343200 | 343200 | 343200 | 343200 | 343200 | 343200 | 343200 | 343200 | 343200 | 343200 | 343200 | 343200 | 343200 | 343200 | 343200 |  |  |  | 12751200 | 0 | 0 | 2059200 | 5544000 | 4118400 | 1029600 | 0 | 0 | 0 | 12751200 | 0 | 0 | 3009600 | 5623200 | 4118400 | 0 | 0 | 0 | 0 | 12751200
[73 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
INSERT ABOVE THIS ROW
Total | [8 empty] | 158400 |  |  | 0 | 1240800 | 1240800 | 1240800 | 1742400 | 1742400 | 1742400 | 2376000 | 2376000 | 2376000 | 2032800 | 2032800 | 2032800 | 1795200 | 1795200 | 1795200 | 1452000 | 1452000 | 1452000 | 1161600 | 1161600 | 1161600 | 1372800 | 1372800 | 1372800 | 1399200 | 1399200 | 1399200 | 1161600 | 1161600 | 1161600 | 1056000 | 1056000 | 1056000 | 1320000 | 1320000 | 1320000 | 1452000 | 1452000 | 1452000 | 1188000 | 1188000 | 1188000 | 1188000 | 1188000 | 1188000 | 1082400 | 1082400 | 1082400 | 1082400 | 1082400 | 1082400 | 1082400 | 1082400 | 1082400 | 1082400 | 1082400 | 1082400 | 0 | 0 | 0 | 78804000 | 8949600 | 22968000 | 15285600 | 15048000 | 13305600 | 3247200 | 0 | 0 | 0 | 78804000 | 16077600 | 19324800 | 14968800 | 15444000 | 12988800 | 0 | 0 | 0 | 0 | 78804000
Notes/Assumptions:
1. $150 Hourly Rate for Consortium Staff
2. 176 hours per month
[13 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 8 | 8 | 8 | 17 | 17 | 17 | 28 | 28 | 28 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 23 | 23 | 23 | 23 | 23 | 23 | 12 | 12 | 12 | 8 | 8 | 8 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 13 | 13 | 13 | 22 | 22 | 22 | 37 | 37 | 37 | 22 | 22 | 22 | 13 | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 11 | 11 | 11 | 11 | 11 | 11 | 8 | 8 | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 5 | 5 | 5 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 0 | 0 | 0
[13 empty] | 10 | 10 | 10 | 11 | 11 | 11 | 12 | 12 | 12 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 22 | 22 | 22 | 23 | 23 | 23 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 11 | 11 | 11 | 11 | 11 | 14 | 14 | 14 | 14 | 14 | 14 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 24 | 24 | 24 | 30 | 30 | 30 | 36 | 36 | 36 | 42 | 42 | 42 | 42 | 42 | 42
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 34 | 34 | 34 | 31 | 31 | 31 | 28 | 28 | 28 | 25 | 25 | 25 | 25 | 25 | 25
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 13 | 13 | 13 | 22 | 22 | 22 | 31 | 31 | 31 | 37 | 37 | 37 | 44 | 44 | 44
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 22 | 22 | 22
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 24 | 24 | 24

## Cover
CalSAWS Migration Project
Request for Proposal - QA Services
Attachment D
Attachment D -
QA DD&I Cost Proposal Schedules

## Sch 5 - Summary
Schedule 5 - Summary Totals | <Columns A-G should not be manually updated> |  |  |  | <Columns H-M should be manually updated to include the invoice month and deliverable total cost by SFY. For recurring deliverables, indicate "Recurring" for Target Invoice Month column>
Deliverable | Deliverable Cost | # of Deliverables |  | Cost per Deliverable | Target Invoice Month | SFY 18/19 | SFY 19/20 | SFY 20/21 | SFY 21/22 | SFY 22/23 | SFY 23/24
DEL #1 - QA Management Plan | 11180 | 1 | 25 | 11180 | 2019-08-01 | 0 | 11180 | 0 | 0 | 0 | 0 | DEL #1 | QA Management Plan
DEL #2 - QA Work Plan (Initial) | 10484 | 1 | 47 | 10484 | 2019-08-01 | 0 | 10484 | 0 | 0 | 0 | 0 | DEL #2 | QA Work Plan (Initial)
DEL #3 - QA Monthly Status Report (Monthly) | 5849826 | 46 | 69 | 127170.1304 | Recurring | 0 | 930161 | 1814052 | 1698838 | 1406775 | 0 | DEL #3 | QA Monthly Status Report (Monthly)
DEL #4 - QA Work Plan (Monthly update) | 506054 | 46 | 91 | 11001.1739 | Recurring | 0 | 114124 | 134376 | 134376 | 123178 | 0 | DEL #4 | QA Work Plan (Monthly update)
DEL #5 - Deliverable Review and Assessment Plan | 23100 | 1 | 113 | 23100 | 2019-08-01 | 0 | 23100 | 0 | 0 | 0 | 0 | DEL #5 | Deliverable Review and Assessment Plan
DEL #6 - QA Testing Plan | 71180 | 1 | 135 | 71180 | 2019-09-01 | 0 | 71180 | 0 | 0 | 0 | 0 | DEL #6 | QA Testing Plan
DEL #7 - QA Test Monthly Report (Monthly) | 4767248 | 46 | 157 | 103635.8261 | Recurring | 0 | 1089496 | 1311096 | 1138208 | 1228448 | 0 | DEL #7 | QA Test Monthly Report (Monthly)
DEL #8 - UAT Weekly Report (Weekly) | 423248 | 22 | 179 | 19238.5455 | Recurring | 0 | 0 | 138544 | 284704 | 0 | 0 | DEL #8 | UAT Weekly Report (Weekly)
DEL #9 - QA Security Review Plan | 83660 | 1 | 201 | 83660 | 2020-11-01 | 0 | 0 | 83660 | 0 | 0 | 0 | DEL #9 | QA Security Review Plan
DEL #10 - Quarterly QA Security Report (Quarterly) | 386096 | 10 | 223 | 38609.6 | Recurring | 0 | 0 | 84336 | 168672 | 133088 | 0 | DEL #10 | Quarterly QA Security Report (Quarterly)
DEL #11 - Assessment of DD&I Vendor CalSAWS Migration Project Control Document Initial | 22508 | 1 | 245 | 22508 | 2019-09-01 | 0 | 22508 | 0 | 0 | 0 | 0 | DEL #11 | Assessment of DD&I Vendor CalSAWS Migration Project Control Document Initial
DEL #12 - Assessment of DD&I Vendor CalSAWS Migration Work Plan Update (Monthly) | 374832 | 1 | 267 | 374832 | Recurring | 0 | 89512 | 97824 | 97824 | 89672 | 0 | DEL #12 | Assessment of DD&I Vendor CalSAWS Migration Work Plan Update (Monthly)
DEL #13 - Assessment of DD&I Vendor CalSAWS General Design | 37692 | 1 | 289 | 37692 | 2019-09-01 | 0 | 37692 | 0 | 0 | 0 | 0 | DEL #13 | Assessment of DD&I Vendor CalSAWS General Design
DEL #14 - Assessment of DD&I Vendor CalACES Master Conversion Plan | 33908 | 1 | 311 | 33908 | 2019-09-01 | 0 | 33908 | 0 | 0 | 0 | 0 | DEL #14 | Assessment of DD&I Vendor CalACES Master Conversion Plan
DEL #15 - Assessment of DD&I Vendor Application Development Preparation and Installation Plan | 28124 | 1 | 333 | 28124 | 2019-10-01 | 0 | 28124 | 0 | 0 | 0 | 0 | DEL #15 | Assessment of DD&I Vendor Application Development Preparation and Installation Plan
DEL #16 - Assessment of DD&I Vendor CalSAWS Master Test Plan | 8528 | 1 | 355 | 8528 | 2019-08-01 | 0 | 8528 | 0 | 0 | 0 | 0 | DEL #16 | Assessment of DD&I Vendor CalSAWS Master Test Plan
DEL #17 - Assessment of DD&I Vendor CalSAWS Business Architecture Design | 16568 | 1 | 377 | 16568 | 2019-08-01 | 0 | 16568 | 0 | 0 | 0 | 0 | DEL #17 | Assessment of DD&I Vendor CalSAWS Business Architecture Design
DEL #18 - Assessment of DD&I Vendor CalSAWS General Design | 18700 | 1 | 399 | 18700 | 2019-08-01 | 0 | 18700 | 0 | 0 | 0 | 0 | DEL #18 | Assessment of DD&I Vendor CalSAWS General Design
DEL #19 - Assessment of DD&I Vendor CalSAWS General Design | 59976 | 1 | 421 | 59976 | 2019-09-01 | 0 | 59976 | 0 | 0 | 0 | 0 | DEL #19 | Assessment of DD&I Vendor CalSAWS General Design
DEL #20 - Assessment of DD&I Vendor C-IV Master Training Plan | 17624 | 1 | 443 | 17624 | 2019-09-01 | 0 | 17624 | 0 | 0 | 0 | 0 | DEL #20 | Assessment of DD&I Vendor C-IV Master Training Plan
DEL #21 - Assessment of DD&I Vendor CalWIN/CalSAWS Master Conversion Plan | 27636 | 1 | 465 | 27636 | 2019-09-01 | 0 | 27636 | 0 | 0 | 0 | 0 | DEL #21 | Assessment of DD&I Vendor CalWIN/CalSAWS Master Conversion Plan
DEL #22 - Assessment of DD&I Vendor CalSAWS Requirements Traceability Matrix - Initial | 31888 | 1 | 487 | 31888 | 2019-11-01 | 0 | 31888 | 0 | 0 | 0 | 0 | DEL #22 | Assessment of DD&I Vendor CalSAWS Requirements Traceability Matrix - Initial
DEL #23 - Assessment of DD&I Vendor CalSAWS General Design (Page/Report/Correspondence Changes per Requirement) | 138104 | 1 | 509 | 138104 | 2019-11-01 | 0 | 138104 | 0 | 0 | 0 | 0 | DEL #23 | Assessment of DD&I Vendor CalSAWS General Design (Page/Report/Correspondence Changes per Requirement)
DEL #24 - Assessment of DD&I Vendor C-IV Deployment Readiness Plan | 63828 | 1 | 531 | 63828 | 2019-11-01 | 0 | 63828 | 0 | 0 | 0 | 0 | DEL #24 | Assessment of DD&I Vendor C-IV Deployment Readiness Plan
DEL #25 - Assessment of DD&I Vendor CalSAWS Requirements Traceability Matrix - Update 1 | 26884 | 1 | 553 | 26884 | 2020-01-01 | 0 | 26884 | 0 | 0 | 0 | 0 | DEL #25 | Assessment of DD&I Vendor CalSAWS Requirements Traceability Matrix - Update 1
DEL #26 - Assessment of DD&I Vendor CalSAWS General Design | 134032 | 1 | 575 | 134032 | 2020-01-01 | 0 | 134032 | 0 | 0 | 0 | 0 | DEL #26 | Assessment of DD&I Vendor CalSAWS General Design
DEL #27 - Assessment of DD&I Vendor CalWIN/CalSAWS Master Conversion Plan - Update 1 | 58176 | 1 | 597 | 58176 | 2020-02-01 | 0 | 58176 | 0 | 0 | 0 | 0 | DEL #27 | Assessment of DD&I Vendor CalWIN/CalSAWS Master Conversion Plan - Update 1
DEL #28 - Assessment of DD&I Vendor CalSAWS General Design | 133484 | 1 | 619 | 133484 | 2020-03-01 | 0 | 133484 | 0 | 0 | 0 | 0 | DEL #28 | Assessment of DD&I Vendor CalSAWS General Design
DEL #29 - Assessment of DD&I Vendor CalSAWS Migration Project Control Document Update | 25620 | 1 | 641 | 25620 | 2020-03-01 | 0 | 25620 | 0 | 0 | 0 | 0 | DEL #29 | Assessment of DD&I Vendor CalSAWS Migration Project Control Document Update
DEL #30 - Assessment of DD&I Vendor CalSAWS Requirements Traceability Matrix - Update 2 | 21832 | 1 | 663 | 21832 | 2020-03-01 | 0 | 21832 | 0 | 0 | 0 | 0 | DEL #30 | Assessment of DD&I Vendor CalSAWS Requirements Traceability Matrix - Update 2
DEL #31 - Assessment of DD&I Vendor CalSAWS General Design | 144808 | 1 | 685 | 144808 | 2020-05-01 | 0 | 144808 | 0 | 0 | 0 | 0 | DEL #31 | Assessment of DD&I Vendor CalSAWS General Design
DEL #32 - Assessment of DD&I Vendor CalSAWS Requirements Traceability Matrix - Update 3 | 26280 | 1 | 707 | 26280 | 2020-05-01 | 0 | 26280 | 0 | 0 | 0 | 0 | DEL #32 | Assessment of DD&I Vendor CalSAWS Requirements Traceability Matrix - Update 3
DEL #33 - Assessment of DD&I Vendor C-IV Change Management Plan | 80296 | 1 | 729 | 80296 | 2020-07-01 | 0 | 0 | 80296 | 0 | 0 | 0 | DEL #33 | Assessment of DD&I Vendor C-IV Change Management Plan
DEL #34 - Assessment of DD&I Vendor CalSAWS Requirements Traceability Matrix - Update 4 | 22584 | 1 | 751 | 22584 | 2020-07-01 | 0 | 0 | 22584 | 0 | 0 | 0 | DEL #34 | Assessment of DD&I Vendor CalSAWS Requirements Traceability Matrix - Update 4
DEL #35 - Assessment of DD&I Vendor CalSAWS General Design | 140016 | 1 | 773 | 140016 | 2020-07-01 | 0 | 0 | 140016 | 0 | 0 | 0 | DEL #35 | Assessment of DD&I Vendor CalSAWS General Design
DEL #36 - Assessment of DD&I Vendor CalSAWS Requirements Traceability Matrix - Update 5 | 28376 | 1 | 795 | 28376 | 2020-09-01 | 0 | 0 | 28376 | 0 | 0 | 0 | DEL #36 | Assessment of DD&I Vendor CalSAWS Requirements Traceability Matrix - Update 5
DEL #37 - Assessment of DD&I Vendor CalSAWS Requirements Traceability Matrix - Update 6 | 28376 | 1 | 817 | 28376 | 2020-11-01 | 0 | 0 | 28376 | 0 | 0 | 0 | DEL #37 | Assessment of DD&I Vendor CalSAWS Requirements Traceability Matrix - Update 6
DEL #38 - Assessment of DD&I Vendor CalSAWS UAT Support Plan | 32468 | 1 | 839 | 32468 | 2020-12-01 | 0 | 0 | 32468 | 0 | 0 | 0 | DEL #38 | Assessment of DD&I Vendor CalSAWS UAT Support Plan
DEL #39 - Assessment of DD&I Vendor CalSAWS Requirements Traceability Matrix - Update 7 | 22584 | 1 | 861 | 22584 | 2021-01-01 | 0 | 0 | 22584 | 0 | 0 | 0 | DEL #39 | Assessment of DD&I Vendor CalSAWS Requirements Traceability Matrix - Update 7
DEL #40 - Assessment of DD&I Vendor CalSAWS (C-IV) UAT Readiness Report/Milestone | 26176 | 1 | 883 | 26176 | 2021-02-01 | 0 | 0 | 26176 | 0 | 0 | 0 | DEL #40 | Assessment of DD&I Vendor CalSAWS (C-IV) UAT Readiness Report/Milestone
DEL #41 - Assessment of DD&I Vendor CalSAWS Migration Project Control Document Update | 19576 | 1 | 905 | 19576 | 2021-03-01 | 0 | 0 | 19576 | 0 | 0 | 0 | DEL #41 | Assessment of DD&I Vendor CalSAWS Migration Project Control Document Update
DEL #42 - Assessment of DD&I Vendor CalSAWS (CalWIN) UAT Readiness Report/Milestone | 19608 | 1 | 927 | 19608 | 2021-05-01 | 0 | 0 | 19608 | 0 | 0 | 0 | DEL #42 | Assessment of DD&I Vendor CalSAWS (CalWIN) UAT Readiness Report/Milestone
DEL #43 - Assessment of DD&I Vendor CalSAWS Requirements Traceability Matrix - Update 8 | 22584 | 1 | 949 | 22584 | 2021-08-01 | 0 | 0 | 0 | 22584 | 0 | 0 | DEL #43 | Assessment of DD&I Vendor CalSAWS Requirements Traceability Matrix - Update 8
DEL #44 - Assessment of DD&I Vendor CalSAWS Requirements Traceability Matrix - Update 9 | 21672 | 1 | 971 | 21672 | 2021-11-01 | 0 | 0 | 0 | 21672 | 0 | 0 | DEL #44 | Assessment of DD&I Vendor CalSAWS Requirements Traceability Matrix - Update 9
DEL #45 - Assessment of DD&I Vendor CalSAWS Deployment Complete Milestone/Report - C-IV | 60936 | 1 | 993 | 60936 | 2021-11-01 | 0 | 0 | 0 | 60936 | 0 | 0 | DEL #45 | Assessment of DD&I Vendor CalSAWS Deployment Complete Milestone/Report - C-IV
DEL #46 - Assessment of DD&I Vendor CalACES Migration Final Acceptance Certification | 19460 | 1 | 1015 | 19460 | 2022-02-01 | 0 | 0 | 0 | 19460 | 0 | 0 | DEL #46 | Assessment of DD&I Vendor CalACES Migration Final Acceptance Certification
DEL #47 - Assessment of DD&I Vendor CalSAWS Deployment Complete Milestone/Report - CalWIN Wave 1 | 149788 | 1 | 1037 | 149788 | 2022-02-01 | 0 | 0 | 0 | 149788 | 0 | 0 | DEL #47 | Assessment of DD&I Vendor CalSAWS Deployment Complete Milestone/Report - CalWIN Wave 1
DEL #48 - Assessment of DD&I Vendor CalSAWS Migration Project Control Document Update | 23408 | 1 | 1059 | 23408 | 2022-03-01 | 0 | 0 | 0 | 23408 | 0 | 0 | DEL #48 | Assessment of DD&I Vendor CalSAWS Migration Project Control Document Update
DEL #49 - Assessment of DD&I Vendor CalSAWS Deployment Complete Milestone/Report - CalWIN Wave 2 | 145136 | 1 | 1081 | 145136 | 2022-05-01 | 0 | 0 | 0 | 145136 | 0 | 0 | DEL #49 | Assessment of DD&I Vendor CalSAWS Deployment Complete Milestone/Report - CalWIN Wave 2
DEL #50 - Assessment of DD&I Vendor CalSAWS Deployment Complete Milestone/Report - CalWIN Wave 3 | 145136 | 1 | 1103 | 145136 | 2022-08-01 | 0 | 0 | 0 | 0 | 145136 | 0 | DEL #50 | Assessment of DD&I Vendor CalSAWS Deployment Complete Milestone/Report - CalWIN Wave 3
DEL #51 - Assessment of DD&I Vendor CalSAWS Deployment Complete Milestone/Report - CalWIN Wave 4 | 145824 | 1 | 1125 | 145824 | 2022-10-01 | 0 | 0 | 0 | 0 | 145824 | 0 | DEL #51 | Assessment of DD&I Vendor CalSAWS Deployment Complete Milestone/Report - CalWIN Wave 4
DEL #52 - Assessment of DD&I Vendor CalSAWS Deployment Complete Milestone/Report - CalWIN Wave 5 | 145136 | 1 | 1147 | 145136 | 2022-12-01 | 0 | 0 | 0 | 0 | 145136 | 0 | DEL #52 | Assessment of DD&I Vendor CalSAWS Deployment Complete Milestone/Report - CalWIN Wave 5
DEL #53 - Assessment of DD&I Vendor CalSAWS Deployment Complete Milestone/Report - CalWIN Wave 6 | 130128 | 1 | 1169 | 130128 | 2023-02-01 | 0 | 0 | 0 | 0 | 130128 | 0 | DEL #53 | Assessment of DD&I Vendor CalSAWS Deployment Complete Milestone/Report - CalWIN Wave 6
DEL #54 - Assessment of DD&I Vendor CalSAWS Deployment Complete Report - CalWIN Wave 1-6 | 61092 | 1 | 1191 | 61092 | 2023-02-01 | 0 | 0 | 0 | 0 | 61092 | 0 | DEL #54 | Assessment of DD&I Vendor CalSAWS Deployment Complete Report - CalWIN Wave 1-6
DEL #55 - Assessment of DD&I Vendor CalSAWS Migration Project Control Document Update | 14272 | 1 | 1213 | 14272 | 2023-03-01 | 0 | 0 | 0 | 0 | 14272 | 0 | DEL #55 | Assessment of DD&I Vendor CalSAWS Migration Project Control Document Update
DEL #56 - Assessment of DD&I Vendor CalSAWS Migration Final Acceptance Certification | 33112 | 1 | 1235 | 33112 | 2023-05-01 | 0 | 0 | 0 | 0 | 33112 | 0 | DEL #56 | Assessment of DD&I Vendor CalSAWS Migration Final Acceptance Certification
DEL #57 - Assessment of CalWIN Implementation Support Vendor CalWIN Migration Work Plan Initial | 10168 | 1 | 1257 | 10168 | 2020-06-01 | 0 | 10168 | 0 | 0 | 0 | 0 | DEL #57 | Assessment of CalWIN Implementation Support Vendor CalWIN Migration Work Plan Initial
DEL #58 - Assessment of CalWIN Implementation Support Vendor CalWIN Migration Project Control Document Initial | 17352 | 1 | 1279 | 17352 | 2020-06-01 | 0 | 17352 | 0 | 0 | 0 | 0 | DEL #58 | Assessment of CalWIN Implementation Support Vendor CalWIN Migration Project Control Document Initial
DEL #59 - Assessment of CalWIN Implementation Support Vendor CalWIN Migration Work Plan Update (Monthly) | 174608 | 30 | 1301 | 5820.2667 | Recurring | 0 | 0 | 72224 | 68256 | 34128 | 0 | DEL #59 | Assessment of CalWIN Implementation Support Vendor CalWIN Migration Work Plan Update (Monthly)
DEL #60 - Assessment of CalWIN Implementation Support Vendor CalWIN Master Training Plan | 47888 | 1 | 1323 | 47888 | 2020-11-01 | 0 | 0 | 47888 | 0 | 0 | 0 | DEL #60 | Assessment of CalWIN Implementation Support Vendor CalWIN Master Training Plan
DEL #61 - Assessment of CalWIN Implementation Support Vendor CalWIN Deployment Readiness Plan | 124080 | 1 | 1345 | 124080 | 2021-04-01 | 0 | 0 | 124080 | 0 | 0 | 0 | DEL #61 | Assessment of CalWIN Implementation Support Vendor CalWIN Deployment Readiness Plan
DEL #62 - Assessment of CalWIN Implementation Support Vendor CalWIN Change Management Plan | 50464 | 1 | 1367 | 50464 | 2021-06-01 | 0 | 0 | 50464 | 0 | 0 | 0 | DEL #62 | Assessment of CalWIN Implementation Support Vendor CalWIN Change Management Plan
DEL #63 - Assessment of CalWIN Implementation Support Vendor CalWIN ILT Training Material | 47408 | 1 | 1389 | 47408 | 2021-09-01 | 0 | 0 | 0 | 47408 | 0 | 0 | DEL #63 | Assessment of CalWIN Implementation Support Vendor CalWIN ILT Training Material
DEL #64 - Assessment of CalWIN Implementation Support Vendor CalWIN WBT Training Material | 48320 | 1 | 1411 | 48320 | 2021-10-01 | 0 | 0 | 0 | 48320 | 0 | 0 | DEL #64 | Assessment of CalWIN Implementation Support Vendor CalWIN WBT Training Material
DEL #65 - QA Status Report (Monthly) | 1726284 | n/a | 1433 |  | Recurring | 0 | 0 | 0 | 0 | 153544 | 1572740 | DEL #65 | QA Status Report (Monthly)
DEL #66 - QA M&O Testing Plan | 11516 | n/a | 1455 | 11516 | 2023-06-01 | 0 | 0 | 0 | 0 | 11516 | 0 | DEL #66 | QA M&O Testing Plan
DEL #67 - QA M&O Monthly Test Report (Monthly) | 1435792 | n/a | 1477 |  | Recurring | 0 | 0 | 0 | 0 | 117460 | 1318332 | DEL #67 | QA M&O Monthly Test Report (Monthly)
DEL #68 - Quarterly QA Security Report (Quarterly) | 136288 | n/a | 1499 |  | Recurring | 0 | 0 | 0 | 0 | 0 | 136288 | DEL #68 | Quarterly QA Security Report (Quarterly)
DEL #69 - Monthly SLA & Performance Review Report (Monthly) | 116784 | n/a | 1521 |  | Recurring | 0 | 0 | 0 | 0 | 9732 | 107052 | DEL #69 | Monthly SLA & Performance Review Report (Monthly)
Total DD&I Phase and Year 1 M&O Deliverables Cost | 19067804 | 258 | 53337 | 3851051.5426 |  | 0 | 3442957 | 4378604 | 4129590 | 3982241 | 3134412
Total DD&I Phase Deliverables Cost | 15641140 | 258 | 106602 | 7680439.0851 |  | 0 | 3442957 | 4378604 | 4129590 | 3689989 | 0
Total Year 1 M&O Deliverables Cost | 3426664 |  | 213044 |  |  | 0 | 0 | 0 | 0 | 292252 | 3134412
[6 empty] | 2018-07-01 | 2019-07-01 | 2020-07-01 | 2021-07-01 | 2022-07-01 | 2023-07-01
2019-05-08
Signature | Date
President | ClearBest, Inc.
Title | Company

## Sch 5 - Summary (OCAT)
Schedule 5 - Summary Totals | <Columns A-G should not be manually updated> |  |  |  | <Columns H-M should be manually updated to include the invoice month and deliverable total cost by SFY. For recurring deliverables, indicate "Recurring" for Target Invoice Month column>
Deliverable | Deliverable Cost | # of Deliverables |  | Cost per Deliverable | Target Invoice Month | SFY 18/19 | SFY 19/20 | SFY 20/21 | SFY 21/22 | SFY 22/23 | SFY 23/24
DEL #1 - QA Monthly Status Report (OCAT) | 307326 | 15 | 25 | 20488.4 | Recurring | 0 | 179022 | 128304 | 0 | 0 | 0 | DEL #1 - QA Monthly Status Report (OCAT)
DEL #2 - QA Assessment of OCAT Project Control Document | 1480 | 1 | 47 | 1480 | 2019-09-01 | 0 | 1480 | 0 | 0 | 0 | 0 | DEL #2 - QA Assessment of OCAT Project Control Document
DEL #3 - QA Assessment of OCAT Work Plan | 1540 | 1 | 69 | 1540 | 2019-09-01 | 0 | 1540 | 0 | 0 | 0 | 0 | DEL #3 - QA Assessment of OCAT Work Plan
DEL #4 - QA Assessment of OCAT RTM | 7138 | 1 | 91 | 7138 | 2019-09-01 | 0 | 7138 | 0 | 0 | 0 | 0 | DEL #4 - QA Assessment of OCAT RTM
DEL #5 - QA Assessment of OCAT General Design Document | 26238 | 1 | 113 | 26238 | 2019-11-01 | 0 | 26238 | 0 | 0 | 0 | 0 | DEL #5 - QA Assessment of OCAT General Design Document
DEL #6 - QA Assessment of OCAT Technical Design | 18272 | 1 | 135 | 18272 | 2019-11-01 | 0 | 18272 | 0 | 0 | 0 | 0 | DEL #6 - QA Assessment of OCAT Technical Design
DEL #7 - QA Assessment of OCAT Application SAWS Interfaces | 46988 | 1 | 157 | 46988 | 2020-05-01 | 0 | 46988 | 0 | 0 | 0 | 0 | DEL #7 - QA Assessment of OCAT Application SAWS Interfaces
DEL #8 - QA Assessment of OCAT Master Test Plan | 10144 | 1 | 179 | 10144 | 2019-10-01 | 0 | 10144 | 0 | 0 | 0 | 0 | DEL #8 - QA Assessment of OCAT Master Test Plan
DEL #9 - QA Assessment of OCAT Training Plan | 9904 | 1 | 201 | 9904 | 2020-03-01 | 0 | 9904 | 0 | 0 | 0 | 0 | DEL #9 - QA Assessment of OCAT Training Plan
DEL #10 - QA Assessment of OCAT Training Materials | 19944 | 1 | 223 | 19944 | 2020-06-01 | 0 | 19944 | 0 | 0 | 0 | 0 | DEL #10 - QA Assessment of OCAT Training Materials
DEL #11 - QA Assessment of OCAT System Documentation | 22016 | 1 | 245 | 22016 | 2020-04-01 | 0 | 22016 | 0 | 0 | 0 | 0 | DEL #11 - QA Assessment of OCAT System Documentation
DEL #12 - QA Assessment of OCAT Final Acceptance | 18888 | 1 | 267 | 18888 | 2020-11-01 | 0 | 0 | 18888 | 0 | 0 | 0 | DEL #12 - QA Assessment of OCAT Final Acceptance
DEL #13 - QA Assessment of OCAT M&O Transition Plan | 11316 | 1 | 289 | 11316 | 2020-12-01 | 0 | 0 | 11316 | 0 | 0 | 0 | DEL #13 - QA Assessment of OCAT M&O Transition Plan
DEL #14 - QA M&O Monthly Status Report (OCAT) | 135272 | 12 | 311 | 11272.6667 | Recurring | 0 | 0 | 76592 | 58680 | 0 | 0 | DEL #14 - QA M&O Monthly Status Report (OCAT)
Total OCAT DD&I and Year 1 OCAT M&O Deliverables Cost | 636466 | 39 | 2352 | 225629.0667 |  | 0 | 342686 | 235100 | 58680 | 0 | 0
Total OCAT DD&I Phase Deliverables Cost | 501194 | 27 | 4632 | 192388 |  | 0 | 342686 | 235100 | 58680 | 0 | 0
Total Year 1 OCAT M&O Deliverables Cost | 135272 | 12 | 9104 | 11272.6667 |  | 0 | 0 | 76592 | 58680 | 0 | 0
[6 empty] | 2018-07-01 | 2019-07-01 | 2020-07-01 | 2021-07-01 | 2022-07-01 | 2023-07-01
2019-08-22
Signature | Date
President | ClearBest, Inc.
Title | Company

## Sch 1 - QA Rates
Schedule 1 - QA Rates Instructions - Use this tab to define the Hourly Rate for each QA Role. Key QA Staff Roles are already included in the table below. All roles defined using Attachment P - QA Role Definition should also be included on this table.
# | QA Role | Hourly Rate
1 | QA Project Manager | 154
2 | QA PMO Lead | 134
3 | QA Functional Manager | 134
4 | QA Technical Manager | 144
5 | QA Implementation Manager | 134
6 | QA Testing Manager | 134
7 | QA UAT Lead | 134
8 | QA PMO Specialist | 114
9 | QA Sr. Administrative Assistant | 45
10 | QA Business Analyst/Tester | 114
11 | QA Conversion Lead | 114
12 | QA Independent Tester | 99
13 | QA Independent Tester/UAT Leader | 114
14 | QA Technical Lead | 139
15 | QA Implementation Lead | 124
16 | QA Executive | 154
17 | QA Technical Lead (OCAT) | 139
18 | QA Specialist (OCAT) | 124
19
20
21
22
23
24
25

## Sch 2 - QA Team Roster
Schedule 2 - QA Team Roster Instructions - Use this tab to define the individual team members of the proposed QA Team. All staff that are expected to participate on the CalSAWS QA Team must be included. All staff included on this tab must have an Attachment I - Staff Resumes/Staff Qualifications included within the Business Proposal. All QA Roles included on this table must be Key Staff or defined by Attachment P - QA Role Definition within the Business Proposal.
# | QA Staff Person Name | QA Role | Expected Start Month | Expected End Month | QA Role Valid
1 | Dan Dean | QA Project Manager | 2019-07-01 | 2024-04-01 | QA Project Manager
2 | Beena Amarnath | QA PMO Lead | 2019-07-01 | 2024-04-02 | QA PMO Lead
3 | Kristin Pepper | QA Functional Manager | 2019-07-01 | 2024-04-03 | QA Functional Manager
4 | Don Coffey | QA Technical Manager | 2019-07-01 | 2024-04-04 | QA Technical Manager
5 | Abby Darrah | QA Implementation Manager | 2019-08-02 | 2023-04-01 | QA Implementation Manager
6 | Cheryl Hofmann | QA Testing Manager | 2019-07-01 | 2024-04-04 | QA Testing Manager
7 | Rachel Hernandez | QA UAT Lead | 2019-07-01 | 2024-04-04 | QA UAT Lead
8 | Timothy King | QA PMO Specialist | 2019-07-01 | 2024-04-04 | QA PMO Specialist
9 | Julie Hereth | QA Sr. Administrative Assistant | 2019-07-01 | 2024-04-04 | QA Sr. Administrative Assistant
10 | Raj Ganesh | QA Conversion Lead | 2019-07-01 | 2023-04-01 | QA Conversion Lead
11 | Pandu Gupta | QA Business Analyst/Tester | 2019-07-01 | 2024-04-04 | QA Business Analyst/Tester
12 | Donna Smith | QA Independent Tester/UAT Leader | 2019-07-01 | 2024-04-04 | QA Independent Tester/UAT Leader
13 | Kim Sinclair | QA Independent Tester | 2019-08-02 | 2024-04-04 | QA Independent Tester
14 | Sindura Kompulira | QA Independent Tester/UAT Leader | 2019-08-03 | 2024-04-04 | QA Independent Tester/UAT Leader
15 | Lalitha Ramabholta | QA Independent Tester/UAT Leader | 2019-08-05 | 2024-04-04 | QA Independent Tester/UAT Leader
16 | Greg FitzGerald | QA Technical Lead | 2019-08-01 | 2024-04-04 | QA Technical Lead
17 | Dustin Lish | QA Technical Lead | 2019-07-01 | 2024-04-04 | QA Technical Lead
18 | Ivan Parra | QA Implementation Lead | 2020-05-01 | 2022-12-01 | QA Implementation Lead
19 | Gail Brown | QA Implementation Lead | 2019-08-02 | 2022-12-01 | QA Implementation Lead
20 | Wendy Battermann | QA Executive | 2019-07-01 | 2024-04-01 | QA Executive
21 | Frank Ono | QA Executive | 2019-07-01 | 2024-04-01 | QA Executive
22 | Venu Gaddam | QA Technical Lead (OCAT) | 2019-08-01 | 2021-10-31 | QA Technical Lead (OCAT)
23 | Gretchen Williams | QA Specialist (OCAT) | 2019-08-01 | 2020-10-31 | QA Specialist (OCAT)
24 |  |  |  |  | Invalid Role
25 |  |  |  |  | Invalid Role
26 |  |  |  |  | Invalid Role
27 |  |  |  |  | Invalid Role
28 |  |  |  |  | Invalid Role
29 |  |  |  |  | Invalid Role

## Sch 3 - QA Staff Loading
| Schedule 3 - QA Staff Loading |  |  | 80 | 168 | 168 | 160 | 168 | 144 | 160 | 168 | 152 | 176 | 168 | 152 | 160 | 168 | 168 | 160 | 160 | 160 | 160 | 152 | 144 | 176 | 168 | 160 | 168 | 160 | 176 | 160 | 152 | 152 | 152 | 160 | 144 | 160 | 160 | 168 | 168 | 152 | 176 | 160 | 160 | 152 | 152 | 160 | 144 | 176 | 160 | 176 | 176 | 160 | 184 | 160 | 168 | 160 | 160 | 168 | 160 | 168 | 176
Schedule 3 - QA Staff Loading | time axis 2019-06-28 to 2023-04-28
| Schedule 3 - QA Staff Loading | [94 empty] | <-- Do Not Delete hidden columns
|  | Nominal Month |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 |  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 |  |  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9
|  | FFY |  | 19 | 19 | 19 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 24 | 24 | 24 | 24 | 24 | 24 | 24 |  |  | SFY | SFY | SFY | SFY | SFY | SFY | SFY | SFY | SFY |  |  |  | FFY | FFY | FFY | FFY | FFY | FFY | FFY | FFY | FFY
|  | SFY |  | 18/19 | 19/20 | 19/20 | 19/20 | 19/20 | 19/20 | 19/20 | 19/20 | 19/20 | 19/20 | 19/20 | 19/20 | 19/20 | 20/21 | 20/21 | 20/21 | 20/21 | 20/21 | 20/21 | 20/21 | 20/21 | 20/21 | 20/21 | 20/21 | 20/21 | 21/22 | 21/22 | 21/22 | 21/22 | 21/22 | 21/22 | 21/22 | 21/22 | 21/22 | 21/22 | 21/22 | 21/22 | 22/23 | 22/23 | 22/23 | 22/23 | 22/23 | 22/23 | 22/23 | 22/23 | 22/23 | 22/23 | 22/23 | 22/23 | 23/24 | 23/24 | 23/24 | 23/24 | 23/24 | 23/24 | 23/24 | 23/24 | 23/24 | 23/24 |  |  | 18/19 | 19/20 | 20/21 | 21/22 | 22/23 | 23/24 | 24/25 | 25/26 | 26/27 |  |  |  | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 |  |  | Invoice Month Summaries
| DELIVERABLE | Month | Bill Rate | [59 empty] | Total |  | Total | Total | Total | Total | Total | Total | Total | Total | Total |  | Total |  | Total | Total | Total | Total | Total | Total | Total | Total | Total |  | Total | Rates | 19/20 | 20/21 | 21/22 | 22/23 | 23/24 | Total | time axis 2019-06-01 to 2024-04-01
# | STAFF NAME | QA ROLE (pulled from Roster tab) | [60 empty] | TOTAL
| DEL #1 - QA Management Plan | [63 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 11180 | 0 | 0 | 0 | 0 | 11180 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2019-07-01: 24 | 24 |  | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 24 |  | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 24 | 154 | 3696 | 0 | 0 | 0 | 0 | 3696
2 | Beena Amarnath | QA PMO Lead | 134 | 2019-07-01: 30 | 30 |  | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 30 |  | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 30 | 134 | 4020 | 0 | 0 | 0 | 0 | 4020
3 | Timothy King | QA PMO Specialist | 114 | 2019-07-01: 18 | 18 |  | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 |  | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | 114 | 2052 | 0 | 0 | 0 | 0 | 2052
4 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2019-07-01: 4 | 4 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | 45 | 180 | 0 | 0 | 0 | 0 | 180
5 | Wendy Battermann | QA Executive | 154 | 2019-07-01: 8 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 154 | 1232 | 0 | 0 | 0 | 0 | 1232
6 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #2 - QA Work Plan (Initial) |  |  | 2019-07-01: Due |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 10484 | 0 | 0 | 0 | 0 | 10484 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2019-07-01: 20 | 20 |  | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 20 |  | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 20 | 154 | 3080 | 0 | 0 | 0 | 0 | 3080
2 | Beena Amarnath | QA PMO Lead | 134 | 2019-07-01: 34 | 34 |  | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 34 |  | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 34 | 134 | 4556 | 0 | 0 | 0 | 0 | 4556
3 | Timothy King | QA PMO Specialist | 114 | 2019-07-01: 18 | 18 |  | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 |  | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | 114 | 2052 | 0 | 0 | 0 | 0 | 2052
4 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2019-07-01: 4 | 4 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | 45 | 180 | 0 | 0 | 0 | 0 | 180
5 | Wendy Battermann | QA Executive | 154 | 2019-07-01: 4 | 4 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | 154 | 616 | 0 | 0 | 0 | 0 | 616
6 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #3 - QA Monthly Status Report (Monthly) |  |  |  | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 930161 | 1814052 | 1698838 | 1406775 | 0 | 5849826 | subtotal
1 | Dan Dean | QA Project Manager | 154 |  | 40 | 48 | 72 | 80 | 80 | 68 | 80 | 80 | 100 | 80 | 80 | 76 | 112 | 96 | 80 | 80 | 80 | 80 | 60 | 60 | 84 | 80 | 96 | 100 | 84 | 104 | 84 | 80 | 84 | 76 | 68 | 60 | 88 | 84 | 100 | 96 | 60 | 108 | 72 | 84 | 64 | 84 | 76 | 100 | 112 | 84 | [12 empty] | 3744 |  | 0 | 884 | 1008 | 1008 | 844 | 0 | 0 | 0 | 0 |  | 3744 |  | 160 | 1012 | 992 | 976 | 604 | 0 | 0 | 0 | 0 |  | 3744 | 154 | 124432 | 151536 | 155848 | 144760 | 0 | 576576
2 | Beena Amarnath | QA PMO Lead | 134 |  | 32 | 36 | 72 | 88 | 88 | 104 | 80 | 80 | 120 | 80 | 48 | 80 | 88 | 96 | 88 | 88 | 80 | 76 | 48 | 32 | 80 | 96 | 88 | 96 | 88 | 100 | 84 | 72 | 64 | 60 | 56 | 40 | 72 | 72 | 80 | 80 | 48 | 88 | 64 | 72 | 40 | 72 | 64 | 64 | 104 | 80 | [12 empty] | 3428 |  | 0 | 908 | 956 | 868 | 696 | 0 | 0 | 0 | 0 |  | 3428 |  | 140 | 1040 | 956 | 796 | 496 | 0 | 0 | 0 | 0 |  | 3428 | 134 | 110952 | 125960 | 118456 | 103984 | 0 | 459352
3 | Kristin Pepper | QA Functional Manager | 134 |  | 16 | 24 | 52 | 40 | 36 | 40 | 48 | 48 | 88 | 64 | 60 | 68 | 136 | 136 | 128 | 128 | 136 | 128 | 120 | 96 | 136 | 160 | 152 | 144 | 128 | 152 | 112 | 96 | 136 | 128 | 112 | 112 | 136 | 128 | 152 | 144 | 112 | 152 | 120 | 136 | 104 | 112 | 104 | 120 | 152 | 120 | [12 empty] | 4952 |  | 0 | 584 | 1600 | 1536 | 1232 | 0 | 0 | 0 | 0 |  | 4952 |  | 92 | 892 | 1592 | 1528 | 848 | 0 | 0 | 0 | 0 |  | 4952 | 134 | 69144 | 204216 | 205824 | 184384 | 0 | 663568
4 | Don Coffey | QA Technical Manager | 144 |  | 24 | 16 | 80 | 20 | 88 | 20 | 56 | 20 | 120 | 52 | 96 | 68 | 144 | 120 | 106 | 98 | 136 | 88 | 80 | 88 | 104 | 128 | 152 | 112 | 104 | 168 | 104 | 96 | 136 | 96 | 88 | 112 | 104 | 104 | 152 | 112 | 88 | 152 | 96 | 112 | 104 | 80 | 72 | 136 | 136 | 120 | [12 empty] | 4488 |  | 0 | 660 | 1356 | 1376 | 1096 | 0 | 0 | 0 | 0 |  | 4488 |  | 120 | 910 | 1362 | 1336 | 760 | 0 | 0 | 0 | 0 |  | 4488 | 144 | 85248 | 188928 | 198144 | 173952 | 0 | 646272
5 | Abby Darrah | QA Implementation Manager | 134 |  |  | 8 | 128 | 136 | 88 | 104 | 112 | 120 | 144 | 136 | 120 | 128 | 160 | 136 | 128 | 128 | 152 | 136 | 120 | 104 | 104 | 136 | 128 | 136 | 80 | 88 | 88 | 36 | 84 | 84 | 40 | 76 | 92 | 52 | 100 | 60 | 24 | 68 | 32 | 52 | 24 | 68 | 44 | 120 | 152 | 128 | [12 empty] | 4384 |  | 0 | 1224 | 1568 | 880 | 712 | 0 | 0 | 0 | 0 |  | 4384 |  | 136 | 1512 | 1400 | 748 | 588 | 0 | 0 | 0 | 0 |  | 4384 | 134 | 146864 | 209040 | 128104 | 103448 | 0 | 587456
6 | Cheryl Hofmann | QA Testing Manager | 134 |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | [12 empty] | 368 |  | 0 | 96 | 96 | 96 | 80 | 0 | 0 | 0 | 0 |  | 368 |  | 24 | 96 | 96 | 96 | 56 | 0 | 0 | 0 | 0 |  | 368 | 134 | 11792 | 12864 | 12864 | 11792 | 0 | 49312
7 | Rachel Hernandez | QA UAT Lead | 134 |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | [12 empty] | 368 |  | 0 | 96 | 96 | 96 | 80 | 0 | 0 | 0 | 0 |  | 368 |  | 24 | 96 | 96 | 96 | 56 | 0 | 0 | 0 | 0 |  | 368 | 134 | 11792 | 12864 | 12864 | 11792 | 0 | 49312
8 | Timothy King | QA PMO Specialist | 114 |  | 24 | 14 | 40 | 40 | 48 | 40 | 40 | 40 | 72 | 40 | 40 | 40 | 64 | 40 | 40 | 40 | 40 | 40 | 20 | 40 | 40 | 40 | 60 | 56 | 40 | 40 | 40 | 40 | 72 | 52 | 16 | 48 | 68 | 56 | 72 | 68 | 40 | 72 | 52 | 48 | 40 | 68 | 32 | 80 | 84 | 56 | [12 empty] | 2182 |  | 0 | 478 | 520 | 612 | 572 | 0 | 0 | 0 | 0 |  | 2182 |  | 78 | 544 | 496 | 656 | 408 | 0 | 0 | 0 | 0 |  | 2182 | 114 | 49932 | 57456 | 68400 | 72960 | 0 | 248748
9 | Julie Hereth | QA Sr. Administrative Assistant | 45 |  | 31 | 40 | 55 | 58 | 48 | 55 | 57 | 52 | 63 | 55 | 47 | 58 | 60 | 58 | 52 | 52 | 55 | 54 | 50 | 49 | 60 | 55 | 55 | 57 | 52 | 60 | 50 | 50 | 55 | 50 | 52 | 50 | 55 | 55 | 62 | 58 | 52 | 63 | 55 | 55 | 54 | 52 | 54 | 52 | 63 | 57 | [12 empty] | 2482 |  | 0 | 619 | 657 | 649 | 557 | 0 | 0 | 0 | 0 |  | 2482 |  | 126 | 663 | 649 | 657 | 387 | 0 | 0 | 0 | 0 |  | 2482 | 45 | 25245 | 29610 | 29160 | 27675 | 0 | 111690
10 | Raj Ganesh | QA Conversion Lead | 114 |  | 8 | 8 | 68 | 68 | 44 | 60 | 68 | 52 | 76 | 68 | 52 | 60 | 168 | 152 | 136 | 136 | 160 | 136 | 120 | 120 | 128 | 152 | 160 | 152 | 136 | 160 | 120 | 104 | 144 | 120 | 104 | 136 | 128 | 120 | 160 | 136 | 104 | 160 | 112 | 128 | 112 | 104 | 96 | 144 | 144 | 128 | [12 empty] | 5152 |  | 0 | 632 | 1720 | 1568 | 1232 | 0 | 0 | 0 | 0 |  | 5152 |  | 84 | 1004 | 1680 | 1528 | 856 | 0 | 0 | 0 | 0 |  | 5152 | 114 | 65208 | 185592 | 180576 | 155952 | 0 | 587328
11 | Pandu Gupta | QA Business Analyst/Tester | 114 |  | 8 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 20 | 16 | 16 | 16 | 80 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 88 | 100 | 100 | 100 | 100 | 100 | [12 empty] | 2296 |  | 0 | 188 | 256 | 864 | 988 | 0 | 0 | 0 | 0 |  | 2296 |  | 40 | 260 | 192 | 1116 | 688 | 0 | 0 | 0 | 0 |  | 2296 | 114 | 19608 | 29184 | 88920 | 124032 | 0 | 261744
12 | Greg FitzGerald | QA Technical Lead | 139 |  | 8 | 24 | 24 | 20 | 8 | 8 | 32 | 8 | 40 | 12 | 36 | 36 | 126 | 102 | 75 | 75 | 120 | 96 | 90 | 108 | 108 | 102 | 120 | 102 | 96 | 132 | 96 | 90 | 114 | 90 | 96 | 108 | 96 | 96 | 126 | 102 | 90 | 132 | 96 | 96 | 114 | 90 | 96 | 88 | 88 | 88 | [12 empty] | 3700 |  | 0 | 256 | 1224 | 1242 | 978 | 0 | 0 | 0 | 0 |  | 3700 |  | 56 | 503 | 1245 | 1236 | 660 | 0 | 0 | 0 | 0 |  | 3700 | 139 | 30580 | 160962 | 172638 | 150120 | 0 | 514300
13 | Dustin Lish | QA Technical Lead | 139 |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | [12 empty] | 368 |  | 0 | 96 | 96 | 96 | 80 | 0 | 0 | 0 | 0 |  | 368 | IFG | 24 | 96 | 96 | 96 | 56 | 0 | 0 | 0 | 0 |  | 368 | 139 | 12232 | 13344 | 13344 | 12232 | 0 | 51152 | IFG
14 | Ivan Parra | QA Implementation Lead | 124 | 2020-05-01: 112; 2020-06-01: 120; 2020-07-01: 168; 2020-08-01: 128; 2020-09-01: 120; 2020-10-01: 120; 2020-11-01: 160; 2020-12-01: 152; 2021-01-01: 136; 2021-02-01: 120; 2021-03-01: 104; 2021-04-01: 128; 2021-05-01: 120; 2021-06-01: 128; 2021-07-01: 80; 2021-08-01: 96; 2021-09-01: 120; 2021-10-01: 92; 2021-11-01: 92; 2021-12-01: 92; 2022-01-01: 44; 2022-02-01: 84; 2022-03-01: 100; 2022-04-01: 60; 2022-05-01: 108; 2022-06-01: 68; 2022-07-01: 32; 2022-08-01: 76; 2022-09-01: 40; 2022-10-01: 60; 2022-11-01: 32; 2022-12-01: 92 | 3184 |  | 0 | 232 | 1584 | 1036 | 332 | 0 | 0 | 0 | 0 |  | 3184 |  | 0 | 648 | 1464 | 888 | 184 | 0 | 0 | 0 | 0 |  | 3184 | 124 | 13888 | 195424 | 135904 | 49600 | 0 | 394816
15 | Gail Brown | QA Implementation Lead | 124 |  |  | 20 | 60 | 60 | 104 | 120 | 128 | 112 | 136 | 128 | 112 | 120 | 168 | 128 | 120 | 120 | 160 | 160 | 136 | 120 | 104 | 128 | 120 | 128 | 80 | 96 | 120 | 92 | 92 | 92 | 44 | 84 | 100 | 60 | 108 | 68 | 32 | 76 | 40 | 60 | 32 | 92 | [16 empty] | 4060 |  | 0 | 1100 | 1592 | 1036 | 332 | 0 | 0 | 0 | 0 |  | 4060 | IFG | 80 | 1436 | 1472 | 888 | 184 | 0 | 0 | 0 | 0 |  | 4060 | 124 | 121520 | 196416 | 135904 | 49600 | 0 | 503440 | IFG
16 | Wendy Battermann | QA Executive | 154 |  |  |  | 10 | 8 | 10 | 12 | 10 | 6 | 10 | 10 | 6 | 4 | 12 | 12 | 12 | 4 | 4 | 12 | 8 | 8 | 4 | 6 | 6 | 10 | 10 | 6 | 6 | 4 | 12 | 12 | 4 | 8 | 12 | 4 | 12 | 12 | 4 | 4 | 4 | 12 | 4 | 6 | 6 | 10 | 6 | 6 | [12 empty] | 348 |  | 0 | 86 | 98 | 102 | 62 | 0 | 0 | 0 | 0 |  | 348 |  | 10 | 112 | 84 | 92 | 50 | 0 | 0 | 0 | 0 |  | 348 | 154 | 12628 | 14168 | 15400 | 11396 | 0 | 53592
17 | Frank Ono | QA Executive | 154 |  |  |  | 16 | 12 | 16 | 12 | 12 | 12 | 16 | 12 | 16 | 12 | 16 | 12 | 12 | 12 | 16 | 16 | 12 | 16 | 16 | 16 | 16 | 16 | 12 | 16 | 16 | 12 | 16 | 16 | 8 | 16 | 16 | 12 | 16 | 16 | 4 | 12 | 4 | 12 | 16 | 12 | 12 | 12 | 12 | 12 | [12 empty] | 592 |  | 0 | 136 | 176 | 172 | 108 | 0 | 0 | 0 | 0 |  | 592 | IFG | 16 | 160 | 180 | 148 | 88 | 0 | 0 | 0 | 0 |  | 592 | 154 | 19096 | 26488 | 26488 | 19096 | 0 | 91168 | IFG
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #4 - QA Work Plan (Monthly update) |  |  |  |  | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 114124 | 134376 | 134376 | 123178 | 0 | 506054 | subtotal
1 | Dan Dean | QA Project Manager | 154 |  |  | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | [12 empty] | 540 |  | 0 | 132 | 144 | 144 | 120 | 0 | 0 | 0 | 0 |  | 540 |  | 24 | 144 | 144 | 144 | 84 | 0 | 0 | 0 | 0 |  | 540 | 154 | 18480 | 22176 | 22176 | 20328 | 0 | 83160
2 | Beena Amarnath | QA PMO Lead | 134 |  |  | 24 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | [12 empty] | 728 |  | 0 | 184 | 192 | 192 | 160 | 0 | 0 | 0 | 0 |  | 728 |  | 40 | 192 | 192 | 192 | 112 | 0 | 0 | 0 | 0 |  | 728 | 134 | 22512 | 25728 | 25728 | 23584 | 0 | 97552
3 | Timothy King | QA PMO Specialist | 114 |  |  | 8 | 16 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | [12 empty] | 540 |  | 0 | 132 | 144 | 144 | 120 | 0 | 0 | 0 | 0 |  | 540 |  | 24 | 144 | 144 | 144 | 84 | 0 | 0 | 0 | 0 |  | 540 | 114 | 13680 | 16416 | 16416 | 15048 | 0 | 61560
4 | Kristin Pepper | QA Functional Manager | 134 |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | [12 empty] | 368 |  | 0 | 96 | 96 | 96 | 80 | 0 | 0 | 0 | 0 |  | 368 |  | 24 | 96 | 96 | 96 | 56 | 0 | 0 | 0 | 0 |  | 368 | 134 | 11792 | 12864 | 12864 | 11792 | 0 | 49312
5 | Don Coffey | QA Technical Manager | 144 |  |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | [12 empty] | 360 |  | 0 | 88 | 96 | 96 | 80 | 0 | 0 | 0 | 0 |  | 360 |  | 16 | 96 | 96 | 96 | 56 | 0 | 0 | 0 | 0 |  | 360 | 144 | 11520 | 13824 | 13824 | 12672 | 0 | 51840
6 | Abby Darrah | QA Implementation Manager | 134 |  |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | [12 empty] | 360 |  | 0 | 88 | 96 | 96 | 80 | 0 | 0 | 0 | 0 |  | 360 |  | 16 | 96 | 96 | 96 | 56 | 0 | 0 | 0 | 0 |  | 360 | 134 | 10720 | 12864 | 12864 | 11792 | 0 | 48240
7 | Cheryl Hofmann | QA Testing Manager | 134 |  |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | [12 empty] | 360 |  | 0 | 88 | 96 | 96 | 80 | 0 | 0 | 0 | 0 |  | 360 |  | 16 | 96 | 96 | 96 | 56 | 0 | 0 | 0 | 0 |  | 360 | 134 | 10720 | 12864 | 12864 | 11792 | 0 | 48240
8 | Rachel Hernandez | QA UAT Lead | 134 |  |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | [12 empty] | 360 |  | 0 | 88 | 96 | 96 | 80 | 0 | 0 | 0 | 0 |  | 360 |  | 16 | 96 | 96 | 96 | 56 | 0 | 0 | 0 | 0 |  | 360 | 134 | 10720 | 12864 | 12864 | 11792 | 0 | 48240
9 | Julie Hereth | QA Sr. Administrative Assistant | 45 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | [12 empty] | 90 |  | 0 | 22 | 24 | 24 | 20 | 0 | 0 | 0 | 0 |  | 90 |  | 4 | 24 | 24 | 24 | 14 | 0 | 0 | 0 | 0 |  | 90 | 45 | 900 | 1080 | 1080 | 990 | 0 | 4050
10 | Wendy Battermann | QA Executive | 154 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | [12 empty] | 90 |  | 0 | 22 | 24 | 24 | 20 | 0 | 0 | 0 | 0 |  | 90 |  | 4 | 24 | 24 | 24 | 14 | 0 | 0 | 0 | 0 |  | 90 | 154 | 3080 | 3696 | 3696 | 3388 | 0 | 13860
11 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #5 - Deliverable Review and Assessment Plan |  |  | 2019-07-01: Due |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 23100 | 0 | 0 | 0 | 0 | 23100 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2019-07-01: 14 | 14 |  | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 14 |  | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 14 | 154 | 2156 | 0 | 0 | 0 | 0 | 2156
2 | Beena Amarnath | QA PMO Lead | 134 | 2019-07-01: 40 | 40 |  | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 |  | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 | 134 | 5360 | 0 | 0 | 0 | 0 | 5360
3 | Timothy King | QA PMO Specialist | 114 | 2019-07-01: 32 | 32 |  | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 |  | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 | 114 | 3648 | 0 | 0 | 0 | 0 | 3648
4 | Kristin Pepper | QA Functional Manager | 134 | 2019-07-01: 24 | 24 |  | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 24 |  | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 24 | 134 | 3216 | 0 | 0 | 0 | 0 | 3216
5 | Don Coffey | QA Technical Manager | 144 | 2019-07-01: 24 | 24 |  | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 24 |  | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 24 | 144 | 3456 | 0 | 0 | 0 | 0 | 3456
6 | Abby Darrah | QA Implementation Manager | 134 | [59 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 134 | 0 | 0 | 0 | 0 | 0 | 0
7 | Cheryl Hofmann | QA Testing Manager | 134 | 2019-07-01: 16 | 16 |  | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16 |  | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16 | 134 | 2144 | 0 | 0 | 0 | 0 | 2144
8 | Rachel Hernandez | QA UAT Lead | 134 | 2019-07-01: 16 | 16 |  | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16 |  | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16 | 134 | 2144 | 0 | 0 | 0 | 0 | 2144
9 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2019-07-01: 8 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 45 | 360 | 0 | 0 | 0 | 0 | 360
10 | Wendy Battermann | QA Executive | 154 | 2019-07-01: 4 | 4 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | 154 | 616 | 0 | 0 | 0 | 0 | 616
11 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #6 - QA Testing Plan |  |  | 2019-08-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 71180 | 0 | 0 | 0 | 0 | 71180 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2019-07-01: 20; 2019-08-01: 8 | 28 |  | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28 |  | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28 | 154 | 4312 | 0 | 0 | 0 | 0 | 4312
2 | Timothy King | QA PMO Specialist | 114 | 2019-07-01: 4; 2019-08-01: 4 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 114 | 912 | 0 | 0 | 0 | 0 | 912
3 | Cheryl Hofmann | QA Testing Manager | 134 | 2019-07-01: 112; 2019-08-01: 80 | 192 |  | 0 | 192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 192 |  | 192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 192 | 134 | 25728 | 0 | 0 | 0 | 0 | 25728
4 | Rachel Hernandez | QA UAT Lead | 134 | 2019-07-01: 112; 2019-08-01: 80 | 192 |  | 0 | 192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 192 |  | 192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 192 | 134 | 25728 | 0 | 0 | 0 | 0 | 25728
5 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2019-08-01: 4 | 4 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | 45 | 180 | 0 | 0 | 0 | 0 | 180
6 | Wendy Battermann | QA Executive | 154 | 2019-08-01: 8 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 154 | 1232 | 0 | 0 | 0 | 0 | 1232
7 | Frank Ono | QA Executive | 154 | 2019-08-01: 8 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | IFG | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 154 | 1232 | 0 | 0 | 0 | 0 | 1232
8 | Donna Smith | QA Independent Tester/UAT Leader | 114 | 2019-07-01: 104 | 104 |  | 0 | 104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 104 |  | 104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 104 | 114 | 11856 | 0 | 0 | 0 | 0 | 11856
9 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #7 - QA Test Monthly Report (Monthly) | [5 empty] | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 1089496 | 1311096 | 1138208 | 1228448 | 0 | 4767248 | subtotal
1 | Dan Dean | QA Project Manager | 154 |  |  | 6 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | [12 empty] | 358 |  | 0 | 86 | 96 | 96 | 80 | 0 | 0 | 0 | 0 |  | 358 |  | 14 | 96 | 96 | 96 | 56 | 0 | 0 | 0 | 0 |  | 358 | 154 | 12012 | 14784 | 14784 | 13552 | 0 | 55132
2 | Beena Amarnath | QA PMO Lead | 134 |  |  | 16 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | [12 empty] | 1072 |  | 0 | 256 | 288 | 288 | 240 | 0 | 0 | 0 | 0 |  | 1072 |  | 40 | 288 | 288 | 288 | 168 | 0 | 0 | 0 | 0 |  | 1072 | 134 | 31088 | 38592 | 38592 | 35376 | 0 | 143648
3 | Timothy King | QA PMO Specialist | 114 |  |  | 4 | 16 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | [12 empty] | 536 |  | 0 | 128 | 144 | 144 | 120 | 0 | 0 | 0 | 0 |  | 536 |  | 20 | 144 | 144 | 144 | 84 | 0 | 0 | 0 | 0 |  | 536 | 114 | 13224 | 16416 | 16416 | 15048 | 0 | 61104
4 | Cheryl Hofmann | QA Testing Manager | 134 |  |  | 16 | 120 | 120 | 104 | 112 | 120 | 120 | 144 | 136 | 120 | 128 | 152 | 152 | 136 | 128 | 116 | 116 | 104 | 104 | 120 | 120 | 128 | 136 | 128 | 136 | 112 | 112 | 120 | 120 | 120 | 112 | 128 | 120 | 136 | 136 | 96 | 144 | 104 | 128 | 80 | 104 | 96 | 128 | 160 | 144 | [12 empty] | 5416 |  | 0 | 1240 | 1512 | 1480 | 1184 | 0 | 0 | 0 | 0 |  | 5416 |  | 136 | 1544 | 1448 | 1448 | 840 | 0 | 0 | 0 | 0 |  | 5416 | 134 | 149008 | 201536 | 198320 | 176880 | 0 | 725744
5 | Rachel Hernandez | QA UAT Lead | 134 |  |  | 16 | 128 | 136 | 104 | 112 | 120 | 120 | 144 | 136 | 120 | 128 | 152 | 152 | 136 | 108 | 96 | 116 | 104 | 104 | 120 | 8 | 8 | 8 | 8 | 8 | 8 | 112 | 120 | 120 | 120 | 112 | 112 | 120 | 136 | 136 | 96 | 144 | 104 | 128 | 80 | 104 | 96 | 128 | 160 | 144 | [12 empty] | 4672 |  | 0 | 1264 | 1112 | 1112 | 1184 | 0 | 0 | 0 | 0 |  | 4672 |  | 144 | 1560 | 696 | 1432 | 840 | 0 | 0 | 0 | 0 |  | 4672 | 134 | 152224 | 165088 | 131856 | 176880 | 0 | 626048
6 | Donna Smith | QA Independent Tester/UAT Leader | 114 |  |  | 160 | 160 | 168 | 144 | 160 | 168 | 152 | 176 | 168 | 152 | 160 | 168 | 160 | 144 | 136 | 160 | 136 | 112 | 144 | 152 | 128 | 160 | 160 | 136 | 176 | 152 | 128 | 152 | 144 | 136 | 144 | 152 | 136 | 168 | 160 | 104 | 176 | 152 | 136 | 152 | 144 | 136 | 144 | 168 | 136 | [12 empty] | 6760 |  | 0 | 1768 | 1760 | 1784 | 1448 | 0 | 0 | 0 | 0 |  | 6760 |  | 320 | 1920 | 1752 | 1752 | 1016 | 0 | 0 | 0 | 0 |  | 6760 | 114 | 183312 | 200640 | 203376 | 183312 | 0 | 770640
7 | Kim Sinclair | QA Independent Tester | 99 |  |  | 160 | 160 | 168 | 144 | 160 | 168 | 152 | 176 | 168 | 152 | 160 | 168 | 168 | 160 | 160 | 160 | 160 | 152 | 144 | 176 | 168 | 160 | 168 | 160 | 176 | 160 | 152 | 152 | 152 | 160 | 144 | 160 | 160 | 168 | 168 | 152 | 176 | 160 | 160 | 152 | 152 | 160 | 144 | 176 | 160 | [12 empty] | 7216 |  | 0 | 1768 | 1944 | 1912 | 1592 | 0 | 0 | 0 | 0 |  | 7216 | IFG | 320 | 1944 | 1944 | 1904 | 1104 | 0 | 0 | 0 | 0 |  | 7216 | 99 | 159192 | 191664 | 189288 | 174240 | 0 | 714384 | IFG
8 | Sindura Kompulira | QA Independent Tester/UAT Leader | 114 |  |  | 160 | 160 | 168 | 144 | 160 | 168 | 152 | 176 | 168 | 152 | 160 | 168 | 168 | 160 | 118 | 118 | 144 | 136 | 144 | 160 | [6 empty] | 152 | 152 | 152 | 160 | 144 | 160 | 160 | 168 | 168 | 152 | 176 | 160 | 160 | 152 | 152 | 160 | 144 | 176 | 160 | [12 empty] | 6092 |  | 0 | 1768 | 1316 | 1416 | 1592 | 0 | 0 | 0 | 0 |  | 6092 | IFG | 320 | 1944 | 820 | 1904 | 1104 | 0 | 0 | 0 | 0 |  | 6092 | 114 | 183312 | 168264 | 142272 | 200640 | 0 | 694488 | IFG
9 | Lalitha Ramabholta | QA Independent Tester/UAT Leader | 114 |  |  | 160 | 160 | 168 | 144 | 160 | 168 | 152 | 176 | 168 | 152 | 160 | 168 | 168 | 160 | 160 | 160 | 160 | 152 | 144 | 176 | [6 empty] | 152 | 152 | 152 | 160 | 144 | 160 | 160 | 168 | 168 | 152 | 176 | 160 | 160 | 152 | 152 | 160 | 144 | 176 | 160 | [12 empty] | 6224 |  | 0 | 1768 | 1448 | 1416 | 1592 | 0 | 0 | 0 | 0 |  | 6224 | IFG | 320 | 1944 | 952 | 1904 | 1104 | 0 | 0 | 0 | 0 |  | 6224 | 114 | 183312 | 183312 | 142272 | 200640 | 0 | 709536 | IFG
10 | Pandu Gupta | QA Business Analyst/Tester | 114 |  |  |  | 8 | 32 | 24 | 8 | 24 | 8 | 24 | 8 | 24 | 16 | 40 | 104 | 96 | 96 | 112 | 112 | 136 | 128 | 160 | 52 | 44 | 20 | 12 | 60 | 12 | 104 | 36 | 36 | 44 | 28 | 44 | 36 | 52 | 52 | 12 | 60 | 20 | 44 | 8 | 20 | 12 | 44 | 76 | 60 | [12 empty] | 2148 |  | 0 | 176 | 1100 | 516 | 356 | 0 | 0 | 0 | 0 |  | 2148 |  | 8 | 408 | 944 | 524 | 264 | 0 | 0 | 0 | 0 |  | 2148 | 114 | 18240 | 124944 | 55176 | 46512 | 0 | 244872
11 | Julie Hereth | QA Sr. Administrative Assistant | 45 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | [12 empty] | 180 |  | 0 | 44 | 48 | 48 | 40 | 0 | 0 | 0 | 0 |  | 180 |  | 8 | 48 | 48 | 48 | 28 | 0 | 0 | 0 | 0 |  | 180 | 45 | 1800 | 2160 | 2160 | 1980 | 0 | 8100
12 | Wendy Battermann | QA Executive | 154 |  |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | [12 empty] | 88 |  | 0 | 20 | 24 | 24 | 20 | 0 | 0 | 0 | 0 |  | 88 |  | 2 | 24 | 24 | 24 | 14 | 0 | 0 | 0 | 0 |  | 88 | 154 | 2772 | 3696 | 3696 | 3388 | 0 | 13552
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #8 - UAT Weekly Report (Weekly) |  |  | 2021-04-01: Due; 2021-05-01: Due; 2021-06-01: Due; 2021-07-01: Due; 2021-08-01: Due; 2021-09-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 138544 | 284704 | 0 | 0 | 423248 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2021-04-01: 4; 2021-05-01: 4; 2021-06-01: 4; 2021-07-01: 4; 2021-08-01: 4; 2021-09-01: 4 | 24 |  | 0 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0 |  | 24 |  | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 |  | 24 | 154 | 0 | 1232 | 2464 | 0 | 0 | 3696
2 | Timothy King | QA PMO Specialist | 114 | 2021-04-01: 4; 2021-05-01: 4; 2021-06-01: 4; 2021-07-01: 4; 2021-08-01: 4; 2021-09-01: 4 | 24 |  | 0 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0 |  | 24 |  | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 |  | 24 | 114 | 0 | 912 | 1824 | 0 | 0 | 2736
3 | Cheryl Hofmann | QA Testing Manager | 134 | 2021-04-01: 16; 2021-05-01: 16; 2021-06-01: 16; 2021-07-01: 16; 2021-08-01: 16; 2021-09-01: 16 | 96 |  | 0 | 0 | 48 | 48 | 0 | 0 | 0 | 0 | 0 |  | 96 |  | 0 | 0 | 96 | 0 | 0 | 0 | 0 | 0 | 0 |  | 96 | 134 | 0 | 4288 | 8576 | 0 | 0 | 12864
4 | Rachel Hernandez | QA UAT Lead | 134 | 2021-04-01: 128; 2021-05-01: 136; 2021-06-01: 144; 2021-07-01: 136; 2021-08-01: 144; 2021-09-01: 120 | 808 |  | 0 | 0 | 408 | 400 | 0 | 0 | 0 | 0 | 0 |  | 808 |  | 0 | 0 | 808 | 0 | 0 | 0 | 0 | 0 | 0 |  | 808 | 134 | 0 | 35376 | 72896 | 0 | 0 | 108272
5 | Sindura Kompulira | QA Independent Tester/UAT Leader | 114 | 2021-04-01: 152; 2021-05-01: 160; 2021-06-01: 168; 2021-07-01: 160; 2021-08-01: 176; 2021-09-01: 160 | 976 |  | 0 | 0 | 480 | 496 | 0 | 0 | 0 | 0 | 0 |  | 976 | IFG | 0 | 0 | 976 | 0 | 0 | 0 | 0 | 0 | 0 |  | 976 | 114 | 0 | 35568 | 75696 | 0 | 0 | 111264 | IFG
6 | Lalitha Ramabholta | QA Independent Tester/UAT Leader | 114 | 2021-04-01: 168; 2021-05-01: 160; 2021-06-01: 168; 2021-07-01: 160; 2021-08-01: 176; 2021-09-01: 160 | 992 |  | 0 | 0 | 496 | 496 | 0 | 0 | 0 | 0 | 0 |  | 992 | IFG | 0 | 0 | 992 | 0 | 0 | 0 | 0 | 0 | 0 |  | 992 | 114 | 0 | 37392 | 75696 | 0 | 0 | 113088 | IFG
7 | Pandu Gupta | QA Business Analyst/Tester | 114 | 2021-04-01: 100; 2021-05-01: 100; 2021-06-01: 100; 2021-07-01: 100; 2021-08-01: 100; 2021-09-01: 100 | 600 |  | 0 | 0 | 300 | 300 | 0 | 0 | 0 | 0 | 0 |  | 600 |  | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 |  | 600 | 114 | 0 | 22800 | 45600 | 0 | 0 | 68400
8 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2021-04-01: 4; 2021-05-01: 4; 2021-06-01: 4; 2021-07-01: 4; 2021-08-01: 4; 2021-09-01: 4 | 24 |  | 0 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0 |  | 24 |  | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 |  | 24 | 45 | 0 | 360 | 720 | 0 | 0 | 1080
9 | Wendy Battermann | QA Executive | 154 | 2021-04-01: 2; 2021-05-01: 2; 2021-06-01: 2; 2021-07-01: 2; 2021-08-01: 2; 2021-09-01: 2 | 12 |  | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 |  | 12 |  | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 |  | 12 | 154 | 0 | 616 | 1232 | 0 | 0 | 1848
10 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #9 - QA Security Review Plan |  |  | 2020-10-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 83660 | 0 | 0 | 0 | 83660 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2020-08-01: 8; 2020-09-01: 16; 2020-10-01: 16 | 40 |  | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 |  | 0 | 24 | 16 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 | 154 | 0 | 6160 | 0 | 0 | 0 | 6160
2 | Don Coffey | QA Technical Manager | 144 | 2020-08-01: 16; 2020-09-01: 30; 2020-10-01: 30 | 76 |  | 0 | 0 | 76 | 0 | 0 | 0 | 0 | 0 | 0 |  | 76 |  | 0 | 46 | 30 | 0 | 0 | 0 | 0 | 0 | 0 |  | 76 | 144 | 0 | 10944 | 0 | 0 | 0 | 10944
3 | Greg FitzGerald | QA Technical Lead | 139 | 2020-08-01: 32; 2020-09-01: 60; 2020-10-01: 60 | 152 |  | 0 | 0 | 152 | 0 | 0 | 0 | 0 | 0 | 0 |  | 152 |  | 0 | 92 | 60 | 0 | 0 | 0 | 0 | 0 | 0 |  | 152 | 139 | 0 | 21128 | 0 | 0 | 0 | 21128
4 | Dustin Lish | QA Technical Lead | 139 | 2020-08-01: 32; 2020-09-01: 60; 2020-10-01: 60 | 152 |  | 0 | 0 | 152 | 0 | 0 | 0 | 0 | 0 | 0 |  | 152 | IFG | 0 | 92 | 60 | 0 | 0 | 0 | 0 | 0 | 0 |  | 152 | 139 | 0 | 21128 | 0 | 0 | 0 | 21128 | IFG
5 | Timothy King | QA PMO Specialist | 114 | 2020-08-01: 16; 2020-09-01: 24; 2020-10-01: 24 | 64 |  | 0 | 0 | 64 | 0 | 0 | 0 | 0 | 0 | 0 |  | 64 |  | 0 | 40 | 24 | 0 | 0 | 0 | 0 | 0 | 0 |  | 64 | 114 | 0 | 7296 | 0 | 0 | 0 | 7296
6 | Raj Ganesh | QA Conversion Lead | 114 | 2020-08-01: 16; 2020-09-01: 24; 2020-10-01: 24 | 64 |  | 0 | 0 | 64 | 0 | 0 | 0 | 0 | 0 | 0 |  | 64 |  | 0 | 40 | 24 | 0 | 0 | 0 | 0 | 0 | 0 |  | 64 | 114 | 0 | 7296 | 0 | 0 | 0 | 7296
7 | Donna Smith | QA Independent Tester/UAT Leader | 114 | 2020-08-01: 8; 2020-09-01: 16; 2020-10-01: 24 | 48 |  | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 |  | 48 |  | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 |  | 48 | 114 | 0 | 5472 | 0 | 0 | 0 | 5472
8 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2020-08-01: 4; 2020-09-01: 4; 2020-10-01: 4 | 12 |  | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 |  | 12 |  | 0 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 12 | 45 | 0 | 540 | 0 | 0 | 0 | 540
9 | Frank Ono | QA Executive | 154 | 2020-08-01: 8; 2020-09-01: 8; 2020-10-01: 8 | 24 |  | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 |  | 24 | IFG | 0 | 16 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 24 | 154 | 0 | 3696 | 0 | 0 | 0 | 3696 | IFG
10 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #10 - Quarterly QA Security Report (Quarterly) |  |  | 2021-01-01: Due; 2021-04-01: Due; 2021-07-01: Due; 2021-10-01: Due; 2022-01-01: Due; 2022-04-01: Due; 2022-07-01: Due; 2022-10-01: Due; 2023-01-01: Due; 2023-04-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 84336 | 168672 | 133088 | 0 | 386096 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2020-12-01: 4; 2021-01-01: 16; 2021-03-01: 4; 2021-04-01: 16; 2021-06-01: 4; 2021-07-01: 16; 2021-09-01: 4; 2021-10-01: 16; 2021-12-01: 4; 2022-01-01: 16; 2022-03-01: 4; 2022-04-01: 16; 2022-06-01: 4; 2022-07-01: 16; 2022-09-01: 4; 2022-10-01: 16; 2022-12-01: 4; 2023-01-01: 16; 2023-03-01: 4; 2023-04-01: 16 | 200 |  | 0 | 0 | 44 | 80 | 76 | 0 | 0 | 0 | 0 |  | 200 |  | 0 | 0 | 64 | 80 | 56 | 0 | 0 | 0 | 0 |  | 200 | 154 | 0 | 6160 | 12320 | 12320 | 0 | 30800
2 | Don Coffey | QA Technical Manager | 144 | 2020-12-01: 32; 2021-01-01: 32; 2021-03-01: 32; 2021-04-01: 32; 2021-06-01: 32; 2021-07-01: 32; 2021-09-01: 32; 2021-10-01: 32; 2021-12-01: 32; 2022-01-01: 32; 2022-03-01: 32; 2022-04-01: 32; 2022-06-01: 32; 2022-07-01: 32; 2022-09-01: 32; 2022-10-01: 32; 2022-12-01: 32; 2023-01-01: 32; 2023-03-01: 32; 2023-04-01: 32 | 640 |  | 0 | 0 | 160 | 256 | 224 | 0 | 0 | 0 | 0 |  | 640 |  | 0 | 0 | 224 | 256 | 160 | 0 | 0 | 0 | 0 |  | 640 | 144 | 0 | 18432 | 36864 | 36864 | 0 | 92160
3 | Greg FitzGerald | QA Technical Lead | 139 | 2020-12-01: 32; 2021-01-01: 32; 2021-03-01: 32; 2021-04-01: 32; 2021-06-01: 32; 2021-07-01: 32; 2021-09-01: 32; 2021-10-01: 32; 2021-12-01: 32; 2022-01-01: 32; 2022-03-01: 32; 2022-04-01: 32; 2022-06-01: 24; 2022-07-01: 24; 2022-09-01: 24; 2022-10-01: 24; 2022-12-01: 24; 2023-01-01: 24; 2023-03-01: 24; 2023-04-01: 24 | 576 |  | 0 | 0 | 160 | 248 | 168 | 0 | 0 | 0 | 0 |  | 576 |  | 0 | 0 | 224 | 232 | 120 | 0 | 0 | 0 | 0 |  | 576 | 139 | 0 | 17792 | 35584 | 26688 | 0 | 80064
4 | Dustin Lish | QA Technical Lead | 139 | 2020-12-01: 32; 2021-01-01: 32; 2021-03-01: 32; 2021-04-01: 32; 2021-06-01: 32; 2021-07-01: 32; 2021-09-01: 32; 2021-10-01: 32; 2021-12-01: 32; 2022-01-01: 32; 2022-03-01: 32; 2022-04-01: 32; 2022-06-01: 8; 2022-07-01: 8; 2022-09-01: 8; 2022-10-01: 8; 2022-12-01: 8; 2023-01-01: 8; 2023-03-01: 8; 2023-04-01: 8 | 448 |  | 0 | 0 | 160 | 232 | 56 | 0 | 0 | 0 | 0 |  | 448 | IFG | 0 | 0 | 224 | 184 | 40 | 0 | 0 | 0 | 0 |  | 448 | 139 | 0 | 17792 | 35584 | 8896 | 0 | 62272 | IG
5 | Timothy King | QA PMO Specialist | 114 | 2020-12-01: 4; 2021-01-01: 24; 2021-03-01: 4; 2021-04-01: 24; 2021-06-01: 4; 2021-07-01: 24; 2021-09-01: 4; 2021-10-01: 24; 2021-12-01: 4; 2022-01-01: 24; 2022-03-01: 4; 2022-04-01: 24; 2022-06-01: 4; 2022-07-01: 24; 2022-09-01: 4; 2022-10-01: 24; 2022-12-01: 4; 2023-01-01: 24; 2023-03-01: 4; 2023-04-01: 24 | 280 |  | 0 | 0 | 60 | 112 | 108 | 0 | 0 | 0 | 0 |  | 280 |  | 0 | 0 | 88 | 112 | 80 | 0 | 0 | 0 | 0 |  | 280 | 114 | 0 | 6384 | 12768 | 12768 | 0 | 31920
6 | Raj Ganesh | QA Conversion Lead | 114 | 2020-12-01: 16; 2021-01-01: 16; 2021-03-01: 16; 2021-04-01: 16; 2021-06-01: 16; 2021-07-01: 16; 2021-09-01: 16; 2021-10-01: 16; 2021-12-01: 16; 2022-01-01: 16; 2022-03-01: 16; 2022-04-01: 16; 2022-06-01: 16; 2022-07-01: 16; 2022-09-01: 16; 2022-10-01: 16; 2022-12-01: 16; 2023-01-01: 16; 2023-03-01: 16; 2023-04-01: 16 | 320 |  | 0 | 0 | 80 | 128 | 112 | 0 | 0 | 0 | 0 |  | 320 |  | 0 | 0 | 112 | 128 | 80 | 0 | 0 | 0 | 0 |  | 320 | 114 | 0 | 7296 | 14592 | 14592 | 0 | 36480
7 | Donna Smith | QA Independent Tester/UAT Leader | 114 | 2020-12-01: 8; 2021-01-01: 24; 2021-03-01: 8; 2021-04-01: 24; 2021-06-01: 8; 2021-07-01: 24; 2021-09-01: 8; 2021-10-01: 24; 2021-12-01: 8; 2022-01-01: 24; 2022-03-01: 8; 2022-04-01: 24; 2022-06-01: 8; 2022-07-01: 24; 2022-09-01: 8; 2022-10-01: 24; 2022-12-01: 8; 2023-01-01: 24; 2023-03-01: 8; 2023-04-01: 24 | 320 |  | 0 | 0 | 72 | 128 | 120 | 0 | 0 | 0 | 0 |  | 320 |  | 0 | 0 | 104 | 128 | 88 | 0 | 0 | 0 | 0 |  | 320 | 114 | 0 | 7296 | 14592 | 14592 | 0 | 36480
8 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2020-12-01: 4; 2021-01-01: 4; 2021-03-01: 4; 2021-04-01: 4; 2021-06-01: 4; 2021-07-01: 4; 2021-09-01: 4; 2021-10-01: 4; 2021-12-01: 4; 2022-01-01: 4; 2022-03-01: 4; 2022-04-01: 4; 2022-06-01: 4; 2022-07-01: 4; 2022-09-01: 4; 2022-10-01: 4; 2022-12-01: 4; 2023-01-01: 4; 2023-03-01: 4; 2023-04-01: 4 | 80 |  | 0 | 0 | 20 | 32 | 28 | 0 | 0 | 0 | 0 |  | 80 |  | 0 | 0 | 28 | 32 | 20 | 0 | 0 | 0 | 0 |  | 80 | 45 | 0 | 720 | 1440 | 1440 | 0 | 3600
9 | Frank Ono | QA Executive | 154 | 2021-01-01: 8; 2021-04-01: 8; 2021-07-01: 8; 2021-10-01: 8; 2022-01-01: 8; 2022-04-01: 8; 2022-07-01: 8; 2022-10-01: 8; 2023-01-01: 8; 2023-04-01: 8 | 80 |  | 0 | 0 | 16 | 32 | 32 | 0 | 0 | 0 | 0 |  | 80 | IFG | 0 | 0 | 24 | 32 | 24 | 0 | 0 | 0 | 0 |  | 80 | 154 | 0 | 2464 | 4928 | 4928 | 0 | 12320 | IFG
10 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #11 - Assessment of DD&I Vendor CalSAWS Migration Project Control Document Initial |  |  | 2019-08-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 22508 | 0 | 0 | 0 | 0 | 22508 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2019-07-01: 16; 2019-08-01: 8 | 24 |  | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 24 |  | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 24 | 154 | 3696 | 0 | 0 | 0 | 0 | 3696
2 | Beena Amarnath | QA PMO Lead | 134 | 2019-07-01: 16; 2019-08-01: 36 | 52 |  | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 52 |  | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 52 | 134 | 6968 | 0 | 0 | 0 | 0 | 6968
3 | Timothy King | QA PMO Specialist | 114 | 2019-07-01: 10; 2019-08-01: 12 | 22 |  | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 22 |  | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 22 | 114 | 2508 | 0 | 0 | 0 | 0 | 2508
4 | Kristin Pepper | QA Functional Manager | 134 | 2019-07-01: 8; 2019-08-01: 24 | 32 |  | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 |  | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 | 134 | 4288 | 0 | 0 | 0 | 0 | 4288
5 | Don Coffey | QA Technical Manager | 144 | 2019-07-01: 8; 2019-08-01: 16 | 24 |  | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 24 |  | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 24 | 144 | 3456 | 0 | 0 | 0 | 0 | 3456
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2019-07-01: 4; 2019-08-01: 4 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 45 | 360 | 0 | 0 | 0 | 0 | 360
7 | Wendy Battermann | QA Executive | 154 | 2019-08-01: 8 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 154 | 1232 | 0 | 0 | 0 | 0 | 1232
8 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #12 - Assessment of DD&I Vendor CalSAWS Migration Work Plan Update (Monthly) |  |  |  | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 89512 | 97824 | 97824 | 89672 | 0 | 374832 | subtotal
1 | Dan Dean | QA Project Manager | 154 |  | 8 | 8 | 32 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | [12 empty] | 1080 |  | 0 | 264 | 288 | 288 | 240 | 0 | 0 | 0 | 0 |  | 1080 |  | 48 | 288 | 288 | 288 | 168 | 0 | 0 | 0 | 0 |  | 1080 | 154 | 36960 | 44352 | 44352 | 40656 | 0 | 166320
2 | Beena Amarnath | QA PMO Lead | 134 |  | 24 | 32 | 32 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | [12 empty] | 776 |  | 0 | 232 | 192 | 192 | 160 | 0 | 0 | 0 | 0 |  | 776 |  | 88 | 192 | 192 | 192 | 112 | 0 | 0 | 0 | 0 |  | 776 | 134 | 28944 | 25728 | 25728 | 23584 | 0 | 103984
3 | Timothy King | QA PMO Specialist | 114 |  | 16 | 8 | 16 | 8 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | [12 empty] | 720 |  | 0 | 176 | 192 | 192 | 160 | 0 | 0 | 0 | 0 |  | 720 |  | 40 | 184 | 192 | 192 | 112 | 0 | 0 | 0 | 0 |  | 720 | 114 | 18240 | 21888 | 21888 | 20064 | 0 | 82080
4 | Julie Hereth | QA Sr. Administrative Assistant | 45 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | [12 empty] | 184 |  | 0 | 48 | 48 | 48 | 40 | 0 | 0 | 0 | 0 |  | 184 |  | 12 | 48 | 48 | 48 | 28 | 0 | 0 | 0 | 0 |  | 184 | 45 | 1980 | 2160 | 2160 | 1980 | 0 | 8280
5 | Wendy Battermann | QA Executive | 154 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | [12 empty] | 92 |  | 0 | 24 | 24 | 24 | 20 | 0 | 0 | 0 | 0 |  | 92 |  | 6 | 24 | 24 | 24 | 14 | 0 | 0 | 0 | 0 |  | 92 | 154 | 3388 | 3696 | 3696 | 3388 | 0 | 14168
6 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #13 - Assessment of DD&I Vendor CalSAWS General Design |  |  | 2019-08-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 37692 | 0 | 0 | 0 | 0 | 37692 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2019-07-01: 6; 2019-08-01: 8 | 14 |  | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 14 |  | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 14 | 154 | 2156 | 0 | 0 | 0 | 0 | 2156
2 | Timothy King | QA PMO Specialist | 114 | 2019-07-01: 6; 2019-08-01: 8 | 14 |  | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 14 |  | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 14 | 114 | 1596 | 0 | 0 | 0 | 0 | 1596
3 | Kristin Pepper | QA Functional Manager | 134 | 2019-07-01: 8; 2019-08-01: 16 | 24 |  | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 24 |  | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 24 | 134 | 3216 | 0 | 0 | 0 | 0 | 3216
4 | Don Coffey | QA Technical Manager | 144 | 2019-07-01: 8; 2019-08-01: 32 | 40 |  | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 |  | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 | 144 | 5760 | 0 | 0 | 0 | 0 | 5760
5 | Abby Darrah | QA Implementation Manager | 134 | 2019-08-01: 32 | 32 |  | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 |  | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 | 134 | 4288 | 0 | 0 | 0 | 0 | 4288
6 | Cheryl Hofmann | QA Testing Manager | 134 | [59 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 134 | 0 | 0 | 0 | 0 | 0 | 0
7 | Rachel Hernandez | QA UAT Lead | 134 | [59 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 134 | 0 | 0 | 0 | 0 | 0 | 0
8 | Pandu Gupta | QA Business Analyst/Tester | 114 | 2019-07-01: 8; 2019-08-01: 48 | 56 |  | 0 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 56 |  | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 56 | 114 | 6384 | 0 | 0 | 0 | 0 | 6384
9 | Greg FitzGerald | QA Technical Lead | 139 | 2019-07-01: 16; 2019-08-01: 28 | 44 |  | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 44 |  | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 44 | 139 | 6116 | 0 | 0 | 0 | 0 | 6116
10 | Dustin Lish | QA Technical Lead | 139 | 2019-07-01: 4; 2019-08-01: 4 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | IFG | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 139 | 1112 | 0 | 0 | 0 | 0 | 1112 | IFG
11 | Raj Ganesh | QA Conversion Lead | 114 | 2019-07-01: 16; 2019-08-01: 32 | 48 |  | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 48 |  | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 48 | 114 | 5472 | 0 | 0 | 0 | 0 | 5472
12 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2019-07-01: 4; 2019-08-01: 4 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 45 | 360 | 0 | 0 | 0 | 0 | 360
13 | Frank Ono | QA Executive | 154 | 2019-08-01: 8 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | IFG | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 154 | 1232 | 0 | 0 | 0 | 0 | 1232
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #14 - Assessment of DD&I Vendor CalACES Master Conversion Plan |  |  | 2019-08-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 33908 | 0 | 0 | 0 | 0 | 33908 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2019-07-01: 4; 2019-08-01: 8 | 12 |  | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 12 |  | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 12 | 154 | 1848 | 0 | 0 | 0 | 0 | 1848
2 | Raj Ganesh | QA Conversion Lead | 114 | 2019-07-01: 52; 2019-08-01: 40 | 92 |  | 0 | 92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 92 |  | 92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 92 | 114 | 10488 | 0 | 0 | 0 | 0 | 10488
3 | Timothy King | QA PMO Specialist | 114 | 2019-07-01: 6; 2019-08-01: 16 | 22 |  | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 22 |  | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 22 | 114 | 2508 | 0 | 0 | 0 | 0 | 2508
4 | Kristin Pepper | QA Functional Manager | 134 | 2019-07-01: 16; 2019-08-01: 16 | 32 |  | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 |  | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 | 134 | 4288 | 0 | 0 | 0 | 0 | 4288
5 | Don Coffey | QA Technical Manager | 144 | 2019-07-01: 16; 2019-08-01: 16 | 32 |  | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 |  | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 | 144 | 4608 | 0 | 0 | 0 | 0 | 4608
6 | Abby Darrah | QA Implementation Manager | 134 | 2019-08-01: 32 | 32 |  | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 |  | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 | 134 | 4288 | 0 | 0 | 0 | 0 | 4288
7 | Cheryl Hofmann | QA Testing Manager | 134 | 2019-08-01: 16 | 16 |  | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16 |  | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16 | 134 | 2144 | 0 | 0 | 0 | 0 | 2144
8 | Rachel Hernandez | QA UAT Lead | 134 | 2019-08-01: 16 | 16 |  | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16 |  | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16 | 134 | 2144 | 0 | 0 | 0 | 0 | 2144
9 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2019-07-01: 4; 2019-08-01: 4 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 45 | 360 | 0 | 0 | 0 | 0 | 360
10 | Frank Ono | QA Executive | 154 | 2019-08-01: 8 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | IFG | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 154 | 1232 | 0 | 0 | 0 | 0 | 1232 | IFG
11 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #15 - Assessment of DD&I Vendor Application Development Preparation and Installation Plan |  |  | 2019-08-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 28124 | 0 | 0 | 0 | 0 | 28124 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2019-07-01: 4; 2019-08-01: 12 | 16 |  | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16 |  | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16 | 154 | 2464 | 0 | 0 | 0 | 0 | 2464
2 | Don Coffey | QA Technical Manager | 144 | 2019-07-01: 24; 2019-08-01: 32 | 56 |  | 0 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 56 |  | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 56 | 144 | 8064 | 0 | 0 | 0 | 0 | 8064
3 | Greg FitzGerald | QA Technical Lead | 139 | 2019-07-01: 16; 2019-08-01: 60 | 76 |  | 0 | 76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 76 |  | 76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 76 | 139 | 10564 | 0 | 0 | 0 | 0 | 10564
4 | Dustin Lish | QA Technical Lead | 139 | 2019-07-01: 8; 2019-08-01: 8 | 16 |  | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16 | IFG | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16 | 139 | 2224 | 0 | 0 | 0 | 0 | 2224 | IFG
5 | Abby Darrah | QA Implementation Manager | 134 | 2019-08-01: 24 | 24 |  | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 24 |  | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 24 | 134 | 3216 | 0 | 0 | 0 | 0 | 3216
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2019-07-01: 4; 2019-08-01: 4 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 45 | 360 | 0 | 0 | 0 | 0 | 360
7 | Frank Ono | QA Executive | 154 | 2019-08-01: 8 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | IFG | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 154 | 1232 | 0 | 0 | 0 | 0 | 1232 | IFG
8 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #16 - Assessment of DD&I Vendor CalSAWS Master Test Plan |  |  | 2019-07-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 8528 | 0 | 0 | 0 | 0 | 8528 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2019-07-01: 4 | 4 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | 154 | 616 | 0 | 0 | 0 | 0 | 616
2 | Timothy King | QA PMO Specialist | 114 | 2019-07-01: 6 | 6 |  | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 6 |  | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 6 | 114 | 684 | 0 | 0 | 0 | 0 | 684
3 | Cheryl Hofmann | QA Testing Manager | 134 | 2019-07-01: 24 | 24 |  | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 24 |  | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 24 | 134 | 3216 | 0 | 0 | 0 | 0 | 3216
4 | Rachel Hernandez | QA UAT Lead | 134 | 2019-07-01: 24 | 24 |  | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 24 |  | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 24 | 134 | 3216 | 0 | 0 | 0 | 0 | 3216
5 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2019-07-01: 4 | 4 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | 45 | 180 | 0 | 0 | 0 | 0 | 180
6 | Wendy Battermann | QA Executive | 154 | 2019-07-01: 4 | 4 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | 154 | 616 | 0 | 0 | 0 | 0 | 616
7 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #17 - Assessment of DD&I Vendor CalSAWS Business Architecture Design |  |  | 2019-07-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 16568 | 0 | 0 | 0 | 0 | 16568 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2019-07-01: 8 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 154 | 1232 | 0 | 0 | 0 | 0 | 1232
2 | Timothy King | QA PMO Specialist | 114 | 2019-07-01: 6 | 6 |  | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 6 |  | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 6 | 114 | 684 | 0 | 0 | 0 | 0 | 684
3 | Kristin Pepper | QA Functional Manager | 134 | 2019-07-01: 16 | 16 |  | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16 |  | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16 | 134 | 2144 | 0 | 0 | 0 | 0 | 2144
4 | Don Coffey | QA Technical Manager | 144 | 2019-07-01: 24 | 24 |  | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 24 |  | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 24 | 144 | 3456 | 0 | 0 | 0 | 0 | 3456
5 | Pandu Gupta | QA Business Analyst/Tester | 114 | 2019-07-01: 12 | 12 |  | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 12 |  | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 12 | 114 | 1368 | 0 | 0 | 0 | 0 | 1368
6 | Greg FitzGerald | QA Technical Lead | 139 | 2019-07-01: 24 | 24 |  | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 24 |  | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 24 | 139 | 3336 | 0 | 0 | 0 | 0 | 3336
7 | Dustin Lish | QA Technical Lead | 139 | 2019-07-01: 8 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | IFG | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 139 | 1112 | 0 | 0 | 0 | 0 | 1112 | IFG
8 | Raj Ganesh | QA Conversion Lead | 114 | 2019-07-01: 16 | 16 |  | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16 |  | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16 | 114 | 1824 | 0 | 0 | 0 | 0 | 1824
9 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2019-07-01: 4 | 4 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | 45 | 180 | 0 | 0 | 0 | 0 | 180
10 | Frank Ono | QA Executive | 154 | 2019-07-01: 8 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | IFG | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 154 | 1232 | 0 | 0 | 0 | 0 | 1232
11 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #18 - Assessment of DD&I Vendor CalSAWS General Design |  |  | 2019-07-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 18700 | 0 | 0 | 0 | 0 | 18700 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2019-07-01: 8 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 154 | 1232 | 0 | 0 | 0 | 0 | 1232
2 | Timothy King | QA PMO Specialist | 114 | 2019-07-01: 6 | 6 |  | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 6 |  | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 6 | 114 | 684 | 0 | 0 | 0 | 0 | 684
3 | Kristin Pepper | QA Functional Manager | 134 | 2019-07-01: 16 | 16 |  | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16 |  | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16 | 134 | 2144 | 0 | 0 | 0 | 0 | 2144
4 | Don Coffey | QA Technical Manager | 144 | 2019-07-01: 16 | 16 |  | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16 |  | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16 | 144 | 2304 | 0 | 0 | 0 | 0 | 2304
5 | Pandu Gupta | QA Business Analyst/Tester | 114 | 2019-07-01: 22 | 22 |  | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 22 |  | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 22 | 114 | 2508 | 0 | 0 | 0 | 0 | 2508
6 | Greg FitzGerald | QA Technical Lead | 139 | 2019-07-01: 24 | 24 |  | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 24 |  | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 24 | 139 | 3336 | 0 | 0 | 0 | 0 | 3336 | I
7 | Dustin Lish | QA Technical Lead | 139 | 2019-07-01: 8 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | IFG | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 139 | 1112 | 0 | 0 | 0 | 0 | 1112 | IFG
8 | Raj Ganesh | QA Conversion Lead | 114 | 2019-07-01: 16 | 16 |  | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16 |  | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16 | 114 | 1824 | 0 | 0 | 0 | 0 | 1824
9 | Cheryl Hofmann | QA Testing Manager | 134 | 2019-07-01: 8 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 134 | 1072 | 0 | 0 | 0 | 0 | 1072
10 | Rachel Hernandez | QA UAT Lead | 134 | 2019-07-01: 8 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 134 | 1072 | 0 | 0 | 0 | 0 | 1072
11 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2019-07-01: 4 | 4 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | 45 | 180 | 0 | 0 | 0 | 0 | 180
12 | Frank Ono | QA Executive | 154 | 2019-07-01: 8 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | IFG | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 154 | 1232 | 0 | 0 | 0 | 0 | 1232
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #19 - Assessment of DD&I Vendor CalSAWS General Design |  |  | 2019-08-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 59976 | 0 | 0 | 0 | 0 | 59976 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2019-08-01: 16 | 16 |  | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16 |  | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16 | 154 | 2464 | 0 | 0 | 0 | 0 | 2464
2 | Timothy King | QA PMO Specialist | 114 | 2019-08-01: 24 | 24 |  | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 24 |  | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 24 | 114 | 2736 | 0 | 0 | 0 | 0 | 2736
3 | Kristin Pepper | QA Functional Manager | 134 | 2019-07-01: 40; 2019-08-01: 24 | 64 |  | 0 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 64 |  | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 64 | 134 | 8576 | 0 | 0 | 0 | 0 | 8576
4 | Don Coffey | QA Technical Manager | 144 | 2019-07-01: 24; 2019-08-01: 16 | 40 |  | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 |  | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 | 144 | 5760 | 0 | 0 | 0 | 0 | 5760
5 | Pandu Gupta | QA Business Analyst/Tester | 114 | 2019-07-01: 54; 2019-08-01: 48 | 102 |  | 0 | 102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 102 |  | 102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 102 | 114 | 11628 | 0 | 0 | 0 | 0 | 11628
6 | Greg FitzGerald | QA Technical Lead | 139 | 2019-07-01: 56; 2019-08-01: 24 | 80 |  | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 80 |  | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 80 | 139 | 11120 | 0 | 0 | 0 | 0 | 11120
7 | Dustin Lish | QA Technical Lead | 139 | 2019-07-01: 8; 2019-08-01: 8 | 16 |  | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16 | IFG | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16 | 139 | 2224 | 0 | 0 | 0 | 0 | 2224 | IFG
8 | Raj Ganesh | QA Conversion Lead | 114 | 2019-07-01: 28; 2019-08-01: 40 | 68 |  | 0 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 68 |  | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 68 | 114 | 7752 | 0 | 0 | 0 | 0 | 7752
9 | Cheryl Hofmann | QA Testing Manager | 134 | 2019-07-01: 8; 2019-08-01: 16 | 24 |  | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 24 |  | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 24 | 134 | 3216 | 0 | 0 | 0 | 0 | 3216
10 | Rachel Hernandez | QA UAT Lead | 134 | 2019-07-01: 8; 2019-08-01: 16 | 24 |  | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 24 |  | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 24 | 134 | 3216 | 0 | 0 | 0 | 0 | 3216
11 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2019-07-01: 4; 2019-08-01: 4 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 45 | 360 | 0 | 0 | 0 | 0 | 360
12 | Frank Ono | QA Executive | 154 | 2019-08-01: 6 | 6 |  | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 6 | IFG | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 6 | 154 | 924 | 0 | 0 | 0 | 0 | 924
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #20 - Assessment of DD&I Vendor C-IV Master Training Plan |  |  | 2019-08-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 17624 | 0 | 0 | 0 | 0 | 17624 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2019-08-01: 8 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 154 | 1232 | 0 | 0 | 0 | 0 | 1232
2 | Timothy King | QA PMO Specialist | 114 | 2019-08-01: 24 | 24 |  | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 24 |  | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 24 | 114 | 2736 | 0 | 0 | 0 | 0 | 2736
3 | Abby Darrah | QA Implementation Manager | 134 | 2019-08-01: 16 | 16 |  | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16 |  | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16 | 134 | 2144 | 0 | 0 | 0 | 0 | 2144
4 | Ivan Parra | QA Implementation Lead | 124 | [59 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 124 | 0 | 0 | 0 | 0 | 0 | 0
5 | Gail Brown | QA Implementation Lead | 124 | 2019-08-01: 80 | 80 |  | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 80 | IFG | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 80 | 124 | 9920 | 0 | 0 | 0 | 0 | 9920
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2019-07-01: 4; 2019-08-01: 4 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 45 | 360 | 0 | 0 | 0 | 0 | 360
7 | Wendy Battermann | QA Executive | 154 | 2019-08-01: 8 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 154 | 1232 | 0 | 0 | 0 | 0 | 1232
8 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #21 - Assessment of DD&I Vendor CalWIN/CalSAWS Master Conversion Plan |  |  | 2019-08-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 27636 | 0 | 0 | 0 | 0 | 27636 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2019-08-01: 8 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 154 | 1232 | 0 | 0 | 0 | 0 | 1232
2 | Raj Ganesh | QA Conversion Lead | 114 | 2019-07-01: 28; 2019-08-01: 40 | 68 |  | 0 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 68 |  | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 68 | 114 | 7752 | 0 | 0 | 0 | 0 | 7752
3 | Timothy King | QA PMO Specialist | 114 | 2019-08-01: 28 | 28 |  | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28 |  | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28 | 114 | 3192 | 0 | 0 | 0 | 0 | 3192
4 | Kristin Pepper | QA Functional Manager | 134 | 2019-07-01: 24; 2019-08-01: 8 | 32 |  | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 |  | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 | 134 | 4288 | 0 | 0 | 0 | 0 | 4288
5 | Don Coffey | QA Technical Manager | 144 | 2019-07-01: 8; 2019-08-01: 16 | 24 |  | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 24 |  | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 24 | 144 | 3456 | 0 | 0 | 0 | 0 | 3456
6 | Abby Darrah | QA Implementation Manager | 134 | 2019-08-01: 16 | 16 |  | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16 |  | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16 | 134 | 2144 | 0 | 0 | 0 | 0 | 2144
7 | Cheryl Hofmann | QA Testing Manager | 134 | 2019-08-01: 16 | 16 |  | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16 |  | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16 | 134 | 2144 | 0 | 0 | 0 | 0 | 2144
8 | Rachel Hernandez | QA UAT Lead | 134 | 2019-08-01: 16 | 16 |  | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16 |  | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16 | 134 | 2144 | 0 | 0 | 0 | 0 | 2144
9 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2019-07-01: 4; 2019-08-01: 4 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 45 | 360 | 0 | 0 | 0 | 0 | 360
10 | Frank Ono | QA Executive | 154 | 2019-08-01: 6 | 6 |  | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 6 | IFG | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 6 | 154 | 924 | 0 | 0 | 0 | 0 | 924 | IFG
11 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #22 - Assessment of DD&I Vendor CalSAWS Requirements Traceability Matrix - Initial |  |  | 2019-10-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 31888 | 0 | 0 | 0 | 0 | 31888 | subtotal
1 | Beena Amarnath | QA PMO Lead | 134 | 2019-08-01: 16; 2019-09-01: 16; 2019-10-01: 24 | 56 |  | 0 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 56 |  | 32 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 56 | 134 | 7504 | 0 | 0 | 0 | 0 | 7504
2 | Kristin Pepper | QA Functional Manager | 134 | 2019-09-01: 16; 2019-10-01: 16 | 32 |  | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 |  | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 | 134 | 4288 | 0 | 0 | 0 | 0 | 4288
3 | Pandu Gupta | QA Business Analyst/Tester | 114 | 2019-09-01: 40; 2019-10-01: 48 | 88 |  | 0 | 88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 88 |  | 40 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 88 | 114 | 10032 | 0 | 0 | 0 | 0 | 10032
4 | Don Coffey | QA Technical Manager | 144 | 2019-09-01: 16; 2019-10-01: 16 | 32 |  | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 |  | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 | 144 | 4608 | 0 | 0 | 0 | 0 | 4608
5 | Timothy King | QA PMO Specialist | 114 | 2019-08-01: 2; 2019-09-01: 16; 2019-10-01: 24 | 42 |  | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 42 |  | 18 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 42 | 114 | 4788 | 0 | 0 | 0 | 0 | 4788
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2019-09-01: 4; 2019-10-01: 4 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 45 | 360 | 0 | 0 | 0 | 0 | 360
7 | Wendy Battermann | QA Executive | 154 | 2019-10-01: 2 | 2 |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 154 | 308 | 0 | 0 | 0 | 0 | 308
8 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #23 - Assessment of DD&I Vendor CalSAWS General Design (Page/Report/Correspondence Changes per Requirement) |  |  | 2019-10-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 138104 | 0 | 0 | 0 | 0 | 138104 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2019-08-01: 8; 2019-09-01: 24; 2019-10-01: 24 | 56 |  | 0 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 56 |  | 32 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 56 | 154 | 8624 | 0 | 0 | 0 | 0 | 8624
2 | Timothy King | QA PMO Specialist | 114 | 2019-09-01: 24; 2019-10-01: 24 | 48 |  | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 48 |  | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 48 | 114 | 5472 | 0 | 0 | 0 | 0 | 5472
3 | Kristin Pepper | QA Functional Manager | 134 | 2019-08-01: 40; 2019-09-01: 60; 2019-10-01: 40 | 140 |  | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 140 |  | 100 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 140 | 134 | 18760 | 0 | 0 | 0 | 0 | 18760
4 | Don Coffey | QA Technical Manager | 144 | 2019-09-01: 32; 2019-10-01: 60 | 92 |  | 0 | 92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 92 |  | 32 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 92 | 144 | 13248 | 0 | 0 | 0 | 0 | 13248
5 | Pandu Gupta | QA Business Analyst/Tester | 114 | 2019-08-01: 48; 2019-09-01: 96; 2019-10-01: 40 | 184 |  | 0 | 184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 184 |  | 144 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 184 | 114 | 20976 | 0 | 0 | 0 | 0 | 20976
6 | Greg FitzGerald | QA Technical Lead | 139 | 2019-08-01: 8; 2019-09-01: 120; 2019-10-01: 100 | 228 |  | 0 | 228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 228 |  | 128 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 228 | 139 | 31692 | 0 | 0 | 0 | 0 | 31692
7 | Dustin Lish | QA Technical Lead | 139 | 2019-08-01: 8; 2019-09-01: 20; 2019-10-01: 20 | 48 |  | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 48 | IFG | 28 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 48 | 139 | 6672 | 0 | 0 | 0 | 0 | 6672 | IFG
8 | Raj Ganesh | QA Conversion Lead | 114 | 2019-09-01: 100; 2019-10-01: 100 | 200 |  | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 200 |  | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 200 | 114 | 22800 | 0 | 0 | 0 | 0 | 22800
9 | Cheryl Hofmann | QA Testing Manager | 134 | 2019-09-01: 16; 2019-10-01: 16 | 32 |  | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 |  | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 | 134 | 4288 | 0 | 0 | 0 | 0 | 4288
10 | Rachel Hernandez | QA UAT Lead | 134 | 2019-09-01: 16; 2019-10-01: 16 | 32 |  | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 |  | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 | 134 | 4288 | 0 | 0 | 0 | 0 | 4288
11 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2019-09-01: 4; 2019-10-01: 4 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 45 | 360 | 0 | 0 | 0 | 0 | 360
12 | Frank Ono | QA Executive | 154 | 2019-10-01: 6 | 6 |  | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 6 | IFG | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 6 | 154 | 924 | 0 | 0 | 0 | 0 | 924
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #24 - Assessment of DD&I Vendor C-IV Deployment Readiness Plan |  |  | 2019-10-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 63828 | 0 | 0 | 0 | 0 | 63828 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2019-08-01: 2; 2019-09-01: 12; 2019-10-01: 12 | 26 |  | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 26 |  | 14 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 26 | 154 | 4004 | 0 | 0 | 0 | 0 | 4004
2 | Abby Darrah | QA Implementation Manager | 134 | 2019-08-01: 24; 2019-09-01: 24; 2019-10-01: 24 | 72 |  | 0 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 72 |  | 48 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 72 | 134 | 9648 | 0 | 0 | 0 | 0 | 9648
3 | Kristin Pepper | QA Functional Manager | 134 | 2019-09-01: 32; 2019-10-01: 40 | 72 |  | 0 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 72 |  | 32 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 72 | 134 | 9648 | 0 | 0 | 0 | 0 | 9648
4 | Don Coffey | QA Technical Manager | 144 | 2019-08-01: 8; 2019-09-01: 24; 2019-10-01: 40 | 72 |  | 0 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 72 |  | 32 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 72 | 144 | 10368 | 0 | 0 | 0 | 0 | 10368
5 | Timothy King | QA PMO Specialist | 114 | 2019-09-01: 16; 2019-10-01: 16 | 32 |  | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 |  | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 | 114 | 3648 | 0 | 0 | 0 | 0 | 3648
6 | Cheryl Hofmann | QA Testing Manager | 134 | 2019-09-01: 8; 2019-10-01: 16 | 24 |  | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 24 |  | 8 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 24 | 134 | 3216 | 0 | 0 | 0 | 0 | 3216
7 | Gail Brown | QA Implementation Lead | 124 | 2019-08-01: 60; 2019-09-01: 60; 2019-10-01: 60 | 180 |  | 0 | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 180 | IFG | 120 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 180 | 124 | 22320 | 0 | 0 | 0 | 0 | 22320
8 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2019-09-01: 4; 2019-10-01: 4 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 45 | 360 | 0 | 0 | 0 | 0 | 360
9 | Wendy Battermann | QA Executive | 154 | 2019-10-01: 4 | 4 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | 154 | 616 | 0 | 0 | 0 | 0 | 616
10 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #25 - Assessment of DD&I Vendor CalSAWS Requirements Traceability Matrix - Update 1 |  |  | 2019-12-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 26884 | 0 | 0 | 0 | 0 | 26884 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2019-11-01: 4; 2019-12-01: 8 | 12 |  | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 12 |  | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 12 | 154 | 1848 | 0 | 0 | 0 | 0 | 1848
2 | Kristin Pepper | QA Functional Manager | 134 | 2019-11-01: 40; 2019-12-01: 24 | 64 |  | 0 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 64 |  | 0 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 64 | 134 | 8576 | 0 | 0 | 0 | 0 | 8576
3 | Pandu Gupta | QA Business Analyst/Tester | 114 | 2019-11-01: 40; 2019-12-01: 32 | 72 |  | 0 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 72 |  | 0 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 72 | 114 | 8208 | 0 | 0 | 0 | 0 | 8208
4 | Don Coffey | QA Technical Manager | 144 | 2019-11-01: 16; 2019-12-01: 24 | 40 |  | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 |  | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 | 144 | 5760 | 0 | 0 | 0 | 0 | 5760
5 | Timothy King | QA PMO Specialist | 114 | 2019-11-01: 8; 2019-12-01: 8 | 16 |  | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16 |  | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16 | 114 | 1824 | 0 | 0 | 0 | 0 | 1824
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2019-11-01: 4; 2019-12-01: 4 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 45 | 360 | 0 | 0 | 0 | 0 | 360
7 | Wendy Battermann | QA Executive | 154 | 2019-12-01: 2 | 2 |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 154 | 308 | 0 | 0 | 0 | 0 | 308
8 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #26 - Assessment of DD&I Vendor CalSAWS General Design |  |  | 2019-12-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 134032 | 0 | 0 | 0 | 0 | 134032 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2019-10-01: 8; 2019-11-01: 8; 2019-12-01: 24 | 40 |  | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 |  | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 | 154 | 6160 | 0 | 0 | 0 | 0 | 6160
2 | Timothy King | QA PMO Specialist | 114 | 2019-10-01: 8; 2019-11-01: 32; 2019-12-01: 24 | 64 |  | 0 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 64 |  | 0 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 64 | 114 | 7296 | 0 | 0 | 0 | 0 | 7296
3 | Kristin Pepper | QA Functional Manager | 134 | 2019-10-01: 24; 2019-11-01: 60; 2019-12-01: 40 | 124 |  | 0 | 124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 124 |  | 0 | 124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 124 | 134 | 16616 | 0 | 0 | 0 | 0 | 16616
4 | Don Coffey | QA Technical Manager | 144 | 2019-10-01: 24; 2019-11-01: 32; 2019-12-01: 60 | 116 |  | 0 | 116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 116 |  | 0 | 116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 116 | 144 | 16704 | 0 | 0 | 0 | 0 | 16704
5 | Pandu Gupta | QA Business Analyst/Tester | 114 | 2019-10-01: 32; 2019-11-01: 64; 2019-12-01: 72 | 168 |  | 0 | 168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 168 |  | 0 | 168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 168 | 114 | 19152 | 0 | 0 | 0 | 0 | 19152
6 | Greg FitzGerald | QA Technical Lead | 139 | 2019-10-01: 32; 2019-11-01: 120; 2019-12-01: 96 | 248 |  | 0 | 248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 248 |  | 0 | 248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 248 | 139 | 34472 | 0 | 0 | 0 | 0 | 34472
7 | Dustin Lish | QA Technical Lead | 139 | 2019-10-01: 8; 2019-11-01: 20; 2019-12-01: 20 | 48 |  | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 48 | IFG | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 48 | 139 | 6672 | 0 | 0 | 0 | 0 | 6672 | IFG
8 | Raj Ganesh | QA Conversion Lead | 114 | 2019-11-01: 100; 2019-12-01: 50 | 150 |  | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 150 |  | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 150 | 114 | 17100 | 0 | 0 | 0 | 0 | 17100
9 | Cheryl Hofmann | QA Testing Manager | 134 | 2019-11-01: 16; 2019-12-01: 16 | 32 |  | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 |  | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 | 134 | 4288 | 0 | 0 | 0 | 0 | 4288
10 | Rachel Hernandez | QA UAT Lead | 134 | 2019-11-01: 16; 2019-12-01: 16 | 32 |  | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 |  | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 | 134 | 4288 | 0 | 0 | 0 | 0 | 4288
11 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2019-11-01: 4; 2019-12-01: 4 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | IFG | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 45 | 360 | 0 | 0 | 0 | 0 | 360
12 | Frank Ono | QA Executive | 154 | 2019-12-01: 6 | 6 |  | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 6 |  | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 6 | 154 | 924 | 0 | 0 | 0 | 0 | 924
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #27 - Assessment of DD&I Vendor CalWIN/CalSAWS Master Conversion Plan - Update 1 |  |  | 2020-01-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 58176 | 0 | 0 | 0 | 0 | 58176 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2019-11-01: 8; 2019-12-01: 8; 2020-01-01: 12 | 28 |  | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28 |  | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28 | 154 | 4312 | 0 | 0 | 0 | 0 | 4312
2 | Raj Ganesh | QA Conversion Lead | 114 | 2019-12-01: 50; 2020-01-01: 50 | 100 |  | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 100 |  | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 100 | 114 | 11400 | 0 | 0 | 0 | 0 | 11400
3 | Timothy King | QA PMO Specialist | 114 | 2019-11-01: 16; 2019-12-01: 16; 2020-01-01: 16 | 48 |  | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 48 |  | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 48 | 114 | 5472 | 0 | 0 | 0 | 0 | 5472
4 | Kristin Pepper | QA Functional Manager | 134 | 2019-12-01: 16; 2020-01-01: 32 | 48 |  | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 48 |  | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 48 | 134 | 6432 | 0 | 0 | 0 | 0 | 6432
5 | Don Coffey | QA Technical Manager | 144 | 2019-12-01: 24; 2020-01-01: 40 | 64 |  | 0 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 64 |  | 0 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 64 | 144 | 9216 | 0 | 0 | 0 | 0 | 9216
6 | Abby Darrah | QA Implementation Manager | 134 | 2019-11-01: 24; 2019-12-01: 24; 2020-01-01: 24 | 72 |  | 0 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 72 |  | 0 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 72 | 134 | 9648 | 0 | 0 | 0 | 0 | 9648
7 | Cheryl Hofmann | QA Testing Manager | 134 | 2019-11-01: 8; 2019-12-01: 16; 2020-01-01: 16 | 40 |  | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 |  | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 | 134 | 5360 | 0 | 0 | 0 | 0 | 5360
8 | Rachel Hernandez | QA UAT Lead | 134 | 2019-11-01: 8; 2019-12-01: 16; 2020-01-01: 16 | 40 |  | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 |  | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 | 134 | 5360 | 0 | 0 | 0 | 0 | 5360
9 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2019-12-01: 4; 2020-01-01: 4 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 45 | 360 | 0 | 0 | 0 | 0 | 360
10 | Frank Ono | QA Executive | 154 | 2020-01-01: 4 | 4 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | IFG | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | 154 | 616 | 0 | 0 | 0 | 0 | 616 | IFG
11 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #28 - Assessment of DD&I Vendor CalSAWS General Design |  |  | 2020-02-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 133484 | 0 | 0 | 0 | 0 | 133484 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2019-12-01: 8; 2020-01-01: 16; 2020-02-01: 12 | 36 |  | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 36 |  | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 36 | 154 | 5544 | 0 | 0 | 0 | 0 | 5544
2 | Timothy King | QA PMO Specialist | 114 | 2019-12-01: 16; 2020-01-01: 16; 2020-02-01: 20 | 52 |  | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 52 |  | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 52 | 114 | 5928 | 0 | 0 | 0 | 0 | 5928
3 | Kristin Pepper | QA Functional Manager | 134 | 2019-12-01: 24; 2020-01-01: 48; 2020-02-01: 40 | 112 |  | 0 | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 112 |  | 0 | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 112 | 134 | 15008 | 0 | 0 | 0 | 0 | 15008
4 | Don Coffey | QA Technical Manager | 144 | 2019-12-01: 24; 2020-01-01: 32; 2020-02-01: 60 | 116 |  | 0 | 116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 116 |  | 0 | 116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 116 | 144 | 16704 | 0 | 0 | 0 | 0 | 16704
5 | Pandu Gupta | QA Business Analyst/Tester | 114 | 2019-12-01: 32; 2020-01-01: 88; 2020-02-01: 72 | 192 |  | 0 | 192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 192 |  | 0 | 192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 192 | 114 | 21888 | 0 | 0 | 0 | 0 | 21888
6 | Greg FitzGerald | QA Technical Lead | 139 | 2019-12-01: 32; 2020-01-01: 120; 2020-02-01: 88 | 240 |  | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 240 |  | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 240 | 139 | 33360 | 0 | 0 | 0 | 0 | 33360
7 | Dustin Lish | QA Technical Lead | 139 | 2019-12-01: 16; 2020-01-01: 20; 2020-02-01: 20 | 56 |  | 0 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 56 | IFG | 0 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 56 | 139 | 7784 | 0 | 0 | 0 | 0 | 7784 | IFG
8 | Raj Ganesh | QA Conversion Lead | 114 | 2020-01-01: 50; 2020-02-01: 100 | 150 |  | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 150 |  | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 150 | 114 | 17100 | 0 | 0 | 0 | 0 | 17100
9 | Cheryl Hofmann | QA Testing Manager | 134 | 2020-01-01: 16; 2020-02-01: 16 | 32 |  | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 |  | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 | 134 | 4288 | 0 | 0 | 0 | 0 | 4288
10 | Rachel Hernandez | QA UAT Lead | 134 | 2020-01-01: 16; 2020-02-01: 16 | 32 |  | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 |  | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 | 134 | 4288 | 0 | 0 | 0 | 0 | 4288
11 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2020-01-01: 4; 2020-02-01: 4 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 45 | 360 | 0 | 0 | 0 | 0 | 360
12 | Frank Ono | QA Executive | 154 | 2020-02-01: 8 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | IFG | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 154 | 1232 | 0 | 0 | 0 | 0 | 1232
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #29 - Assessment of DD&I Vendor CalSAWS Migration Project Control Document Update |  |  | 2020-02-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 25620 | 0 | 0 | 0 | 0 | 25620 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2020-01-01: 8; 2020-02-01: 8 | 16 |  | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16 |  | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16 | 154 | 2464 | 0 | 0 | 0 | 0 | 2464
2 | Beena Amarnath | QA PMO Lead | 134 | 2020-01-01: 32; 2020-02-01: 16 | 48 |  | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 48 |  | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 48 | 134 | 6432 | 0 | 0 | 0 | 0 | 6432
3 | Timothy King | QA PMO Specialist | 114 | 2020-01-01: 24; 2020-02-01: 24 | 48 |  | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 48 |  | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 48 | 114 | 5472 | 0 | 0 | 0 | 0 | 5472
4 | Kristin Pepper | QA Functional Manager | 134 | 2019-12-01: 8; 2020-01-01: 16; 2020-02-01: 16 | 40 |  | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 |  | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 | 134 | 5360 | 0 | 0 | 0 | 0 | 5360
5 | Don Coffey | QA Technical Manager | 144 | 2020-01-01: 16; 2020-02-01: 16 | 32 |  | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 |  | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 | 144 | 4608 | 0 | 0 | 0 | 0 | 4608
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2020-01-01: 4; 2020-02-01: 4 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 45 | 360 | 0 | 0 | 0 | 0 | 360
7 | Wendy Battermann | QA Executive | 154 | 2020-02-01: 6 | 6 |  | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 6 |  | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 6 | 154 | 924 | 0 | 0 | 0 | 0 | 924
8 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #30 - Assessment of DD&I Vendor CalSAWS Requirements Traceability Matrix - Update 2 |  |  | 2020-02-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 21832 | 0 | 0 | 0 | 0 | 21832 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2020-01-01: 8; 2020-02-01: 4 | 12 |  | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 12 |  | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 12 | 154 | 1848 | 0 | 0 | 0 | 0 | 1848
2 | Kristin Pepper | QA Functional Manager | 134 | 2020-01-01: 16; 2020-02-01: 16 | 32 |  | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 |  | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 | 134 | 4288 | 0 | 0 | 0 | 0 | 4288
3 | Pandu Gupta | QA Business Analyst/Tester | 114 | 2020-01-01: 40; 2020-02-01: 32 | 72 |  | 0 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 72 |  | 0 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 72 | 114 | 8208 | 0 | 0 | 0 | 0 | 8208
4 | Don Coffey | QA Technical Manager | 144 | 2020-01-01: 16; 2020-02-01: 24 | 40 |  | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 |  | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 | 144 | 5760 | 0 | 0 | 0 | 0 | 5760
5 | Timothy King | QA PMO Specialist | 114 | 2020-01-01: 8; 2020-02-01: 4 | 12 |  | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 12 |  | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 12 | 114 | 1368 | 0 | 0 | 0 | 0 | 1368
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2020-01-01: 4; 2020-02-01: 4 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 45 | 360 | 0 | 0 | 0 | 0 | 360
7 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #31 - Assessment of DD&I Vendor CalSAWS General Design |  |  | 2020-04-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 144808 | 0 | 0 | 0 | 0 | 144808 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2020-02-01: 4; 2020-03-01: 16; 2020-04-01: 12 | 32 |  | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 |  | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 | 154 | 4928 | 0 | 0 | 0 | 0 | 4928
2 | Timothy King | QA PMO Specialist | 114 | 2020-02-01: 16; 2020-03-01: 16; 2020-04-01: 24 | 56 |  | 0 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 56 |  | 0 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 56 | 114 | 6384 | 0 | 0 | 0 | 0 | 6384
3 | Kristin Pepper | QA Functional Manager | 134 | 2020-02-01: 24; 2020-03-01: 64; 2020-04-01: 40 | 128 |  | 0 | 128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 128 |  | 0 | 128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 128 | 134 | 17152 | 0 | 0 | 0 | 0 | 17152
4 | Don Coffey | QA Technical Manager | 144 | 2020-02-01: 24; 2020-03-01: 32; 2020-04-01: 60 | 116 |  | 0 | 116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 116 |  | 0 | 116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 116 | 144 | 16704 | 0 | 0 | 0 | 0 | 16704
5 | Pandu Gupta | QA Business Analyst/Tester | 114 | 2020-02-01: 24; 2020-03-01: 100; 2020-04-01: 88 | 212 |  | 0 | 212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 212 |  | 0 | 212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 212 | 114 | 24168 | 0 | 0 | 0 | 0 | 24168
6 | Greg FitzGerald | QA Technical Lead | 139 | 2020-02-01: 32; 2020-03-01: 120; 2020-04-01: 100 | 252 |  | 0 | 252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 252 |  | 0 | 252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 252 | 139 | 35028 | 0 | 0 | 0 | 0 | 35028
7 | Dustin Lish | QA Technical Lead | 139 | 2020-02-01: 16; 2020-03-01: 20; 2020-04-01: 20 | 56 |  | 0 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 56 | IFG | 0 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 56 | 139 | 7784 | 0 | 0 | 0 | 0 | 7784 | IFG
8 | Raj Ganesh | QA Conversion Lead | 114 | 2020-03-01: 100; 2020-04-01: 100 | 200 |  | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 200 |  | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 200 | 114 | 22800 | 0 | 0 | 0 | 0 | 22800
9 | Cheryl Hofmann | QA Testing Manager | 134 | 2020-03-01: 16; 2020-04-01: 16 | 32 |  | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 |  | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 | 134 | 4288 | 0 | 0 | 0 | 0 | 4288
10 | Rachel Hernandez | QA UAT Lead | 134 | 2020-03-01: 16; 2020-04-01: 16 | 32 |  | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 |  | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 | 134 | 4288 | 0 | 0 | 0 | 0 | 4288
11 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2020-03-01: 4; 2020-04-01: 4 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 45 | 360 | 0 | 0 | 0 | 0 | 360
12 | Frank Ono | QA Executive | 154 | 2020-04-01: 6 | 6 |  | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 6 | IFG | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 6 | 154 | 924 | 0 | 0 | 0 | 0 | 924
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #32 - Assessment of DD&I Vendor CalSAWS Requirements Traceability Matrix - Update 3 |  |  | 2020-04-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 26280 | 0 | 0 | 0 | 0 | 26280 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2020-03-01: 16; 2020-04-01: 16 | 32 |  | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 |  | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 | 154 | 4928 | 0 | 0 | 0 | 0 | 4928
2 | Kristin Pepper | QA Functional Manager | 134 | 2020-03-01: 16; 2020-04-01: 16 | 32 |  | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 |  | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 | 134 | 4288 | 0 | 0 | 0 | 0 | 4288
3 | Pandu Gupta | QA Business Analyst/Tester | 114 | 2020-03-01: 32; 2020-04-01: 32 | 64 |  | 0 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 64 |  | 0 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 64 | 114 | 7296 | 0 | 0 | 0 | 0 | 7296
4 | Don Coffey | QA Technical Manager | 144 | 2020-03-01: 16; 2020-04-01: 24 | 40 |  | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 |  | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 | 144 | 5760 | 0 | 0 | 0 | 0 | 5760
5 | Timothy King | QA PMO Specialist | 114 | 2020-03-01: 16; 2020-04-01: 16 | 32 |  | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 |  | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 | 114 | 3648 | 0 | 0 | 0 | 0 | 3648
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2020-03-01: 4; 2020-04-01: 4 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 45 | 360 | 0 | 0 | 0 | 0 | 360
7 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #33 - Assessment of DD&I Vendor C-IV Change Management Plan |  |  | 2020-06-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 62988 | 17308 | 0 | 0 | 0 | 80296 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2020-05-01: 4; 2020-06-01: 12 | 16 |  | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16 |  | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16 | 154 | 616 | 1848 | 0 | 0 | 0 | 2464
2 | Timothy King | QA PMO Specialist | 114 | 2020-06-01: 8 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 114 | 0 | 912 | 0 | 0 | 0 | 912
3 | Abby Darrah | QA Implementation Manager | 134 | 2019-11-01: 24; 2019-12-01: 24; 2020-01-01: 24; 2020-02-01: 24; 2020-03-01: 24; 2020-04-01: 24; 2020-05-01: 24; 2020-06-01: 24 | 192 |  | 0 | 192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 192 |  | 0 | 192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 192 | 134 | 22512 | 3216 | 0 | 0 | 0 | 25728
4 | Ivan Parra | QA Implementation Lead | 124 | 2020-05-01: 40; 2020-06-01: 40 | 80 |  | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 80 |  | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 80 | 124 | 4960 | 4960 | 0 | 0 | 0 | 9920
5 | Gail Brown | QA Implementation Lead | 124 | 2019-11-01: 40; 2019-12-01: 40; 2020-01-01: 40; 2020-02-01: 40; 2020-03-01: 40; 2020-04-01: 40; 2020-05-01: 40; 2020-06-01: 40 | 320 |  | 0 | 320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 320 | IFG | 0 | 320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 320 | 124 | 34720 | 4960 | 0 | 0 | 0 | 39680
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2020-05-01: 4; 2020-06-01: 4 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 45 | 180 | 180 | 0 | 0 | 0 | 360
7 | Wendy Battermann | QA Executive | 154 | 2020-06-01: 8 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 154 | 0 | 1232 | 0 | 0 | 0 | 1232
8 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #34 - Assessment of DD&I Vendor CalSAWS Requirements Traceability Matrix - Update 4 |  |  | 2020-06-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 10716 | 11868 | 0 | 0 | 0 | 22584 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2020-05-01: 4; 2020-06-01: 4 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 154 | 616 | 616 | 0 | 0 | 0 | 1232
2 | Kristin Pepper | QA Functional Manager | 134 | 2020-05-01: 16; 2020-06-01: 16 | 32 |  | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 |  | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 | 134 | 2144 | 2144 | 0 | 0 | 0 | 4288
3 | Pandu Gupta | QA Business Analyst/Tester | 114 | 2020-05-01: 32; 2020-06-01: 32 | 64 |  | 0 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 64 |  | 0 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 64 | 114 | 3648 | 3648 | 0 | 0 | 0 | 7296
4 | Don Coffey | QA Technical Manager | 144 | 2020-05-01: 16; 2020-06-01: 24 | 40 |  | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 |  | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 | 144 | 2304 | 3456 | 0 | 0 | 0 | 5760
5 | Timothy King | QA PMO Specialist | 114 | 2020-05-01: 16; 2020-06-01: 16 | 32 |  | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 |  | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 | 114 | 1824 | 1824 | 0 | 0 | 0 | 3648
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2020-05-01: 4; 2020-06-01: 4 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 45 | 180 | 180 | 0 | 0 | 0 | 360
7 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #35 - Assessment of DD&I Vendor CalSAWS General Design |  |  | 2020-06-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 73252 | 66764 | 0 | 0 | 0 | 140016 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2020-05-01: 4; 2020-06-01: 16 | 20 |  | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 20 |  | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 20 | 154 | 616 | 2464 | 0 | 0 | 0 | 3080
2 | Timothy King | QA PMO Specialist | 114 | 2020-04-01: 16; 2020-05-01: 16; 2020-06-01: 16 | 48 |  | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 48 |  | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 48 | 114 | 3648 | 1824 | 0 | 0 | 0 | 5472
3 | Kristin Pepper | QA Functional Manager | 134 | 2020-04-01: 24; 2020-05-01: 44; 2020-06-01: 68 | 136 |  | 0 | 136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 136 |  | 0 | 136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 136 | 134 | 9112 | 9112 | 0 | 0 | 0 | 18224
4 | Don Coffey | QA Technical Manager | 144 | 2020-04-01: 24; 2020-05-01: 32; 2020-06-01: 60 | 116 |  | 0 | 116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 116 |  | 0 | 116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 116 | 144 | 8064 | 8640 | 0 | 0 | 0 | 16704
5 | Pandu Gupta | QA Business Analyst/Tester | 114 | 2020-04-01: 24; 2020-05-01: 80; 2020-06-01: 96 | 200 |  | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 200 |  | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 200 | 114 | 11856 | 10944 | 0 | 0 | 0 | 22800
6 | Greg FitzGerald | QA Technical Lead | 139 | 2020-04-01: 32; 2020-05-01: 100; 2020-06-01: 100 | 232 |  | 0 | 232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 232 |  | 0 | 232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 232 | 139 | 18348 | 13900 | 0 | 0 | 0 | 32248
7 | Dustin Lish | QA Technical Lead | 139 | 2020-04-01: 20; 2020-05-01: 20; 2020-06-01: 20 | 60 |  | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 60 | IFG | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 60 | 139 | 5560 | 2780 | 0 | 0 | 0 | 8340 | IFG
8 | Raj Ganesh | QA Conversion Lead | 114 | 2020-05-01: 100; 2020-06-01: 100 | 200 |  | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 200 |  | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 200 | 114 | 11400 | 11400 | 0 | 0 | 0 | 22800
9 | Cheryl Hofmann | QA Testing Manager | 134 | 2020-05-01: 16; 2020-06-01: 16 | 32 |  | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 |  | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 | 134 | 2144 | 2144 | 0 | 0 | 0 | 4288
10 | Rachel Hernandez | QA UAT Lead | 134 | 2020-05-01: 16; 2020-06-01: 16 | 32 |  | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 |  | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 | 134 | 2144 | 2144 | 0 | 0 | 0 | 4288
11 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2020-04-01: 4; 2020-05-01: 4; 2020-06-01: 4 | 12 |  | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 12 |  | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 12 | 45 | 360 | 180 | 0 | 0 | 0 | 540
12 | Frank Ono | QA Executive | 154 | 2020-06-01: 8 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | IFG | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 154 | 0 | 1232 | 0 | 0 | 0 | 1232
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #36 - Assessment of DD&I Vendor CalSAWS Requirements Traceability Matrix - Update 5 |  |  | 2020-08-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 28376 | 0 | 0 | 0 | 28376 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2020-07-01: 4; 2020-08-01: 4 | 8 |  | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 154 | 0 | 1232 | 0 | 0 | 0 | 1232
2 | Kristin Pepper | QA Functional Manager | 134 | 2020-07-01: 24; 2020-08-01: 24 | 48 |  | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 |  | 48 |  | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 48 | 134 | 0 | 6432 | 0 | 0 | 0 | 6432
3 | Pandu Gupta | QA Business Analyst/Tester | 114 | 2020-07-01: 48; 2020-08-01: 48 | 96 |  | 0 | 0 | 96 | 0 | 0 | 0 | 0 | 0 | 0 |  | 96 |  | 0 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 96 | 114 | 0 | 10944 | 0 | 0 | 0 | 10944
4 | Don Coffey | QA Technical Manager | 144 | 2020-07-01: 16; 2020-08-01: 24 | 40 |  | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 |  | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 | 144 | 0 | 5760 | 0 | 0 | 0 | 5760
5 | Timothy King | QA PMO Specialist | 114 | 2020-07-01: 16; 2020-08-01: 16 | 32 |  | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 |  | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 | 114 | 0 | 3648 | 0 | 0 | 0 | 3648
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2020-07-01: 4; 2020-08-01: 4 | 8 |  | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 45 | 0 | 360 | 0 | 0 | 0 | 360
7 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #37 - Assessment of DD&I Vendor CalSAWS Requirements Traceability Matrix - Update 6 |  |  | 2020-10-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 28376 | 0 | 0 | 0 | 28376 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2020-09-01: 4; 2020-10-01: 4 | 8 |  | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 154 | 0 | 1232 | 0 | 0 | 0 | 1232
2 | Kristin Pepper | QA Functional Manager | 134 | 2020-09-01: 24; 2020-10-01: 24 | 48 |  | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 |  | 48 |  | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 |  | 48 | 134 | 0 | 6432 | 0 | 0 | 0 | 6432
3 | Pandu Gupta | QA Business Analyst/Tester | 114 | 2020-09-01: 48; 2020-10-01: 48 | 96 |  | 0 | 0 | 96 | 0 | 0 | 0 | 0 | 0 | 0 |  | 96 |  | 0 | 48 | 48 | 0 | 0 | 0 | 0 | 0 | 0 |  | 96 | 114 | 0 | 10944 | 0 | 0 | 0 | 10944
4 | Don Coffey | QA Technical Manager | 144 | 2020-09-01: 16; 2020-10-01: 24 | 40 |  | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 |  | 0 | 16 | 24 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 | 144 | 0 | 5760 | 0 | 0 | 0 | 5760
5 | Timothy King | QA PMO Specialist | 114 | 2020-09-01: 16; 2020-10-01: 16 | 32 |  | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 |  | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 | 114 | 0 | 3648 | 0 | 0 | 0 | 3648
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2020-09-01: 4; 2020-10-01: 4 | 8 |  | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 45 | 0 | 360 | 0 | 0 | 0 | 360
7 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #38 - Assessment of DD&I Vendor CalSAWS UAT Support Plan |  |  | 2020-11-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 32468 | 0 | 0 | 0 | 32468 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2020-11-01: 8 | 8 |  | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 154 | 0 | 1232 | 0 | 0 | 0 | 1232
2 | Timothy King | QA PMO Specialist | 114 | 2020-09-01: 4; 2020-11-01: 16 | 20 |  | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 |  | 20 |  | 0 | 4 | 16 | 0 | 0 | 0 | 0 | 0 | 0 |  | 20 | 114 | 0 | 2280 | 0 | 0 | 0 | 2280
3 | Cheryl Hofmann | QA Testing Manager | 134 | 2020-09-01: 8; 2020-10-01: 16; 2020-11-01: 16 | 40 |  | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 |  | 0 | 8 | 32 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 | 134 | 0 | 5360 | 0 | 0 | 0 | 5360
4 | Rachel Hernandez | QA UAT Lead | 134 | 2020-09-01: 16; 2020-10-01: 36; 2020-11-01: 36 | 88 |  | 0 | 0 | 88 | 0 | 0 | 0 | 0 | 0 | 0 |  | 88 |  | 0 | 16 | 72 | 0 | 0 | 0 | 0 | 0 | 0 |  | 88 | 134 | 0 | 11792 | 0 | 0 | 0 | 11792
5 | Sindura Kompulira | QA Independent Tester/UAT Leader | 114 | 2020-09-01: 4; 2020-10-01: 42; 2020-11-01: 42 | 88 |  | 0 | 0 | 88 | 0 | 0 | 0 | 0 | 0 | 0 |  | 88 | IFG | 0 | 4 | 84 | 0 | 0 | 0 | 0 | 0 | 0 |  | 88 | 114 | 0 | 10032 | 0 | 0 | 0 | 10032 | IFG
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2020-09-01: 4; 2020-10-01: 4; 2020-11-01: 4 | 12 |  | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 |  | 12 |  | 0 | 4 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 12 | 45 | 0 | 540 | 0 | 0 | 0 | 540
7 | Wendy Battermann | QA Executive | 154 | 2020-11-01: 8 | 8 |  | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 154 | 0 | 1232 | 0 | 0 | 0 | 1232
8 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #39 - Assessment of DD&I Vendor CalSAWS Requirements Traceability Matrix - Update 7 |  |  | 2020-12-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 22584 | 0 | 0 | 0 | 22584 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2020-11-01: 4; 2020-12-01: 4 | 8 |  | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 154 | 0 | 1232 | 0 | 0 | 0 | 1232
2 | Kristin Pepper | QA Functional Manager | 134 | 2020-11-01: 16; 2020-12-01: 16 | 32 |  | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 |  | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 | 134 | 0 | 4288 | 0 | 0 | 0 | 4288
3 | Pandu Gupta | QA Business Analyst/Tester | 114 | 2020-11-01: 32; 2020-12-01: 32 | 64 |  | 0 | 0 | 64 | 0 | 0 | 0 | 0 | 0 | 0 |  | 64 |  | 0 | 0 | 64 | 0 | 0 | 0 | 0 | 0 | 0 |  | 64 | 114 | 0 | 7296 | 0 | 0 | 0 | 7296
4 | Don Coffey | QA Technical Manager | 144 | 2020-11-01: 16; 2020-12-01: 24 | 40 |  | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 |  | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 | 144 | 0 | 5760 | 0 | 0 | 0 | 5760
5 | Timothy King | QA PMO Specialist | 114 | 2020-11-01: 16; 2020-12-01: 16 | 32 |  | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 |  | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 | 114 | 0 | 3648 | 0 | 0 | 0 | 3648
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2020-11-01: 4; 2020-12-01: 4 | 8 |  | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 45 | 0 | 360 | 0 | 0 | 0 | 360
7 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #40 - Assessment of DD&I Vendor CalSAWS (C-IV) UAT Readiness Report/Milestone |  |  | 2021-01-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 26176 | 0 | 0 | 0 | 26176 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2020-11-01: 8; 2020-12-01: 8; 2021-01-01: 8 | 24 |  | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 |  | 24 |  | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 |  | 24 | 154 | 0 | 3696 | 0 | 0 | 0 | 3696
2 | Timothy King | QA PMO Specialist | 114 | 2020-11-01: 8; 2020-12-01: 16; 2021-01-01: 16 | 40 |  | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 |  | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 | 114 | 0 | 4560 | 0 | 0 | 0 | 4560
3 | Cheryl Hofmann | QA Testing Manager | 134 | 2020-11-01: 4; 2020-12-01: 16; 2021-01-01: 16 | 36 |  | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 |  | 36 |  | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 |  | 36 | 134 | 0 | 4824 | 0 | 0 | 0 | 4824
4 | Rachel Hernandez | QA UAT Lead | 134 | 2020-11-01: 4; 2020-12-01: 16; 2021-01-01: 16 | 36 |  | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 |  | 36 |  | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 |  | 36 | 134 | 0 | 4824 | 0 | 0 | 0 | 4824
5 | Donna Smith | QA Independent Tester/UAT Leader | 114 | 2020-12-01: 16; 2021-01-01: 16 | 32 |  | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 |  | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 | 114 | 0 | 3648 | 0 | 0 | 0 | 3648
6 | Sindura Kompulira | QA Independent Tester/UAT Leader | 114 | 2020-12-01: 16; 2021-01-01: 16 | 32 |  | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 | IFG | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 | 114 | 0 | 3648 | 0 | 0 | 0 | 3648
7 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2020-12-01: 4; 2021-01-01: 4 | 8 |  | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 45 | 0 | 360 | 0 | 0 | 0 | 360
8 | Wendy Battermann | QA Executive | 154 | 2021-01-01: 4 | 4 |  | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | 154 | 0 | 616 | 0 | 0 | 0 | 616
9 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #41 - Assessment of DD&I Vendor CalSAWS Migration Project Control Document Update |  |  | 2021-02-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 19576 | 0 | 0 | 0 | 19576 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2021-02-01: 8 | 8 |  | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 154 | 0 | 1232 | 0 | 0 | 0 | 1232
2 | Beena Amarnath | QA PMO Lead | 134 | 2021-01-01: 16; 2021-02-01: 16 | 32 |  | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 |  | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 | 134 | 0 | 4288 | 0 | 0 | 0 | 4288
3 | Timothy King | QA PMO Specialist | 114 | 2021-01-01: 12; 2021-02-01: 24 | 36 |  | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 |  | 36 |  | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 |  | 36 | 114 | 0 | 4104 | 0 | 0 | 0 | 4104
4 | Kristin Pepper | QA Functional Manager | 134 | 2021-01-01: 8; 2021-02-01: 16 | 24 |  | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 |  | 24 |  | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 |  | 24 | 134 | 0 | 3216 | 0 | 0 | 0 | 3216
5 | Don Coffey | QA Technical Manager | 144 | 2021-01-01: 16; 2021-02-01: 24 | 40 |  | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 |  | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 | 144 | 0 | 5760 | 0 | 0 | 0 | 5760
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2021-01-01: 4; 2021-02-01: 4 | 8 |  | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 45 | 0 | 360 | 0 | 0 | 0 | 360
7 | Wendy Battermann | QA Executive | 154 | 2021-02-01: 4 | 4 |  | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | 154 | 0 | 616 | 0 | 0 | 0 | 616
8 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #42 - Assessment of DD&I Vendor CalSAWS (CalWIN) UAT Readiness Report/Milestone |  |  | 2021-04-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 19608 | 0 | 0 | 0 | 19608 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2021-03-01: 4; 2021-04-01: 8 | 12 |  | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 |  | 12 |  | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 |  | 12 | 154 | 0 | 1848 | 0 | 0 | 0 | 1848
2 | Timothy King | QA PMO Specialist | 114 | 2021-03-01: 4; 2021-04-01: 4 | 8 |  | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 114 | 0 | 912 | 0 | 0 | 0 | 912
3 | Cheryl Hofmann | QA Testing Manager | 134 | 2021-03-01: 16; 2021-04-01: 16 | 32 |  | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 |  | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 | 134 | 0 | 4288 | 0 | 0 | 0 | 4288
4 | Rachel Hernandez | QA UAT Lead | 134 | 2021-03-01: 16; 2021-04-01: 16 | 32 |  | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 |  | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 | 134 | 0 | 4288 | 0 | 0 | 0 | 4288
5 | Donna Smith | QA Independent Tester/UAT Leader | 114 | 2021-03-01: 16; 2021-04-01: 16 | 32 |  | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 |  | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 | 114 | 0 | 3648 | 0 | 0 | 0 | 3648
6 | Sindura Kompulira | QA Independent Tester/UAT Leader | 114 | 2021-03-01: 16; 2021-04-01: 16 | 32 |  | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 | IFG | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 | 114 | 0 | 3648 | 0 | 0 | 0 | 3648
7 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2021-03-01: 4; 2021-04-01: 4 | 8 |  | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 45 | 0 | 360 | 0 | 0 | 0 | 360
8 | Wendy Battermann | QA Executive | 154 | 2021-04-01: 4 | 4 |  | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | 154 | 0 | 616 | 0 | 0 | 0 | 616
9 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #43 - Assessment of DD&I Vendor CalSAWS Requirements Traceability Matrix - Update 8 |  |  | 2021-07-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 22584 | 0 | 0 | 22584 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2021-06-01: 4; 2021-07-01: 4 | 8 |  | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 154 | 0 | 0 | 1232 | 0 | 0 | 1232
2 | Kristin Pepper | QA Functional Manager | 134 | 2021-06-01: 16; 2021-07-01: 16 | 32 |  | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 |  | 32 |  | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 | 134 | 0 | 0 | 4288 | 0 | 0 | 4288
3 | Pandu Gupta | QA Business Analyst/Tester | 114 | 2021-06-01: 32; 2021-07-01: 32 | 64 |  | 0 | 0 | 32 | 32 | 0 | 0 | 0 | 0 | 0 |  | 64 |  | 0 | 0 | 64 | 0 | 0 | 0 | 0 | 0 | 0 |  | 64 | 114 | 0 | 0 | 7296 | 0 | 0 | 7296
4 | Don Coffey | QA Technical Manager | 144 | 2021-06-01: 16; 2021-07-01: 24 | 40 |  | 0 | 0 | 16 | 24 | 0 | 0 | 0 | 0 | 0 |  | 40 |  | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 | 144 | 0 | 0 | 5760 | 0 | 0 | 5760
5 | Timothy King | QA PMO Specialist | 114 | 2021-06-01: 16; 2021-07-01: 16 | 32 |  | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 |  | 32 |  | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 | 114 | 0 | 0 | 3648 | 0 | 0 | 3648
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2021-06-01: 4; 2021-07-01: 4 | 8 |  | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 45 | 0 | 0 | 360 | 0 | 0 | 360
7 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #44 - Assessment of DD&I Vendor CalSAWS Requirements Traceability Matrix - Update 9 |  |  | 2021-10-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 21672 | 0 | 0 | 21672 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2021-09-01: 4; 2021-10-01: 4 | 8 |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 |  | 8 | 154 | 0 | 0 | 1232 | 0 | 0 | 1232
2 | Kristin Pepper | QA Functional Manager | 134 | 2021-09-01: 16; 2021-10-01: 16 | 32 |  | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 |  | 32 |  | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 |  | 32 | 134 | 0 | 0 | 4288 | 0 | 0 | 4288
3 | Pandu Gupta | QA Business Analyst/Tester | 114 | 2021-09-01: 32; 2021-10-01: 32 | 64 |  | 0 | 0 | 0 | 64 | 0 | 0 | 0 | 0 | 0 |  | 64 |  | 0 | 0 | 32 | 32 | 0 | 0 | 0 | 0 | 0 |  | 64 | 114 | 0 | 0 | 7296 | 0 | 0 | 7296
4 | Don Coffey | QA Technical Manager | 144 | 2021-09-01: 16; 2021-10-01: 24 | 40 |  | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 |  | 40 |  | 0 | 0 | 16 | 24 | 0 | 0 | 0 | 0 | 0 |  | 40 | 144 | 0 | 0 | 5760 | 0 | 0 | 5760
5 | Timothy King | QA PMO Specialist | 114 | 2021-09-01: 8; 2021-10-01: 16 | 24 |  | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 |  | 24 |  | 0 | 0 | 8 | 16 | 0 | 0 | 0 | 0 | 0 |  | 24 | 114 | 0 | 0 | 2736 | 0 | 0 | 2736
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2021-09-01: 4; 2021-10-01: 4 | 8 |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 |  | 8 | 45 | 0 | 0 | 360 | 0 | 0 | 360
7 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #45 - Assessment of DD&I Vendor CalSAWS Deployment Complete Milestone/Report - C-IV |  |  | 2021-10-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 60936 | 0 | 0 | 60936 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2021-08-01: 4; 2021-09-01: 4; 2021-10-01: 8 | 16 |  | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 |  | 16 |  | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 |  | 16 | 154 | 0 | 0 | 2464 | 0 | 0 | 2464
2 | Beena Amarnath | QA PMO Lead | 134 | 2021-08-01: 4; 2021-09-01: 4; 2021-10-01: 8 | 16 |  | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 |  | 16 |  | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 |  | 16 | 134 | 0 | 0 | 2144 | 0 | 0 | 2144
3 | Timothy King | QA PMO Specialist | 114 | 2021-08-01: 0; 2021-09-01: 8; 2021-10-01: 16 | 24 |  | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 |  | 24 |  | 0 | 0 | 8 | 16 | 0 | 0 | 0 | 0 | 0 |  | 24 | 114 | 0 | 0 | 2736 | 0 | 0 | 2736
4 | Kristin Pepper | QA Functional Manager | 134 | 2021-07-01: 8; 2021-08-01: 16; 2021-09-01: 24; 2021-10-01: 32 | 80 |  | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 |  | 80 |  | 0 | 0 | 48 | 32 | 0 | 0 | 0 | 0 | 0 |  | 80 | 134 | 0 | 0 | 10720 | 0 | 0 | 10720
5 | Don Coffey | QA Technical Manager | 144 | [59 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 144 | 0 | 0 | 0 | 0 | 0 | 0
6 | Abby Darrah | QA Implementation Manager | 134 | 2021-07-01: 24; 2021-08-01: 32; 2021-09-01: 40; 2021-10-01: 48 | 144 |  | 0 | 0 | 0 | 144 | 0 | 0 | 0 | 0 | 0 |  | 144 |  | 0 | 0 | 96 | 48 | 0 | 0 | 0 | 0 | 0 |  | 144 | 134 | 0 | 0 | 19296 | 0 | 0 | 19296
7 | Cheryl Hofmann | QA Testing Manager | 134 | 2021-08-01: 8; 2021-09-01: 16; 2021-10-01: 24 | 48 |  | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 |  | 48 |  | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 |  | 48 | 134 | 0 | 0 | 6432 | 0 | 0 | 6432
8 | Rachel Hernandez | QA UAT Lead | 134 | 2021-08-01: 8; 2021-09-01: 16; 2021-10-01: 24 | 48 |  | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 |  | 48 |  | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 |  | 48 | 134 | 0 | 0 | 6432 | 0 | 0 | 6432
9 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2021-09-01: 4; 2021-10-01: 4 | 8 |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 |  | 8 | 45 | 0 | 0 | 360 | 0 | 0 | 360
10 | Raj Ganesh | QA Conversion Lead | 114 | 2021-07-01: 8; 2021-08-01: 16; 2021-09-01: 24; 2021-10-01: 32 | 80 |  | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 |  | 80 |  | 0 | 0 | 48 | 32 | 0 | 0 | 0 | 0 | 0 |  | 80 | 114 | 0 | 0 | 9120 | 0 | 0 | 9120
11 | Wendy Battermann | QA Executive | 154 | 2021-10-01: 8 | 8 |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 |  | 8 | 154 | 0 | 0 | 1232 | 0 | 0 | 1232
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #46 - Assessment of DD&I Vendor CalACES Migration Final Acceptance Certification |  |  | 2022-01-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 19460 | 0 | 0 | 19460 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2021-12-01: 4; 2022-01-01: 4 | 8 |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 |  | 8 | 154 | 0 | 0 | 1232 | 0 | 0 | 1232
2 | Beena Amarnath | QA PMO Lead | 134 | 2021-12-01: 4; 2022-01-01: 4 | 8 |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 |  | 8 | 134 | 0 | 0 | 1072 | 0 | 0 | 1072
3 | Timothy King | QA PMO Specialist | 114 | 2021-12-01: 16; 2022-01-01: 16 | 32 |  | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 |  | 32 |  | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 |  | 32 | 114 | 0 | 0 | 3648 | 0 | 0 | 3648
4 | Abby Darrah | QA Implementation Manager | 134 | 2022-01-01: 32 | 32 |  | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 |  | 32 |  | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 |  | 32 | 134 | 0 | 0 | 4288 | 0 | 0 | 4288
5 | Gail Brown | QA Implementation Lead | 124 | 2022-01-01: 16 | 16 |  | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 |  | 16 | IFG | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 |  | 16 | 124 | 0 | 0 | 1984 | 0 | 0 | 1984
6 | Ivan Parra | QA Implementation Lead | 124 | 2022-01-01: 16 | 16 |  | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 |  | 16 |  | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 |  | 16 | 124 | 0 | 0 | 1984 | 0 | 0 | 1984
7 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2021-12-01: 4; 2022-01-01: 4 | 8 |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 |  | 8 | 45 | 0 | 0 | 360 | 0 | 0 | 360
8 | Raj Ganesh | QA Conversion Lead | 114 | 2022-01-01: 16 | 16 |  | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 |  | 16 |  | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 |  | 16 | 114 | 0 | 0 | 1824 | 0 | 0 | 1824
9 | Don Coffey | QA Technical Manager | 144 | [59 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 144 | 0 | 0 | 0 | 0 | 0 | 0
10 | Kristin Pepper | QA Functional Manager | 134 | 2022-01-01: 16 | 16 |  | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 |  | 16 |  | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 |  | 16 | 134 | 0 | 0 | 2144 | 0 | 0 | 2144
11 | Wendy Battermann | QA Executive | 154 | 2022-01-01: 6 | 6 |  | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 |  | 6 |  | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 |  | 6 | 154 | 0 | 0 | 924 | 0 | 0 | 924
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #47 - Assessment of DD&I Vendor CalSAWS Deployment Complete Milestone/Report - CalWIN Wave 1 |  |  | 2022-01-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 149788 | 0 | 0 | 149788 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2021-11-01: 16; 2021-12-01: 16; 2022-01-01: 16 | 48 |  | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 |  | 48 |  | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 |  | 48 | 154 | 0 | 0 | 7392 | 0 | 0 | 7392
2 | Beena Amarnath | QA PMO Lead | 134 | 2021-11-01: 16; 2021-12-01: 16; 2022-01-01: 16 | 48 |  | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 |  | 48 |  | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 |  | 48 | 134 | 0 | 0 | 6432 | 0 | 0 | 6432
3 | Timothy King | QA PMO Specialist | 114 | 2021-11-01: 16; 2021-12-01: 16; 2022-01-01: 16 | 48 |  | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 |  | 48 |  | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 |  | 48 | 114 | 0 | 0 | 5472 | 0 | 0 | 5472
4 | Kristin Pepper | QA Functional Manager | 134 | 2021-11-01: 8; 2021-12-01: 16; 2022-01-01: 24 | 48 |  | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 |  | 48 |  | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 |  | 48 | 134 | 0 | 0 | 6432 | 0 | 0 | 6432
5 | Don Coffey | QA Technical Manager | 144 | 2021-11-01: 8; 2021-12-01: 16; 2022-01-01: 24 | 48 |  | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 |  | 48 |  | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 |  | 48 | 144 | 0 | 0 | 6912 | 0 | 0 | 6912
6 | Abby Darrah | QA Implementation Manager | 134 | 2021-10-01: 60; 2021-11-01: 60; 2021-12-01: 60; 2022-01-01: 40 | 220 |  | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 |  | 220 |  | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 |  | 220 | 134 | 0 | 0 | 29480 | 0 | 0 | 29480
7 | Cheryl Hofmann | QA Testing Manager | 134 | 2021-11-01: 16; 2021-12-01: 16; 2022-01-01: 24 | 56 |  | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 0 | 0 |  | 56 |  | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 0 | 0 |  | 56 | 134 | 0 | 0 | 7504 | 0 | 0 | 7504
8 | Rachel Hernandez | QA UAT Lead | 134 | 2021-11-01: 16; 2021-12-01: 16; 2022-01-01: 24 | 56 |  | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 0 | 0 |  | 56 |  | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 0 | 0 |  | 56 | 134 | 0 | 0 | 7504 | 0 | 0 | 7504
9 | Pandu Gupta | QA Business Analyst/Tester | 114 | 2021-11-01: 16; 2021-12-01: 16; 2022-01-01: 24 | 56 |  | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 0 | 0 |  | 56 |  | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 0 | 0 |  | 56 | 114 | 0 | 0 | 6384 | 0 | 0 | 6384
10 | Gail Brown | QA Implementation Lead | 124 | 2021-10-01: 60; 2021-11-01: 60; 2021-12-01: 60; 2022-01-01: 60 | 240 |  | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 |  | 240 | IFG | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 |  | 240 | 124 | 0 | 0 | 29760 | 0 | 0 | 29760
11 | Ivan Parra | QA Implementation Lead | 124 | 2021-10-01: 60; 2021-11-01: 60; 2021-12-01: 60; 2022-01-01: 60 | 240 |  | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 |  | 240 |  | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 |  | 240 | 124 | 0 | 0 | 29760 | 0 | 0 | 29760
12 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2021-12-01: 4; 2022-01-01: 4 | 8 |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 |  | 8 | 45 | 0 | 0 | 360 | 0 | 0 | 360
13 | Raj Ganesh | QA Conversion Lead | 114 | 2021-11-01: 8; 2021-12-01: 16; 2022-01-01: 24 | 48 |  | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 |  | 48 |  | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 |  | 48 | 114 | 0 | 0 | 5472 | 0 | 0 | 5472
14 | Wendy Battermann | QA Executive | 154 | 2022-01-01: 6 | 6 |  | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 |  | 6 |  | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 |  | 6 | 154 | 0 | 0 | 924 | 0 | 0 | 924
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #48 - Assessment of DD&I Vendor CalSAWS Migration Project Control Document Update |  |  | 2022-02-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 23408 | 0 | 0 | 23408 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2022-01-01: 12; 2022-02-01: 16 | 28 |  | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 |  | 28 |  | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 |  | 28 | 154 | 0 | 0 | 4312 | 0 | 0 | 4312
2 | Beena Amarnath | QA PMO Lead | 134 | 2022-01-01: 12; 2022-02-01: 16 | 28 |  | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 |  | 28 |  | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 |  | 28 | 134 | 0 | 0 | 3752 | 0 | 0 | 3752
3 | Timothy King | QA PMO Specialist | 114 | 2022-01-01: 24; 2022-02-01: 24 | 48 |  | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 |  | 48 |  | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 |  | 48 | 114 | 0 | 0 | 5472 | 0 | 0 | 5472
4 | Kristin Pepper | QA Functional Manager | 134 | 2022-01-01: 16; 2022-02-01: 16 | 32 |  | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 |  | 32 |  | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 |  | 32 | 134 | 0 | 0 | 4288 | 0 | 0 | 4288
5 | Don Coffey | QA Technical Manager | 144 | 2022-01-01: 16; 2022-02-01: 16 | 32 |  | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 |  | 32 |  | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 |  | 32 | 144 | 0 | 0 | 4608 | 0 | 0 | 4608
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2022-01-01: 4; 2022-02-01: 4 | 8 |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 |  | 8 | 45 | 0 | 0 | 360 | 0 | 0 | 360
7 | Wendy Battermann | QA Executive | 154 | 2022-02-01: 4 | 4 |  | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 |  | 4 | 154 | 0 | 0 | 616 | 0 | 0 | 616
8 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #49 - Assessment of DD&I Vendor CalSAWS Deployment Complete Milestone/Report - CalWIN Wave 2 |  |  | 2022-04-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 145136 | 0 | 0 | 145136 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2022-02-01: 16; 2022-03-01: 16; 2022-04-01: 16 | 48 |  | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 |  | 48 |  | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 |  | 48 | 154 | 0 | 0 | 7392 | 0 | 0 | 7392
2 | Beena Amarnath | QA PMO Lead | 134 | 2022-02-01: 16; 2022-03-01: 16; 2022-04-01: 16 | 48 |  | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 |  | 48 |  | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 |  | 48 | 134 | 0 | 0 | 6432 | 0 | 0 | 6432
3 | Timothy King | QA PMO Specialist | 114 | 2022-02-01: 16; 2022-03-01: 16; 2022-04-01: 16 | 48 |  | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 |  | 48 |  | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 |  | 48 | 114 | 0 | 0 | 5472 | 0 | 0 | 5472
4 | Kristin Pepper | QA Functional Manager | 134 | 2022-02-01: 8; 2022-03-01: 16; 2022-04-01: 24 | 48 |  | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 |  | 48 |  | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 |  | 48 | 134 | 0 | 0 | 6432 | 0 | 0 | 6432
5 | Don Coffey | QA Technical Manager | 144 | 2022-02-01: 8; 2022-03-01: 16; 2022-04-01: 24 | 48 |  | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 |  | 48 |  | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 |  | 48 | 144 | 0 | 0 | 6912 | 0 | 0 | 6912
6 | Abby Darrah | QA Implementation Manager | 134 | 2022-01-01: 40; 2022-02-01: 60; 2022-03-01: 60; 2022-04-01: 60 | 220 |  | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 |  | 220 |  | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 |  | 220 | 134 | 0 | 0 | 29480 | 0 | 0 | 29480
7 | Cheryl Hofmann | QA Testing Manager | 134 | 2022-02-01: 16; 2022-03-01: 16; 2022-04-01: 24 | 56 |  | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 0 | 0 |  | 56 |  | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 0 | 0 |  | 56 | 134 | 0 | 0 | 7504 | 0 | 0 | 7504
8 | Rachel Hernandez | QA UAT Lead | 134 | 2022-02-01: 16; 2022-03-01: 16; 2022-04-01: 24 | 56 |  | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 0 | 0 |  | 56 |  | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 0 | 0 |  | 56 | 134 | 0 | 0 | 7504 | 0 | 0 | 7504
9 | Pandu Gupta | QA Business Analyst/Tester | 114 | 2022-02-01: 16; 2022-03-01: 16; 2022-04-01: 24 | 56 |  | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 0 | 0 |  | 56 |  | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 0 | 0 |  | 56 | 114 | 0 | 0 | 6384 | 0 | 0 | 6384
10 | Gail Brown | QA Implementation Lead | 124 | 2022-01-01: 40; 2022-02-01: 60; 2022-03-01: 60; 2022-04-01: 60 | 220 |  | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 |  | 220 | IFG | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 |  | 220 | 124 | 0 | 0 | 27280 | 0 | 0 | 27280
11 | Ivan Parra | QA Implementation Lead | 124 | 2022-01-01: 40; 2022-02-01: 60; 2022-03-01: 60; 2022-04-01: 60 | 220 |  | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 |  | 220 |  | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 |  | 220 | 124 | 0 | 0 | 27280 | 0 | 0 | 27280
12 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2022-03-01: 4; 2022-04-01: 4 | 8 |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 |  | 8 | 45 | 0 | 0 | 360 | 0 | 0 | 360
13 | Raj Ganesh | QA Conversion Lead | 114 | 2022-02-01: 8; 2022-03-01: 16; 2022-04-01: 24 | 48 |  | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 |  | 48 |  | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 |  | 48 | 114 | 0 | 0 | 5472 | 0 | 0 | 5472
14 | Wendy Battermann | QA Executive | 154 | 2022-04-01: 8 | 8 |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 |  | 8 | 154 | 0 | 0 | 1232 | 0 | 0 | 1232
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #50 - Assessment of DD&I Vendor CalSAWS Deployment Complete Milestone/Report - CalWIN Wave 3 |  |  | 2022-07-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 53880 | 91256 | 0 | 145136 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2022-05-01: 16; 2022-06-01: 16; 2022-07-01: 16 | 48 |  | 0 | 0 | 0 | 32 | 16 | 0 | 0 | 0 | 0 |  | 48 |  | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 |  | 48 | 154 | 0 | 0 | 2464 | 4928 | 0 | 7392
2 | Beena Amarnath | QA PMO Lead | 134 | 2022-05-01: 16; 2022-06-01: 16; 2022-07-01: 16 | 48 |  | 0 | 0 | 0 | 32 | 16 | 0 | 0 | 0 | 0 |  | 48 |  | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 |  | 48 | 134 | 0 | 0 | 2144 | 4288 | 0 | 6432
3 | Timothy King | QA PMO Specialist | 114 | 2022-05-01: 16; 2022-06-01: 16; 2022-07-01: 16 | 48 |  | 0 | 0 | 0 | 32 | 16 | 0 | 0 | 0 | 0 |  | 48 |  | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 |  | 48 | 114 | 0 | 0 | 1824 | 3648 | 0 | 5472
4 | Kristin Pepper | QA Functional Manager | 134 | 2022-05-01: 8; 2022-06-01: 16; 2022-07-01: 24 | 48 |  | 0 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 |  | 48 |  | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 |  | 48 | 134 | 0 | 0 | 1072 | 5360 | 0 | 6432
5 | Don Coffey | QA Technical Manager | 144 | 2022-05-01: 8; 2022-06-01: 16; 2022-07-01: 24 | 48 |  | 0 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 |  | 48 |  | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 |  | 48 | 144 | 0 | 0 | 1152 | 5760 | 0 | 6912
6 | Abby Darrah | QA Implementation Manager | 134 | 2022-04-01: 40; 2022-05-01: 60; 2022-06-01: 60; 2022-07-01: 60 | 220 |  | 0 | 0 | 0 | 160 | 60 | 0 | 0 | 0 | 0 |  | 220 |  | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 |  | 220 | 134 | 0 | 0 | 13400 | 16080 | 0 | 29480
7 | Cheryl Hofmann | QA Testing Manager | 134 | 2022-05-01: 16; 2022-06-01: 16; 2022-07-01: 24 | 56 |  | 0 | 0 | 0 | 32 | 24 | 0 | 0 | 0 | 0 |  | 56 |  | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 0 | 0 |  | 56 | 134 | 0 | 0 | 2144 | 5360 | 0 | 7504
8 | Rachel Hernandez | QA UAT Lead | 134 | 2022-05-01: 16; 2022-06-01: 16; 2022-07-01: 24 | 56 |  | 0 | 0 | 0 | 32 | 24 | 0 | 0 | 0 | 0 |  | 56 |  | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 0 | 0 |  | 56 | 134 | 0 | 0 | 2144 | 5360 | 0 | 7504
9 | Pandu Gupta | QA Business Analyst/Tester | 114 | 2022-05-01: 16; 2022-06-01: 16; 2022-07-01: 24 | 56 |  | 0 | 0 | 0 | 32 | 24 | 0 | 0 | 0 | 0 |  | 56 |  | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 0 | 0 |  | 56 | 114 | 0 | 0 | 1824 | 4560 | 0 | 6384
10 | Gail Brown | QA Implementation Lead | 124 | 2022-04-01: 40; 2022-05-01: 60; 2022-06-01: 60; 2022-07-01: 60 | 220 |  | 0 | 0 | 0 | 160 | 60 | 0 | 0 | 0 | 0 |  | 220 | IFG | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 |  | 220 | 124 | 0 | 0 | 12400 | 14880 | 0 | 27280
11 | Ivan Parra | QA Implementation Lead | 124 | 2022-04-01: 40; 2022-05-01: 60; 2022-06-01: 60; 2022-07-01: 60 | 220 |  | 0 | 0 | 0 | 160 | 60 | 0 | 0 | 0 | 0 |  | 220 |  | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 |  | 220 | 124 | 0 | 0 | 12400 | 14880 | 0 | 27280
12 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2022-06-01: 4; 2022-07-01: 4 | 8 |  | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 |  | 8 | 45 | 0 | 0 | 0 | 360 | 0 | 360
13 | Raj Ganesh | QA Conversion Lead | 114 | 2022-05-01: 8; 2022-06-01: 16; 2022-07-01: 24 | 48 |  | 0 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 |  | 48 |  | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 |  | 48 | 114 | 0 | 0 | 912 | 4560 | 0 | 5472
14 | Wendy Battermann | QA Executive | 154 | 2022-07-01: 8 | 8 |  | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 |  | 8 | 154 | 0 | 0 | 0 | 1232 | 0 | 1232
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #51 - Assessment of DD&I Vendor CalSAWS Deployment Complete Milestone/Report - CalWIN Wave 4 |  |  | 2022-09-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 145824 | 0 | 145824 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2022-07-01: 16; 2022-08-01: 16; 2022-09-01: 16 | 48 |  | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 |  | 48 |  | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 |  | 48 | 154 | 0 | 0 | 0 | 7392 | 0 | 7392
2 | Beena Amarnath | QA PMO Lead | 134 | 2022-07-01: 16; 2022-08-01: 16; 2022-09-01: 16 | 48 |  | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 |  | 48 |  | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 |  | 48 | 134 | 0 | 0 | 0 | 6432 | 0 | 6432
3 | Timothy King | QA PMO Specialist | 114 | 2022-07-01: 16; 2022-08-01: 16; 2022-09-01: 16 | 48 |  | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 |  | 48 |  | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 |  | 48 | 114 | 0 | 0 | 0 | 5472 | 0 | 5472
4 | Kristin Pepper | QA Functional Manager | 134 | 2022-07-01: 8; 2022-08-01: 16; 2022-09-01: 24 | 48 |  | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 |  | 48 |  | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 |  | 48 | 134 | 0 | 0 | 0 | 6432 | 0 | 6432
5 | Don Coffey | QA Technical Manager | 144 | 2022-07-01: 8; 2022-08-01: 16; 2022-09-01: 24 | 48 |  | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 |  | 48 |  | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 |  | 48 | 144 | 0 | 0 | 0 | 6912 | 0 | 6912
6 | Abby Darrah | QA Implementation Manager | 134 | 2022-06-01: 40; 2022-07-01: 60; 2022-08-01: 60; 2022-09-01: 60 | 220 |  | 0 | 0 | 0 | 40 | 180 | 0 | 0 | 0 | 0 |  | 220 |  | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 |  | 220 | 134 | 0 | 0 | 0 | 29480 | 0 | 29480
7 | Cheryl Hofmann | QA Testing Manager | 134 | 2022-07-01: 16; 2022-08-01: 16; 2022-09-01: 24 | 56 |  | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 0 |  | 56 |  | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 0 | 0 |  | 56 | 134 | 0 | 0 | 0 | 7504 | 0 | 7504
8 | Rachel Hernandez | QA UAT Lead | 134 | 2022-07-01: 16; 2022-08-01: 16; 2022-09-01: 24 | 56 |  | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 0 |  | 56 |  | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 0 | 0 |  | 56 | 134 | 0 | 0 | 0 | 7504 | 0 | 7504
9 | Pandu Gupta | QA Business Analyst/Tester | 114 | 2022-07-01: 16; 2022-08-01: 16; 2022-09-01: 24 | 56 |  | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 0 |  | 56 |  | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 0 | 0 |  | 56 | 114 | 0 | 0 | 0 | 6384 | 0 | 6384
10 | Gail Brown | QA Implementation Lead | 124 | 2022-06-01: 40; 2022-07-01: 60; 2022-08-01: 60; 2022-09-01: 60 | 220 |  | 0 | 0 | 0 | 40 | 180 | 0 | 0 | 0 | 0 |  | 220 | IFG | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 |  | 220 | 124 | 0 | 0 | 0 | 27280 | 0 | 27280
11 | Ivan Parra | QA Implementation Lead | 124 | 2022-06-01: 40; 2022-07-01: 60; 2022-08-01: 60; 2022-09-01: 60 | 220 |  | 0 | 0 | 0 | 40 | 180 | 0 | 0 | 0 | 0 |  | 220 |  | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 |  | 220 | 124 | 0 | 0 | 0 | 27280 | 0 | 27280
12 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2022-08-01: 4; 2022-09-01: 4 | 8 |  | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 |  | 8 | 45 | 0 | 0 | 0 | 360 | 0 | 360
13 | Wendy Battermann | QA Executive | 154 | 2022-07-01: 8; 2022-08-01: 16; 2022-09-01: 24 | 48 |  | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 |  | 48 |  | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 |  | 48 | 154 | 0 | 0 | 0 | 7392 | 0 | 7392
14 |  |  |  | 2022-09-01: 8 | 8 |  | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #52 - Assessment of DD&I Vendor CalSAWS Deployment Complete Milestone/Report - CalWIN Wave 5 |  |  | 2022-11-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 145136 | 0 | 145136 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2022-09-01: 16; 2022-10-01: 16; 2022-11-01: 16 | 48 |  | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 |  | 48 |  | 0 | 0 | 0 | 16 | 32 | 0 | 0 | 0 | 0 |  | 48 | 154 | 0 | 0 | 0 | 7392 | 0 | 7392
2 | Beena Amarnath | QA PMO Lead | 134 | 2022-09-01: 16; 2022-10-01: 16; 2022-11-01: 16 | 48 |  | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 |  | 48 |  | 0 | 0 | 0 | 16 | 32 | 0 | 0 | 0 | 0 |  | 48 | 134 | 0 | 0 | 0 | 6432 | 0 | 6432
3 | Timothy King | QA PMO Specialist | 114 | 2022-09-01: 16; 2022-10-01: 16; 2022-11-01: 16 | 48 |  | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 |  | 48 |  | 0 | 0 | 0 | 16 | 32 | 0 | 0 | 0 | 0 |  | 48 | 114 | 0 | 0 | 0 | 5472 | 0 | 5472
4 | Kristin Pepper | QA Functional Manager | 134 | 2022-09-01: 8; 2022-10-01: 16; 2022-11-01: 24 | 48 |  | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 |  | 48 |  | 0 | 0 | 0 | 8 | 40 | 0 | 0 | 0 | 0 |  | 48 | 134 | 0 | 0 | 0 | 6432 | 0 | 6432
5 | Don Coffey | QA Technical Manager | 144 | 2022-09-01: 8; 2022-10-01: 16; 2022-11-01: 24 | 48 |  | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 |  | 48 |  | 0 | 0 | 0 | 8 | 40 | 0 | 0 | 0 | 0 |  | 48 | 144 | 0 | 0 | 0 | 6912 | 0 | 6912
6 | Abby Darrah | QA Implementation Manager | 134 | 2022-08-01: 40; 2022-09-01: 60; 2022-10-01: 60; 2022-11-01: 60 | 220 |  | 0 | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 |  | 220 |  | 0 | 0 | 0 | 100 | 120 | 0 | 0 | 0 | 0 |  | 220 | 134 | 0 | 0 | 0 | 29480 | 0 | 29480
7 | Cheryl Hofmann | QA Testing Manager | 134 | 2022-09-01: 16; 2022-10-01: 16; 2022-11-01: 24 | 56 |  | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 0 |  | 56 |  | 0 | 0 | 0 | 16 | 40 | 0 | 0 | 0 | 0 |  | 56 | 134 | 0 | 0 | 0 | 7504 | 0 | 7504
8 | Rachel Hernandez | QA UAT Lead | 134 | 2022-09-01: 16; 2022-10-01: 16; 2022-11-01: 24 | 56 |  | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 0 |  | 56 |  | 0 | 0 | 0 | 16 | 40 | 0 | 0 | 0 | 0 |  | 56 | 134 | 0 | 0 | 0 | 7504 | 0 | 7504
9 | Pandu Gupta | QA Business Analyst/Tester | 114 | 2022-09-01: 16; 2022-10-01: 16; 2022-11-01: 24 | 56 |  | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 0 |  | 56 |  | 0 | 0 | 0 | 16 | 40 | 0 | 0 | 0 | 0 |  | 56 | 114 | 0 | 0 | 0 | 6384 | 0 | 6384
10 | Gail Brown | QA Implementation Lead | 124 | 2022-08-01: 40; 2022-09-01: 60; 2022-10-01: 60; 2022-11-01: 60 | 220 |  | 0 | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 |  | 220 | IFG | 0 | 0 | 0 | 100 | 120 | 0 | 0 | 0 | 0 |  | 220 | 124 | 0 | 0 | 0 | 27280 | 0 | 27280
11 | Ivan Parra | QA Implementation Lead | 124 | 2022-08-01: 40; 2022-09-01: 60; 2022-10-01: 60; 2022-11-01: 60 | 220 |  | 0 | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 |  | 220 |  | 0 | 0 | 0 | 100 | 120 | 0 | 0 | 0 | 0 |  | 220 | 124 | 0 | 0 | 0 | 27280 | 0 | 27280
12 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2022-10-01: 4; 2022-11-01: 4 | 8 |  | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 |  | 8 | 45 | 0 | 0 | 0 | 360 | 0 | 360
13 | Raj Ganesh | QA Conversion Lead | 114 | 2022-09-01: 8; 2022-10-01: 16; 2022-11-01: 24 | 48 |  | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 |  | 48 |  | 0 | 0 | 0 | 8 | 40 | 0 | 0 | 0 | 0 |  | 48 | 114 | 0 | 0 | 0 | 5472 | 0 | 5472
14 | Wendy Battermann | QA Executive | 154 | 2022-11-01: 8 | 8 |  | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 |  | 8 | 154 | 0 | 0 | 0 | 1232 | 0 | 1232
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #53 - Assessment of DD&I Vendor CalSAWS Deployment Complete Milestone/Report - CalWIN Wave 6 |  |  | 2023-01-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 130128 | 0 | 130128 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2022-11-01: 16; 2022-12-01: 16; 2023-01-01: 16 | 48 |  | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 |  | 48 |  | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 |  | 48 | 154 | 0 | 0 | 0 | 7392 | 0 | 7392
2 | Beena Amarnath | QA PMO Lead | 134 | 2022-11-01: 16; 2022-12-01: 16; 2023-01-01: 16 | 48 |  | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 |  | 48 |  | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 |  | 48 | 134 | 0 | 0 | 0 | 6432 | 0 | 6432
3 | Timothy King | QA PMO Specialist | 114 | 2022-11-01: 16; 2022-12-01: 16; 2023-01-01: 16 | 48 |  | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 |  | 48 |  | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 |  | 48 | 114 | 0 | 0 | 0 | 5472 | 0 | 5472
4 | Kristin Pepper | QA Functional Manager | 134 | 2022-11-01: 8; 2022-12-01: 16; 2023-01-01: 24 | 48 |  | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 |  | 48 |  | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 |  | 48 | 134 | 0 | 0 | 0 | 6432 | 0 | 6432
5 | Don Coffey | QA Technical Manager | 144 | 2022-11-01: 8; 2022-12-01: 16; 2023-01-01: 24 | 48 |  | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 |  | 48 |  | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 |  | 48 | 144 | 0 | 0 | 0 | 6912 | 0 | 6912
6 | Abby Darrah | QA Implementation Manager | 134 | 2022-10-01: 40; 2022-11-01: 60; 2022-12-01: 60; 2023-01-01: 60 | 220 |  | 0 | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 |  | 220 |  | 0 | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 |  | 220 | 134 | 0 | 0 | 0 | 29480 | 0 | 29480
7 | Cheryl Hofmann | QA Testing Manager | 134 | 2022-11-01: 16; 2022-12-01: 16; 2023-01-01: 24 | 56 |  | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 0 |  | 56 |  | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 0 |  | 56 | 134 | 0 | 0 | 0 | 7504 | 0 | 7504
8 | Rachel Hernandez | QA UAT Lead | 134 | 2022-11-01: 16; 2022-12-01: 16; 2023-01-01: 24 | 56 |  | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 0 |  | 56 |  | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 0 |  | 56 | 134 | 0 | 0 | 0 | 7504 | 0 | 7504
9 | Pandu Gupta | QA Business Analyst/Tester | 114 | 2022-11-01: 16; 2022-12-01: 16; 2023-01-01: 24 | 56 |  | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 0 |  | 56 |  | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 0 |  | 56 | 114 | 0 | 0 | 0 | 6384 | 0 | 6384
10 | Gail Brown | QA Implementation Lead | 124 | 2022-10-01: 40; 2022-11-01: 60; 2022-12-01: 60 | 160 |  | 0 | 0 | 0 | 0 | 160 | 0 | 0 | 0 | 0 |  | 160 | IFG | 0 | 0 | 0 | 0 | 160 | 0 | 0 | 0 | 0 |  | 160 | 124 | 0 | 0 | 0 | 19840 | 0 | 19840
11 | Ivan Parra | QA Implementation Lead | 124 | 2022-10-01: 40; 2022-11-01: 60; 2022-12-01: 60 | 160 |  | 0 | 0 | 0 | 0 | 160 | 0 | 0 | 0 | 0 |  | 160 |  | 0 | 0 | 0 | 0 | 160 | 0 | 0 | 0 | 0 |  | 160 | 124 | 0 | 0 | 0 | 19840 | 0 | 19840
12 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2022-11-01: 4; 2022-12-01: 4; 2023-01-01: 4 | 12 |  | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 |  | 12 |  | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 |  | 12 | 45 | 0 | 0 | 0 | 540 | 0 | 540
13 | Raj Ganesh | QA Conversion Lead | 114 | 2022-11-01: 8; 2022-12-01: 16; 2023-01-01: 24 | 48 |  | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 |  | 48 |  | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 |  | 48 | 114 | 0 | 0 | 0 | 5472 | 0 | 5472
14 | Wendy Battermann | QA Executive | 154 | 2023-01-01: 6 | 6 |  | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 |  | 6 |  | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 |  | 6 | 154 | 0 | 0 | 0 | 924 | 0 | 924
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #54 - Assessment of DD&I Vendor CalSAWS Deployment Complete Report - CalWIN Wave 1-6 |  |  | 2023-01-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 61092 | 0 | 61092 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2022-11-01: 4; 2022-12-01: 4; 2023-01-01: 8 | 16 |  | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 |  | 16 |  | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 |  | 16 | 154 | 0 | 0 | 0 | 2464 | 0 | 2464
2 | Beena Amarnath | QA PMO Lead | 134 | 2022-11-01: 8; 2022-12-01: 8; 2023-01-01: 8 | 24 |  | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 |  | 24 |  | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 |  | 24 | 134 | 0 | 0 | 0 | 3216 | 0 | 3216
3 | Timothy King | QA PMO Specialist | 114 | 2022-11-01: 16; 2022-12-01: 16; 2023-01-01: 16 | 48 |  | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 |  | 48 |  | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 |  | 48 | 114 | 0 | 0 | 0 | 5472 | 0 | 5472
4 | Kristin Pepper | QA Functional Manager | 134 | 2022-11-01: 8; 2022-12-01: 16; 2023-01-01: 24 | 48 |  | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 |  | 48 |  | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 |  | 48 | 134 | 0 | 0 | 0 | 6432 | 0 | 6432
5 | Don Coffey | QA Technical Manager | 144 | 2022-11-01: 8; 2022-12-01: 16; 2023-01-01: 24 | 48 |  | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 |  | 48 |  | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 |  | 48 | 144 | 0 | 0 | 0 | 6912 | 0 | 6912
6 | Abby Darrah | QA Implementation Manager | 134 | 2022-12-01: 16; 2023-01-01: 48 | 64 |  | 0 | 0 | 0 | 0 | 64 | 0 | 0 | 0 | 0 |  | 64 |  | 0 | 0 | 0 | 0 | 64 | 0 | 0 | 0 | 0 |  | 64 | 134 | 0 | 0 | 0 | 8576 | 0 | 8576
7 | Cheryl Hofmann | QA Testing Manager | 134 | 2022-11-01: 16; 2022-12-01: 16; 2023-01-01: 24 | 56 |  | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 0 |  | 56 |  | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 0 |  | 56 | 134 | 0 | 0 | 0 | 7504 | 0 | 7504
8 | Rachel Hernandez | QA UAT Lead | 134 | 2022-11-01: 16; 2022-12-01: 16; 2023-01-01: 24 | 56 |  | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 0 |  | 56 |  | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 0 |  | 56 | 134 | 0 | 0 | 0 | 7504 | 0 | 7504
9 | Pandu Gupta | QA Business Analyst/Tester | 114 | 2022-11-01: 16; 2022-12-01: 16; 2023-01-01: 24 | 56 |  | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 0 |  | 56 |  | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 0 |  | 56 | 114 | 0 | 0 | 0 | 6384 | 0 | 6384
10 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2022-11-01: 4; 2022-12-01: 4; 2023-01-01: 4 | 12 |  | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 |  | 12 |  | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 |  | 12 | 45 | 0 | 0 | 0 | 540 | 0 | 540
11 | Raj Ganesh | QA Conversion Lead | 114 | 2022-11-01: 8; 2022-12-01: 16; 2023-01-01: 24 | 48 |  | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 |  | 48 |  | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 |  | 48 | 114 | 0 | 0 | 0 | 5472 | 0 | 5472
12 | Wendy Battermann | QA Executive | 154 | 2023-01-01: 4 | 4 |  | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 |  | 4 |  | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 |  | 4 | 154 | 0 | 0 | 0 | 616 | 0 | 616
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #55 - Assessment of DD&I Vendor CalSAWS Migration Project Control Document Update |  |  | 2023-02-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 14272 | 0 | 14272 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2023-01-01: 8 | 8 |  | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 |  | 8 | 154 | 0 | 0 | 0 | 1232 | 0 | 1232
2 | Beena Amarnath | QA PMO Lead | 134 | 2023-01-01: 16; 2023-02-01: 24 | 40 |  | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 |  | 40 |  | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 |  | 40 | 134 | 0 | 0 | 0 | 5360 | 0 | 5360
3 | Timothy King | QA PMO Specialist | 114 | 2023-01-01: 16; 2023-02-01: 24 | 40 |  | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 |  | 40 |  | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 |  | 40 | 114 | 0 | 0 | 0 | 4560 | 0 | 4560
4 | Kristin Pepper | QA Functional Manager | 134 | 2023-02-01: 16 | 16 |  | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 |  | 16 |  | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 |  | 16 | 134 | 0 | 0 | 0 | 2144 | 0 | 2144
5 | Don Coffey | QA Technical Manager | 144 | [59 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 144 | 0 | 0 | 0 | 0 | 0 | 0
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2023-01-01: 4; 2023-02-01: 4 | 8 |  | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 |  | 8 | 45 | 0 | 0 | 0 | 360 | 0 | 360
7 | Wendy Battermann | QA Executive | 154 | 2023-02-01: 4 | 4 |  | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 |  | 4 |  | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 |  | 4 | 154 | 0 | 0 | 0 | 616 | 0 | 616
8 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #56 - Assessment of DD&I Vendor CalSAWS Migration Final Acceptance Certification |  |  | 2023-04-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 33112 | 0 | 33112 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2023-03-01: 16; 2023-04-01: 24 | 40 |  | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 |  | 40 |  | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 |  | 40 | 154 | 0 | 0 | 0 | 6160 | 0 | 6160
2 | Beena Amarnath | QA PMO Lead | 134 | 2023-03-01: 16; 2023-04-01: 24 | 40 |  | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 |  | 40 |  | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 |  | 40 | 134 | 0 | 0 | 0 | 5360 | 0 | 5360
3 | Timothy King | QA PMO Specialist | 114 | 2023-03-01: 16; 2023-04-01: 24 | 40 |  | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 |  | 40 |  | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 |  | 40 | 114 | 0 | 0 | 0 | 4560 | 0 | 4560
4 | Abby Darrah | QA Implementation Manager | 134 | 2023-02-01: 16; 2023-03-01: 16; 2023-04-01: 24 | 56 |  | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 0 |  | 56 |  | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 0 |  | 56 | 134 | 0 | 0 | 0 | 7504 | 0 | 7504
5 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2023-03-01: 4; 2023-04-01: 4 | 8 |  | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 |  | 8 | 45 | 0 | 0 | 0 | 360 | 0 | 360
6 | Don Coffey | QA Technical Manager | 144 | [59 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 144 | 0 | 0 | 0 | 0 | 0 | 0
7 | Kristin Pepper | QA Functional Manager | 134 | 2023-03-01: 16; 2023-04-01: 16 | 32 |  | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 |  | 32 |  | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 |  | 32 | 134 | 0 | 0 | 0 | 4288 | 0 | 4288
8 | Raj Ganesh | QA Conversion Lead | 114 | 2023-03-01: 16; 2023-04-01: 16 | 32 |  | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 |  | 32 |  | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 |  | 32 | 114 | 0 | 0 | 0 | 3648 | 0 | 3648
9 | Wendy Battermann | QA Executive | 154 | 2023-04-01: 8 | 8 |  | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 |  | 8 | 154 | 0 | 0 | 0 | 1232 | 0 | 1232
10 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #57 - Assessment of CalWIN Implementation Support Vendor CalWIN Migration Work Plan Initial |  |  | 2020-05-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 10168 | 0 | 0 | 0 | 0 | 10168 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2020-04-01: 8; 2020-05-01: 8 | 16 |  | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16 |  | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16 | 154 | 2464 | 0 | 0 | 0 | 0 | 2464
2 | Beena Amarnath | QA PMO Lead | 134 | 2020-04-01: 16; 2020-05-01: 24 | 40 |  | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 |  | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 | 134 | 5360 | 0 | 0 | 0 | 0 | 5360
3 | Timothy King | QA PMO Specialist | 114 | 2020-04-01: 4; 2020-05-01: 8 | 12 |  | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 12 |  | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 12 | 114 | 1368 | 0 | 0 | 0 | 0 | 1368
4 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2020-04-01: 4; 2020-05-01: 4 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 45 | 360 | 0 | 0 | 0 | 0 | 360
5 | Wendy Battermann | QA Executive | 154 | 2020-05-01: 4 | 4 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | 154 | 616 | 0 | 0 | 0 | 0 | 616
6 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #58 - Assessment of CalWIN Implementation Support Vendor CalWIN Migration Project Control Document Initial |  |  | 2020-05-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 17352 | 0 | 0 | 0 | 0 | 17352 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2020-04-01: 8; 2020-05-01: 8 | 16 |  | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16 |  | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16 | 154 | 2464 | 0 | 0 | 0 | 0 | 2464
2 | Beena Amarnath | QA PMO Lead | 134 | 2020-04-01: 16; 2020-05-01: 24 | 40 |  | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 |  | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 | 134 | 5360 | 0 | 0 | 0 | 0 | 5360
3 | Timothy King | QA PMO Specialist | 114 | 2020-04-01: 4; 2020-05-01: 24 | 28 |  | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28 |  | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28 | 114 | 3192 | 0 | 0 | 0 | 0 | 3192
4 | Kristin Pepper | QA Functional Manager | 134 | 2020-04-01: 16; 2020-05-01: 24 | 40 |  | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 |  | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 | 134 | 5360 | 0 | 0 | 0 | 0 | 5360
5 | Don Coffey | QA Technical Manager | 144 | [59 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 144 | 0 | 0 | 0 | 0 | 0 | 0
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2020-04-01: 4; 2020-05-01: 4 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 45 | 360 | 0 | 0 | 0 | 0 | 360
7 | Wendy Battermann | QA Executive | 154 | 2020-05-01: 4 | 4 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | 154 | 616 | 0 | 0 | 0 | 0 | 616
8 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #59 - Assessment of CalWIN Implementation Support Vendor CalWIN Migration Work Plan Update (Monthly) |  |  | 2020-06-01: Due; 2020-07-01: Due; 2020-08-01: Due; 2020-09-01: Due; 2020-10-01: Due; 2020-11-01: Due; 2020-12-01: Due; 2021-01-01: Due; 2021-02-01: Due; 2021-03-01: Due; 2021-04-01: Due; 2021-05-01: Due; 2021-06-01: Due; 2021-07-01: Due; 2021-08-01: Due; 2021-09-01: Due; 2021-10-01: Due; 2021-11-01: Due; 2021-12-01: Due; 2022-01-01: Due; 2022-02-01: Due; 2022-03-01: Due; 2022-04-01: Due; 2022-05-01: Due; 2022-06-01: Due; 2022-07-01: Due; 2022-08-01: Due; 2022-09-01: Due; 2022-10-01: Due; 2022-11-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 72224 | 68256 | 34128 | 0 | 174608 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2020-06-01: 8; 2020-07-01: 8; 2020-08-01: 8; 2020-09-01: 8; 2020-10-01: 8; 2020-11-01: 8; 2020-12-01: 8; 2021-01-01: 8; 2021-02-01: 8; 2021-03-01: 8; 2021-04-01: 8; 2021-05-01: 8; 2021-06-01: 8; 2021-07-01: 8; 2021-08-01: 8; 2021-09-01: 8; 2021-10-01: 8; 2021-11-01: 8; 2021-12-01: 8; 2022-01-01: 8; 2022-02-01: 8; 2022-03-01: 8; 2022-04-01: 8; 2022-05-01: 8; 2022-06-01: 8; 2022-07-01: 8; 2022-08-01: 8; 2022-09-01: 8; 2022-10-01: 8; 2022-11-01: 8 | 240 |  | 0 | 8 | 96 | 96 | 40 | 0 | 0 | 0 | 0 |  | 240 |  | 0 | 32 | 96 | 96 | 16 | 0 | 0 | 0 | 0 |  | 240 | 154 | 0 | 14784 | 14784 | 7392 | 0 | 36960
2 | Beena Amarnath | QA PMO Lead | 134 | 2020-06-01: 24; 2020-07-01: 24; 2020-08-01: 16; 2020-09-01: 16; 2020-10-01: 16; 2020-11-01: 16; 2020-12-01: 16; 2021-01-01: 16; 2021-02-01: 16; 2021-03-01: 16; 2021-04-01: 16; 2021-05-01: 16; 2021-06-01: 16; 2021-07-01: 16; 2021-08-01: 16; 2021-09-01: 16; 2021-10-01: 16; 2021-11-01: 16; 2021-12-01: 16; 2022-01-01: 16; 2022-02-01: 16; 2022-03-01: 16; 2022-04-01: 16; 2022-05-01: 16; 2022-06-01: 16; 2022-07-01: 16; 2022-08-01: 16; 2022-09-01: 16; 2022-10-01: 16; 2022-11-01: 16 | 496 |  | 0 | 24 | 200 | 192 | 80 | 0 | 0 | 0 | 0 |  | 496 |  | 0 | 80 | 192 | 192 | 32 | 0 | 0 | 0 | 0 |  | 496 | 134 | 0 | 27872 | 25728 | 12864 | 0 | 66464
3 | Timothy King | QA PMO Specialist | 114 | 2020-06-01: 24; 2020-07-01: 24; 2020-08-01: 16; 2020-09-01: 16; 2020-10-01: 16; 2020-11-01: 16; 2020-12-01: 16; 2021-01-01: 16; 2021-02-01: 16; 2021-03-01: 16; 2021-04-01: 16; 2021-05-01: 16; 2021-06-01: 16; 2021-07-01: 16; 2021-08-01: 16; 2021-09-01: 16; 2021-10-01: 16; 2021-11-01: 16; 2021-12-01: 16; 2022-01-01: 16; 2022-02-01: 16; 2022-03-01: 16; 2022-04-01: 16; 2022-05-01: 16; 2022-06-01: 16; 2022-07-01: 16; 2022-08-01: 16; 2022-09-01: 16; 2022-10-01: 16; 2022-11-01: 16 | 496 |  | 0 | 24 | 200 | 192 | 80 | 0 | 0 | 0 | 0 |  | 496 |  | 0 | 80 | 192 | 192 | 32 | 0 | 0 | 0 | 0 |  | 496 | 114 | 0 | 23712 | 21888 | 10944 | 0 | 56544
4 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2020-06-01: 4; 2020-07-01: 4; 2020-08-01: 4; 2020-09-01: 4; 2020-10-01: 4; 2020-11-01: 4; 2020-12-01: 4; 2021-01-01: 4; 2021-02-01: 4; 2021-03-01: 4; 2021-04-01: 4; 2021-05-01: 4; 2021-06-01: 4; 2021-07-01: 4; 2021-08-01: 4; 2021-09-01: 4; 2021-10-01: 4; 2021-11-01: 4; 2021-12-01: 4; 2022-01-01: 4; 2022-02-01: 4; 2022-03-01: 4; 2022-04-01: 4; 2022-05-01: 4; 2022-06-01: 4; 2022-07-01: 4; 2022-08-01: 4; 2022-09-01: 4; 2022-10-01: 4; 2022-11-01: 4 | 120 |  | 0 | 4 | 48 | 48 | 20 | 0 | 0 | 0 | 0 |  | 120 |  | 0 | 16 | 48 | 48 | 8 | 0 | 0 | 0 | 0 |  | 120 | 45 | 0 | 2160 | 2160 | 1080 | 0 | 5400
5 | Wendy Battermann | QA Executive | 154 | 2020-06-01: 2; 2020-07-01: 2; 2020-08-01: 2; 2020-09-01: 2; 2020-10-01: 2; 2020-11-01: 2; 2020-12-01: 2; 2021-01-01: 2; 2021-02-01: 2; 2021-03-01: 2; 2021-04-01: 2; 2021-05-01: 2; 2021-06-01: 2; 2021-07-01: 2; 2021-08-01: 2; 2021-09-01: 2; 2021-10-01: 2; 2021-11-01: 2; 2021-12-01: 2; 2022-01-01: 2; 2022-02-01: 2; 2022-03-01: 2; 2022-04-01: 2; 2022-05-01: 2; 2022-06-01: 2; 2022-07-01: 2; 2022-08-01: 2; 2022-09-01: 2; 2022-10-01: 2; 2022-11-01: 2 | 60 |  | 0 | 2 | 24 | 24 | 10 | 0 | 0 | 0 | 0 |  | 60 |  | 0 | 8 | 24 | 24 | 4 | 0 | 0 | 0 | 0 |  | 60 | 154 | 0 | 3696 | 3696 | 1848 | 0 | 9240
6 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #60 - Assessment of CalWIN Implementation Support Vendor CalWIN Master Training Plan |  |  | 2020-10-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 47888 | 0 | 0 | 0 | 47888 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2020-08-01: 8; 2020-09-01: 8; 2020-10-01: 8 | 24 |  | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 |  | 24 |  | 0 | 16 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 24 | 154 | 0 | 3696 | 0 | 0 | 0 | 3696
2 | Timothy King | QA PMO Specialist | 114 | 2020-08-01: 16; 2020-09-01: 4; 2020-10-01: 8 | 28 |  | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28 |  | 0 | 20 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28 | 114 | 0 | 3192 | 0 | 0 | 0 | 3192
3 | Abby Darrah | QA Implementation Manager | 134 | 2020-08-01: 24; 2020-09-01: 24; 2020-10-01: 24 | 72 |  | 0 | 0 | 72 | 0 | 0 | 0 | 0 | 0 | 0 |  | 72 |  | 0 | 48 | 24 | 0 | 0 | 0 | 0 | 0 | 0 |  | 72 | 134 | 0 | 9648 | 0 | 0 | 0 | 9648
4 | Ivan Parra | QA Implementation Lead | 124 | 2020-08-01: 40; 2020-09-01: 40; 2020-10-01: 40 | 120 |  | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 |  | 120 |  | 0 | 80 | 40 | 0 | 0 | 0 | 0 | 0 | 0 |  | 120 | 124 | 0 | 14880 | 0 | 0 | 0 | 14880
5 | Gail Brown | QA Implementation Lead | 124 | 2020-08-01: 40; 2020-09-01: 40; 2020-10-01: 40 | 120 |  | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 |  | 120 | IFG | 0 | 80 | 40 | 0 | 0 | 0 | 0 | 0 | 0 |  | 120 | 124 | 0 | 14880 | 0 | 0 | 0 | 14880 | IFG
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2020-09-01: 4; 2020-10-01: 4 | 8 |  | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 45 | 0 | 360 | 0 | 0 | 0 | 360
7 | Wendy Battermann | QA Executive | 154 | 2020-10-01: 8 | 8 |  | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 154 | 0 | 1232 | 0 | 0 | 0 | 1232
8 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #61 - Assessment of CalWIN Implementation Support Vendor CalWIN Deployment Readiness Plan |  |  | 2021-03-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 124080 | 0 | 0 | 0 | 124080 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2020-11-01: 8; 2020-12-01: 12; 2021-01-01: 16; 2021-02-01: 24; 2021-03-01: 24 | 84 |  | 0 | 0 | 84 | 0 | 0 | 0 | 0 | 0 | 0 |  | 84 |  | 0 | 0 | 84 | 0 | 0 | 0 | 0 | 0 | 0 |  | 84 | 154 | 0 | 12936 | 0 | 0 | 0 | 12936
2 | Beena Amarnath | QA PMO Lead | 134 | 2020-11-01: 8; 2020-12-01: 12; 2021-01-01: 16; 2021-02-01: 24; 2021-03-01: 24 | 84 |  | 0 | 0 | 84 | 0 | 0 | 0 | 0 | 0 | 0 |  | 84 |  | 0 | 0 | 84 | 0 | 0 | 0 | 0 | 0 | 0 |  | 84 | 134 | 0 | 11256 | 0 | 0 | 0 | 11256
3 | Timothy King | QA PMO Specialist | 114 | 2020-11-01: 8; 2020-12-01: 12; 2021-01-01: 16; 2021-02-01: 24; 2021-03-01: 24 | 84 |  | 0 | 0 | 84 | 0 | 0 | 0 | 0 | 0 | 0 |  | 84 |  | 0 | 0 | 84 | 0 | 0 | 0 | 0 | 0 | 0 |  | 84 | 114 | 0 | 9576 | 0 | 0 | 0 | 9576
4 | Kristin Pepper | QA Functional Manager | 134 | 2020-12-01: 8; 2021-01-01: 16; 2021-02-01: 24; 2021-03-01: 32 | 80 |  | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 |  | 80 |  | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 |  | 80 | 134 | 0 | 10720 | 0 | 0 | 0 | 10720
5 | Don Coffey | QA Technical Manager | 144 | 2020-12-01: 8; 2021-01-01: 16; 2021-02-01: 24; 2021-03-01: 32 | 80 |  | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 |  | 80 |  | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 |  | 80 | 144 | 0 | 11520 | 0 | 0 | 0 | 11520
6 | Abby Darrah | QA Implementation Manager | 134 | 2020-12-01: 16; 2021-01-01: 24; 2021-02-01: 32; 2021-03-01: 40 | 112 |  | 0 | 0 | 112 | 0 | 0 | 0 | 0 | 0 | 0 |  | 112 |  | 0 | 0 | 112 | 0 | 0 | 0 | 0 | 0 | 0 |  | 112 | 134 | 0 | 15008 | 0 | 0 | 0 | 15008
7 | Cheryl Hofmann | QA Testing Manager | 134 | 2020-11-01: 8; 2020-12-01: 12; 2021-01-01: 16; 2021-02-01: 24; 2021-03-01: 24 | 84 |  | 0 | 0 | 84 | 0 | 0 | 0 | 0 | 0 | 0 |  | 84 |  | 0 | 0 | 84 | 0 | 0 | 0 | 0 | 0 | 0 |  | 84 | 134 | 0 | 11256 | 0 | 0 | 0 | 11256
8 | Rachel Hernandez | QA UAT Lead | 134 | 2020-11-01: 8; 2020-12-01: 12; 2021-01-01: 16; 2021-02-01: 24; 2021-03-01: 24 | 84 |  | 0 | 0 | 84 | 0 | 0 | 0 | 0 | 0 | 0 |  | 84 |  | 0 | 0 | 84 | 0 | 0 | 0 | 0 | 0 | 0 |  | 84 | 134 | 0 | 11256 | 0 | 0 | 0 | 11256
9 | Gail Brown | QA Implementation Lead | 124 | 2020-12-01: 8; 2021-01-01: 16; 2021-02-01: 24; 2021-03-01: 32 | 80 |  | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 |  | 80 | IFG | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 |  | 80 | 124 | 0 | 9920 | 0 | 0 | 0 | 9920 | IFG
10 | Ivan Parra | QA Implementation Lead | 124 | 2020-12-01: 8; 2021-01-01: 16; 2021-02-01: 24; 2021-03-01: 32 | 80 |  | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 |  | 80 |  | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 |  | 80 | 124 | 0 | 9920 | 0 | 0 | 0 | 9920
11 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2021-02-01: 4; 2021-03-01: 4 | 8 |  | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 45 | 0 | 360 | 0 | 0 | 0 | 360
12 | Raj Ganesh | QA Conversion Lead | 114 | 2020-12-01: 8; 2021-01-01: 16; 2021-02-01: 24; 2021-03-01: 32 | 80 |  | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 |  | 80 |  | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 |  | 80 | 114 | 0 | 9120 | 0 | 0 | 0 | 9120
13 | Wendy Battermann | QA Executive | 154 | 2021-03-01: 8 | 8 |  | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 154 | 0 | 1232 | 0 | 0 | 0 | 1232
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #62 - Assessment of CalWIN Implementation Support Vendor CalWIN Change Management Plan |  |  | 2021-05-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 50464 | 0 | 0 | 0 | 50464 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2021-03-01: 8; 2021-04-01: 8; 2021-05-01: 8 | 24 |  | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 |  | 24 |  | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 |  | 24 | 154 | 0 | 3696 | 0 | 0 | 0 | 3696
2 | Timothy King | QA PMO Specialist | 114 | 2021-03-01: 16; 2021-04-01: 16; 2021-05-01: 24 | 56 |  | 0 | 0 | 56 | 0 | 0 | 0 | 0 | 0 | 0 |  | 56 |  | 0 | 0 | 56 | 0 | 0 | 0 | 0 | 0 | 0 |  | 56 | 114 | 0 | 6384 | 0 | 0 | 0 | 6384
3 | Abby Darrah | QA Implementation Manager | 134 | 2021-03-01: 24; 2021-04-01: 24; 2021-05-01: 24 | 72 |  | 0 | 0 | 72 | 0 | 0 | 0 | 0 | 0 | 0 |  | 72 |  | 0 | 0 | 72 | 0 | 0 | 0 | 0 | 0 | 0 |  | 72 | 134 | 0 | 9648 | 0 | 0 | 0 | 9648
4 | Ivan Parra | QA Implementation Lead | 124 | 2021-03-01: 40; 2021-04-01: 40; 2021-05-01: 40 | 120 |  | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 |  | 120 |  | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 |  | 120 | 124 | 0 | 14880 | 0 | 0 | 0 | 14880
5 | Gail Brown | QA Implementation Lead | 124 | 2021-03-01: 40; 2021-04-01: 40; 2021-05-01: 40 | 120 |  | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 |  | 120 | IFG | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 |  | 120 | 124 | 0 | 14880 | 0 | 0 | 0 | 14880 | IFG
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2021-04-01: 4; 2021-05-01: 4 | 8 |  | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 45 | 0 | 360 | 0 | 0 | 0 | 360
7 | Wendy Battermann | QA Executive | 154 | 2021-05-01: 4 | 4 |  | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | 154 | 0 | 616 | 0 | 0 | 0 | 616
8 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #63 - Assessment of CalWIN Implementation Support Vendor CalWIN ILT Training Material |  |  | 2021-08-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 47408 | 0 | 0 | 47408 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2021-06-01: 4; 2021-07-01: 4; 2021-08-01: 8 | 16 |  | 0 | 0 | 4 | 12 | 0 | 0 | 0 | 0 | 0 |  | 16 |  | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16 | 154 | 0 | 0 | 2464 | 0 | 0 | 2464
2 | Timothy King | QA PMO Specialist | 114 | 2021-06-01: 8; 2021-07-01: 8; 2021-08-01: 24 | 40 |  | 0 | 0 | 8 | 32 | 0 | 0 | 0 | 0 | 0 |  | 40 |  | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 | 114 | 0 | 0 | 4560 | 0 | 0 | 4560
3 | Abby Darrah | QA Implementation Manager | 134 | 2021-06-01: 24; 2021-07-01: 24; 2021-08-01: 24 | 72 |  | 0 | 0 | 24 | 48 | 0 | 0 | 0 | 0 | 0 |  | 72 |  | 0 | 0 | 72 | 0 | 0 | 0 | 0 | 0 | 0 |  | 72 | 134 | 0 | 0 | 9648 | 0 | 0 | 9648
4 | Ivan Parra | QA Implementation Lead | 124 | 2021-06-01: 40; 2021-07-01: 40; 2021-08-01: 40 | 120 |  | 0 | 0 | 40 | 80 | 0 | 0 | 0 | 0 | 0 |  | 120 |  | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 |  | 120 | 124 | 0 | 0 | 14880 | 0 | 0 | 14880
5 | Gail Brown | QA Implementation Lead | 124 | 2021-06-01: 40; 2021-07-01: 40; 2021-08-01: 40 | 120 |  | 0 | 0 | 40 | 80 | 0 | 0 | 0 | 0 | 0 |  | 120 | IFG | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 |  | 120 | 124 | 0 | 0 | 14880 | 0 | 0 | 14880 | IFG
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2021-07-01: 4; 2021-08-01: 4 | 8 |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 45 | 0 | 0 | 360 | 0 | 0 | 360
7 | Wendy Battermann | QA Executive | 154 | 2021-08-01: 4 | 4 |  | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | 154 | 0 | 0 | 616 | 0 | 0 | 616
8 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #64 - Assessment of CalWIN Implementation Support Vendor CalWIN WBT Training Material |  |  | 2021-09-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 48320 | 0 | 0 | 48320 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2021-07-01: 4; 2021-08-01: 4; 2021-09-01: 8 | 16 |  | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 |  | 16 |  | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16 | 154 | 0 | 0 | 2464 | 0 | 0 | 2464
2 | Timothy King | QA PMO Specialist | 114 | 2021-07-01: 4; 2021-08-01: 20; 2021-09-01: 24 | 48 |  | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 |  | 48 |  | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 |  | 48 | 114 | 0 | 0 | 5472 | 0 | 0 | 5472
3 | Abby Darrah | QA Implementation Manager | 134 | 2021-07-01: 24; 2021-08-01: 24; 2021-09-01: 24 | 72 |  | 0 | 0 | 0 | 72 | 0 | 0 | 0 | 0 | 0 |  | 72 |  | 0 | 0 | 72 | 0 | 0 | 0 | 0 | 0 | 0 |  | 72 | 134 | 0 | 0 | 9648 | 0 | 0 | 9648
4 | Ivan Parra | QA Implementation Lead | 124 | 2021-07-01: 40; 2021-08-01: 40; 2021-09-01: 40 | 120 |  | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 |  | 120 |  | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 |  | 120 | 124 | 0 | 0 | 14880 | 0 | 0 | 14880
5 | Gail Brown | QA Implementation Lead | 124 | 2021-07-01: 40; 2021-08-01: 40; 2021-09-01: 40 | 120 |  | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 |  | 120 | IFG | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 |  | 120 | 124 | 0 | 0 | 14880 | 0 | 0 | 14880 | IFG
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2021-08-01: 4; 2021-09-01: 4 | 8 |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 45 | 0 | 0 | 360 | 0 | 0 | 360
7 | Wendy Battermann | QA Executive | 154 | 2021-09-01: 4 | 4 |  | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | 154 | 0 | 0 | 616 | 0 | 0 | 616
8 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #65 - QA Status Report (Monthly) | [61 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 153544 | 1572740 | 1726284 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2023-05-01: 152; 2023-06-01: 156; 2023-07-01: 128; 2023-08-01: 168; 2023-09-01: 140; 2023-10-01: 136; 2023-11-01: 144; 2023-12-01: 140; 2024-01-01: 136; 2024-02-01: 144; 2024-03-01: 148; 2024-04-01: 144 | 1736 |  | 0 | 0 | 0 | 0 | 308 | 1428 | 0 | 0 | 0 |  | 1736 |  | 0 | 0 | 0 | 0 | 744 | 992 | 0 | 0 | 0 |  | 1736 | 154 | 0 | 0 | 0 | 23408 | 243936 | 267344
2 | Beena Amarnath | QA PMO Lead | 134 | 2023-05-01: 168; 2023-06-01: 168; 2023-07-01: 152; 2023-08-01: 176; 2023-09-01: 152; 2023-10-01: 160; 2023-11-01: 152; 2023-12-01: 152; 2024-01-01: 160; 2024-02-01: 152; 2024-03-01: 160; 2024-04-01: 168 | 1920 |  | 0 | 0 | 0 | 0 | 336 | 1584 | 0 | 0 | 0 |  | 1920 |  | 0 | 0 | 0 | 0 | 816 | 1104 | 0 | 0 | 0 |  | 1920 | 134 | 0 | 0 | 0 | 22512 | 234768 | 257280
3 | Kristin Pepper | QA Functional Manager | 134 | 2023-05-01: 176; 2023-06-01: 176; 2023-07-01: 160; 2023-08-01: 184; 2023-09-01: 160; 2023-10-01: 168; 2023-11-01: 160; 2023-12-01: 160; 2024-01-01: 168; 2024-02-01: 160; 2024-03-01: 168; 2024-04-01: 176 | 2016 |  | 0 | 0 | 0 | 0 | 352 | 1664 | 0 | 0 | 0 |  | 2016 |  | 0 | 0 | 0 | 0 | 856 | 1160 | 0 | 0 | 0 |  | 2016 | 134 | 0 | 0 | 0 | 23584 | 246560 | 270144
4 | Don Coffey | QA Technical Manager | 144 | 2023-05-01: 152; 2023-06-01: 120; 2023-07-01: 104; 2023-08-01: 160; 2023-09-01: 104; 2023-10-01: 112; 2023-11-01: 136; 2023-12-01: 104; 2024-01-01: 112; 2024-02-01: 136; 2024-03-01: 112; 2024-04-01: 120 | 1472 |  | 0 | 0 | 0 | 0 | 272 | 1200 | 0 | 0 | 0 |  | 1472 |  | 0 | 0 | 0 | 0 | 640 | 832 | 0 | 0 | 0 |  | 1472 | 144 | 0 | 0 | 0 | 21888 | 190080 | 211968
5 | Cheryl Hofmann | QA Testing Manager | 134 | 2023-05-01: 16; 2023-06-01: 16; 2023-07-01: 16; 2023-08-01: 16; 2023-09-01: 16; 2023-10-01: 16; 2023-11-01: 16; 2023-12-01: 16; 2024-01-01: 16; 2024-02-01: 16; 2024-03-01: 16; 2024-04-01: 16 | 192 |  | 0 | 0 | 0 | 0 | 32 | 160 | 0 | 0 | 0 |  | 192 |  | 0 | 0 | 0 | 0 | 80 | 112 | 0 | 0 | 0 |  | 192 | 134 | 0 | 0 | 0 | 2144 | 23584 | 25728
6 | Timothy King | QA PMO Specialist | 114 | 2023-05-01: 111; 2023-06-01: 102; 2023-07-01: 108; 2023-08-01: 123; 2023-09-01: 90; 2023-10-01: 114; 2023-11-01: 105; 2023-12-01: 90; 2024-01-01: 114; 2024-02-01: 105; 2024-03-01: 96; 2024-04-01: 126 | 1284 |  | 0 | 0 | 0 | 0 | 213 | 1071 | 0 | 0 | 0 |  | 1284 |  | 0 | 0 | 0 | 0 | 534 | 750 | 0 | 0 | 0 |  | 1284 | 114 | 0 | 0 | 0 | 12654 | 133722 | 146376
7 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2023-05-01: 68; 2023-06-01: 68; 2023-07-01: 68; 2023-08-01: 72; 2023-09-01: 68; 2023-10-01: 68; 2023-11-01: 72; 2023-12-01: 68; 2024-01-01: 68; 2024-02-01: 72; 2024-03-01: 68; 2024-04-01: 68 | 828 |  | 0 | 0 | 0 | 0 | 136 | 692 | 0 | 0 | 0 |  | 828 |  | 0 | 0 | 0 | 0 | 344 | 484 | 0 | 0 | 0 |  | 828 | 45 | 0 | 0 | 0 | 3060 | 34200 | 37260
8 | Pandu Gupta | QA Business Analyst/Tester | 114 | 2023-05-01: 176; 2023-06-01: 176; 2023-07-01: 160; 2023-08-01: 184; 2023-09-01: 160; 2023-10-01: 168; 2023-11-01: 160; 2023-12-01: 160; 2024-01-01: 168; 2024-02-01: 160; 2024-03-01: 168; 2024-04-01: 176 | 2016 |  | 0 | 0 | 0 | 0 | 352 | 1664 | 0 | 0 | 0 |  | 2016 |  | 0 | 0 | 0 | 0 | 856 | 1160 | 0 | 0 | 0 |  | 2016 | 114 | 0 | 0 | 0 | 20064 | 209760 | 229824
9 | Greg FitzGerald | QA Technical Lead | 139 | 2023-05-01: 114; 2023-06-01: 90; 2023-07-01: 78; 2023-08-01: 120; 2023-09-01: 78; 2023-10-01: 84; 2023-11-01: 102; 2023-12-01: 78; 2024-01-01: 84; 2024-02-01: 102; 2024-03-01: 84; 2024-04-01: 90 | 1104 |  | 0 | 0 | 0 | 0 | 204 | 900 | 0 | 0 | 0 |  | 1104 |  | 0 | 0 | 0 | 0 | 480 | 624 | 0 | 0 | 0 |  | 1104 | 139 | 0 | 0 | 0 | 15846 | 137610 | 153456
10 | Dustin Lish | QA Technical Lead | 139 | 2023-05-01: 16; 2023-06-01: 16; 2023-07-01: 16; 2023-08-01: 30; 2023-09-01: 24; 2023-10-01: 42; 2023-11-01: 24; 2023-12-01: 24; 2024-01-01: 42; 2024-02-01: 24; 2024-03-01: 26; 2024-04-01: 44 | 328 |  | 0 | 0 | 0 | 0 | 32 | 296 | 0 | 0 | 0 |  | 328 | IFG | 0 | 0 | 0 | 0 | 102 | 226 | 0 | 0 | 0 |  | 328 | 139 | 0 | 0 | 0 | 2224 | 43368 | 45592 | IFG
11 | Wendy Battermann | QA Executive | 154 | 2023-05-01: 20; 2023-06-01: 24; 2023-07-01: 24; 2023-08-01: 24; 2023-09-01: 24; 2023-10-01: 24; 2023-11-01: 24; 2023-12-01: 24; 2024-01-01: 24; 2024-02-01: 24; 2024-03-01: 24; 2024-04-01: 24 | 284 |  | 0 | 0 | 0 | 0 | 44 | 240 | 0 | 0 | 0 |  | 284 |  | 0 | 0 | 0 | 0 | 116 | 168 | 0 | 0 | 0 |  | 284 | 154 | 0 | 0 | 0 | 3080 | 40656 | 43736
12 | Frank Ono | QA Executive | 154 | 2023-05-01: 20; 2023-06-01: 20; 2023-07-01: 20; 2023-08-01: 20; 2023-09-01: 20; 2023-10-01: 20; 2023-11-01: 20; 2023-12-01: 20; 2024-01-01: 20; 2024-02-01: 20; 2024-03-01: 20; 2024-04-01: 24 | 244 |  | 0 | 0 | 0 | 0 | 40 | 204 | 0 | 0 | 0 |  | 244 | IFG | 0 | 0 | 0 | 0 | 100 | 144 | 0 | 0 | 0 |  | 244 | 154 | 0 | 0 | 0 | 3080 | 34496 | 37576
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #66 - QA M&O Testing Plan | [61 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 11516 | 0 | 11516 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2023-05-01: 8 | 8 |  | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 |  | 8 | 154 | 0 | 0 | 0 | 1232 | 0 | 1232
2 | Timothy King | QA PMO Specialist | 114 | 2023-05-01: 8 | 8 |  | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 |  | 8 | 114 | 0 | 0 | 0 | 912 | 0 | 912
3 | Cheryl Hofmann | QA Testing Manager | 134 | 2023-05-01: 48 | 48 |  | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 |  | 48 |  | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 |  | 48 | 134 | 0 | 0 | 0 | 6432 | 0 | 6432
4 | Rachel Hernandez | QA UAT Lead | 134 | 2023-05-01: 16 | 16 |  | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 |  | 16 |  | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 |  | 16 | 134 | 0 | 0 | 0 | 2144 | 0 | 2144
5 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2023-05-01: 4 | 4 |  | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 |  | 4 |  | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 |  | 4 | 45 | 0 | 0 | 0 | 180 | 0 | 180
6 | Wendy Battermann | QA Executive | 154 | 2023-05-01: 4 | 4 |  | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 |  | 4 |  | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 |  | 4 | 154 | 0 | 0 | 0 | 616 | 0 | 616
7 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #67 - QA M&O Monthly Test Report (Monthly) | [61 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 117460 | 1318332 | 1435792 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2023-05-01: 8; 2023-06-01: 8; 2023-07-01: 8; 2023-08-01: 8; 2023-09-01: 8; 2023-10-01: 8; 2023-11-01: 8; 2023-12-01: 8; 2024-01-01: 8; 2024-02-01: 8; 2024-03-01: 8; 2024-04-01: 8 | 96 |  | 0 | 0 | 0 | 0 | 16 | 80 | 0 | 0 | 0 |  | 96 |  | 0 | 0 | 0 | 0 | 40 | 56 | 0 | 0 | 0 |  | 96 | 154 | 0 | 0 | 0 | 1232 | 13552 | 14784
2 | Beena Amarnath | QA PMO Lead | 134 | 2023-05-01: 8; 2023-06-01: 8; 2023-07-01: 8; 2023-08-01: 8; 2023-09-01: 8; 2023-10-01: 8; 2023-11-01: 8; 2023-12-01: 8; 2024-01-01: 8; 2024-02-01: 8; 2024-03-01: 8; 2024-04-01: 8 | 96 |  | 0 | 0 | 0 | 0 | 16 | 80 | 0 | 0 | 0 |  | 96 |  | 0 | 0 | 0 | 0 | 40 | 56 | 0 | 0 | 0 |  | 96 | 134 | 0 | 0 | 0 | 1072 | 11792 | 12864
3 | Timothy King | QA PMO Specialist | 114 | 2023-05-01: 8; 2023-06-01: 8; 2023-07-01: 8; 2023-08-01: 8; 2023-09-01: 8; 2023-10-01: 8; 2023-11-01: 8; 2023-12-01: 8; 2024-01-01: 8; 2024-02-01: 8; 2024-03-01: 8; 2024-04-01: 8 | 96 |  | 0 | 0 | 0 | 0 | 16 | 80 | 0 | 0 | 0 |  | 96 |  | 0 | 0 | 0 | 0 | 40 | 56 | 0 | 0 | 0 |  | 96 | 114 | 0 | 0 | 0 | 912 | 10032 | 10944
4 | Cheryl Hofmann | QA Testing Manager | 134 | 2023-05-01: 112; 2023-06-01: 160; 2023-07-01: 144; 2023-08-01: 168; 2023-09-01: 144; 2023-10-01: 152; 2023-11-01: 144; 2023-12-01: 144; 2024-01-01: 152; 2024-02-01: 144; 2024-03-01: 152; 2024-04-01: 160 | 1776 |  | 0 | 0 | 0 | 0 | 272 | 1504 | 0 | 0 | 0 |  | 1776 |  | 0 | 0 | 0 | 0 | 728 | 1048 | 0 | 0 | 0 |  | 1776 | 134 | 0 | 0 | 0 | 15008 | 222976 | 237984
5 | Rachel Hernandez | QA UAT Lead | 134 | 2023-05-01: 160; 2023-06-01: 176; 2023-07-01: 160; 2023-08-01: 184; 2023-09-01: 160; 2023-10-01: 168; 2023-11-01: 160; 2023-12-01: 160; 2024-01-01: 168; 2024-02-01: 160; 2024-03-01: 168; 2024-04-01: 176 | 2000 |  | 0 | 0 | 0 | 0 | 336 | 1664 | 0 | 0 | 0 |  | 2000 |  | 0 | 0 | 0 | 0 | 840 | 1160 | 0 | 0 | 0 |  | 2000 | 134 | 0 | 0 | 0 | 21440 | 246560 | 268000
6 | Donna Smith | QA Independent Tester/UAT Leader | 114 | 2023-05-01: 176; 2023-06-01: 176; 2023-07-01: 160; 2023-08-01: 184; 2023-09-01: 160; 2023-10-01: 168; 2023-11-01: 160; 2023-12-01: 160; 2024-01-01: 168; 2024-02-01: 160; 2024-03-01: 168; 2024-04-01: 176 | 2016 |  | 0 | 0 | 0 | 0 | 352 | 1664 | 0 | 0 | 0 |  | 2016 |  | 0 | 0 | 0 | 0 | 856 | 1160 | 0 | 0 | 0 |  | 2016 | 114 | 0 | 0 | 0 | 20064 | 209760 | 229824
7 | Sindura Kompulira | QA Independent Tester/UAT Leader | 114 | 2023-05-01: 176; 2023-06-01: 176; 2023-07-01: 160; 2023-08-01: 184; 2023-09-01: 160; 2023-10-01: 168; 2023-11-01: 160; 2023-12-01: 160; 2024-01-01: 168; 2024-02-01: 160; 2024-03-01: 168; 2024-04-01: 176 | 2016 |  | 0 | 0 | 0 | 0 | 352 | 1664 | 0 | 0 | 0 |  | 2016 | IFG | 0 | 0 | 0 | 0 | 856 | 1160 | 0 | 0 | 0 |  | 2016 | 114 | 0 | 0 | 0 | 20064 | 209760 | 229824 | IFG
8 | Kim Sinclair | QA Independent Tester | 99 | 2023-05-01: 176; 2023-06-01: 176; 2023-07-01: 160; 2023-08-01: 184; 2023-09-01: 160; 2023-10-01: 168; 2023-11-01: 160; 2023-12-01: 160; 2024-01-01: 168; 2024-02-01: 160; 2024-03-01: 168; 2024-04-01: 176 | 2016 |  | 0 | 0 | 0 | 0 | 352 | 1664 | 0 | 0 | 0 |  | 2016 | IFG | 0 | 0 | 0 | 0 | 856 | 1160 | 0 | 0 | 0 |  | 2016 | 99 | 0 | 0 | 0 | 17424 | 182160 | 199584 | IFG
9 | Lalitha Ramabholta | QA Independent Tester/UAT Leader | 114 | 2023-05-01: 176; 2023-06-01: 176; 2023-07-01: 160; 2023-08-01: 184; 2023-09-01: 160; 2023-10-01: 168; 2023-11-01: 160; 2023-12-01: 160; 2024-01-01: 168; 2024-02-01: 160; 2024-03-01: 168; 2024-04-01: 176 | 2016 |  | 0 | 0 | 0 | 0 | 352 | 1664 | 0 | 0 | 0 |  | 2016 |  | 0 | 0 | 0 | 0 | 856 | 1160 | 0 | 0 | 0 |  | 2016 | 114 | 0 | 0 | 0 | 20064 | 209760 | 229824
10 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2023-05-01: 4; 2023-06-01: 4; 2023-07-01: 4; 2023-08-01: 4; 2023-09-01: 4; 2023-10-01: 4; 2023-11-01: 4; 2023-12-01: 4; 2024-01-01: 4; 2024-02-01: 4; 2024-03-01: 4; 2024-04-01: 4 | 48 |  | 0 | 0 | 0 | 0 | 8 | 40 | 0 | 0 | 0 |  | 48 |  | 0 | 0 | 0 | 0 | 20 | 28 | 0 | 0 | 0 |  | 48 | 45 | 0 | 0 | 0 | 180 | 1980 | 2160
11 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #68 - Quarterly QA Security Report (Quarterly) | [61 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 136288 | 136288 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2023-06-01: 4; 2023-07-01: 16; 2023-09-01: 4; 2023-10-01: 16; 2023-12-01: 4; 2024-01-01: 16; 2024-03-01: 4; 2024-04-01: 16 | 80 |  | 0 | 0 | 0 | 0 | 4 | 76 | 0 | 0 | 0 |  | 80 |  | 0 | 0 | 0 | 0 | 24 | 56 | 0 | 0 | 0 |  | 80 | 154 | 0 | 0 | 0 | 0 | 12320 | 12320
2 | Don Coffey | QA Technical Manager | 144 | 2023-06-01: 32; 2023-07-01: 32; 2023-09-01: 32; 2023-10-01: 32; 2023-12-01: 32; 2024-01-01: 32; 2024-03-01: 32; 2024-04-01: 32 | 256 |  | 0 | 0 | 0 | 0 | 32 | 224 | 0 | 0 | 0 |  | 256 |  | 0 | 0 | 0 | 0 | 96 | 160 | 0 | 0 | 0 |  | 256 | 144 | 0 | 0 | 0 | 0 | 36864 | 36864
3 | Greg FitzGerald | QA Technical Lead | 139 | 2023-06-01: 32; 2023-07-01: 32; 2023-09-01: 32; 2023-10-01: 32; 2023-12-01: 32; 2024-01-01: 32; 2024-03-01: 32; 2024-04-01: 32 | 256 |  | 0 | 0 | 0 | 0 | 32 | 224 | 0 | 0 | 0 |  | 256 |  | 0 | 0 | 0 | 0 | 96 | 160 | 0 | 0 | 0 |  | 256 | 139 | 0 | 0 | 0 | 0 | 35584 | 35584
4 | Dustin Lish | QA Technical Lead | 139 | 2023-06-01: 16; 2023-07-01: 16; 2023-09-01: 16; 2023-10-01: 16; 2023-12-01: 16; 2024-01-01: 16; 2024-03-01: 16; 2024-04-01: 16 | 128 |  | 0 | 0 | 0 | 0 | 16 | 112 | 0 | 0 | 0 |  | 128 | IFG | 0 | 0 | 0 | 0 | 48 | 80 | 0 | 0 | 0 |  | 128 | 139 | 0 | 0 | 0 | 0 | 17792 | 17792 | IFG
5 | Timothy King | QA PMO Specialist | 114 | 2023-06-01: 4; 2023-07-01: 24; 2023-09-01: 4; 2023-10-01: 24; 2023-12-01: 4; 2024-01-01: 24; 2024-03-01: 4; 2024-04-01: 24 | 112 |  | 0 | 0 | 0 | 0 | 4 | 108 | 0 | 0 | 0 |  | 112 |  | 0 | 0 | 0 | 0 | 32 | 80 | 0 | 0 | 0 |  | 112 | 114 | 0 | 0 | 0 | 0 | 12768 | 12768
6 | Donna Smith | QA Independent Tester/UAT Leader | 114 | 2023-06-01: 8; 2023-07-01: 24; 2023-09-01: 8; 2023-10-01: 24; 2023-12-01: 8; 2024-01-01: 24; 2024-03-01: 8; 2024-04-01: 24 | 128 |  | 0 | 0 | 0 | 0 | 8 | 120 | 0 | 0 | 0 |  | 128 |  | 0 | 0 | 0 | 0 | 40 | 88 | 0 | 0 | 0 |  | 128 | 114 | 0 | 0 | 0 | 0 | 14592 | 14592
7 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2023-06-01: 4; 2023-07-01: 4; 2023-09-01: 4; 2023-10-01: 4; 2023-12-01: 4; 2024-01-01: 4; 2024-03-01: 4; 2024-04-01: 4 | 32 |  | 0 | 0 | 0 | 0 | 4 | 28 | 0 | 0 | 0 |  | 32 |  | 0 | 0 | 0 | 0 | 12 | 20 | 0 | 0 | 0 |  | 32 | 45 | 0 | 0 | 0 | 0 | 1440 | 1440
8 | Frank Ono | QA Executive | 154 | 2023-07-01: 8; 2023-10-01: 8; 2024-01-01: 8; 2024-04-01: 8 | 32 |  | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  | 32 | IFG | 0 | 0 | 0 | 0 | 8 | 24 | 0 | 0 | 0 |  | 32 | 154 | 0 | 0 | 0 | 0 | 4928 | 4928 | IFG
9 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #69 - Monthly SLA & Performance Review Report (Monthly) | [61 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 9732 | 107052 | 116784 | subtotal
1 | Dan Dean | QA Project Manager | 154 | 2023-05-01: 8; 2023-06-01: 8; 2023-07-01: 8; 2023-08-01: 8; 2023-09-01: 8; 2023-10-01: 8; 2023-11-01: 8; 2023-12-01: 8; 2024-01-01: 8; 2024-02-01: 8; 2024-03-01: 8; 2024-04-01: 8 | 96 |  | 0 | 0 | 0 | 0 | 16 | 80 | 0 | 0 | 0 |  | 96 |  | 0 | 0 | 0 | 0 | 40 | 56 | 0 | 0 | 0 |  | 96 | 154 | 0 | 0 | 0 | 1232 | 13552 | 14784
2 | Don Coffey | QA Technical Manager | 144 | 2023-05-01: 24; 2023-06-01: 24; 2023-07-01: 24; 2023-08-01: 24; 2023-09-01: 24; 2023-10-01: 24; 2023-11-01: 24; 2023-12-01: 24; 2024-01-01: 24; 2024-02-01: 24; 2024-03-01: 24; 2024-04-01: 24 | 288 |  | 0 | 0 | 0 | 0 | 48 | 240 | 0 | 0 | 0 |  | 288 |  | 0 | 0 | 0 | 0 | 120 | 168 | 0 | 0 | 0 |  | 288 | 144 | 0 | 0 | 0 | 3456 | 38016 | 41472
3 | Greg FitzGerald | QA Technical Lead | 139 | 2023-05-01: 24; 2023-06-01: 24; 2023-07-01: 24; 2023-08-01: 24; 2023-09-01: 24; 2023-10-01: 24; 2023-11-01: 24; 2023-12-01: 24; 2024-01-01: 24; 2024-02-01: 24; 2024-03-01: 24; 2024-04-01: 24 | 288 |  | 0 | 0 | 0 | 0 | 48 | 240 | 0 | 0 | 0 |  | 288 |  | 0 | 0 | 0 | 0 | 120 | 168 | 0 | 0 | 0 |  | 288 | 139 | 0 | 0 | 0 | 3336 | 36696 | 40032
4 | Timothy King | QA PMO Specialist | 114 | 2023-05-01: 8; 2023-06-01: 8; 2023-07-01: 8; 2023-08-01: 8; 2023-09-01: 8; 2023-10-01: 8; 2023-11-01: 8; 2023-12-01: 8; 2024-01-01: 8; 2024-02-01: 8; 2024-03-01: 8; 2024-04-01: 8 | 96 |  | 0 | 0 | 0 | 0 | 16 | 80 | 0 | 0 | 0 |  | 96 |  | 0 | 0 | 0 | 0 | 40 | 56 | 0 | 0 | 0 |  | 96 | 114 | 0 | 0 | 0 | 912 | 10032 | 10944
5 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2023-05-01: 4; 2023-06-01: 4; 2023-07-01: 4; 2023-08-01: 4; 2023-09-01: 4; 2023-10-01: 4; 2023-11-01: 4; 2023-12-01: 4; 2024-01-01: 4; 2024-02-01: 4; 2024-03-01: 4; 2024-04-01: 4 | 48 |  | 0 | 0 | 0 | 0 | 8 | 40 | 0 | 0 | 0 |  | 48 |  | 0 | 0 | 0 | 0 | 20 | 28 | 0 | 0 | 0 |  | 48 | 45 | 0 | 0 | 0 | 180 | 1980 | 2160
6 | Frank Ono | QA Executive | 154 | 2023-05-01: 4; 2023-06-01: 4; 2023-07-01: 4; 2023-08-01: 4; 2023-09-01: 4; 2023-10-01: 4; 2023-11-01: 4; 2023-12-01: 4; 2024-01-01: 4; 2024-02-01: 4; 2024-03-01: 4; 2024-04-01: 4 | 48 |  | 0 | 0 | 0 | 0 | 8 | 40 | 0 | 0 | 0 |  | 48 | IFG | 0 | 0 | 0 | 0 | 20 | 28 | 0 | 0 | 0 |  | 48 | 154 | 0 | 0 | 0 | 616 | 6776 | 7392 | IFG
7 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[65 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 3578733 | 4231648 | 4183470 | 3928361 | 3134412 | 19056624
[65 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 724924 | 932228 | 835648 | 701704 | 464784 | 3659288
[65 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 20.26% | 22.03% | 19.97% | 17.86% | 14.83% | 19.2% | IFG Percentage by Invoice Month and SFY
|  |  |  | 0 | 1897 | 2726 | 2641 | 2754 | 2414 | 2679 | 2791 | 2556 | 2909 | 2807 | 2701 | 2832 | 2912 | 2958 | 2881 | 2869 | 2785 | 2836 | 2702 | 2527 | 3086 | 2967 | 2785 | 2957 | 2858 | 3046 | 2832 | 2726 | 2651 | 2698 | 2882 | 2524 | 2809 | 2853 | 2910 | 2922 | 2660 | 3029 | 2797 | 2813 | 2662 | 2652 | 2490 | 2210 | 2665 | 2459 | 2353 | 2372 | 2234 | 2465 | 2180 | 2360 | 2159 | 2180 | 2360 | 2159 | 2282 | 2472 | 153696 |  | 0 | 31707 | 34265 | 33711 | 31162 | 22851 | 0 | 0 | 0 |  | 153696 |  | 7264 | 33194 | 34250 | 33461 | 29555 | 15972 | 0 | 0 | 0 |  | 153696
Summary by Staff Name
1 | Dan Dean | QA Project Manager |  | 0 | 176 | 160 | 160 | 168 | 144 | 160 | 168 | 152 | 176 | 168 | 152 | 160 | 168 | 168 | 160 | 160 | 160 | 160 | 152 | 144 | 176 | 168 | 160 | 168 | 168 | 176 | 160 | 160 | 152 | 152 | 168 | 144 | 160 | 168 | 168 | 168 | 160 | 176 | 160 | 168 | 152 | 152 | 168 | 144 | 176 | 168 | 176 | 176 | 160 | 184 | 160 | 168 | 160 | 160 | 168 | 160 | 168 | 176 | 9472 | 7456 | 0 | 1944 | 1944 | 1944 | 1976 | 1664 | 0 | 0 | 0 |  | 9472 |  | 496 | 1944 | 1952 | 1936 | 1984 | 1160 | 0 | 0 | 0 |  | 9472
2 | Beena Amarnath | QA PMO Lead |  | 0 | 176 | 160 | 160 | 168 | 144 | 160 | 168 | 152 | 176 | 168 | 152 | 160 | 168 | 168 | 160 | 160 | 160 | 160 | 152 | 144 | 176 | 168 | 160 | 168 | 160 | 176 | 160 | 152 | 152 | 152 | 160 | 144 | 160 | 160 | 168 | 168 | 152 | 176 | 168 | 160 | 152 | 152 | 160 | 144 | 176 | 160 | 176 | 176 | 160 | 184 | 160 | 168 | 160 | 160 | 168 | 160 | 168 | 176 | 9416 | 7400 | 0 | 1944 | 1944 | 1912 | 1952 | 1664 | 0 | 0 | 0 |  | 9416 |  | 496 | 1944 | 1944 | 1912 | 1960 | 1160 | 0 | 0 | 0 |  | 9416
3 | Kristin Pepper | QA Functional Manager |  | 0 | 176 | 160 | 168 | 168 | 144 | 160 | 168 | 152 | 176 | 168 | 152 | 160 | 168 | 168 | 160 | 160 | 160 | 160 | 152 | 144 | 176 | 168 | 160 | 168 | 160 | 176 | 160 | 152 | 152 | 152 | 176 | 144 | 160 | 160 | 168 | 168 | 152 | 176 | 160 | 160 | 152 | 152 | 160 | 144 | 176 | 144 | 176 | 176 | 160 | 184 | 160 | 168 | 160 | 160 | 168 | 160 | 168 | 176 | 9416 | 7400 | 0 | 1952 | 1944 | 1928 | 1928 | 1664 | 0 | 0 | 0 |  | 9416 |  | 504 | 1944 | 1944 | 1920 | 1944 | 1160 | 0 | 0 | 0 |  | 9416
4 | Don Coffey | QA Technical Manager |  | 0 | 176 | 160 | 160 | 168 | 144 | 160 | 168 | 152 | 176 | 168 | 152 | 160 | 168 | 168 | 160 | 160 | 160 | 160 | 152 | 144 | 176 | 168 | 160 | 168 | 168 | 176 | 160 | 160 | 152 | 152 | 168 | 144 | 160 | 168 | 168 | 168 | 160 | 176 | 168 | 168 | 152 | 152 | 160 | 144 | 176 | 160 | 176 | 176 | 160 | 184 | 160 | 168 | 160 | 160 | 168 | 160 | 168 | 176 | 9464 | 7448 | 0 | 1944 | 1944 | 1944 | 1968 | 1664 | 0 | 0 | 0 |  | 9464 |  | 496 | 1944 | 1952 | 1944 | 1968 | 1160 | 0 | 0 | 0 |  | 9464
5 | Abby Darrah | QA Implementation Manager |  | 0 | 0 | 160 | 160 | 168 | 144 | 160 | 168 | 152 | 176 | 168 | 152 | 160 | 168 | 168 | 160 | 160 | 160 | 160 | 152 | 144 | 176 | 168 | 160 | 168 | 160 | 176 | 160 | 152 | 152 | 152 | 160 | 144 | 160 | 160 | 168 | 168 | 152 | 176 | 160 | 160 | 152 | 152 | 160 | 144 | 176 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7216 | 7216 | 0 | 1768 | 1944 | 1912 | 1592 | 0 | 0 | 0 | 0 |  | 7216 |  | 320 | 1944 | 1944 | 1904 | 1104 | 0 | 0 | 0 | 0 |  | 7216
6 | Cheryl Hofmann | QA Testing Manager |  | 0 | 176 | 160 | 160 | 168 | 144 | 160 | 168 | 152 | 176 | 168 | 152 | 160 | 168 | 168 | 160 | 160 | 160 | 160 | 152 | 144 | 176 | 168 | 160 | 168 | 160 | 176 | 160 | 152 | 152 | 152 | 160 | 144 | 160 | 160 | 168 | 168 | 152 | 176 | 160 | 160 | 152 | 152 | 160 | 144 | 176 | 160 | 176 | 176 | 160 | 184 | 160 | 168 | 160 | 160 | 168 | 160 | 168 | 176 | 9408 | 7392 | 0 | 1944 | 1944 | 1912 | 1944 | 1664 | 0 | 0 | 0 |  | 9408 |  | 496 | 1944 | 1944 | 1904 | 1960 | 1160 | 0 | 0 | 0 |  | 9408
7 | Rachel Hernandez | QA UAT Lead |  | 0 | 176 | 160 | 160 | 168 | 144 | 160 | 168 | 152 | 176 | 168 | 152 | 160 | 168 | 168 | 168 | 160 | 160 | 160 | 152 | 144 | 176 | 168 | 160 | 168 | 160 | 176 | 160 | 152 | 152 | 152 | 160 | 144 | 144 | 160 | 168 | 168 | 152 | 176 | 160 | 160 | 152 | 152 | 160 | 144 | 176 | 160 | 176 | 176 | 160 | 184 | 160 | 168 | 160 | 160 | 168 | 160 | 168 | 176 | 9400 | 7384 | 0 | 1944 | 1952 | 1896 | 1944 | 1664 | 0 | 0 | 0 |  | 9400 |  | 496 | 1952 | 1944 | 1888 | 1960 | 1160 | 0 | 0 | 0 |  | 9400
8 | Timothy King | QA PMO Specialist |  | 0 | 152 | 152 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 152 | 144 | 144 | 152 | 144 | 144 | 152 | 144 | 144 | 152 | 144 | 144 | 152 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 135 | 122 | 148 | 139 | 110 | 154 | 121 | 110 | 154 | 121 | 116 | 166 | 8276 | 6680 | 0 | 1744 | 1728 | 1760 | 1705 | 1339 | 0 | 0 | 0 |  | 8276 |  | 448 | 1728 | 1736 | 1760 | 1662 | 942 | 0 | 0 | 0 |  | 8276
9 | Julie Hereth | QA Sr. Administrative Assistant |  | 0 | 91 | 82 | 77 | 80 | 66 | 77 | 83 | 74 | 81 | 85 | 77 | 84 | 78 | 80 | 82 | 82 | 77 | 80 | 76 | 71 | 86 | 85 | 77 | 83 | 82 | 86 | 84 | 76 | 69 | 76 | 82 | 68 | 77 | 77 | 76 | 80 | 74 | 81 | 77 | 77 | 80 | 74 | 80 | 66 | 81 | 75 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 4572 | 3612 | 0 | 957 | 957 | 933 | 925 | 800 | 0 | 0 | 0 |  | 4572 |  | 250 | 947 | 969 | 913 | 933 | 560 | 0 | 0 | 0 |  | 4572
10 | Raj Ganesh | QA Conversion Lead |  | 0 | 164 | 160 | 168 | 168 | 144 | 160 | 168 | 152 | 176 | 168 | 152 | 160 | 168 | 168 | 160 | 160 | 160 | 160 | 152 | 144 | 176 | 168 | 160 | 168 | 160 | 176 | 160 | 152 | 152 | 152 | 160 | 144 | 160 | 160 | 168 | 168 | 144 | 160 | 136 | 160 | 152 | 152 | 160 | 144 | 176 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7340 | 7340 | 0 | 1940 | 1944 | 1912 | 1544 | 0 | 0 | 0 | 0 |  | 7340 |  | 492 | 1944 | 1944 | 1856 | 1104 | 0 | 0 | 0 | 0 |  | 7340
11 | Pandu Gupta | QA Business Analyst/Tester |  | 0 | 104 | 160 | 160 | 168 | 144 | 160 | 168 | 152 | 176 | 168 | 152 | 160 | 168 | 168 | 160 | 160 | 160 | 160 | 152 | 144 | 176 | 168 | 160 | 168 | 160 | 176 | 160 | 152 | 152 | 152 | 168 | 144 | 160 | 160 | 168 | 168 | 152 | 176 | 160 | 160 | 152 | 152 | 160 | 144 | 176 | 160 | 176 | 176 | 160 | 184 | 160 | 168 | 160 | 160 | 168 | 160 | 168 | 176 | 9344 | 7328 | 0 | 1872 | 1944 | 1920 | 1944 | 1664 | 0 | 0 | 0 |  | 9344 |  | 424 | 1944 | 1944 | 1912 | 1960 | 1160 | 0 | 0 | 0 |  | 9344
12 | Donna Smith | QA Independent Tester/UAT Leader |  | 0 | 104 | 160 | 160 | 168 | 144 | 160 | 168 | 152 | 176 | 168 | 152 | 160 | 168 | 168 | 160 | 160 | 160 | 160 | 152 | 144 | 176 | 168 | 160 | 168 | 160 | 176 | 160 | 152 | 152 | 152 | 160 | 144 | 160 | 160 | 168 | 168 | 128 | 176 | 160 | 160 | 152 | 152 | 160 | 144 | 176 | 160 | 176 | 184 | 184 | 184 | 168 | 192 | 160 | 168 | 192 | 160 | 176 | 200 | 9440 | 7296 | 0 | 1872 | 1944 | 1912 | 1928 | 1784 | 0 | 0 | 0 |  | 9440 |  | 424 | 1944 | 1944 | 1880 | 2000 | 1248 | 0 | 0 | 0 |  | 9440
13 | Kim Sinclair | QA Independent Tester |  | 0 | 0 | 160 | 160 | 168 | 144 | 160 | 168 | 152 | 176 | 168 | 152 | 160 | 168 | 168 | 160 | 160 | 160 | 160 | 152 | 144 | 176 | 168 | 160 | 168 | 160 | 176 | 160 | 152 | 152 | 152 | 160 | 144 | 160 | 160 | 168 | 168 | 152 | 176 | 160 | 160 | 152 | 152 | 160 | 144 | 176 | 160 | 176 | 176 | 160 | 184 | 160 | 168 | 160 | 160 | 168 | 160 | 168 | 176 | 9232 | 7216 | 0 | 1768 | 1944 | 1912 | 1944 | 1664 | 0 | 0 | 0 |  | 9232 | IFG | 320 | 1944 | 1944 | 1904 | 1960 | 1160 | 0 | 0 | 0 |  | 9232 | [7 empty] | IFG
14 | Sindura Kompulira | QA Independent Tester/UAT Leader |  | 0 | 0 | 160 | 160 | 168 | 144 | 160 | 168 | 152 | 176 | 168 | 152 | 160 | 168 | 168 | 164 | 160 | 160 | 160 | 152 | 144 | 176 | 168 | 160 | 168 | 160 | 176 | 160 | 152 | 152 | 152 | 160 | 144 | 160 | 160 | 168 | 168 | 152 | 176 | 160 | 160 | 152 | 152 | 160 | 144 | 176 | 160 | 176 | 176 | 160 | 184 | 160 | 168 | 160 | 160 | 168 | 160 | 168 | 176 | 9236 | 7220 | 0 | 1768 | 1948 | 1912 | 1944 | 1664 | 0 | 0 | 0 |  | 9236 | IFG | 320 | 1948 | 1944 | 1904 | 1960 | 1160 | 0 | 0 | 0 |  | 9236 | [7 empty] | IFG
15 | Lalitha Ramabholta | QA Independent Tester/UAT Leader |  | 0 | 0 | 160 | 160 | 168 | 144 | 160 | 168 | 152 | 176 | 168 | 152 | 160 | 168 | 168 | 160 | 160 | 160 | 160 | 152 | 144 | 176 | 168 | 160 | 168 | 160 | 176 | 160 | 152 | 152 | 152 | 160 | 144 | 160 | 160 | 168 | 168 | 152 | 176 | 160 | 160 | 152 | 152 | 160 | 144 | 176 | 160 | 176 | 176 | 160 | 184 | 160 | 168 | 160 | 160 | 168 | 160 | 168 | 176 | 9232 | 7216 | 0 | 1768 | 1944 | 1912 | 1944 | 1664 | 0 | 0 | 0 |  | 9232 | IFG | 320 | 1944 | 1944 | 1904 | 1960 | 1160 | 0 | 0 | 0 |  | 9232 | [7 empty] | IFG
16 | Greg FitzGerald | QA Technical Lead |  | 0 | 144 | 144 | 144 | 152 | 128 | 136 | 152 | 128 | 160 | 144 | 136 | 136 | 126 | 134 | 135 | 135 | 120 | 128 | 122 | 108 | 140 | 134 | 120 | 134 | 128 | 132 | 128 | 122 | 114 | 122 | 128 | 108 | 128 | 128 | 126 | 126 | 114 | 132 | 120 | 120 | 114 | 114 | 120 | 88 | 112 | 112 | 138 | 146 | 134 | 144 | 134 | 140 | 126 | 134 | 140 | 126 | 140 | 146 | 7524 | 5876 | 0 | 1704 | 1536 | 1490 | 1430 | 1364 | 0 | 0 | 0 |  | 7524 |  | 432 | 1667 | 1529 | 1468 | 1476 | 952 | 0 | 0 | 0 |  | 7524
17 | Dustin Lish | QA Technical Lead |  | 0 | 44 | 36 | 28 | 36 | 28 | 44 | 28 | 44 | 28 | 48 | 28 | 28 | 8 | 40 | 68 | 68 | 8 | 40 | 40 | 8 | 40 | 40 | 8 | 40 | 40 | 8 | 40 | 40 | 8 | 40 | 40 | 8 | 40 | 40 | 8 | 16 | 16 | 8 | 16 | 16 | 8 | 16 | 16 | 8 | 16 | 16 | 16 | 32 | 32 | 30 | 40 | 58 | 24 | 40 | 58 | 24 | 42 | 60 | 1748 | 1292 | 0 | 420 | 408 | 328 | 184 | 408 | 0 | 0 | 0 |  | 1748 |  | 108 | 428 | 380 | 280 | 246 | 306 | 0 | 0 | 0 |  | 1748
18 | Ivan Parra | QA Implementation Lead |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152 | 160 | 168 | 168 | 160 | 160 | 160 | 160 | 152 | 144 | 176 | 168 | 160 | 168 | 160 | 176 | 160 | 152 | 152 | 152 | 160 | 144 | 160 | 160 | 168 | 168 | 152 | 176 | 160 | 160 | 152 | 152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5120 | 5120 | 0 | 312 | 1944 | 1912 | 952 | 0 | 0 | 0 | 0 |  | 5120 | IFG | 0 | 808 | 1944 | 1904 | 464 | 0 | 0 | 0 | 0 |  | 5120 | [7 empty] | IFG
19 | Gail Brown | QA Implementation Lead |  | 0 | 0 | 160 | 120 | 120 | 144 | 160 | 168 | 152 | 176 | 168 | 152 | 160 | 168 | 168 | 160 | 160 | 160 | 168 | 152 | 144 | 176 | 168 | 160 | 168 | 160 | 176 | 160 | 152 | 152 | 152 | 160 | 144 | 160 | 160 | 168 | 168 | 152 | 176 | 160 | 160 | 152 | 152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6496 | 6496 | 0 | 1680 | 1952 | 1912 | 952 | 0 | 0 | 0 | 0 |  | 6496 |  | 280 | 1896 | 1952 | 1904 | 464 | 0 | 0 | 0 | 0 |  | 6496
20 | Wendy Battermann | QA Executive |  | 0 | 22 | 28 | 16 | 20 | 16 | 20 | 16 | 18 | 16 | 16 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 24 | 20 | 20 | 20 | 20 | 20 | 28 | 28 | 36 | 20 | 20 | 12 | 22 | 20 | 12 | 20 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 1218 | 930 | 0 | 228 | 240 | 244 | 266 | 240 | 0 | 0 | 0 |  | 1218 | IFG | 66 | 222 | 240 | 276 | 246 | 168 | 0 | 0 | 0 |  | 1218 | [7 empty] | IFG
21 | Frank Ono | QA Executive |  | 0 | 16 | 44 | 16 | 18 | 16 | 18 | 16 | 20 | 16 | 18 | 16 | 20 | 16 | 20 | 20 | 20 | 16 | 16 | 20 | 16 | 16 | 24 | 16 | 16 | 20 | 16 | 16 | 20 | 16 | 16 | 16 | 16 | 16 | 20 | 16 | 16 | 12 | 12 | 4 | 20 | 16 | 12 | 20 | 12 | 12 | 20 | 24 | 24 | 32 | 24 | 24 | 32 | 24 | 24 | 32 | 24 | 24 | 36 | 1118 | 794 | 0 | 234 | 216 | 204 | 188 | 276 | 0 | 0 | 0 |  | 1118 |  | 76 | 214 | 212 | 180 | 240 | 196 | 0 | 0 | 0 |  | 1118
22 | Venu Gaddam | QA Technical Lead (OCAT) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | IFG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | IFG
23 | Gretchen Williams | QA Specialist (OCAT) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
24 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
25 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
26 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
27 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
28 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
29 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| Total |  |  | 0 | 1897 | 2726 | 2641 | 2754 | 2414 | 2679 | 2791 | 2556 | 2909 | 2807 | 2701 | 2832 | 2912 | 2958 | 2881 | 2869 | 2785 | 2836 | 2702 | 2527 | 3086 | 2967 | 2785 | 2957 | 2858 | 3046 | 2832 | 2726 | 2651 | 2698 | 2882 | 2524 | 2809 | 2853 | 2910 | 2922 | 2660 | 3029 | 2789 | 2813 | 2662 | 2652 | 2490 | 2210 | 2665 | 2459 | 2353 | 2372 | 2234 | 2465 | 2180 | 2360 | 2159 | 2180 | 2360 | 2159 | 2282 | 2472 | 153688 |  | 0 | 31707 | 34265 | 33711 | 31154 | 22851 | 0 | 0 | 0 | 0 | 153688 |  | 7264 | 33194 | 34250 | 33453 | 29555 | 15972 | 0 | 0 | 0 |  | 153688
Summary by QA Role
1 |  | QA Project Manager |  | 0 | 176 | 160 | 160 | 168 | 144 | 160 | 168 | 152 | 176 | 168 | 152 | 160 | 168 | 168 | 160 | 160 | 160 | 160 | 152 | 144 | 176 | 168 | 160 | 168 | 168 | 176 | 160 | 160 | 152 | 152 | 168 | 144 | 160 | 168 | 168 | 168 | 160 | 176 | 160 | 168 | 152 | 152 | 168 | 144 | 176 | 168 | 176 | 176 | 160 | 184 | 160 | 168 | 160 | 160 | 168 | 160 | 168 | 176 | 7456 | 2016 | 0 | 1944 | 1944 | 1944 | 1976 | 1664 | 0 | 0 | 0 |  | 9472 |  | 496 | 1944 | 1952 | 1936 | 1984 | 1160 | 0 | 0 | 0 |  | 9472
2 |  | QA PMO Lead |  | 0 | 176 | 160 | 160 | 168 | 144 | 160 | 168 | 152 | 176 | 168 | 152 | 160 | 168 | 168 | 160 | 160 | 160 | 160 | 152 | 144 | 176 | 168 | 160 | 168 | 160 | 176 | 160 | 152 | 152 | 152 | 160 | 144 | 160 | 160 | 168 | 168 | 152 | 176 | 168 | 160 | 152 | 152 | 160 | 144 | 176 | 160 | 176 | 176 | 160 | 184 | 160 | 168 | 160 | 160 | 168 | 160 | 168 | 176 | 7400 | 2016 | 0 | 1944 | 1944 | 1912 | 1952 | 1664 | 0 | 0 | 0 |  | 9416 |  | 496 | 1944 | 1944 | 1912 | 1960 | 1160 | 0 | 0 | 0 |  | 9416
3 |  | QA Functional Manager |  | 0 | 176 | 160 | 168 | 168 | 144 | 160 | 168 | 152 | 176 | 168 | 152 | 160 | 168 | 168 | 160 | 160 | 160 | 160 | 152 | 144 | 176 | 168 | 160 | 168 | 160 | 176 | 160 | 152 | 152 | 152 | 176 | 144 | 160 | 160 | 168 | 168 | 152 | 176 | 160 | 160 | 152 | 152 | 160 | 144 | 176 | 144 | 176 | 176 | 160 | 184 | 160 | 168 | 160 | 160 | 168 | 160 | 168 | 176 | 7400 | 2016 | 0 | 1952 | 1944 | 1928 | 1928 | 1664 | 0 | 0 | 0 |  | 9416 |  | 504 | 1944 | 1944 | 1920 | 1944 | 1160 | 0 | 0 | 0 |  | 9416
4 |  | QA Technical Manager |  | 0 | 176 | 160 | 160 | 168 | 144 | 160 | 168 | 152 | 176 | 168 | 152 | 160 | 168 | 168 | 160 | 160 | 160 | 160 | 152 | 144 | 176 | 168 | 160 | 168 | 168 | 176 | 160 | 160 | 152 | 152 | 168 | 144 | 160 | 168 | 168 | 168 | 160 | 176 | 168 | 168 | 152 | 152 | 160 | 144 | 176 | 160 | 176 | 176 | 160 | 184 | 160 | 168 | 160 | 160 | 168 | 160 | 168 | 176 | 7448 | 2016 | 0 | 1944 | 1944 | 1944 | 1968 | 1664 | 0 | 0 | 0 |  | 9464 |  | 496 | 1944 | 1952 | 1944 | 1968 | 1160 | 0 | 0 | 0 |  | 9464
5 |  | QA Implementation Manager |  | 0 | 0 | 160 | 160 | 168 | 144 | 160 | 168 | 152 | 176 | 168 | 152 | 160 | 168 | 168 | 160 | 160 | 160 | 160 | 152 | 144 | 176 | 168 | 160 | 168 | 160 | 176 | 160 | 152 | 152 | 152 | 160 | 144 | 160 | 160 | 168 | 168 | 152 | 176 | 160 | 160 | 152 | 152 | 160 | 144 | 176 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7216 | 0 | 0 | 1768 | 1944 | 1912 | 1592 | 0 | 0 | 0 | 0 |  | 7216 |  | 320 | 1944 | 1944 | 1904 | 1104 | 0 | 0 | 0 | 0 |  | 7216
6 |  | QA Testing Manager |  | 0 | 176 | 160 | 160 | 168 | 144 | 160 | 168 | 152 | 176 | 168 | 152 | 160 | 168 | 168 | 160 | 160 | 160 | 160 | 152 | 144 | 176 | 168 | 160 | 168 | 160 | 176 | 160 | 152 | 152 | 152 | 160 | 144 | 160 | 160 | 168 | 168 | 152 | 176 | 160 | 160 | 152 | 152 | 160 | 144 | 176 | 160 | 176 | 176 | 160 | 184 | 160 | 168 | 160 | 160 | 168 | 160 | 168 | 176 | 7392 | 2016 | 0 | 1944 | 1944 | 1912 | 1944 | 1664 | 0 | 0 | 0 |  | 9408 |  | 496 | 1944 | 1944 | 1904 | 1960 | 1160 | 0 | 0 | 0 |  | 9408
7 |  | QA UAT Lead |  | 0 | 176 | 160 | 160 | 168 | 144 | 160 | 168 | 152 | 176 | 168 | 152 | 160 | 168 | 168 | 168 | 160 | 160 | 160 | 152 | 144 | 176 | 168 | 160 | 168 | 160 | 176 | 160 | 152 | 152 | 152 | 160 | 144 | 144 | 160 | 168 | 168 | 152 | 176 | 160 | 160 | 152 | 152 | 160 | 144 | 176 | 160 | 176 | 176 | 160 | 184 | 160 | 168 | 160 | 160 | 168 | 160 | 168 | 176 | 7384 | 2016 | 0 | 1944 | 1952 | 1896 | 1944 | 1664 | 0 | 0 | 0 |  | 9400 |  | 496 | 1952 | 1944 | 1888 | 1960 | 1160 | 0 | 0 | 0 |  | 9400
8 |  | QA PMO Specialist |  | 0 | 152 | 152 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 152 | 144 | 144 | 152 | 144 | 144 | 152 | 144 | 144 | 152 | 144 | 144 | 152 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 135 | 122 | 148 | 139 | 110 | 154 | 121 | 110 | 154 | 121 | 116 | 166 | 6680 | 1596 | 0 | 1744 | 1728 | 1760 | 1705 | 1339 | 0 | 0 | 0 |  | 8276 |  | 448 | 1728 | 1736 | 1760 | 1662 | 942 | 0 | 0 | 0 |  | 8276
9 |  | QA Sr. Administrative Assistant |  | 0 | 91 | 82 | 77 | 80 | 66 | 77 | 83 | 74 | 81 | 85 | 77 | 84 | 78 | 80 | 82 | 82 | 77 | 80 | 76 | 71 | 86 | 85 | 77 | 83 | 82 | 86 | 84 | 76 | 69 | 76 | 82 | 68 | 77 | 77 | 76 | 80 | 74 | 81 | 77 | 77 | 80 | 74 | 80 | 66 | 81 | 75 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 3612 | 960 | 0 | 957 | 957 | 933 | 925 | 800 | 0 | 0 | 0 |  | 4572 |  | 250 | 947 | 969 | 913 | 933 | 560 | 0 | 0 | 0 |  | 4572
10 |  | QA Business Analyst/Tester |  | 0 | 104 | 160 | 160 | 168 | 144 | 160 | 168 | 152 | 176 | 168 | 152 | 160 | 168 | 168 | 160 | 160 | 160 | 160 | 152 | 144 | 176 | 168 | 160 | 168 | 160 | 176 | 160 | 152 | 152 | 152 | 168 | 144 | 160 | 160 | 168 | 168 | 152 | 176 | 160 | 160 | 152 | 152 | 160 | 144 | 176 | 160 | 176 | 176 | 160 | 184 | 160 | 168 | 160 | 160 | 168 | 160 | 168 | 176 | 7328 | 2016 | 0 | 1872 | 1944 | 1920 | 1944 | 1664 | 0 | 0 | 0 |  | 9344 |  | 424 | 1944 | 1944 | 1912 | 1960 | 1160 | 0 | 0 | 0 |  | 9344
11 |  | QA Conversion Lead |  | 0 | 164 | 160 | 168 | 168 | 144 | 160 | 168 | 152 | 176 | 168 | 152 | 160 | 168 | 168 | 160 | 160 | 160 | 160 | 152 | 144 | 176 | 168 | 160 | 168 | 160 | 176 | 160 | 152 | 152 | 152 | 160 | 144 | 160 | 160 | 168 | 168 | 144 | 160 | 136 | 160 | 152 | 152 | 160 | 144 | 176 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7340 | 0 | 0 | 1940 | 1944 | 1912 | 1544 | 0 | 0 | 0 | 0 |  | 7340 |  | 492 | 1944 | 1944 | 1856 | 1104 | 0 | 0 | 0 | 0 |  | 7340
12 |  | QA Independent Tester |  | 0 | 0 | 160 | 160 | 168 | 144 | 160 | 168 | 152 | 176 | 168 | 152 | 160 | 168 | 168 | 160 | 160 | 160 | 160 | 152 | 144 | 176 | 168 | 160 | 168 | 160 | 176 | 160 | 152 | 152 | 152 | 160 | 144 | 160 | 160 | 168 | 168 | 152 | 176 | 160 | 160 | 152 | 152 | 160 | 144 | 176 | 160 | 176 | 176 | 160 | 184 | 160 | 168 | 160 | 160 | 168 | 160 | 168 | 176 | 7216 | 2016 | 0 | 1768 | 1944 | 1912 | 1944 | 1664 | 0 | 0 | 0 |  | 9232 |  | 320 | 1944 | 1944 | 1904 | 1960 | 1160 | 0 | 0 | 0 |  | 9232
13 |  | QA Independent Tester/UAT Leader |  | 0 | 104 | 480 | 480 | 504 | 432 | 480 | 504 | 456 | 528 | 504 | 456 | 480 | 504 | 504 | 484 | 480 | 480 | 480 | 456 | 432 | 528 | 504 | 480 | 504 | 480 | 528 | 480 | 456 | 456 | 456 | 480 | 432 | 480 | 480 | 504 | 504 | 432 | 528 | 480 | 480 | 456 | 456 | 480 | 432 | 528 | 480 | 528 | 536 | 504 | 552 | 488 | 528 | 480 | 488 | 528 | 480 | 512 | 552 | 21732 | 6176 | 0 | 5408 | 5836 | 5736 | 5816 | 5112 | 0 | 0 | 0 |  | 27908 |  | 1064 | 5836 | 5832 | 5688 | 5920 | 3568 | 0 | 0 | 0 |  | 27908
14 |  | QA Technical Lead |  | 0 | 188 | 180 | 172 | 188 | 156 | 180 | 180 | 172 | 188 | 192 | 164 | 164 | 134 | 174 | 203 | 203 | 128 | 168 | 162 | 116 | 180 | 174 | 128 | 174 | 168 | 140 | 168 | 162 | 122 | 162 | 168 | 116 | 168 | 168 | 134 | 142 | 130 | 140 | 136 | 136 | 122 | 130 | 136 | 96 | 128 | 128 | 154 | 178 | 166 | 174 | 174 | 198 | 150 | 174 | 198 | 150 | 182 | 206 | 7168 | 2104 | 0 | 2124 | 1944 | 1818 | 1614 | 1772 | 0 | 0 | 0 |  | 9272 |  | 540 | 2095 | 1909 | 1748 | 1722 | 1258 | 0 | 0 | 0 |  | 9272
15 |  | QA Implementation Lead |  | 0 | 0 | 160 | 120 | 120 | 144 | 160 | 168 | 152 | 176 | 168 | 304 | 320 | 336 | 336 | 320 | 320 | 320 | 328 | 304 | 288 | 352 | 336 | 320 | 336 | 320 | 352 | 320 | 304 | 304 | 304 | 320 | 288 | 320 | 320 | 336 | 336 | 304 | 352 | 320 | 320 | 304 | 304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11616 | 0 | 0 | 1992 | 3896 | 3824 | 1904 | 0 | 0 | 0 | 0 |  | 11616 |  | 280 | 2704 | 3896 | 3808 | 928 | 0 | 0 | 0 | 0 |  | 11616
16 |  | QA Executive |  | 0 | 38 | 72 | 32 | 38 | 32 | 38 | 32 | 38 | 32 | 34 | 36 | 40 | 36 | 40 | 40 | 40 | 36 | 36 | 40 | 36 | 36 | 44 | 36 | 36 | 40 | 36 | 36 | 40 | 36 | 36 | 40 | 36 | 36 | 40 | 36 | 36 | 40 | 40 | 40 | 40 | 36 | 24 | 42 | 32 | 24 | 40 | 48 | 48 | 56 | 48 | 48 | 56 | 48 | 48 | 56 | 48 | 48 | 60 | 1724 | 612 | 0 | 462 | 456 | 448 | 454 | 516 | 0 | 0 | 0 |  | 2336 |  | 142 | 436 | 452 | 456 | 486 | 364 | 0 | 0 | 0 |  | 2336
17 |  | QA Technical Lead (OCAT) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| Total |  |  | 0 | 1897 | 2726 | 2641 | 2754 | 2414 | 2679 | 2791 | 2556 | 2909 | 2807 | 2701 | 2832 | 2912 | 2958 | 2881 | 2869 | 2785 | 2836 | 2702 | 2527 | 3086 | 2967 | 2785 | 2957 | 2858 | 3046 | 2832 | 2726 | 2651 | 2698 | 2882 | 2524 | 2809 | 2853 | 2910 | 2922 | 2660 | 3029 | 2789 | 2813 | 2662 | 2652 | 2490 | 2210 | 2665 | 2459 | 2353 | 2372 | 2234 | 2465 | 2180 | 2360 | 2159 | 2180 | 2360 | 2159 | 2282 | 2472 | 153688 | 27576 | 0 | 31707 | 34265 | 33711 | 31154 | 22851 | 0 | 0 | 0 | 0 | 153688 |  | 7264 | 33194 | 34250 | 33453 | 29555 | 15972 | 0 | 0 | 0 | 428410 | 153688
4032
#DIV/0!
IFG Work Percentage Calculations
[65 empty] | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | IFG
[65 empty] | SFY | SFY | SFY | SFY | SFY | SFY | Involved
[65 empty] | 18/19 | 19/20 | 20/21 | 21/22 | 22/23 | 23/24 | Deliverable
[65 empty] | 0% | 16.1% | 12.76% | 9.851% | 5.21% | 0% | DEL #3 - QA Monthly Status Report (Monthly)
[65 empty] | 0% | 1.471% | 0% | 0% | 0% | 0% | DEL #6 - QA Testing Plan
[65 empty] | 0% | 51.57% | 43.62% | 46.35% | 50.55% | 0% | DEL #7 - QA Test Monthly Report (Monthly)
[65 empty] | 0% | 0% | 55.02% | 55.67% | 0% | 0% | DEL #8 - UAT Weekly Report (Weekly)
[65 empty] | 0% | 0% | 27.85% | 0% | 0% | 0% | DEL #9 - QA Security Review Plan
[65 empty] | 0% | 0% | 22.8% | 21.15% | 9.524% | 0% | DEL #10 - Quarterly QA Security Report (Quarterly)
[65 empty] | 0% | 5.405% | 0% | 0% | 0% | 0% | DEL #13 - Assessment of DD&I Vendor CalSAWS General Design
[65 empty] | 0% | 2.963% | 0% | 0% | 0% | 0% | DEL #14 - Assessment of DD&I Vendor CalACES Master Conversion Plan
[65 empty] | 0% | 11.76% | 0% | 0% | 0% | 0% | DEL #15 - Assessment of DD&I Vendor Application Development Preparation and Installation Plan
[65 empty] | 0% | 12.7% | 0% | 0% | 0% | 0% | DEL #17 - Assessment of DD&I Vendor CalSAWS Business Architecture Design
[65 empty] | 0% | 11.11% | 0% | 0% | 0% | 0% | DEL #18 - Assessment of DD&I Vendor CalSAWS General Design
[65 empty] | 0% | 4.661% | 0% | 0% | 0% | 0% | DEL #19 - Assessment of DD&I Vendor CalSAWS General Design
[65 empty] | 0% | 55.56% | 0% | 0% | 0% | 0% | DEL #20 - Assessment of DD&I Vendor C-IV Master Training Plan
[65 empty] | 0% | 2.703% | 0% | 0% | 0% | 0% | DEL #21 - Assessment of DD&I Vendor CalWIN/CalSAWS Master Conversion Plan
[65 empty] | 0% | 5.028% | 0% | 0% | 0% | 0% | DEL #23 - Assessment of DD&I Vendor CalSAWS General Design (Page/Report/Correspondence Changes per Requirement)
[65 empty] | 0% | 36.73% | 0% | 0% | 0% | 0% | DEL #24 - Assessment of DD&I Vendor C-IV Deployment Readiness Plan
[65 empty] | 0% | 5.405% | 0% | 0% | 0% | 0% | DEL #26 - Assessment of DD&I Vendor CalSAWS General Design
[65 empty] | 0% | 0.885% | 0% | 0% | 0% | 0% | DEL #27 - Assessment of DD&I Vendor CalWIN/CalSAWS Master Conversion Plan - Update 1
[65 empty] | 0% | 6.19% | 0% | 0% | 0% | 0% | DEL #28 - Assessment of DD&I Vendor CalSAWS General Design
[65 empty] | 0% | 5.487% | 0% | 0% | 0% | 0% | DEL #31 - Assessment of DD&I Vendor CalSAWS General Design
[65 empty] | 0% | 50.63% | 0% | 0% | 0% | 0% | DEL #33 - Assessment of DD&I Vendor C-IV Change Management Plan
[65 empty] | 0% | 40% | 0% | 0% | 0% | 0% | DEL #35 - Assessment of DD&I Vendor CalSAWS General Design
[65 empty] | 0% | 0% | 33.33% | 0% | 0% | 0% | DEL #38 - Assessment of DD&I Vendor CalSAWS UAT Support Plan
[65 empty] | 0% | 0% | 15.09% | 0% | 0% | 0% | DEL #40 - Assessment of DD&I Vendor CalSAWS (C-IV) UAT Readiness Report/Milestone
[65 empty] | 0% | 0% | 20% | 0% | 0% | 0% | DEL #42 - Assessment of DD&I Vendor CalSAWS (CalWIN) UAT Readiness Report/Milestone
[65 empty] | 0% | 0% | 0% | 10.13% | 0% | 0% | DEL #46 - Assessment of DD&I Vendor CalACES Migration Final Acceptance Certification
[65 empty] | 0% | 0% | 0% | 20.51% | 0% | 0% | DEL #47 - Assessment of DD&I Vendor CalSAWS Deployment Complete Milestone/Report - CalWIN Wave 1
[65 empty] | 0% | 0% | 0% | 19.43% | 0% | 0% | DEL #49 - Assessment of DD&I Vendor CalSAWS Deployment Complete Milestone/Report - CalWIN Wave 2
[65 empty] | 0% | 0% | 0% | 21.39% | 15.62% | 0% | DEL #50 - Assessment of DD&I Vendor CalSAWS Deployment Complete Milestone/Report - CalWIN Wave 3
[65 empty] | 0% | 0% | 0% | 33.33% | 17.79% | 0% | DEL #51 - Assessment of DD&I Vendor CalSAWS Deployment Complete Milestone/Report - CalWIN Wave 4
[65 empty] | 0% | 0% | 0% | 0% | 19.43% | 0% | DEL #52 - Assessment of DD&I Vendor CalSAWS Deployment Complete Milestone/Report - CalWIN Wave 5
[65 empty] | 0% | 0% | 0% | 0% | 15.78% | 0% | DEL #53 - Assessment of DD&I Vendor CalSAWS Deployment Complete Milestone/Report - CalWIN Wave 6
[65 empty] | 0% | 0% | 31.58% | 0% | 0% | 0% | DEL #60 - Assessment of CalWIN Implementation Support Vendor CalWIN Master Training Plan
[65 empty] | 0% | 0% | 8.439% | 0% | 0% | 0% | DEL #61 - Assessment of CalWIN Implementation Support Vendor CalWIN Deployment Readiness Plan
[65 empty] | 0% | 0% | 29.7% | 0% | 0% | 0% | DEL #62 - Assessment of CalWIN Implementation Support Vendor CalWIN Change Management Plan
[65 empty] | 0% | 0% | 34.48% | 30.3% | 0% | 0% | DEL #63 - Assessment of CalWIN Implementation Support Vendor CalWIN ILT Training Material
[65 empty] | 0% | 0% | 0% | 30.93% | 0% | 0% | DEL #64 - Assessment of CalWIN Implementation Support Vendor CalWIN WBT Training Material
[65 empty] | 0% | 0% | 0% | 0% | 3.102% | 4.503% | DEL #65 - QA Status Report (Monthly)
[65 empty] | 0% | 0% | 0% | 0% | 33.98% | 32.94% | DEL #67 - QA M&O Monthly Test Report (Monthly)
[65 empty] | 0% | 0% | 0% | 0% | 16% | 15.58% | DEL #68 - Quarterly QA Security Report (Quarterly)
[65 empty] | 0% | 0% | 0% | 0% | 5.556% | 5.556% | DEL #69 - Monthly SLA & Performance Review Report (Monthly)
[65 empty] | 0 | 5844 | 8020 | 7892 | 7050 | 5232
[65 empty] | #DIV/0! | 18.43% | 23.41% | 23.41% | 22.63% | 22.9%

## Sch 3 - QA Staff Loading (OCAT)
| Schedule 3 - QA Staff Loading |  |  | 80 | 168 | 168 | 160 | 168 | 144 | 160 | 168 | 152 | 176 | 168 | 152 | 160 | 168 | 168 | 160 | 160 | 160 | 160 | 152 | 144 | 176 | 168 | 160 | 168 | 160 | 176 | 160 | 152 | 152 | 152 | 160 | 144 | 160 | 160 | 168 | 168 | 152 | 176 | 160 | 160 | 152 | 152 | 160 | 144 | 176 | 160 | 176 | 176 | 160 | 184 | 160 | 168 | 160 | 160 | 168 | 160 | 168 | 176
Schedule 3 - QA Staff Loading | time axis 2019-06-28 to 2023-04-28
Schedule 3 - QA Staff Loading (OCAT) | [95 empty] | <-- Do Not Delete hidden columns
|  | Nominal Month |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 |  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 |  |  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9
|  | FFY |  | 19 | 19 | 19 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 24 | 24 | 24 | 24 | 24 | 24 | 24 |  |  | SFY | SFY | SFY | SFY | SFY | SFY | SFY | SFY | SFY |  |  |  | FFY | FFY | FFY | FFY | FFY | FFY | FFY | FFY | FFY
|  | SFY |  | 18/19 | 19/20 | 19/20 | 19/20 | 19/20 | 19/20 | 19/20 | 19/20 | 19/20 | 19/20 | 19/20 | 19/20 | 19/20 | 20/21 | 20/21 | 20/21 | 20/21 | 20/21 | 20/21 | 20/21 | 20/21 | 20/21 | 20/21 | 20/21 | 20/21 | 21/22 | 21/22 | 21/22 | 21/22 | 21/22 | 21/22 | 21/22 | 21/22 | 21/22 | 21/22 | 21/22 | 21/22 | 22/23 | 22/23 | 22/23 | 22/23 | 22/23 | 22/23 | 22/23 | 22/23 | 22/23 | 22/23 | 22/23 | 22/23 | 23/24 | 23/24 | 23/24 | 23/24 | 23/24 | 23/24 | 23/24 | 23/24 | 23/24 | 23/24 |  |  | 18/19 | 19/20 | 20/21 | 21/22 | 22/23 | 23/24 | 24/25 | 25/26 | 26/27 |  |  |  | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 |  |  | Invoice Month Summaries
| DELIVERABLE | Month | Bill Rate | [59 empty] | Total |  | Total | Total | Total | Total | Total | Total | Total | Total | Total |  | Total |  | Total | Total | Total | Total | Total | Total | Total | Total | Total |  | Total | Rates | 19/20 | 20/21 | 21/22 | 22/23 | 23/24 | Total | time axis 2019-06-01 to 2024-04-01
# | STAFF NAME | QA ROLE (pulled from Roster tab) | [60 empty] | TOTAL
| DEL #1 - QA Monthly Status Report (OCAT) |  |  | 2019-08-01: Due; 2019-09-01: Due; 2019-10-01: Due; 2019-11-01: Due; 2019-12-01: Due; 2020-01-01: Due; 2020-02-01: Due; 2020-03-01: Due; 2020-04-01: Due; 2020-05-01: Due; 2020-06-01: Due; 2020-07-01: Due; 2020-08-01: Due; 2020-09-01: Due; 2020-10-01: Due |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 7960 | 3980 | 0 | 0 | 0 | 11940 | subtotal
1 | Venu Gaddam | QA Technical Lead (OCAT) | 139 | 2019-08-01: 62; 2019-09-01: 12; 2019-10-01: 48; 2019-11-01: 104; 2019-12-01: 120; 2020-01-01: 128; 2020-02-01: 72; 2020-03-01: 96; 2020-04-01: 148; 2020-05-01: 132; 2020-06-01: 140; 2020-07-01: 148; 2020-08-01: 148; 2020-09-01: 140; 2020-10-01: 140 | 1638 |  | 0 | 1062 | 576 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1638 |  | 74 | 1424 | 140 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1638 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Gretchen Williams | QA Specialist (OCAT) | 124 | 2019-09-01: 30; 2019-10-01: 64; 2019-11-01: 72; 2019-12-01: 80; 2020-01-01: 44; 2020-02-01: 2; 2020-03-01: 2; 2020-04-01: 16; 2020-05-01: 36; 2020-06-01: 40; 2020-07-01: 40; 2020-08-01: 40; 2020-09-01: 40; 2020-10-01: 40 | 546 |  | 0 | 386 | 160 | 0 | 0 | 0 | 0 | 0 | 0 |  | 546 |  | 30 | 476 | 40 | 0 | 0 | 0 | 0 | 0 | 0 |  | 546 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Wendy Battermann | QA Executive | 154 | 2019-08-01: 2; 2019-09-01: 2; 2019-10-01: 2; 2019-11-01: 2; 2019-12-01: 2; 2020-01-01: 2; 2020-02-01: 2; 2020-03-01: 2; 2020-04-01: 2; 2020-05-01: 2; 2020-06-01: 2; 2020-07-01: 2; 2020-08-01: 2; 2020-09-01: 2; 2020-10-01: 2 | 30 |  | 0 | 22 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 30 |  | 4 | 24 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  | 30 | 154 | 3080 | 1540 | 0 | 0 | 0 | 4620
4 | Frank Ono | QA Executive | 154 | 2019-08-01: 2; 2019-09-01: 2; 2019-10-01: 2; 2019-11-01: 2; 2019-12-01: 2; 2020-01-01: 2; 2020-02-01: 2; 2020-03-01: 2; 2020-04-01: 2; 2020-05-01: 2; 2020-06-01: 2; 2020-07-01: 2; 2020-08-01: 2; 2020-09-01: 2; 2020-10-01: 2 | 30 |  | 0 | 22 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 30 |  | 4 | 24 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  | 30 | 154 | 3080 | 1540 | 0 | 0 | 0 | 4620
5 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2019-08-01: 4; 2019-09-01: 4; 2019-10-01: 4; 2019-11-01: 4; 2019-12-01: 4; 2020-01-01: 4; 2020-02-01: 4; 2020-03-01: 4; 2020-04-01: 4; 2020-05-01: 4; 2020-06-01: 4; 2020-07-01: 4; 2020-08-01: 4; 2020-09-01: 4; 2020-10-01: 4 | 60 |  | 0 | 44 | 16 | 0 | 0 | 0 | 0 | 0 | 0 |  | 60 |  | 8 | 48 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 60 | 45 | 1800 | 900 | 0 | 0 | 0 | 2700
| DEL #2 - QA Assessment of OCAT Project Control Document |  |  | 2019-08-01: Due |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 488 | 0 | 0 | 0 | 0 | 488 | subtotal
1 | Venu Gaddam | QA Technical Lead (OCAT) | 139 | [59 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Gretchen Williams | QA Specialist (OCAT) | 124 | 2019-08-01: 8 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Wendy Battermann | QA Executive | 154 | 2019-08-01: 2 | 2 |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 154 | 308 | 0 | 0 | 0 | 0 | 308
4 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2019-08-01: 4 | 4 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | 45 | 180 | 0 | 0 | 0 | 0 | 180
| DEL #3 - QA Assessment of OCAT Work Plan |  |  | 2019-07-01: Due |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 488 | 0 | 0 | 0 | 0 | 488 | subtotal
1 | Venu Gaddam | QA Technical Lead (OCAT) | 139 | 2019-07-01: 4 | 4 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Gretchen Williams | QA Specialist (OCAT) | 124 | 2019-07-01: 4 | 4 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Wendy Battermann | QA Executive | 154 | 2019-07-01: 2 | 2 |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 154 | 308 | 0 | 0 | 0 | 0 | 308
4 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2019-07-01: 4 | 4 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | 45 | 180 | 0 | 0 | 0 | 0 | 180
| DEL #4 - QA Assessment of OCAT RTM |  |  | 2019-08-01: Due |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 488 | 0 | 0 | 0 | 0 | 488 | subtotal
1 | Venu Gaddam | QA Technical Lead (OCAT) | 139 | 2019-08-01: 30 | 30 |  | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 30 |  | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Gretchen Williams | QA Specialist (OCAT) | 124 | 2019-08-01: 20 | 20 |  | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 20 |  | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Wendy Battermann | QA Executive | 154 | 2019-08-01: 2 | 2 |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 154 | 308 | 0 | 0 | 0 | 0 | 308
4 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2019-08-01: 4 | 4 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | 45 | 180 | 0 | 0 | 0 | 0 | 180
| DEL #5 - QA Assessment of OCAT General Design Document |  |  | 2019-10-01: Due |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 2118 | 0 | 0 | 0 | 0 | 2118 | subtotal
1 | Venu Gaddam | QA Technical Lead (OCAT) | 139 | 2019-08-01: 60; 2019-09-01: 40; 2019-10-01: 20 | 120 |  | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 120 |  | 100 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Gretchen Williams | QA Specialist (OCAT) | 124 | 2019-08-01: 20; 2019-09-01: 20; 2019-10-01: 20 | 60 |  | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 60 |  | 40 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Frank Ono | QA Executive | 154 | 2019-08-01: 4; 2019-09-01: 4; 2019-10-01: 4 | 12 |  | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 12 |  | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 12 | 154 | 1848 | 0 | 0 | 0 | 0 | 1848
4 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2019-08-01: 2; 2019-10-01: 4 | 6 |  | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 6 |  | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 6 | 45 | 270 | 0 | 0 | 0 | 0 | 270
| DEL #6 - QA Assessment of OCAT Technical Design Document |  |  | 2019-10-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 1592 | 0 | 0 | 0 | 0 | 1592 | subtotal
1 | Venu Gaddam | QA Technical Lead (OCAT) | 139 | 2019-09-01: 60; 2019-10-01: 60 | 120 |  | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 120 |  | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Gretchen Williams | QA Specialist (OCAT) | 124 | [59 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Frank Ono | QA Executive | 154 | 2019-09-01: 4; 2019-10-01: 4 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 154 | 1232 | 0 | 0 | 0 | 0 | 1232
4 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2019-09-01: 4; 2019-10-01: 4 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 45 | 360 | 0 | 0 | 0 | 0 | 360
| DEL #7 - QA Assessment of OCAT Application SAWS Interfaces |  |  | 2020-04-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 5288 | 0 | 0 | 0 | 0 | 5288 | subtotal
1 | Venu Gaddam | QA Technical Lead (OCAT) | 139 | 2019-09-01: 40; 2019-10-01: 40; 2019-11-01: 40; 2019-12-01: 40; 2020-01-01: 40; 2020-02-01: 40; 2020-03-01: 40; 2020-04-01: 20 | 300 |  | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 300 |  | 40 | 260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Gretchen Williams | QA Specialist (OCAT) | 124 | [59 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Frank Ono | QA Executive | 154 | 2019-09-01: 4; 2019-10-01: 4; 2019-11-01: 4; 2019-12-01: 4; 2020-01-01: 4; 2020-02-01: 4; 2020-03-01: 4; 2020-04-01: 4 | 32 |  | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 |  | 4 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 | 154 | 4928 | 0 | 0 | 0 | 0 | 4928
4 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2019-09-01: 4; 2020-04-01: 4 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 45 | 360 | 0 | 0 | 0 | 0 | 360
| DEL #8 - QA Assessment of OCAT Master Test Plan |  |  | 2019-09-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 976 | 0 | 0 | 0 | 0 | 976 | subtotal
1 | Venu Gaddam | QA Technical Lead (OCAT) | 139 | 2019-08-01: 8; 2019-09-01: 8 | 16 |  | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16 |  | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Gretchen Williams | QA Specialist (OCAT) | 124 | 2019-08-01: 24; 2019-09-01: 32 | 56 |  | 0 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 56 |  | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Wendy Battermann | QA Executive | 154 | 2019-08-01: 2; 2019-09-01: 2 | 4 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | IFG | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | 154 | 616 | 0 | 0 | 0 | 0 | 616 | IFG
4 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2019-08-01: 4; 2019-09-01: 4 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | IFG | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 45 | 360 | 0 | 0 | 0 | 0 | 360 | IFG
| DEL #9 - QA Assessment of OCAT Training Plan |  |  | 2020-02-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 976 | 0 | 0 | 0 | 0 | 976 | subtotal
1 | Venu Gaddam | QA Technical Lead (OCAT) | 139 | [59 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Gretchen Williams | QA Specialist (OCAT) | 124 | 2020-01-01: 40; 2020-02-01: 32 | 72 |  | 0 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 72 | IFG | 0 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | IFG
3 | Wendy Battermann | QA Executive | 154 | 2020-01-01: 2; 2020-02-01: 2 | 4 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | 154 | 616 | 0 | 0 | 0 | 0 | 616
4 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2020-01-01: 4; 2020-02-01: 4 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 45 | 360 | 0 | 0 | 0 | 0 | 360
| DEL #10 - QA Assessment of OCAT Training Materials |  |  | 2020-05-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 1592 | 0 | 0 | 0 | 0 | 1592 | subtotal
1 | Venu Gaddam | QA Technical Lead (OCAT) | 139 | [59 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Gretchen Williams | QA Specialist (OCAT) | 124 | 2020-02-01: 20; 2020-03-01: 48; 2020-04-01: 40; 2020-05-01: 40 | 148 |  | 0 | 148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 148 | IFG | 0 | 148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | IG
3 | Wendy Battermann | QA Executive | 154 | 2020-02-01: 2; 2020-03-01: 2; 2020-04-01: 2; 2020-05-01: 2 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 154 | 1232 | 0 | 0 | 0 | 0 | 1232
4 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2020-02-01: 4; 2020-05-01: 4 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 45 | 360 | 0 | 0 | 0 | 0 | 360
| DEL #11 - QA Assessment of OCAT System Documentation |  |  | 2020-03-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 976 | 0 | 0 | 0 | 0 | 976 | subtotal
1 | Venu Gaddam | QA Technical Lead (OCAT) | 139 | 2020-02-01: 40; 2020-03-01: 40 | 80 |  | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 80 |  | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Gretchen Williams | QA Specialist (OCAT) | 124 | 2020-02-01: 40; 2020-03-01: 40 | 80 |  | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 80 |  | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Wendy Battermann | QA Executive | 154 | 2020-02-01: 2; 2020-03-01: 2 | 4 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | 154 | 616 | 0 | 0 | 0 | 0 | 616
4 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2020-02-01: 4; 2020-03-01: 4 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 45 | 360 | 0 | 0 | 0 | 0 | 360
| DEL #12 - QA Assessment of OCAT Final Acceptance |  |  | 2020-10-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 488 | 1720 | 0 | 0 | 0 | 2208 | subtotal
1 | Venu Gaddam | QA Technical Lead (OCAT) | 139 | 2020-05-01: 20; 2020-06-01: 20; 2020-07-01: 20; 2020-08-01: 20; 2020-09-01: 20; 2020-10-01: 20 | 120 |  | 0 | 40 | 80 | 0 | 0 | 0 | 0 | 0 | 0 |  | 120 |  | 0 | 100 | 20 | 0 | 0 | 0 | 0 | 0 | 0 |  | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Gretchen Williams | QA Specialist (OCAT) | 124 | [59 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Wendy Battermann | QA Executive | 154 | 2020-05-01: 2; 2020-06-01: 2; 2020-07-01: 2; 2020-08-01: 2; 2020-09-01: 2; 2020-10-01: 2 | 12 |  | 0 | 4 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 12 |  | 0 | 10 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  | 12 | 154 | 308 | 1540 | 0 | 0 | 0 | 1848
4 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2020-05-01: 4; 2020-10-01: 4 | 8 |  | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 45 | 180 | 180 | 0 | 0 | 0 | 360
| DEL #13 - QA Assessment of OCAT M&O Transition Plan |  |  | 2020-11-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 796 | 0 | 0 | 0 | 796 | subtotal
1 | Venu Gaddam | QA Technical Lead (OCAT) | 139 | 2020-11-01: 40 | 40 |  | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 |  | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Gretchen Williams | QA Specialist (OCAT) | 124 | 2020-11-01: 40 | 40 |  | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 |  | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Frank Ono | QA Executive | 154 | 2020-11-01: 4 | 4 |  | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | 154 | 0 | 616 | 0 | 0 | 0 | 616
4 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2020-11-01: 4 | 4 |  | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | 45 | 0 | 180 | 0 | 0 | 0 | 180
| DEL #14 - QA M&O Monthly Status Report (OCAT) |  |  | 2020-11-01: Due; 2020-12-01: Due; 2021-01-01: Due; 2021-02-01: Due; 2021-03-01: Due; 2021-04-01: Due; 2021-05-01: Due; 2021-06-01: Due; 2021-07-01: Due; 2021-08-01: Due; 2021-09-01: Due; 2021-10-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 4312 | 3080 | 0 | 0 | 7392 | subtotal
1 | Venu Gaddam | QA Technical Lead (OCAT) | 139 | 2020-11-01: 40; 2020-12-01: 80; 2021-01-01: 80; 2021-02-01: 80; 2021-03-01: 80; 2021-04-01: 80; 2021-05-01: 80; 2021-06-01: 80; 2021-07-01: 80; 2021-08-01: 80; 2021-09-01: 80; 2021-10-01: 80 | 920 |  | 0 | 0 | 600 | 320 | 0 | 0 | 0 | 0 | 0 |  | 920 |  | 0 | 0 | 840 | 80 | 0 | 0 | 0 | 0 | 0 |  | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Gretchen Williams | QA Specialist (OCAT) | 124 | [59 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Wendy Battermann | QA Executive | 154 | 2020-11-01: 2; 2020-12-01: 2; 2021-01-01: 2; 2021-02-01: 2; 2021-03-01: 2; 2021-04-01: 2; 2021-05-01: 2; 2021-06-01: 2; 2021-07-01: 2; 2021-08-01: 2; 2021-09-01: 2; 2021-10-01: 2 | 24 |  | 0 | 0 | 16 | 8 | 0 | 0 | 0 | 0 | 0 |  | 24 |  | 0 | 0 | 22 | 2 | 0 | 0 | 0 | 0 | 0 |  | 24 | 154 | 0 | 2156 | 1540 | 0 | 0 | 3696
4 | Frank Ono | QA Executive | 154 | 2020-11-01: 2; 2020-12-01: 2; 2021-01-01: 2; 2021-02-01: 2; 2021-03-01: 2; 2021-04-01: 2; 2021-05-01: 2; 2021-06-01: 2; 2021-07-01: 2; 2021-08-01: 2; 2021-09-01: 2; 2021-10-01: 2 | 24 |  | 0 | 0 | 16 | 8 | 0 | 0 | 0 | 0 | 0 |  | 24 |  | 0 | 0 | 22 | 2 | 0 | 0 | 0 | 0 | 0 |  | 24 | 154 | 0 | 2156 | 1540 | 0 | 0 | 3696
|  |  |  | 0 | 14 | 264 | 276 | 280 | 228 | 252 | 270 | 276 | 286 | 242 | 248 | 210 | 218 | 218 | 210 | 214 | 132 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4762 |  | 0 | 2846 | 1580 | 336 | 0 | 0 | 0 | 0 | 0 |  | 4762 |  | 554 | 2938 | 1186 | 84 | 0 | 0 | 0 | 0 | 0 |  | 4762
Summary by Staff Name
1 | Venu Gaddam | QA Technical Lead (OCAT) | 139 | 0 | 4 | 160 | 160 | 168 | 144 | 160 | 168 | 152 | 176 | 168 | 152 | 160 | 168 | 168 | 160 | 160 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3388 | 3388 | 0 | 1772 | 1296 | 320 | 0 | 0 | 0 | 0 | 0 |  | 3388 |  | 324 | 1944 | 1040 | 80 | 0 | 0 | 0 | 0 | 0 |  | 3388
2 | Gretchen Williams | QA Specialist (OCAT) | 124 | 0 | 4 | 72 | 82 | 84 | 72 | 80 | 84 | 94 | 90 | 56 | 76 | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1034 | 1034 | 0 | 834 | 200 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1034 |  | 158 | 796 | 80 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1034
3 | Wendy Battermann | QA Executive | 154 | 0 | 2 | 8 | 4 | 2 | 2 | 2 | 4 | 8 | 6 | 4 | 6 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | 92 | 0 | 52 | 32 | 8 | 0 | 0 | 0 | 0 | 0 |  | 92 |  | 14 | 50 | 26 | 2 | 0 | 0 | 0 | 0 | 0 |  | 92
4 | Frank Ono | QA Executive | 154 | 0 | 0 | 6 | 14 | 14 | 6 | 6 | 6 | 6 | 6 | 6 | 2 | 2 | 2 | 2 | 2 | 2 | 6 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 110 | 0 | 74 | 28 | 8 | 0 | 0 | 0 | 0 | 0 |  | 110 |  | 20 | 60 | 28 | 2 | 0 | 0 | 0 | 0 | 0 |  | 110
5 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 0 | 4 | 18 | 16 | 12 | 4 | 4 | 8 | 16 | 8 | 8 | 12 | 4 | 4 | 4 | 4 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138 |  | 0 | 114 | 24 | 0 | 0 | 0 | 0 | 0 | 0 |  | 138 | IFG | 38 | 88 | 12 | 0 | 0 | 0 | 0 | 0 | 0 |  | 138 | [7 empty] | IFG
| Total |  |  | 0 | 14 | 264 | 276 | 280 | 228 | 252 | 270 | 276 | 286 | 242 | 248 | 210 | 218 | 218 | 210 | 214 | 132 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4762 |  | 0 | 2846 | 1580 | 336 | 0 | 0 | 0 | 0 | 0 | 0 | 4762 |  | 554 | 2938 | 1186 | 84 | 0 | 0 | 0 | 0 | 0 |  | 4762
Summary by QA Role
|  | QA Technical Lead (OCAT) |  | 0 | 4 | 160 | 160 | 168 | 144 | 160 | 168 | 152 | 176 | 168 | 152 | 160 | 168 | 168 | 160 | 160 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3388 | 0 | 0 | 1772 | 1296 | 320 | 0 | 0 | 0 | 0 | 0 |  | 3388 |  | 324 | 1944 | 1040 | 80 | 0 | 0 | 0 | 0 | 0 |  | 3388
|  | QA Specialist (OCAT) |  | 0 | 4 | 72 | 82 | 84 | 72 | 80 | 84 | 94 | 90 | 56 | 76 | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1034 | 0 | 0 | 834 | 200 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1034 |  | 158 | 796 | 80 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1034
|  | QA PMO Specialist |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  | QA Executive |  | 0 | 2 | 14 | 18 | 16 | 8 | 8 | 10 | 14 | 12 | 10 | 8 | 6 | 6 | 6 | 6 | 6 | 8 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 202 | 0 | 0 | 126 | 60 | 16 | 0 | 0 | 0 | 0 | 0 |  | 202 |  | 34 | 110 | 54 | 4 | 0 | 0 | 0 | 0 | 0 |  | 202
|  | QA Sr. Administrative Assistant |  | 0 | 4 | 18 | 16 | 12 | 4 | 4 | 8 | 16 | 8 | 8 | 12 | 4 | 4 | 4 | 4 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138 | 0 | 0 | 114 | 24 | 0 | 0 | 0 | 0 | 0 | 0 |  | 138 |  | 38 | 88 | 12 | 0 | 0 | 0 | 0 | 0 | 0 |  | 138
| Total |  |  | 0 | 14 | 264 | 276 | 280 | 228 | 252 | 270 | 276 | 286 | 242 | 248 | 210 | 218 | 218 | 210 | 214 | 132 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4762 | 0 | 0 | 2846 | 1580 | 336 | 0 | 0 | 0 | 0 | 0 | 0 | 4762 |  | 554 | 2938 | 1186 | 84 | 0 | 0 | 0 | 0 | 0 | 10028 | 4762
0
#REF!
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #6 - QA Testing Plan
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #7 - QA Test Monthly Report (Monthly)
[65 empty] | 0% | 14.29% | 0% | 0% | 0% | 0% | DEL #8 - UAT Weekly Report (Weekly)
[65 empty] | 0% | 85.71% | 0% | 0% | 0% | 0% | DEL #9 - QA Security Review Plan
[65 empty] | 0% | 90.24% | 0% | 0% | 0% | 0% | DEL #10 - Quarterly QA Security Report (Quarterly)
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #13 - Assessment of DD&I Vendor CalSAWS General Design
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #14 - Assessment of DD&I Vendor CalACES Master Conversion Plan
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #15 - Assessment of DD&I Vendor Application Development Preparation and Installation Plan
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #17 - Assessment of DD&I Vendor CalSAWS Business Architecture Design
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #18 - Assessment of DD&I Vendor CalSAWS General Design
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #19 - Assessment of DD&I Vendor CalSAWS General Design
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #20 - Assessment of DD&I Vendor C-IV Master Training Plan
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #21 - Assessment of DD&I Vendor CalWIN/CalSAWS Master Conversion Plan
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #23 - Assessment of DD&I Vendor CalSAWS General Design (Page/Report/Correspondence Changes per Requirement)
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #24 - Assessment of DD&I Vendor C-IV Deployment Readiness Plan
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #26 - Assessment of DD&I Vendor CalSAWS General Design
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #27 - Assessment of DD&I Vendor CalWIN/CalSAWS Master Conversion Plan - Update 1
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #28 - Assessment of DD&I Vendor CalSAWS General Design
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #31 - Assessment of DD&I Vendor CalSAWS General Design
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #33 - Assessment of DD&I Vendor C-IV Change Management Plan
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #35 - Assessment of DD&I Vendor CalSAWS General Design
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #38 - Assessment of DD&I Vendor CalSAWS UAT Support Plan
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #40 - Assessment of DD&I Vendor CalSAWS (C-IV) UAT Readiness Report/Milestone
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #42 - Assessment of DD&I Vendor CalSAWS (CalWIN) UAT Readiness Report/Milestone
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #46 - Assessment of DD&I Vendor CalACES Migration Final Acceptance Certification
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #47 - Assessment of DD&I Vendor CalSAWS Deployment Complete Milestone/Report - CalWIN Wave 1
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #49 - Assessment of DD&I Vendor CalSAWS Deployment Complete Milestone/Report - CalWIN Wave 2
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #50 - Assessment of DD&I Vendor CalSAWS Deployment Complete Milestone/Report - CalWIN Wave 3
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #51 - Assessment of DD&I Vendor CalSAWS Deployment Complete Milestone/Report - CalWIN Wave 4
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #52 - Assessment of DD&I Vendor CalSAWS Deployment Complete Milestone/Report - CalWIN Wave 5
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #53 - Assessment of DD&I Vendor CalSAWS Deployment Complete Milestone/Report - CalWIN Wave 6
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #60 - Assessment of CalWIN Implementation Support Vendor CalWIN Master Training Plan
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #61 - Assessment of CalWIN Implementation Support Vendor CalWIN Deployment Readiness Plan
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #62 - Assessment of CalWIN Implementation Support Vendor CalWIN Change Management Plan
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #63 - Assessment of CalWIN Implementation Support Vendor CalWIN ILT Training Material
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #64 - Assessment of CalWIN Implementation Support Vendor CalWIN WBT Training Material
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #65 - QA Status Report (Monthly)
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #67 - QA M&O Monthly Test Report (Monthly)
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #68 - Quarterly QA Security Report (Quarterly)
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #69 - Monthly SLA & Performance Review Report (Monthly)
[65 empty] | 0 | 114 | 24 | 0 | 0 | 0
[65 empty] | #DIV/0! | 4.006% | 1.519% | 0% | #DIV/0! | #DIV/0!
0
0
0

## Sch 4 - Deliverables
Schedule 4 - Deliverable Detail |  |  |  |  | <This entire tab should not be manually updated>
# | Deliverable | Position | Hourly Rate | Total Hours | Cost
DEL #1 - QA Management Plan
1 | Dan Dean | QA Project Manager | 154 | 24 | 3696
2 | Beena Amarnath | QA PMO Lead | 134 | 30 | 4020
3 | Timothy King | QA PMO Specialist | 114 | 18 | 2052
4 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 4 | 180
5 | Wendy Battermann | QA Executive | 154 | 8 | 1232
6 |  |  |  | 0 | 0
7 |  |  |  | 0 | 0
8 |  |  |  | 0 | 0
9 |  |  |  | 0 | 0
10 |  |  |  | 0 | 0
11 |  |  |  | 0 | 0
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 84 | 11180
DEL #2 - QA Work Plan (Initial)
1 | Dan Dean | QA Project Manager | 154 | 20 | 3080
2 | Beena Amarnath | QA PMO Lead | 134 | 34 | 4556
3 | Timothy King | QA PMO Specialist | 114 | 18 | 2052
4 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 4 | 180
5 | Wendy Battermann | QA Executive | 154 | 4 | 616
6 |  |  |  | 0 | 0
7 |  |  |  | 0 | 0
8 |  |  |  | 0 | 0
9 |  |  |  | 0 | 0
10 |  |  |  | 0 | 0
11 |  |  |  | 0 | 0
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 80 | 10484
DEL #3 - QA Monthly Status Report (Monthly)
1 | Dan Dean | QA Project Manager | 154 | 3744 | 576576
2 | Beena Amarnath | QA PMO Lead | 134 | 3428 | 459352
3 | Kristin Pepper | QA Functional Manager | 134 | 4952 | 663568
4 | Don Coffey | QA Technical Manager | 144 | 4488 | 646272
5 | Abby Darrah | QA Implementation Manager | 134 | 4384 | 587456
6 | Cheryl Hofmann | QA Testing Manager | 134 | 368 | 49312
7 | Rachel Hernandez | QA UAT Lead | 134 | 368 | 49312
8 | Timothy King | QA PMO Specialist | 114 | 2182 | 248748
9 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2482 | 111690
10 | Raj Ganesh | QA Conversion Lead | 114 | 5152 | 587328
11 | Pandu Gupta | QA Business Analyst/Tester | 114 | 2296 | 261744
12 | Greg FitzGerald | QA Technical Lead | 139 | 3700 | 514300
13 | Dustin Lish | QA Technical Lead | 139 | 368 | 51152
14 | Ivan Parra | QA Implementation Lead | 124 | 3184 | 394816
15 | Gail Brown | QA Implementation Lead | 124 | 4060 | 503440
16 | Wendy Battermann | QA Executive | 154 | 348 | 53592
17 | Frank Ono | QA Executive | 154 | 592 | 91168
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 46096 | 5849826
DEL #4 - QA Work Plan (Monthly update)
1 | Dan Dean | QA Project Manager | 154 | 540 | 83160
2 | Beena Amarnath | QA PMO Lead | 134 | 728 | 97552
3 | Timothy King | QA PMO Specialist | 114 | 540 | 61560
4 | Kristin Pepper | QA Functional Manager | 134 | 368 | 49312
5 | Don Coffey | QA Technical Manager | 144 | 360 | 51840
6 | Abby Darrah | QA Implementation Manager | 134 | 360 | 48240
7 | Cheryl Hofmann | QA Testing Manager | 134 | 360 | 48240
8 | Rachel Hernandez | QA UAT Lead | 134 | 360 | 48240
9 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 90 | 4050
10 | Wendy Battermann | QA Executive | 154 | 90 | 13860
11 |  |  |  | 0 | 0
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 3796 | 506054
DEL #5 - Deliverable Review and Assessment Plan
1 | Dan Dean | QA Project Manager | 154 | 14 | 2156
2 | Beena Amarnath | QA PMO Lead | 134 | 40 | 5360
3 | Timothy King | QA PMO Specialist | 114 | 32 | 3648
4 | Kristin Pepper | QA Functional Manager | 134 | 24 | 3216
5 | Don Coffey | QA Technical Manager | 144 | 24 | 3456
6 | Abby Darrah | QA Implementation Manager | 134 | 0 | 0
7 | Cheryl Hofmann | QA Testing Manager | 134 | 16 | 2144
8 | Rachel Hernandez | QA UAT Lead | 134 | 16 | 2144
9 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 8 | 360
10 | Wendy Battermann | QA Executive | 154 | 4 | 616
11 |  |  |  | 0 | 0
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 178 | 23100
DEL #6 - QA Testing Plan
1 | Dan Dean | QA Project Manager | 154 | 28 | 4312
2 | Timothy King | QA PMO Specialist | 114 | 8 | 912
3 | Cheryl Hofmann | QA Testing Manager | 134 | 192 | 25728
4 | Rachel Hernandez | QA UAT Lead | 134 | 192 | 25728
5 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 4 | 180
6 | Wendy Battermann | QA Executive | 154 | 8 | 1232
7 | Frank Ono | QA Executive | 154 | 8 | 1232
8 | Donna Smith | QA Independent Tester/UAT Leader | 114 | 104 | 11856
9 |  |  |  | 0 | 0
10 |  |  |  | 0 | 0
11 |  |  |  | 0 | 0
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 544 | 71180
DEL #7 - QA Test Monthly Report (Monthly)
1 | Dan Dean | QA Project Manager | 154 | 358 | 55132
2 | Beena Amarnath | QA PMO Lead | 134 | 1072 | 143648
3 | Timothy King | QA PMO Specialist | 114 | 536 | 61104
4 | Cheryl Hofmann | QA Testing Manager | 134 | 5416 | 725744
5 | Rachel Hernandez | QA UAT Lead | 134 | 4672 | 626048
6 | Donna Smith | QA Independent Tester/UAT Leader | 114 | 6760 | 770640
7 | Kim Sinclair | QA Independent Tester | 99 | 7216 | 714384
8 | Sindura Kompulira | QA Independent Tester/UAT Leader | 114 | 6092 | 694488
9 | Lalitha Ramabholta | QA Independent Tester/UAT Leader | 114 | 6224 | 709536
10 | Pandu Gupta | QA Business Analyst/Tester | 114 | 2148 | 244872
11 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 180 | 8100
12 | Wendy Battermann | QA Executive | 154 | 88 | 13552
13 |  | 0 |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 40762 | 4767248
DEL #8 - UAT Weekly Report (Weekly)
1 | Dan Dean | QA Project Manager | 154 | 24 | 3696
2 | Timothy King | QA PMO Specialist | 114 | 24 | 2736
3 | Cheryl Hofmann | QA Testing Manager | 134 | 96 | 12864
4 | Rachel Hernandez | QA UAT Lead | 134 | 808 | 108272
5 | Sindura Kompulira | QA Independent Tester/UAT Leader | 114 | 976 | 111264
6 | Lalitha Ramabholta | QA Independent Tester/UAT Leader | 114 | 992 | 113088
7 | Pandu Gupta | QA Business Analyst/Tester | 114 | 600 | 68400
8 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 24 | 1080
9 | Wendy Battermann | QA Executive | 154 | 12 | 1848
10 |  | 0 |  | 0 | 0
11 |  |  |  | 0 | 0
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 3556 | 423248
DEL #9 - QA Security Review Plan
1 | Dan Dean | QA Project Manager | 154 | 40 | 6160
2 | Don Coffey | QA Technical Manager | 144 | 76 | 10944
3 | Greg FitzGerald | QA Technical Lead | 139 | 152 | 21128
4 | Dustin Lish | QA Technical Lead | 139 | 152 | 21128
5 | Timothy King | QA PMO Specialist | 114 | 64 | 7296
6 | Raj Ganesh | QA Conversion Lead | 114 | 64 | 7296
7 | Donna Smith | QA Independent Tester/UAT Leader | 114 | 48 | 5472
8 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 12 | 540
9 | Frank Ono | QA Executive | 154 | 24 | 3696
10 |  |  |  | 0 | 0
11 |  |  |  | 0 | 0
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 632 | 83660
DEL #10 - Quarterly QA Security Report (Quarterly)
1 | Dan Dean | QA Project Manager | 154 | 200 | 30800
2 | Don Coffey | QA Technical Manager | 144 | 640 | 92160
3 | Greg FitzGerald | QA Technical Lead | 139 | 576 | 80064
4 | Dustin Lish | QA Technical Lead | 139 | 448 | 62272
5 | Timothy King | QA PMO Specialist | 114 | 280 | 31920
6 | Raj Ganesh | QA Conversion Lead | 114 | 320 | 36480
7 | Donna Smith | QA Independent Tester/UAT Leader | 114 | 320 | 36480
8 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 80 | 3600
9 | Frank Ono | QA Executive | 154 | 80 | 12320
10 |  |  |  | 0 | 0
11 |  |  |  | 0 | 0
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 2944 | 386096
DEL #11 - Assessment of DD&I Vendor CalSAWS Migration Project Control Document Initial
1 | Dan Dean | QA Project Manager | 154 | 24 | 3696
2 | Beena Amarnath | QA PMO Lead | 134 | 52 | 6968
3 | Timothy King | QA PMO Specialist | 114 | 22 | 2508
4 | Kristin Pepper | QA Functional Manager | 134 | 32 | 4288
5 | Don Coffey | QA Technical Manager | 144 | 24 | 3456
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 8 | 360
7 | Wendy Battermann | QA Executive | 154 | 8 | 1232
8 |  |  |  | 0 | 0
9 |  |  |  | 0 | 0
10 |  |  |  | 0 | 0
11 |  |  |  | 0 | 0
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 170 | 22508
DEL #12 - Assessment of DD&I Vendor CalSAWS Migration Work Plan Update (Monthly)
1 | Dan Dean | QA Project Manager | 154 | 1080 | 166320
2 | Beena Amarnath | QA PMO Lead | 134 | 776 | 103984
3 | Timothy King | QA PMO Specialist | 114 | 720 | 82080
4 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 184 | 8280
5 | Wendy Battermann | QA Executive | 154 | 92 | 14168
6 |  |  |  | 0 | 0
7 |  |  |  | 0 | 0
8 |  |  |  | 0 | 0
9 |  |  |  | 0 | 0
10 |  |  |  | 0 | 0
11 |  |  |  | 0 | 0
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 2852 | 374832
DEL #13 - Assessment of DD&I Vendor CalSAWS General Design
1 | Dan Dean | QA Project Manager | 154 | 14 | 2156
2 | Timothy King | QA PMO Specialist | 114 | 14 | 1596
3 | Kristin Pepper | QA Functional Manager | 134 | 24 | 3216
4 | Don Coffey | QA Technical Manager | 144 | 40 | 5760
5 | Abby Darrah | QA Implementation Manager | 134 | 32 | 4288
6 | Cheryl Hofmann | QA Testing Manager | 134 | 0 | 0
7 | Rachel Hernandez | QA UAT Lead | 134 | 0 | 0
8 | Pandu Gupta | QA Business Analyst/Tester | 114 | 56 | 6384
9 | Greg FitzGerald | QA Technical Lead | 139 | 44 | 6116
10 | Dustin Lish | QA Technical Lead | 139 | 8 | 1112
11 | Raj Ganesh | QA Conversion Lead | 114 | 48 | 5472
12 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 8 | 360
13 | Frank Ono | QA Executive | 154 | 8 | 1232
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 296 | 37692
DEL #14 - Assessment of DD&I Vendor CalACES Master Conversion Plan
1 | Dan Dean | QA Project Manager | 154 | 12 | 1848
2 | Raj Ganesh | QA Conversion Lead | 114 | 92 | 10488
3 | Timothy King | QA PMO Specialist | 114 | 22 | 2508
4 | Kristin Pepper | QA Functional Manager | 134 | 32 | 4288
5 | Don Coffey | QA Technical Manager | 144 | 32 | 4608
6 | Abby Darrah | QA Implementation Manager | 134 | 32 | 4288
7 | Cheryl Hofmann | QA Testing Manager | 134 | 16 | 2144
8 | Rachel Hernandez | QA UAT Lead | 134 | 16 | 2144
9 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 8 | 360
10 | Frank Ono | QA Executive | 154 | 8 | 1232
11 |  |  |  | 0 | 0
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 270 | 33908
DEL #15 - Assessment of DD&I Vendor Application Development Preparation and Installation Plan
1 | Dan Dean | QA Project Manager | 154 | 16 | 2464
2 | Don Coffey | QA Technical Manager | 144 | 56 | 8064
3 | Greg FitzGerald | QA Technical Lead | 139 | 76 | 10564
4 | Dustin Lish | QA Technical Lead | 139 | 16 | 2224
5 | Abby Darrah | QA Implementation Manager | 134 | 24 | 3216
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 8 | 360
7 | Frank Ono | QA Executive | 154 | 8 | 1232
8 |  |  |  | 0 | 0
9 |  |  |  | 0 | 0
10 |  |  |  | 0 | 0
11 |  |  |  | 0 | 0
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 204 | 28124
DEL #16 - Assessment of DD&I Vendor CalSAWS Master Test Plan
1 | Dan Dean | QA Project Manager | 154 | 4 | 616
2 | Timothy King | QA PMO Specialist | 114 | 6 | 684
3 | Cheryl Hofmann | QA Testing Manager | 134 | 24 | 3216
4 | Rachel Hernandez | QA UAT Lead | 134 | 24 | 3216
5 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 4 | 180
6 | Wendy Battermann | QA Executive | 154 | 4 | 616
7 |  |  |  | 0 | 0
8 |  |  |  | 0 | 0
9 |  |  |  | 0 | 0
10 |  |  |  | 0 | 0
11 |  |  |  | 0 | 0
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 66 | 8528
DEL #17 - Assessment of DD&I Vendor CalSAWS Business Architecture Design
1 | Dan Dean | QA Project Manager | 154 | 8 | 1232
2 | Timothy King | QA PMO Specialist | 114 | 6 | 684
3 | Kristin Pepper | QA Functional Manager | 134 | 16 | 2144
4 | Don Coffey | QA Technical Manager | 144 | 24 | 3456
5 | Pandu Gupta | QA Business Analyst/Tester | 114 | 12 | 1368
6 | Greg FitzGerald | QA Technical Lead | 139 | 24 | 3336
7 | Dustin Lish | QA Technical Lead | 139 | 8 | 1112
8 | Raj Ganesh | QA Conversion Lead | 114 | 16 | 1824
9 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 4 | 180
10 | Frank Ono | QA Executive | 154 | 8 | 1232
11 |  |  |  | 0 | 0
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 126 | 16568
DEL #18 - Assessment of DD&I Vendor CalSAWS General Design
1 | Dan Dean | QA Project Manager | 154 | 8 | 1232
2 | Timothy King | QA PMO Specialist | 114 | 6 | 684
3 | Kristin Pepper | QA Functional Manager | 134 | 16 | 2144
4 | Don Coffey | QA Technical Manager | 144 | 16 | 2304
5 | Pandu Gupta | QA Business Analyst/Tester | 114 | 22 | 2508
6 | Greg FitzGerald | QA Technical Lead | 139 | 24 | 3336
7 | Dustin Lish | QA Technical Lead | 139 | 8 | 1112
8 | Raj Ganesh | QA Conversion Lead | 114 | 16 | 1824
9 | Cheryl Hofmann | QA Testing Manager | 134 | 8 | 1072
10 | Rachel Hernandez | QA UAT Lead | 134 | 8 | 1072
11 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 4 | 180
12 | Frank Ono | QA Executive | 154 | 8 | 1232
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 144 | 18700
DEL #19 - Assessment of DD&I Vendor CalSAWS General Design
1 | Dan Dean | QA Project Manager | 154 | 16 | 2464
2 | Timothy King | QA PMO Specialist | 114 | 24 | 2736
3 | Kristin Pepper | QA Functional Manager | 134 | 64 | 8576
4 | Don Coffey | QA Technical Manager | 144 | 40 | 5760
5 | Pandu Gupta | QA Business Analyst/Tester | 114 | 102 | 11628
6 | Greg FitzGerald | QA Technical Lead | 139 | 80 | 11120
7 | Dustin Lish | QA Technical Lead | 139 | 16 | 2224
8 | Raj Ganesh | QA Conversion Lead | 114 | 68 | 7752
9 | Cheryl Hofmann | QA Testing Manager | 134 | 24 | 3216
10 | Rachel Hernandez | QA UAT Lead | 134 | 24 | 3216
11 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 8 | 360
12 | Frank Ono | QA Executive | 154 | 6 | 924
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 472 | 59976
DEL #20 - Assessment of DD&I Vendor C-IV Master Training Plan
1 | Dan Dean | QA Project Manager | 154 | 8 | 1232
2 | Timothy King | QA PMO Specialist | 114 | 24 | 2736
3 | Abby Darrah | QA Implementation Manager | 134 | 16 | 2144
4 | Ivan Parra | QA Implementation Lead | 124 | 0 | 0
5 | Gail Brown | QA Implementation Lead | 124 | 80 | 9920
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 8 | 360
7 | Wendy Battermann | QA Executive | 154 | 8 | 1232
8 |  |  |  | 0 | 0
9 |  |  |  | 0 | 0
10 |  |  |  | 0 | 0
11 |  |  |  | 0 | 0
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 144 | 17624
DEL #21 - Assessment of DD&I Vendor CalWIN/CalSAWS Master Conversion Plan
1 | Dan Dean | QA Project Manager | 154 | 8 | 1232
2 | Raj Ganesh | QA Conversion Lead | 114 | 68 | 7752
3 | Timothy King | QA PMO Specialist | 114 | 28 | 3192
4 | Kristin Pepper | QA Functional Manager | 134 | 32 | 4288
5 | Don Coffey | QA Technical Manager | 144 | 24 | 3456
6 | Abby Darrah | QA Implementation Manager | 134 | 16 | 2144
7 | Cheryl Hofmann | QA Testing Manager | 134 | 16 | 2144
8 | Rachel Hernandez | QA UAT Lead | 134 | 16 | 2144
9 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 8 | 360
10 | Frank Ono | QA Executive | 154 | 6 | 924
11 |  |  |  | 0 | 0
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 222 | 27636
DEL #22 - Assessment of DD&I Vendor CalSAWS Requirements Traceability Matrix - Initial
1 | Beena Amarnath | QA PMO Lead | 134 | 56 | 7504
2 | Kristin Pepper | QA Functional Manager | 134 | 32 | 4288
3 | Pandu Gupta | QA Business Analyst/Tester | 114 | 88 | 10032
4 | Don Coffey | QA Technical Manager | 144 | 32 | 4608
5 | Timothy King | QA PMO Specialist | 114 | 42 | 4788
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 8 | 360
7 | Wendy Battermann | QA Executive | 154 | 2 | 308
8 |  |  |  | 0 | 0
9 |  |  |  | 0 | 0
10 |  |  |  | 0 | 0
11 |  |  |  | 0 | 0
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 260 | 31888
DEL #23 - Assessment of DD&I Vendor CalSAWS General Design (Page/Report/Correspondence Changes per Requirement)
1 | Dan Dean | QA Project Manager | 154 | 56 | 8624
2 | Timothy King | QA PMO Specialist | 114 | 48 | 5472
3 | Kristin Pepper | QA Functional Manager | 134 | 140 | 18760
4 | Don Coffey | QA Technical Manager | 144 | 92 | 13248
5 | Pandu Gupta | QA Business Analyst/Tester | 114 | 184 | 20976
6 | Greg FitzGerald | QA Technical Lead | 139 | 228 | 31692
7 | Dustin Lish | QA Technical Lead | 139 | 48 | 6672
8 | Raj Ganesh | QA Conversion Lead | 114 | 200 | 22800
9 | Cheryl Hofmann | QA Testing Manager | 134 | 32 | 4288
10 | Rachel Hernandez | QA UAT Lead | 134 | 32 | 4288
11 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 8 | 360
12 | Frank Ono | QA Executive | 154 | 6 | 924
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 1074 | 138104
DEL #24 - Assessment of DD&I Vendor C-IV Deployment Readiness Plan
1 | Dan Dean | QA Project Manager | 154 | 26 | 4004
2 | Abby Darrah | QA Implementation Manager | 134 | 72 | 9648
3 | Kristin Pepper | QA Functional Manager | 134 | 72 | 9648
4 | Don Coffey | QA Technical Manager | 144 | 72 | 10368
5 | Timothy King | QA PMO Specialist | 114 | 32 | 3648
6 | Cheryl Hofmann | QA Testing Manager | 134 | 24 | 3216
7 | Gail Brown | QA Implementation Lead | 124 | 180 | 22320
8 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 8 | 360
9 | Wendy Battermann | QA Executive | 154 | 4 | 616
10 |  |  |  | 0 | 0
11 |  |  |  | 0 | 0
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 490 | 63828
DEL #25 - Assessment of DD&I Vendor CalSAWS Requirements Traceability Matrix - Update 1
1 | Dan Dean | QA Project Manager | 154 | 12 | 1848
2 | Kristin Pepper | QA Functional Manager | 134 | 64 | 8576
3 | Pandu Gupta | QA Business Analyst/Tester | 114 | 72 | 8208
4 | Don Coffey | QA Technical Manager | 144 | 40 | 5760
5 | Timothy King | QA PMO Specialist | 114 | 16 | 1824
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 8 | 360
7 | Wendy Battermann | QA Executive | 154 | 2 | 308
8 |  |  |  | 0 | 0
9 |  |  |  | 0 | 0
10 |  |  |  | 0 | 0
11 |  |  |  | 0 | 0
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 214 | 26884
DEL #26 - Assessment of DD&I Vendor CalSAWS General Design
1 | Dan Dean | QA Project Manager | 154 | 40 | 6160
2 | Timothy King | QA PMO Specialist | 114 | 64 | 7296
3 | Kristin Pepper | QA Functional Manager | 134 | 124 | 16616
4 | Don Coffey | QA Technical Manager | 144 | 116 | 16704
5 | Pandu Gupta | QA Business Analyst/Tester | 114 | 168 | 19152
6 | Greg FitzGerald | QA Technical Lead | 139 | 248 | 34472
7 | Dustin Lish | QA Technical Lead | 139 | 48 | 6672
8 | Raj Ganesh | QA Conversion Lead | 114 | 150 | 17100
9 | Cheryl Hofmann | QA Testing Manager | 134 | 32 | 4288
10 | Rachel Hernandez | QA UAT Lead | 134 | 32 | 4288
11 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 8 | 360
12 | Frank Ono | QA Executive | 154 | 6 | 924
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 1036 | 134032
DEL #27 - Assessment of DD&I Vendor CalWIN/CalSAWS Master Conversion Plan - Update 1
1 | Dan Dean | QA Project Manager | 154 | 28 | 4312
2 | Raj Ganesh | QA Conversion Lead | 114 | 100 | 11400
3 | Timothy King | QA PMO Specialist | 114 | 48 | 5472
4 | Kristin Pepper | QA Functional Manager | 134 | 48 | 6432
5 | Don Coffey | QA Technical Manager | 144 | 64 | 9216
6 | Abby Darrah | QA Implementation Manager | 134 | 72 | 9648
7 | Cheryl Hofmann | QA Testing Manager | 134 | 40 | 5360
8 | Rachel Hernandez | QA UAT Lead | 134 | 40 | 5360
9 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 8 | 360
10 | Frank Ono | QA Executive | 154 | 4 | 616
11 |  |  |  | 0 | 0
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 452 | 58176
DEL #28 - Assessment of DD&I Vendor CalSAWS General Design
1 | Dan Dean | QA Project Manager | 154 | 36 | 5544
2 | Timothy King | QA PMO Specialist | 114 | 52 | 5928
3 | Kristin Pepper | QA Functional Manager | 134 | 112 | 15008
4 | Don Coffey | QA Technical Manager | 144 | 116 | 16704
5 | Pandu Gupta | QA Business Analyst/Tester | 114 | 192 | 21888
6 | Greg FitzGerald | QA Technical Lead | 139 | 240 | 33360
7 | Dustin Lish | QA Technical Lead | 139 | 56 | 7784
8 | Raj Ganesh | QA Conversion Lead | 114 | 150 | 17100
9 | Cheryl Hofmann | QA Testing Manager | 134 | 32 | 4288
10 | Rachel Hernandez | QA UAT Lead | 134 | 32 | 4288
11 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 8 | 360
12 | Frank Ono | QA Executive | 154 | 8 | 1232
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 1034 | 133484
DEL #29 - Assessment of DD&I Vendor CalSAWS Migration Project Control Document Update
1 | Dan Dean | QA Project Manager | 154 | 16 | 2464
2 | Beena Amarnath | QA PMO Lead | 134 | 48 | 6432
3 | Timothy King | QA PMO Specialist | 114 | 48 | 5472
4 | Kristin Pepper | QA Functional Manager | 134 | 40 | 5360
5 | Don Coffey | QA Technical Manager | 144 | 32 | 4608
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 8 | 360
7 | Wendy Battermann | QA Executive | 154 | 6 | 924
8 |  |  |  | 0 | 0
9 |  |  |  | 0 | 0
10 |  |  |  | 0 | 0
11 |  |  |  | 0 | 0
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 198 | 25620
DEL #30 - Assessment of DD&I Vendor CalSAWS Requirements Traceability Matrix - Update 2
1 | Dan Dean | QA Project Manager | 154 | 12 | 1848
2 | Kristin Pepper | QA Functional Manager | 134 | 32 | 4288
3 | Pandu Gupta | QA Business Analyst/Tester | 114 | 72 | 8208
4 | Don Coffey | QA Technical Manager | 144 | 40 | 5760
5 | Timothy King | QA PMO Specialist | 114 | 12 | 1368
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 8 | 360
7 |  |  |  | 0 | 0
8 |  |  |  | 0 | 0
9 |  |  |  | 0 | 0
10 |  |  |  | 0 | 0
11 |  |  |  | 0 | 0
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 176 | 21832
DEL #31 - Assessment of DD&I Vendor CalSAWS General Design
1 | Dan Dean | QA Project Manager | 154 | 32 | 4928
2 | Timothy King | QA PMO Specialist | 114 | 56 | 6384
3 | Kristin Pepper | QA Functional Manager | 134 | 128 | 17152
4 | Don Coffey | QA Technical Manager | 144 | 116 | 16704
5 | Pandu Gupta | QA Business Analyst/Tester | 114 | 212 | 24168
6 | Greg FitzGerald | QA Technical Lead | 139 | 252 | 35028
7 | Dustin Lish | QA Technical Lead | 139 | 56 | 7784
8 | Raj Ganesh | QA Conversion Lead | 114 | 200 | 22800
9 | Cheryl Hofmann | QA Testing Manager | 134 | 32 | 4288
10 | Rachel Hernandez | QA UAT Lead | 134 | 32 | 4288
11 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 8 | 360
12 | Frank Ono | QA Executive | 154 | 6 | 924
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 1130 | 144808
DEL #32 - Assessment of DD&I Vendor CalSAWS Requirements Traceability Matrix - Update 3
1 | Dan Dean | QA Project Manager | 154 | 32 | 4928
2 | Kristin Pepper | QA Functional Manager | 134 | 32 | 4288
3 | Pandu Gupta | QA Business Analyst/Tester | 114 | 64 | 7296
4 | Don Coffey | QA Technical Manager | 144 | 40 | 5760
5 | Timothy King | QA PMO Specialist | 114 | 32 | 3648
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 8 | 360
7 |  |  |  | 0 | 0
8 |  |  |  | 0 | 0
9 |  |  |  | 0 | 0
10 |  |  |  | 0 | 0
11 |  |  |  | 0 | 0
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 208 | 26280
DEL #33 - Assessment of DD&I Vendor C-IV Change Management Plan
1 | Dan Dean | QA Project Manager | 154 | 16 | 2464
2 | Timothy King | QA PMO Specialist | 114 | 8 | 912
3 | Abby Darrah | QA Implementation Manager | 134 | 192 | 25728
4 | Ivan Parra | QA Implementation Lead | 124 | 80 | 9920
5 | Gail Brown | QA Implementation Lead | 124 | 320 | 39680
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 8 | 360
7 | Wendy Battermann | QA Executive | 154 | 8 | 1232
8 |  |  |  | 0 | 0
9 |  |  |  | 0 | 0
10 |  |  |  | 0 | 0
11 |  |  |  | 0 | 0
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 632 | 80296
DEL #34 - Assessment of DD&I Vendor CalSAWS Requirements Traceability Matrix - Update 4
1 | Dan Dean | QA Project Manager | 154 | 8 | 1232
2 | Kristin Pepper | QA Functional Manager | 134 | 32 | 4288
3 | Pandu Gupta | QA Business Analyst/Tester | 114 | 64 | 7296
4 | Don Coffey | QA Technical Manager | 144 | 40 | 5760
5 | Timothy King | QA PMO Specialist | 114 | 32 | 3648
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 8 | 360
7 |  |  |  | 0 | 0
8 |  |  |  | 0 | 0
9 |  |  |  | 0 | 0
10 |  |  |  | 0 | 0
11 |  |  |  | 0 | 0
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 184 | 22584
DEL #35 - Assessment of DD&I Vendor CalSAWS General Design
1 | Dan Dean | QA Project Manager | 154 | 20 | 3080
2 | Timothy King | QA PMO Specialist | 114 | 48 | 5472
3 | Kristin Pepper | QA Functional Manager | 134 | 136 | 18224
4 | Don Coffey | QA Technical Manager | 144 | 116 | 16704
5 | Pandu Gupta | QA Business Analyst/Tester | 114 | 200 | 22800
6 | Greg FitzGerald | QA Technical Lead | 139 | 232 | 32248
7 | Dustin Lish | QA Technical Lead | 139 | 60 | 8340
8 | Raj Ganesh | QA Conversion Lead | 114 | 200 | 22800
9 | Cheryl Hofmann | QA Testing Manager | 134 | 32 | 4288
10 | Rachel Hernandez | QA UAT Lead | 134 | 32 | 4288
11 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 12 | 540
12 | Frank Ono | QA Executive | 154 | 8 | 1232
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 1096 | 140016
DEL #36 - Assessment of DD&I Vendor CalSAWS Requirements Traceability Matrix - Update 5
1 | Dan Dean | QA Project Manager | 154 | 8 | 1232
2 | Kristin Pepper | QA Functional Manager | 134 | 48 | 6432
3 | Pandu Gupta | QA Business Analyst/Tester | 114 | 96 | 10944
4 | Don Coffey | QA Technical Manager | 144 | 40 | 5760
5 | Timothy King | QA PMO Specialist | 114 | 32 | 3648
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 8 | 360
7 |  |  |  | 0 | 0
8 |  |  |  | 0 | 0
9 |  |  |  | 0 | 0
10 |  |  |  | 0 | 0
11 |  |  |  | 0 | 0
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 232 | 28376
DEL #37 - Assessment of DD&I Vendor CalSAWS Requirements Traceability Matrix - Update 6
1 | Dan Dean | QA Project Manager | 154 | 8 | 1232
2 | Kristin Pepper | QA Functional Manager | 134 | 48 | 6432
3 | Pandu Gupta | QA Business Analyst/Tester | 114 | 96 | 10944
4 | Don Coffey | QA Technical Manager | 144 | 40 | 5760
5 | Timothy King | QA PMO Specialist | 114 | 32 | 3648
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 8 | 360
7 |  |  |  | 0 | 0
8 |  |  |  | 0 | 0
9 |  |  |  | 0 | 0
10 |  |  |  | 0 | 0
11 |  |  |  | 0 | 0
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 232 | 28376
DEL #38 - Assessment of DD&I Vendor CalSAWS UAT Support Plan
1 | Dan Dean | QA Project Manager | 154 | 8 | 1232
2 | Timothy King | QA PMO Specialist | 114 | 20 | 2280
3 | Cheryl Hofmann | QA Testing Manager | 134 | 40 | 5360
4 | Rachel Hernandez | QA UAT Lead | 134 | 88 | 11792
5 | Sindura Kompulira | QA Independent Tester/UAT Leader | 114 | 88 | 10032
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 12 | 540
7 | Wendy Battermann | QA Executive | 154 | 8 | 1232
8 |  |  |  | 0 | 0
9 |  |  |  | 0 | 0
10 |  |  |  | 0 | 0
11 |  |  |  | 0 | 0
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 264 | 32468
DEL #39 - Assessment of DD&I Vendor CalSAWS Requirements Traceability Matrix - Update 7
1 | Dan Dean | QA Project Manager | 154 | 8 | 1232
2 | Kristin Pepper | QA Functional Manager | 134 | 32 | 4288
3 | Pandu Gupta | QA Business Analyst/Tester | 114 | 64 | 7296
4 | Don Coffey | QA Technical Manager | 144 | 40 | 5760
5 | Timothy King | QA PMO Specialist | 114 | 32 | 3648
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 8 | 360
7 |  |  |  | 0 | 0
8 |  |  |  | 0 | 0
9 |  |  |  | 0 | 0
10 |  |  |  | 0 | 0
11 |  |  |  | 0 | 0
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 184 | 22584
DEL #40 - Assessment of DD&I Vendor CalSAWS (C-IV) UAT Readiness Report/Milestone
1 | Dan Dean | QA Project Manager | 154 | 24 | 3696
2 | Timothy King | QA PMO Specialist | 114 | 40 | 4560
3 | Cheryl Hofmann | QA Testing Manager | 134 | 36 | 4824
4 | Rachel Hernandez | QA UAT Lead | 134 | 36 | 4824
5 | Donna Smith | QA Independent Tester/UAT Leader | 114 | 32 | 3648
6 | Sindura Kompulira | QA Independent Tester/UAT Leader | 114 | 32 | 3648
7 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 8 | 360
8 | Wendy Battermann | QA Executive | 154 | 4 | 616
9 |  |  |  | 0 | 0
10 |  |  |  | 0 | 0
11 |  |  |  | 0 | 0
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 212 | 26176
DEL #41 - Assessment of DD&I Vendor CalSAWS Migration Project Control Document Update
1 | Dan Dean | QA Project Manager | 154 | 8 | 1232
2 | Beena Amarnath | QA PMO Lead | 134 | 32 | 4288
3 | Timothy King | QA PMO Specialist | 114 | 36 | 4104
4 | Kristin Pepper | QA Functional Manager | 134 | 24 | 3216
5 | Don Coffey | QA Technical Manager | 144 | 40 | 5760
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 8 | 360
7 | Wendy Battermann | QA Executive | 154 | 4 | 616
8 |  |  |  | 0 | 0
9 |  |  |  | 0 | 0
10 |  |  |  | 0 | 0
11 |  |  |  | 0 | 0
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 152 | 19576
DEL #42 - Assessment of DD&I Vendor CalSAWS (CalWIN) UAT Readiness Report/Milestone
1 | Dan Dean | QA Project Manager | 154 | 12 | 1848
2 | Timothy King | QA PMO Specialist | 114 | 8 | 912
3 | Cheryl Hofmann | QA Testing Manager | 134 | 32 | 4288
4 | Rachel Hernandez | QA UAT Lead | 134 | 32 | 4288
5 | Donna Smith | QA Independent Tester/UAT Leader | 114 | 32 | 3648
6 | Sindura Kompulira | QA Independent Tester/UAT Leader | 114 | 32 | 3648
7 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 8 | 360
8 | Wendy Battermann | QA Executive | 154 | 4 | 616
9 |  |  |  | 0 | 0
10 |  |  |  | 0 | 0
11 |  |  |  | 0 | 0
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 160 | 19608
DEL #43 - Assessment of DD&I Vendor CalSAWS Requirements Traceability Matrix - Update 8
1 | Dan Dean | QA Project Manager | 154 | 8 | 1232
2 | Kristin Pepper | QA Functional Manager | 134 | 32 | 4288
3 | Pandu Gupta | QA Business Analyst/Tester | 114 | 64 | 7296
4 | Don Coffey | QA Technical Manager | 144 | 40 | 5760
5 | Timothy King | QA PMO Specialist | 114 | 32 | 3648
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 8 | 360
7 |  |  |  | 0 | 0
8 |  |  |  | 0 | 0
9 |  |  |  | 0 | 0
10 |  |  |  | 0 | 0
11 |  |  |  | 0 | 0
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 184 | 22584
DEL #44 - Assessment of DD&I Vendor CalSAWS Requirements Traceability Matrix - Update 9
1 | Dan Dean | QA Project Manager | 154 | 8 | 1232
2 | Kristin Pepper | QA Functional Manager | 134 | 32 | 4288
3 | Pandu Gupta | QA Business Analyst/Tester | 114 | 64 | 7296
4 | Don Coffey | QA Technical Manager | 144 | 40 | 5760
5 | Timothy King | QA PMO Specialist | 114 | 24 | 2736
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 8 | 360
7 |  |  |  | 0 | 0
8 |  |  |  | 0 | 0
9 |  |  |  | 0 | 0
10 |  |  |  | 0 | 0
11 |  |  |  | 0 | 0
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 176 | 21672
DEL #45 - Assessment of DD&I Vendor CalSAWS Deployment Complete Milestone/Report - C-IV
1 | Dan Dean | QA Project Manager | 154 | 16 | 2464
2 | Beena Amarnath | QA PMO Lead | 134 | 16 | 2144
3 | Timothy King | QA PMO Specialist | 114 | 24 | 2736
4 | Kristin Pepper | QA Functional Manager | 134 | 80 | 10720
5 | Don Coffey | QA Technical Manager | 144 | 0 | 0
6 | Abby Darrah | QA Implementation Manager | 134 | 144 | 19296
7 | Cheryl Hofmann | QA Testing Manager | 134 | 48 | 6432
8 | Rachel Hernandez | QA UAT Lead | 134 | 48 | 6432
9 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 8 | 360
10 | Raj Ganesh | QA Conversion Lead | 114 | 80 | 9120
11 | Wendy Battermann | QA Executive | 154 | 8 | 1232
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 472 | 60936
DEL #46 - Assessment of DD&I Vendor CalACES Migration Final Acceptance Certification
1 | Dan Dean | QA Project Manager | 154 | 8 | 1232
2 | Beena Amarnath | QA PMO Lead | 134 | 8 | 1072
3 | Timothy King | QA PMO Specialist | 114 | 32 | 3648
4 | Abby Darrah | QA Implementation Manager | 134 | 32 | 4288
5 | Gail Brown | QA Implementation Lead | 124 | 16 | 1984
6 | Ivan Parra | QA Implementation Lead | 124 | 16 | 1984
7 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 8 | 360
8 | Raj Ganesh | QA Conversion Lead | 114 | 16 | 1824
9 | Don Coffey | QA Technical Manager | 144 | 0 | 0
10 | Kristin Pepper | QA Functional Manager | 134 | 16 | 2144
11 | Wendy Battermann | QA Executive | 154 | 6 | 924
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 158 | 19460
DEL #47 - Assessment of DD&I Vendor CalSAWS Deployment Complete Milestone/Report - CalWIN Wave 1
1 | Dan Dean | QA Project Manager | 154 | 48 | 7392
2 | Beena Amarnath | QA PMO Lead | 134 | 48 | 6432
3 | Timothy King | QA PMO Specialist | 114 | 48 | 5472
4 | Kristin Pepper | QA Functional Manager | 134 | 48 | 6432
5 | Don Coffey | QA Technical Manager | 144 | 48 | 6912
6 | Abby Darrah | QA Implementation Manager | 134 | 220 | 29480
7 | Cheryl Hofmann | QA Testing Manager | 134 | 56 | 7504
8 | Rachel Hernandez | QA UAT Lead | 134 | 56 | 7504
9 | Pandu Gupta | QA Business Analyst/Tester | 114 | 56 | 6384
10 | Gail Brown | QA Implementation Lead | 124 | 240 | 29760
11 | Ivan Parra | QA Implementation Lead | 124 | 240 | 29760
12 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 8 | 360
13 | Raj Ganesh | QA Conversion Lead | 114 | 48 | 5472
14 | Wendy Battermann | QA Executive | 154 | 6 | 924
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 1170 | 149788
DEL #48 - Assessment of DD&I Vendor CalSAWS Migration Project Control Document Update
1 | Dan Dean | QA Project Manager | 154 | 28 | 4312
2 | Beena Amarnath | QA PMO Lead | 134 | 28 | 3752
3 | Timothy King | QA PMO Specialist | 114 | 48 | 5472
4 | Kristin Pepper | QA Functional Manager | 134 | 32 | 4288
5 | Don Coffey | QA Technical Manager | 144 | 32 | 4608
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 8 | 360
7 | Wendy Battermann | QA Executive | 154 | 4 | 616
8 |  |  |  | 0 | 0
9 |  |  |  | 0 | 0
10 |  |  |  | 0 | 0
11 |  |  |  | 0 | 0
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 180 | 23408
DEL #49 - Assessment of DD&I Vendor CalSAWS Deployment Complete Milestone/Report - CalWIN Wave 2
1 | Dan Dean | QA Project Manager | 154 | 48 | 7392
2 | Beena Amarnath | QA PMO Lead | 134 | 48 | 6432
3 | Timothy King | QA PMO Specialist | 114 | 48 | 5472
4 | Kristin Pepper | QA Functional Manager | 134 | 48 | 6432
5 | Don Coffey | QA Technical Manager | 144 | 48 | 6912
6 | Abby Darrah | QA Implementation Manager | 134 | 220 | 29480
7 | Cheryl Hofmann | QA Testing Manager | 134 | 56 | 7504
8 | Rachel Hernandez | QA UAT Lead | 134 | 56 | 7504
9 | Pandu Gupta | QA Business Analyst/Tester | 114 | 56 | 6384
10 | Gail Brown | QA Implementation Lead | 124 | 220 | 27280
11 | Ivan Parra | QA Implementation Lead | 124 | 220 | 27280
12 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 8 | 360
13 | Raj Ganesh | QA Conversion Lead | 114 | 48 | 5472
14 | Wendy Battermann | QA Executive | 154 | 8 | 1232
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 1132 | 145136
DEL #50 - Assessment of DD&I Vendor CalSAWS Deployment Complete Milestone/Report - CalWIN Wave 3
1 | Dan Dean | QA Project Manager | 154 | 48 | 7392
2 | Beena Amarnath | QA PMO Lead | 134 | 48 | 6432
3 | Timothy King | QA PMO Specialist | 114 | 48 | 5472
4 | Kristin Pepper | QA Functional Manager | 134 | 48 | 6432
5 | Don Coffey | QA Technical Manager | 144 | 48 | 6912
6 | Abby Darrah | QA Implementation Manager | 134 | 220 | 29480
7 | Cheryl Hofmann | QA Testing Manager | 134 | 56 | 7504
8 | Rachel Hernandez | QA UAT Lead | 134 | 56 | 7504
9 | Pandu Gupta | QA Business Analyst/Tester | 114 | 56 | 6384
10 | Gail Brown | QA Implementation Lead | 124 | 220 | 27280
11 | Ivan Parra | QA Implementation Lead | 124 | 220 | 27280
12 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 8 | 360
13 | Raj Ganesh | QA Conversion Lead | 114 | 48 | 5472
14 | Wendy Battermann | QA Executive | 154 | 8 | 1232
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 1132 | 145136
DEL #51 - Assessment of DD&I Vendor CalSAWS Deployment Complete Milestone/Report - CalWIN Wave 4
1 | Dan Dean | QA Project Manager | 154 | 48 | 7392
2 | Beena Amarnath | QA PMO Lead | 134 | 48 | 6432
3 | Timothy King | QA PMO Specialist | 114 | 48 | 5472
4 | Kristin Pepper | QA Functional Manager | 134 | 48 | 6432
5 | Don Coffey | QA Technical Manager | 144 | 48 | 6912
6 | Abby Darrah | QA Implementation Manager | 134 | 220 | 29480
7 | Cheryl Hofmann | QA Testing Manager | 134 | 56 | 7504
8 | Rachel Hernandez | QA UAT Lead | 134 | 56 | 7504
9 | Pandu Gupta | QA Business Analyst/Tester | 114 | 56 | 6384
10 | Gail Brown | QA Implementation Lead | 124 | 220 | 27280
11 | Ivan Parra | QA Implementation Lead | 124 | 220 | 27280
12 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 8 | 360
13 | Wendy Battermann | QA Executive | 154 | 48 | 7392
14 |  |  |  | 8 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 1132 | 145824
DEL #52 - Assessment of DD&I Vendor CalSAWS Deployment Complete Milestone/Report - CalWIN Wave 5
1 | Dan Dean | QA Project Manager | 154 | 48 | 7392
2 | Beena Amarnath | QA PMO Lead | 134 | 48 | 6432
3 | Timothy King | QA PMO Specialist | 114 | 48 | 5472
4 | Kristin Pepper | QA Functional Manager | 134 | 48 | 6432
5 | Don Coffey | QA Technical Manager | 144 | 48 | 6912
6 | Abby Darrah | QA Implementation Manager | 134 | 220 | 29480
7 | Cheryl Hofmann | QA Testing Manager | 134 | 56 | 7504
8 | Rachel Hernandez | QA UAT Lead | 134 | 56 | 7504
9 | Pandu Gupta | QA Business Analyst/Tester | 114 | 56 | 6384
10 | Gail Brown | QA Implementation Lead | 124 | 220 | 27280
11 | Ivan Parra | QA Implementation Lead | 124 | 220 | 27280
12 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 8 | 360
13 | Raj Ganesh | QA Conversion Lead | 114 | 48 | 5472
14 | Wendy Battermann | QA Executive | 154 | 8 | 1232
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 1132 | 145136
DEL #53 - Assessment of DD&I Vendor CalSAWS Deployment Complete Milestone/Report - CalWIN Wave 6
1 | Dan Dean | QA Project Manager | 154 | 48 | 7392
2 | Beena Amarnath | QA PMO Lead | 134 | 48 | 6432
3 | Timothy King | QA PMO Specialist | 114 | 48 | 5472
4 | Kristin Pepper | QA Functional Manager | 134 | 48 | 6432
5 | Don Coffey | QA Technical Manager | 144 | 48 | 6912
6 | Abby Darrah | QA Implementation Manager | 134 | 220 | 29480
7 | Cheryl Hofmann | QA Testing Manager | 134 | 56 | 7504
8 | Rachel Hernandez | QA UAT Lead | 134 | 56 | 7504
9 | Pandu Gupta | QA Business Analyst/Tester | 114 | 56 | 6384
10 | Gail Brown | QA Implementation Lead | 124 | 160 | 19840
11 | Ivan Parra | QA Implementation Lead | 124 | 160 | 19840
12 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 12 | 540
13 | Raj Ganesh | QA Conversion Lead | 114 | 48 | 5472
14 | Wendy Battermann | QA Executive | 154 | 6 | 924
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 1014 | 130128
DEL #54 - Assessment of DD&I Vendor CalSAWS Deployment Complete Report - CalWIN Wave 1-6
1 | Dan Dean | QA Project Manager | 154 | 16 | 2464
2 | Beena Amarnath | QA PMO Lead | 134 | 24 | 3216
3 | Timothy King | QA PMO Specialist | 114 | 48 | 5472
4 | Kristin Pepper | QA Functional Manager | 134 | 48 | 6432
5 | Don Coffey | QA Technical Manager | 144 | 48 | 6912
6 | Abby Darrah | QA Implementation Manager | 134 | 64 | 8576
7 | Cheryl Hofmann | QA Testing Manager | 134 | 56 | 7504
8 | Rachel Hernandez | QA UAT Lead | 134 | 56 | 7504
9 | Pandu Gupta | QA Business Analyst/Tester | 114 | 56 | 6384
10 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 12 | 540
11 | Raj Ganesh | QA Conversion Lead | 114 | 48 | 5472
12 | Wendy Battermann | QA Executive | 154 | 4 | 616
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 480 | 61092
DEL #55 - Assessment of DD&I Vendor CalSAWS Migration Project Control Document Update
1 | Dan Dean | QA Project Manager | 154 | 8 | 1232
2 | Beena Amarnath | QA PMO Lead | 134 | 40 | 5360
3 | Timothy King | QA PMO Specialist | 114 | 40 | 4560
4 | Kristin Pepper | QA Functional Manager | 134 | 16 | 2144
5 | Don Coffey | QA Technical Manager | 144 | 0 | 0
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 8 | 360
7 | Wendy Battermann | QA Executive | 154 | 4 | 616
8 |  |  |  | 0 | 0
9 |  |  |  | 0 | 0
10 |  |  |  | 0 | 0
11 |  |  |  | 0 | 0
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 116 | 14272
DEL #56 - Assessment of DD&I Vendor CalSAWS Migration Final Acceptance Certification
1 | Dan Dean | QA Project Manager | 154 | 40 | 6160
2 | Beena Amarnath | QA PMO Lead | 134 | 40 | 5360
3 | Timothy King | QA PMO Specialist | 114 | 40 | 4560
4 | Abby Darrah | QA Implementation Manager | 134 | 56 | 7504
5 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 8 | 360
6 | Don Coffey | QA Technical Manager | 144 | 0 | 0
7 | Kristin Pepper | QA Functional Manager | 134 | 32 | 4288
8 | Raj Ganesh | QA Conversion Lead | 114 | 32 | 3648
9 | Wendy Battermann | QA Executive | 154 | 8 | 1232
10 |  |  |  | 0 | 0
11 |  |  |  | 0 | 0
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 256 | 33112
DEL #57 - Assessment of CalWIN Implementation Support Vendor CalWIN Migration Work Plan Initial
1 | Dan Dean | QA Project Manager | 154 | 16 | 2464
2 | Beena Amarnath | QA PMO Lead | 134 | 40 | 5360
3 | Timothy King | QA PMO Specialist | 114 | 12 | 1368
4 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 8 | 360
5 | Wendy Battermann | QA Executive | 154 | 4 | 616
6 |  |  |  | 0 | 0
7 |  |  |  | 0 | 0
8 |  |  |  | 0 | 0
9 |  |  |  | 0 | 0
10 |  |  |  | 0 | 0
11 |  |  |  | 0 | 0
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 80 | 10168
DEL #58 - Assessment of CalWIN Implementation Support Vendor CalWIN Migration Project Control Document Initial
1 | Dan Dean | QA Project Manager | 154 | 16 | 2464
2 | Beena Amarnath | QA PMO Lead | 134 | 40 | 5360
3 | Timothy King | QA PMO Specialist | 114 | 28 | 3192
4 | Kristin Pepper | QA Functional Manager | 134 | 40 | 5360
5 | Don Coffey | QA Technical Manager | 144 | 0 | 0
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 8 | 360
7 | Wendy Battermann | QA Executive | 154 | 4 | 616
8 |  |  |  | 0 | 0
9 |  |  |  | 0 | 0
10 |  |  |  | 0 | 0
11 |  |  |  | 0 | 0
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 136 | 17352
DEL #59 - Assessment of CalWIN Implementation Support Vendor CalWIN Migration Work Plan Update (Monthly)
1 | Dan Dean | QA Project Manager | 154 | 240 | 36960
2 | Beena Amarnath | QA PMO Lead | 134 | 496 | 66464
3 | Timothy King | QA PMO Specialist | 114 | 496 | 56544
4 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 120 | 5400
5 | Wendy Battermann | QA Executive | 154 | 60 | 9240
6 |  |  |  | 0 | 0
7 |  |  |  | 0 | 0
8 |  |  |  | 0 | 0
9 |  |  |  | 0 | 0
10 |  |  |  | 0 | 0
11 |  |  |  | 0 | 0
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 1412 | 174608
DEL #60 - Assessment of CalWIN Implementation Support Vendor CalWIN Master Training Plan
1 | Dan Dean | QA Project Manager | 154 | 24 | 3696
2 | Timothy King | QA PMO Specialist | 114 | 28 | 3192
3 | Abby Darrah | QA Implementation Manager | 134 | 72 | 9648
4 | Ivan Parra | QA Implementation Lead | 124 | 120 | 14880
5 | Gail Brown | QA Implementation Lead | 124 | 120 | 14880
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 8 | 360
7 | Wendy Battermann | QA Executive | 154 | 8 | 1232
8 |  |  |  | 0 | 0
9 |  |  |  | 0 | 0
10 |  |  |  | 0 | 0
11 |  |  |  | 0 | 0
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 380 | 47888
DEL #61 - Assessment of CalWIN Implementation Support Vendor CalWIN Deployment Readiness Plan
1 | Dan Dean | QA Project Manager | 154 | 84 | 12936
2 | Beena Amarnath | QA PMO Lead | 134 | 84 | 11256
3 | Timothy King | QA PMO Specialist | 114 | 84 | 9576
4 | Kristin Pepper | QA Functional Manager | 134 | 80 | 10720
5 | Don Coffey | QA Technical Manager | 144 | 80 | 11520
6 | Abby Darrah | QA Implementation Manager | 134 | 112 | 15008
7 | Cheryl Hofmann | QA Testing Manager | 134 | 84 | 11256
8 | Rachel Hernandez | QA UAT Lead | 134 | 84 | 11256
9 | Gail Brown | QA Implementation Lead | 124 | 80 | 9920
10 | Ivan Parra | QA Implementation Lead | 124 | 80 | 9920
11 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 8 | 360
12 | Raj Ganesh | QA Conversion Lead | 114 | 80 | 9120
13 | Wendy Battermann | QA Executive | 154 | 8 | 1232
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 948 | 124080
DEL #62 - Assessment of CalWIN Implementation Support Vendor CalWIN Change Management Plan
1 | Dan Dean | QA Project Manager | 154 | 24 | 3696
2 | Timothy King | QA PMO Specialist | 114 | 56 | 6384
3 | Abby Darrah | QA Implementation Manager | 134 | 72 | 9648
4 | Ivan Parra | QA Implementation Lead | 124 | 120 | 14880
5 | Gail Brown | QA Implementation Lead | 124 | 120 | 14880
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 8 | 360
7 | Wendy Battermann | QA Executive | 154 | 4 | 616
8 |  |  |  | 0 | 0
9 |  |  |  | 0 | 0
10 |  |  |  | 0 | 0
11 |  |  |  | 0 | 0
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 404 | 50464
DEL #63 - Assessment of CalWIN Implementation Support Vendor CalWIN ILT Training Material
1 | Dan Dean | QA Project Manager | 154 | 16 | 2464
2 | Timothy King | QA PMO Specialist | 114 | 40 | 4560
3 | Abby Darrah | QA Implementation Manager | 134 | 72 | 9648
4 | Ivan Parra | QA Implementation Lead | 124 | 120 | 14880
5 | Gail Brown | QA Implementation Lead | 124 | 120 | 14880
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 8 | 360
7 | Wendy Battermann | QA Executive | 154 | 4 | 616
8 |  |  |  | 0 | 0
9 |  |  |  | 0 | 0
10 |  |  |  | 0 | 0
11 |  |  |  | 0 | 0
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 380 | 47408
DEL #64 - Assessment of CalWIN Implementation Support Vendor CalWIN WBT Training Material
1 | Dan Dean | QA Project Manager | 154 | 16 | 2464
2 | Timothy King | QA PMO Specialist | 114 | 48 | 5472
3 | Abby Darrah | QA Implementation Manager | 134 | 72 | 9648
4 | Ivan Parra | QA Implementation Lead | 124 | 120 | 14880
5 | Gail Brown | QA Implementation Lead | 124 | 120 | 14880
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 8 | 360
7 | Wendy Battermann | QA Executive | 154 | 4 | 616
8 |  |  |  | 0 | 0
9 |  |  |  | 0 | 0
10 |  |  |  | 0 | 0
11 |  |  |  | 0 | 0
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 388 | 48320
DEL #65 - QA Status Report (Monthly)
1 | Dan Dean | QA Project Manager | 154 | 1736 | 267344
2 | Beena Amarnath | QA PMO Lead | 134 | 1920 | 257280
3 | Kristin Pepper | QA Functional Manager | 134 | 2016 | 270144
4 | Don Coffey | QA Technical Manager | 144 | 1472 | 211968
5 | Cheryl Hofmann | QA Testing Manager | 134 | 192 | 25728
6 | Timothy King | QA PMO Specialist | 114 | 1284 | 146376
7 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 828 | 37260
8 | Pandu Gupta | QA Business Analyst/Tester | 114 | 2016 | 229824
9 | Greg FitzGerald | QA Technical Lead | 139 | 1104 | 153456
10 | Dustin Lish | QA Technical Lead | 139 | 328 | 45592
11 | Wendy Battermann | QA Executive | 154 | 284 | 43736
12 | Frank Ono | QA Executive | 154 | 244 | 37576
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 13424 | 1726284
DEL #66 - QA M&O Testing Plan
1 | Dan Dean | QA Project Manager | 154 | 8 | 1232
2 | Timothy King | QA PMO Specialist | 114 | 8 | 912
3 | Cheryl Hofmann | QA Testing Manager | 134 | 48 | 6432
4 | Rachel Hernandez | QA UAT Lead | 134 | 16 | 2144
5 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 4 | 180
6 | Wendy Battermann | QA Executive | 154 | 4 | 616
7 |  |  |  | 0 | 0
8 |  |  |  | 0 | 0
9 |  |  |  | 0 | 0
10 |  |  |  | 0 | 0
11 |  |  |  | 0 | 0
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 88 | 11516
DEL #67 - QA M&O Monthly Test Report (Monthly)
1 | Dan Dean | QA Project Manager | 154 | 96 | 14784
2 | Beena Amarnath | QA PMO Lead | 134 | 96 | 12864
3 | Timothy King | QA PMO Specialist | 114 | 96 | 10944
4 | Cheryl Hofmann | QA Testing Manager | 134 | 1776 | 237984
5 | Rachel Hernandez | QA UAT Lead | 134 | 2000 | 268000
6 | Donna Smith | QA Independent Tester/UAT Leader | 114 | 2016 | 229824
7 | Sindura Kompulira | QA Independent Tester/UAT Leader | 114 | 2016 | 229824
8 | Kim Sinclair | QA Independent Tester | 99 | 2016 | 199584
9 | Lalitha Ramabholta | QA Independent Tester/UAT Leader | 114 | 2016 | 229824
10 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 48 | 2160
11 |  |  |  | 0 | 0
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 12176 | 1435792
DEL #68 - Quarterly QA Security Report (Quarterly)
1 | Dan Dean | QA Project Manager | 154 | 80 | 12320
2 | Don Coffey | QA Technical Manager | 144 | 256 | 36864
3 | Greg FitzGerald | QA Technical Lead | 139 | 256 | 35584
4 | Dustin Lish | QA Technical Lead | 139 | 128 | 17792
5 | Timothy King | QA PMO Specialist | 114 | 112 | 12768
6 | Donna Smith | QA Independent Tester/UAT Leader | 114 | 128 | 14592
7 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 32 | 1440
8 | Frank Ono | QA Executive | 154 | 32 | 4928
9 |  |  |  | 0 | 0
10 |  |  |  | 0 | 0
11 |  |  |  | 0 | 0
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 1024 | 136288
DEL #69 - Monthly SLA & Performance Review Report (Monthly)
1 | Dan Dean | QA Project Manager | 154 | 96 | 14784
2 | Don Coffey | QA Technical Manager | 144 | 288 | 41472
3 | Greg FitzGerald | QA Technical Lead | 139 | 288 | 40032
4 | Timothy King | QA PMO Specialist | 114 | 96 | 10944
5 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 48 | 2160
6 | Frank Ono | QA Executive | 154 | 48 | 7392
7 |  |  |  | 0 | 0
8 |  |  |  | 0 | 0
9 |  |  |  | 0 | 0
10 |  |  |  | 0 | 0
11 |  |  |  | 0 | 0
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20
| Total |  |  | 864 | 116784
|  |  | Total Hours | 153696

## Sch 4 - Deliverables (OCAT)
Schedule 4 - Deliverable Detail (OCAT)
# | Deliverable | Position | Hourly Rate | Total Hours | Cost
DEL #1 - QA Monthly Status Report (OCAT)
1 | Venu Gaddam | QA Technical Lead (OCAT) | 139 | 1638 | 227682
2 | Gretchen Williams | QA Specialist (OCAT) | 124 | 546 | 67704
3 | Wendy Battermann | QA Executive | 154 | 30 | 4620
4 | Frank Ono | QA Executive | 154 | 30 | 4620
5 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 60 | 2700
| Total |  |  | 2304 | 307326
DEL #2 - QA Assessment of OCAT Project Control Document
1 | Venu Gaddam | QA Technical Lead (OCAT) | 139 | 0 | 0
2 | Gretchen Williams | QA Specialist (OCAT) | 124 | 8 | 992
3 | Wendy Battermann | QA Executive | 154 | 2 | 308
4 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 4 | 180
| Total |  |  | 14 | 1480
DEL #3 - QA Assessment of OCAT Work Plan
1 | Venu Gaddam | QA Technical Lead (OCAT) | 139 | 4 | 556
2 | Gretchen Williams | QA Specialist (OCAT) | 124 | 4 | 496
3 | Wendy Battermann | QA Executive | 154 | 2 | 308
4 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 4 | 180
| Total |  |  | 14 | 1540
DEL #4 - QA Assessment of OCAT RTM
1 | Venu Gaddam | QA Technical Lead (OCAT) | 139 | 30 | 4170
2 | Gretchen Williams | QA Specialist (OCAT) | 124 | 20 | 2480
3 | Wendy Battermann | QA Executive | 154 | 2 | 308
4 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 4 | 180
| Total |  |  | 56 | 7138
DEL #5 - QA Assessment of OCAT General Design Document
1 | Venu Gaddam | QA Technical Lead (OCAT) | 139 | 120 | 16680
2 | Gretchen Williams | QA Specialist (OCAT) | 124 | 60 | 7440
3 | Frank Ono | QA Executive | 154 | 12 | 1848
4 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 6 | 270
| Total |  |  | 198 | 26238
DEL #6 - QA Assessment of OCAT Technical Design Document
1 | Venu Gaddam | QA Technical Lead (OCAT) | 139 | 120 | 16680
2 | Gretchen Williams | QA Specialist (OCAT) | 124 | 0 | 0
3 | Frank Ono | QA Executive | 154 | 8 | 1232
4 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 8 | 360
| Total |  |  | 136 | 18272
DEL #7 - QA Assessment of OCAT Application SAWS Interfaces
1 | Venu Gaddam | QA Technical Lead (OCAT) | 139 | 300 | 41700
2 | Gretchen Williams | QA Specialist (OCAT) | 124 | 0 | 0
3 | Frank Ono | QA Executive | 154 | 32 | 4928
4 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 8 | 360
| Total |  |  | 340 | 46988
DEL #8 - QA Assessment of OCAT Master Test Plan
1 | Venu Gaddam | QA Technical Lead (OCAT) | 139 | 16 | 2224
2 | Gretchen Williams | QA Specialist (OCAT) | 124 | 56 | 6944
3 | Wendy Battermann | QA Executive | 154 | 4 | 616
4 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 8 | 360
| Total |  |  | 84 | 10144
DEL #9 - QA Assessment of OCAT Training Plan
1 | Venu Gaddam | QA Technical Lead (OCAT) | 139 | 0 | 0
2 | Gretchen Williams | QA Specialist (OCAT) | 124 | 72 | 8928
3 | Wendy Battermann | QA Executive | 154 | 4 | 616
4 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 8 | 360
| Total |  |  | 84 | 9904
DEL #10 - QA Assessment of OCAT Training Materials
1 | Venu Gaddam | QA Technical Lead (OCAT) | 139 | 0 | 0
2 | Gretchen Williams | QA Specialist (OCAT) | 124 | 148 | 18352
3 | Wendy Battermann | QA Executive | 154 | 8 | 1232
4 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 8 | 360
| Total |  |  | 164 | 19944
DEL #11 - QA Assessment of OCAT System Documentation
1 | Venu Gaddam | QA Technical Lead (OCAT) | 139 | 80 | 11120
2 | Gretchen Williams | QA Specialist (OCAT) | 124 | 80 | 9920
3 | Wendy Battermann | QA Executive | 154 | 4 | 616
4 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 8 | 360
| Total |  |  | 172 | 22016
DEL #12 - QA Assessment of OCAT Final Acceptance
1 | Venu Gaddam | QA Technical Lead (OCAT) | 139 | 120 | 16680
2 | Gretchen Williams | QA Specialist (OCAT) | 124 | 0 | 0
3 | Wendy Battermann | QA Executive | 154 | 12 | 1848
4 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 8 | 360
| Total |  |  | 140 | 18888
DEL #13 - QA Assessment of OCAT M&O Transition Plan
1 | Venu Gaddam | QA Technical Lead (OCAT) | 139 | 40 | 5560
2 | Gretchen Williams | QA Specialist (OCAT) | 124 | 40 | 4960
3 | Frank Ono | QA Executive | 154 | 4 | 616
4 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 4 | 180
| Total |  |  | 88 | 11316
DEL #14 - QA M&O Monthly Status Report (OCAT)
1 | Venu Gaddam | QA Technical Lead (OCAT) | 139 | 920 | 127880
2 | Gretchen Williams | QA Specialist (OCAT) | 124 | 0 | 0
3 | Wendy Battermann | QA Executive | 154 | 24 | 3696
4 | Frank Ono | QA Executive | 154 | 24 | 3696
| Total |  |  | 968 | 135272
|  |  | OCAT DD&I Total | 3794 | 501194
|  |  | OCAT M&O Total | 968 | 135272
|  |  | OCAT Total | 4762 | 636466

## Sch 3 - QA Staff Load OCAT old (hidden)
| Schedule 3 - QA Staff Loading |  |  | 80 | 168 | 168 | 160 | 168 | 144 | 160 | 168 | 152 | 176 | 168 | 152 | 160 | 168 | 168 | 160 | 160 | 160 | 160 | 152 | 144 | 176 | 168 | 160 | 168 | 160 | 176 | 160 | 152 | 152 | 152 | 160 | 144 | 160 | 160 | 168 | 168 | 152 | 176 | 160 | 160 | 152 | 152 | 160 | 144 | 176 | 160 | 176 | 176 | 160 | 184 | 160 | 168 | 160 | 160 | 168 | 160 | 168 | 176
Schedule 3 - QA Staff Loading | time axis 2019-06-28 to 2023-04-28
| Schedule 3 - QA Staff Loading (OCAT) | [94 empty] | <-- Do Not Delete hidden columns
|  | Nominal Month |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 |  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 |  |  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9
|  | FFY |  | 19 | 19 | 19 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 24 | 24 | 24 | 24 | 24 | 24 | 24 |  |  | SFY | SFY | SFY | SFY | SFY | SFY | SFY | SFY | SFY |  |  |  | FFY | FFY | FFY | FFY | FFY | FFY | FFY | FFY | FFY
|  | SFY |  | 18/19 | 19/20 | 19/20 | 19/20 | 19/20 | 19/20 | 19/20 | 19/20 | 19/20 | 19/20 | 19/20 | 19/20 | 19/20 | 20/21 | 20/21 | 20/21 | 20/21 | 20/21 | 20/21 | 20/21 | 20/21 | 20/21 | 20/21 | 20/21 | 20/21 | 21/22 | 21/22 | 21/22 | 21/22 | 21/22 | 21/22 | 21/22 | 21/22 | 21/22 | 21/22 | 21/22 | 21/22 | 22/23 | 22/23 | 22/23 | 22/23 | 22/23 | 22/23 | 22/23 | 22/23 | 22/23 | 22/23 | 22/23 | 22/23 | 23/24 | 23/24 | 23/24 | 23/24 | 23/24 | 23/24 | 23/24 | 23/24 | 23/24 | 23/24 |  |  | 18/19 | 19/20 | 20/21 | 21/22 | 22/23 | 23/24 | 24/25 | 25/26 | 26/27 |  |  |  | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 |  |  | Invoice Month Summaries
| DELIVERABLE | Month | Bill Rate | [59 empty] | Total |  | Total | Total | Total | Total | Total | Total | Total | Total | Total |  | Total |  | Total | Total | Total | Total | Total | Total | Total | Total | Total |  | Total | Rates | 19/20 | 20/21 | 21/22 | 22/23 | 23/24 | Total | time axis 2019-06-01 to 2024-04-01
# | STAFF NAME | QA ROLE (pulled from Roster tab) | [60 empty] | TOTAL
| DEL #1 - QA Monthly Status Report (OCAT) |  |  | 2019-08-01: Due; 2019-09-01: Due; 2019-10-01: Due; 2019-11-01: Due; 2019-12-01: Due; 2020-01-01: Due; 2020-02-01: Due; 2020-03-01: Due; 2020-04-01: Due; 2020-05-01: Due; 2020-06-01: Due; 2020-07-01: Due; 2020-08-01: Due; 2020-09-01: Due; 2020-10-01: Due; 2020-11-01: Due |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 21184 | 14808 | 0 | 0 | 0 | 35992 | subtotal
1 | Dan Dean | QA Project Manager | 154 | [59 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 154 | 0 | 0 | 0 | 0 | 0 | 0
2 | Timothy King | QA PMO Specialist | 114 | 2019-09-01: 12; 2019-10-01: 8; 2019-11-01: 16; 2019-12-01: 16; 2020-01-01: 16; 2020-02-01: 12; 2020-03-01: 12; 2020-04-01: 12; 2020-05-01: 12; 2020-06-01: 16; 2020-07-01: 16; 2020-08-01: 16; 2020-09-01: 16; 2020-10-01: 12; 2020-11-01: 12 | 204 |  | 0 | 132 | 72 | 0 | 0 | 0 | 0 | 0 | 0 |  | 204 |  | 12 | 168 | 24 | 0 | 0 | 0 | 0 | 0 | 0 |  | 204 | 114 | 13224 | 10032 | 0 | 0 | 0 | 23256
3 | TBD 1 |  |  | 2019-08-01: 62; 2019-09-01: 12; 2019-10-01: 48; 2019-11-01: 104; 2019-12-01: 120; 2020-01-01: 128; 2020-02-01: 72; 2020-03-01: 96; 2020-04-01: 148; 2020-05-01: 132; 2020-06-01: 140; 2020-07-01: 148; 2020-08-01: 148; 2020-09-01: 140; 2020-10-01: 140; 2020-11-01: 120 | 1758 |  | 0 | 1062 | 696 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1758 |  | 74 | 1424 | 260 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1758 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | TBD 2 |  |  | 2019-09-01: 30; 2019-10-01: 64; 2019-11-01: 72; 2019-12-01: 80; 2020-01-01: 44; 2020-02-01: 2; 2020-03-01: 2; 2020-04-01: 16; 2020-05-01: 36; 2020-06-01: 40; 2020-07-01: 40; 2020-08-01: 40; 2020-09-01: 40; 2020-10-01: 40; 2020-11-01: 40 | 586 |  | 0 | 386 | 200 | 0 | 0 | 0 | 0 | 0 | 0 |  | 586 |  | 30 | 476 | 80 | 0 | 0 | 0 | 0 | 0 | 0 |  | 586 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Wendy Battermann | QA Executive | 154 | 2019-08-01: 2; 2019-09-01: 2; 2019-10-01: 2; 2019-11-01: 2; 2019-12-01: 2; 2020-01-01: 2; 2020-02-01: 2; 2020-03-01: 2; 2020-04-01: 2; 2020-05-01: 2; 2020-06-01: 2; 2020-07-01: 2; 2020-08-01: 2; 2020-09-01: 2; 2020-10-01: 2; 2020-11-01: 2 | 32 |  | 0 | 22 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 |  | 4 | 24 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 | 154 | 3080 | 1848 | 0 | 0 | 0 | 4928
6 | Frank Ono | QA Executive | 154 | 2019-08-01: 2; 2019-09-01: 2; 2019-10-01: 2; 2019-11-01: 2; 2019-12-01: 2; 2020-01-01: 2; 2020-02-01: 2; 2020-03-01: 2; 2020-04-01: 2; 2020-05-01: 2; 2020-06-01: 2; 2020-07-01: 2; 2020-08-01: 2; 2020-09-01: 2; 2020-10-01: 2; 2020-11-01: 2 | 32 |  | 0 | 22 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 |  | 4 | 24 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 | 154 | 3080 | 1848 | 0 | 0 | 0 | 4928
7 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2019-08-01: 4; 2019-09-01: 4; 2019-10-01: 4; 2019-11-01: 4; 2019-12-01: 4; 2020-01-01: 4; 2020-02-01: 4; 2020-03-01: 4; 2020-04-01: 4; 2020-05-01: 4; 2020-06-01: 4; 2020-07-01: 4; 2020-08-01: 4; 2020-09-01: 4; 2020-10-01: 4; 2020-11-01: 4 | 64 |  | 0 | 44 | 20 | 0 | 0 | 0 | 0 | 0 | 0 |  | 64 |  | 8 | 48 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 64 | 45 | 1800 | 1080 | 0 | 0 | 0 | 2880
8 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #2 - Assessment of OCAT Project Control Document |  |  | 2019-08-01: Due |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 3224 | 0 | 0 | 0 | 0 | 3224 | subtotal
1 | Dan Dean | QA Project Manager | 154 | [59 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 154 | 0 | 0 | 0 | 0 | 0 | 0
2 | Timothy King | QA PMO Specialist | 114 | 2019-07-01: 8; 2019-08-01: 16 | 24 |  | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 24 |  | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 24 | 114 | 2736 | 0 | 0 | 0 | 0 | 2736
3 | TBD 1 | [61 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | TBD 2 |  |  | 2019-08-01: 8 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Wendy Battermann | QA Executive | 154 | 2019-08-01: 2 | 2 |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 154 | 308 | 0 | 0 | 0 | 0 | 308
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2019-08-01: 4 | 4 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | 45 | 180 | 0 | 0 | 0 | 0 | 180
7 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #3 - QA Assessment of OCAT Work Plan |  |  | 2019-07-01: Due |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 2312 | 0 | 0 | 0 | 0 | 2312 | subtotal
1 | Dan Dean | QA Project Manager | 154 | [59 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 154 | 0 | 0 | 0 | 0 | 0 | 0
2 | Timothy King | QA PMO Specialist | 114 | 2019-07-01: 16 | 16 |  | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16 |  | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16 | 114 | 1824 | 0 | 0 | 0 | 0 | 1824
3 | TBD 1 |  |  | 2019-07-01: 4 | 4 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | TBD 2 |  |  | 2019-07-01: 4 | 4 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Wendy Battermann | QA Executive | 154 | 2019-07-01: 2 | 2 |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 154 | 308 | 0 | 0 | 0 | 0 | 308
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2019-07-01: 4 | 4 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | 45 | 180 | 0 | 0 | 0 | 0 | 180
7 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | IFG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | IFG
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | IFG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | IFG
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | IFG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | IFG
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #4 - QA Assessment of OCAT RTM |  |  | 2019-08-01: Due |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 488 | 0 | 0 | 0 | 0 | 488 | subtotal
1 | Dan Dean | QA Project Manager | 154 | [59 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 154 | 0 | 0 | 0 | 0 | 0 | 0
2 | Timothy King | QA PMO Specialist | 114 | [59 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 114 | 0 | 0 | 0 | 0 | 0 | 0
3 | TBD 1 |  |  | 2019-08-01: 30 | 30 |  | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 30 |  | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | TBD 2 |  |  | 2019-08-01: 20 | 20 |  | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 20 |  | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Wendy Battermann | QA Executive | 154 | 2019-08-01: 2 | 2 |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 154 | 308 | 0 | 0 | 0 | 0 | 308
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2019-08-01: 4 | 4 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | 45 | 180 | 0 | 0 | 0 | 0 | 180
7 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #5 - QA Assessment of OCAT General Design Document |  |  | 2019-10-01: Due |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 2574 | 0 | 0 | 0 | 0 | 2574 | subtotal
1 | Dan Dean | QA Project Manager | 154 | [59 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 154 | 0 | 0 | 0 | 0 | 0 | 0
2 | Timothy King | QA PMO Specialist | 114 | 2019-10-01: 4 | 4 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | 114 | 456 | 0 | 0 | 0 | 0 | 456
3 | TBD 1 |  |  | 2019-08-01: 60; 2019-09-01: 40; 2019-10-01: 20 | 120 |  | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 120 |  | 100 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | TBD 2 |  |  | 2019-08-01: 20; 2019-09-01: 20; 2019-10-01: 20 | 60 |  | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 60 |  | 40 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Frank Ono | QA Executive | 154 | 2019-08-01: 4; 2019-09-01: 4; 2019-10-01: 4 | 12 |  | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 12 |  | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 12 | 154 | 1848 | 0 | 0 | 0 | 0 | 1848
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2019-08-01: 2; 2019-10-01: 4 | 6 |  | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 6 |  | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 6 | 45 | 270 | 0 | 0 | 0 | 0 | 270
7 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #6 - Technical Design Document |  |  | 2019-10-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 2048 | 0 | 0 | 0 | 0 | 2048 | subtotal
1 | Dan Dean | QA Project Manager | 154 | [59 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 154 | 0 | 0 | 0 | 0 | 0 | 0
2 | Timothy King | QA PMO Specialist | 114 | 2019-10-01: 4 | 4 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | 114 | 456 | 0 | 0 | 0 | 0 | 456
3 | TBD 1 |  |  | 2019-09-01: 60; 2019-10-01: 60 | 120 |  | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 120 |  | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | TBD 2 | [61 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Frank Ono | QA Executive | 154 | 2019-09-01: 4; 2019-10-01: 4 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 154 | 1232 | 0 | 0 | 0 | 0 | 1232
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2019-09-01: 4; 2019-10-01: 4 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 45 | 360 | 0 | 0 | 0 | 0 | 360
7 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | IFG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #7 - QA Assessment of OCAT Application SAWS Interfaces |  |  | 2020-04-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 5744 | 0 | 0 | 0 | 0 | 5744 | subtotal
1 | Dan Dean | QA Project Manager | 154 | [59 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 154 | 0 | 0 | 0 | 0 | 0 | 0
2 | Timothy King | QA PMO Specialist | 114 | 2020-04-01: 4 | 4 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | 114 | 456 | 0 | 0 | 0 | 0 | 456
3 | TBD 1 |  |  | 2019-09-01: 40; 2019-10-01: 40; 2019-11-01: 40; 2019-12-01: 40; 2020-01-01: 40; 2020-02-01: 40; 2020-03-01: 40; 2020-04-01: 20 | 300 |  | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 300 |  | 40 | 260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | TBD 2 | [61 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Frank Ono | QA Executive | 154 | 2019-09-01: 4; 2019-10-01: 4; 2019-11-01: 4; 2019-12-01: 4; 2020-01-01: 4; 2020-02-01: 4; 2020-03-01: 4; 2020-04-01: 4 | 32 |  | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 |  | 4 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 | 154 | 4928 | 0 | 0 | 0 | 0 | 4928
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2019-09-01: 4; 2020-04-01: 4 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 45 | 360 | 0 | 0 | 0 | 0 | 360
7 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | IFG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | IFG
8 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | IFG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | IFG
9 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | IFG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | IFG
10 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2021-10-01 to 2022-11-01
11 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #8 - QA Assessment of OCAT Master Test Plan |  |  | 2019-09-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 1432 | 0 | 0 | 0 | 0 | 1432 | subtotal
1 | Dan Dean | QA Project Manager | 154 | [59 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 154 | 0 | 0 | 0 | 0 | 0 | 0
2 | Timothy King | QA PMO Specialist | 114 | 2019-09-01: 4 | 4 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | 114 | 456 | 0 | 0 | 0 | 0 | 456
3 | TBD 1 |  |  | 2019-08-01: 8; 2019-09-01: 8 | 16 |  | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16 |  | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | TBD 2 |  |  | 2019-08-01: 24; 2019-09-01: 32 | 56 |  | 0 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 56 |  | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Wendy Battermann | QA Executive | 154 | 2019-08-01: 2; 2019-09-01: 2 | 4 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | IFG | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | 154 | 616 | 0 | 0 | 0 | 0 | 616 | IFG
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2019-08-01: 4; 2019-09-01: 4 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | IFG | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 45 | 360 | 0 | 0 | 0 | 0 | 360 | IFG
7 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #9 - QA Assessment of OCAT Training Plan |  |  | 2020-02-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 1432 | 0 | 0 | 0 | 0 | 1432 | subtotal
1 | Dan Dean | QA Project Manager | 154 | [59 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 154 | 0 | 0 | 0 | 0 | 0 | 0
2 | Timothy King | QA PMO Specialist | 114 | 2020-02-01: 4 | 4 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | 114 | 456 | 0 | 0 | 0 | 0 | 456
3 | TBD 1 | [61 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | TBD 2 |  |  | 2020-01-01: 40; 2020-02-01: 32 | 72 |  | 0 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 72 | IFG | 0 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | IFG
5 | Wendy Battermann | QA Executive | 154 | 2020-01-01: 2; 2020-02-01: 2 | 4 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | 154 | 616 | 0 | 0 | 0 | 0 | 616
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2020-01-01: 4; 2020-02-01: 4 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 45 | 360 | 0 | 0 | 0 | 0 | 360
7 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | IFG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | IFG
10 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #10 - QA Assessment of OCAT Training Materials |  |  | 2020-05-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 2048 | 0 | 0 | 0 | 0 | 2048 | subtotal
1 | Dan Dean | QA Project Manager | 154 | [59 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 154 | 0 | 0 | 0 | 0 | 0 | 0
2 | Timothy King | QA PMO Specialist | 114 | 2020-05-01: 4 | 4 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | 114 | 456 | 0 | 0 | 0 | 0 | 456
3 | TBD 1 | [61 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | TBD 2 |  |  | 2020-02-01: 20; 2020-03-01: 48; 2020-04-01: 40; 2020-05-01: 40 | 148 |  | 0 | 148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 148 | IFG | 0 | 148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | IG
5 | Wendy Battermann | QA Executive | 154 | 2020-02-01: 2; 2020-03-01: 2; 2020-04-01: 2; 2020-05-01: 2 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 154 | 1232 | 0 | 0 | 0 | 0 | 1232
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2020-02-01: 4; 2020-05-01: 4 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 45 | 360 | 0 | 0 | 0 | 0 | 360
7 |  |  |  | 2021-03-01: 8; 2021-04-01: 24; 2021-06-01: 8; 2021-07-01: 24; 2021-09-01: 8; 2021-10-01: 24; 2021-12-01: 8; 2022-01-01: 24; 2022-03-01: 8; 2022-04-01: 24; 2022-06-01: 8; 2022-07-01: 24; 2022-09-01: 8; 2022-10-01: 24; 2022-12-01: 8; 2023-01-01: 24; 2023-03-01: 8; 2023-04-01: 24 | 288 |  | 0 | 0 | 40 | 128 | 120 | 0 | 0 | 0 | 0 |  | 288 |  | 0 | 0 | 72 | 128 | 88 | 0 | 0 | 0 | 0 |  | 288 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 |  |  |  | 2021-03-01: 4; 2021-04-01: 4; 2021-06-01: 4; 2021-07-01: 4; 2021-09-01: 4; 2021-10-01: 4; 2021-12-01: 4; 2022-01-01: 4; 2022-03-01: 4; 2022-04-01: 4; 2022-06-01: 4; 2022-07-01: 4; 2022-09-01: 4; 2022-10-01: 4; 2022-12-01: 4; 2023-01-01: 4; 2023-03-01: 4; 2023-04-01: 4 | 72 |  | 0 | 0 | 12 | 32 | 28 | 0 | 0 | 0 | 0 |  | 72 |  | 0 | 0 | 20 | 32 | 20 | 0 | 0 | 0 | 0 |  | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 |  |  |  | 2021-04-01: 8; 2021-07-01: 8; 2021-10-01: 8; 2022-01-01: 8; 2022-04-01: 8; 2022-07-01: 8; 2022-10-01: 8; 2023-01-01: 8; 2023-04-01: 8 | 72 |  | 0 | 0 | 8 | 32 | 32 | 0 | 0 | 0 | 0 |  | 72 | IFG | 0 | 0 | 16 | 32 | 24 | 0 | 0 | 0 | 0 |  | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | IFG
10 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #11 - QA Assessment of OCAT System Documentation |  |  | 2020-03-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 1432 | 0 | 0 | 0 | 0 | 1432 | subtotal
1 | Dan Dean | QA Project Manager | 154 | [59 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 154 | 0 | 0 | 0 | 0 | 0 | 0
2 | Timothy King | QA PMO Specialist | 114 | 2020-03-01: 4 | 4 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | 114 | 456 | 0 | 0 | 0 | 0 | 456
3 | TBD 1 |  |  | 2020-02-01: 40; 2020-03-01: 40 | 80 |  | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 80 |  | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | TBD 2 |  |  | 2020-02-01: 40; 2020-03-01: 40 | 80 |  | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 80 |  | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Wendy Battermann | QA Executive | 154 | 2020-02-01: 2; 2020-03-01: 2 | 4 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | 154 | 616 | 0 | 0 | 0 | 0 | 616
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2020-02-01: 4; 2020-03-01: 4 | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 45 | 360 | 0 | 0 | 0 | 0 | 360
7 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #12 - QA Assessment of OCAT Final Acceptance |  |  | 2020-10-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 488 | 2176 | 0 | 0 | 0 | 2664 | subtotal
1 | Dan Dean | QA Project Manager | 154 | [59 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 154 | 0 | 0 | 0 | 0 | 0 | 0
2 | Timothy King | QA PMO Specialist | 114 | 2020-10-01: 4 | 4 |  | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | 114 | 0 | 456 | 0 | 0 | 0 | 456
3 | TBD 1 |  |  | 2020-05-01: 20; 2020-06-01: 20; 2020-07-01: 20; 2020-08-01: 20; 2020-09-01: 20; 2020-10-01: 20 | 120 |  | 0 | 40 | 80 | 0 | 0 | 0 | 0 | 0 | 0 |  | 120 |  | 0 | 100 | 20 | 0 | 0 | 0 | 0 | 0 | 0 |  | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | TBD 2 | [61 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Wendy Battermann | QA Executive | 154 | 2020-05-01: 2; 2020-06-01: 2; 2020-07-01: 2; 2020-08-01: 2; 2020-09-01: 2; 2020-10-01: 2 | 12 |  | 0 | 4 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 12 |  | 0 | 10 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  | 12 | 154 | 308 | 1540 | 0 | 0 | 0 | 1848
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2020-05-01: 4; 2020-10-01: 4 | 8 |  | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 45 | 180 | 180 | 0 | 0 | 0 | 360
7 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [62 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #13 - QA Assessment of OCAT M&O Transition Plan |  |  | 2020-11-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 1252 | 0 | 0 | 0 | 1252 | subtotal
1 | Dan Dean | QA Project Manager | 154 | [59 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 154 | 0 | 0 | 0 | 0 | 0 | 0
2 | Timothy King | QA PMO Specialist | 114 | 2020-11-01: 4 | 4 |  | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | 114 | 0 | 456 | 0 | 0 | 0 | 456
3 | TBD 1 |  |  | 2020-11-01: 40 | 40 |  | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 |  | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | TBD 2 |  |  | 2020-11-01: 40 | 40 |  | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 |  | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Frank Ono | QA Executive | 154 | 2020-11-01: 4 | 4 |  | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | 154 | 0 | 616 | 0 | 0 | 0 | 616
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2020-11-01: 4 | 4 |  | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | 45 | 0 | 180 | 0 | 0 | 0 | 180
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | IFG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | IFG
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | IFG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DEL #14 - QA M&O Monthly Status Report (OCAT) |  |  | 2020-12-01: Due; 2021-01-01: Due; 2021-02-01: Due; 2021-03-01: Due; 2021-04-01: Due; 2021-05-01: Due; 2021-06-01: Due; 2021-07-01: Due; 2021-08-01: Due; 2021-09-01: Due; 2021-10-01: Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 4236 | 3530 | 0 | 0 | 7766 | subtotal
1 | Dan Dean | QA Project Manager | 154 | [59 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 154 | 0 | 0 | 0 | 0 | 0 | 0
2 | Timothy King | QA PMO Specialist | 114 | [59 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 114 | 0 | 0 | 0 | 0 | 0 | 0
3 | TBD 1 |  |  | 2020-12-01: 80; 2021-01-01: 80; 2021-02-01: 80; 2021-03-01: 80; 2021-04-01: 80; 2021-05-01: 80; 2021-06-01: 80; 2021-07-01: 80; 2021-08-01: 80; 2021-09-01: 80; 2021-10-01: 80 | 880 |  | 0 | 0 | 560 | 320 | 0 | 0 | 0 | 0 | 0 |  | 880 |  | 0 | 0 | 800 | 80 | 0 | 0 | 0 | 0 | 0 |  | 880 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | TBD 2 | [61 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Wendy Battermann | QA Executive | 154 | 2020-12-01: 2; 2021-01-01: 2; 2021-02-01: 2; 2021-03-01: 2; 2021-04-01: 2; 2021-05-01: 2; 2021-06-01: 2; 2021-07-01: 2; 2021-08-01: 2; 2021-09-01: 2; 2021-10-01: 2 | 22 |  | 0 | 0 | 14 | 8 | 0 | 0 | 0 | 0 | 0 |  | 22 |  | 0 | 0 | 20 | 2 | 0 | 0 | 0 | 0 | 0 |  | 22 | 154 | 0 | 1848 | 1540 | 0 | 0 | 3388
6 | Frank Ono | QA Executive | 154 | 2020-12-01: 2; 2021-01-01: 2; 2021-02-01: 2; 2021-03-01: 2; 2021-04-01: 2; 2021-05-01: 2; 2021-06-01: 2; 2021-07-01: 2; 2021-08-01: 2; 2021-09-01: 2; 2021-10-01: 2 | 22 |  | 0 | 0 | 14 | 8 | 0 | 0 | 0 | 0 | 0 |  | 22 |  | 0 | 0 | 20 | 2 | 0 | 0 | 0 | 0 | 0 |  | 22 | 154 | 0 | 1848 | 1540 | 0 | 0 | 3388
7 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 2020-12-01: 2; 2021-01-01: 2; 2021-02-01: 2; 2021-03-01: 2; 2021-04-01: 2; 2021-05-01: 2; 2021-06-01: 2; 2021-07-01: 2; 2021-08-01: 2; 2021-09-01: 2; 2021-10-01: 2 | 22 |  | 0 | 0 | 14 | 8 | 0 | 0 | 0 | 0 | 0 |  | 22 |  | 0 | 0 | 20 | 2 | 0 | 0 | 0 | 0 | 0 |  | 22 | 45 | 0 | 540 | 450 | 0 | 0 | 990
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | IFG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | IFG
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | subtotal
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | IFG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | IFG
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | IFG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | IFG
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | subtotal
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | subtotal
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | IFG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | IFG
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | IFG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | subtotal
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | I
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | IFG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | IFG
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | IFG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | subtotal
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | IFG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | IFG
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | IFG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | subtotal
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | IFG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[63 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 38 | 280 | 292 | 296 | 244 | 268 | 286 | 292 | 302 | 258 | 264 | 226 | 234 | 234 | 226 | 230 | 272 | 86 | 86 | 86 | 98 | 122 | 86 | 98 | 122 | 86 | 98 | 122 | 0 | 12 | 36 | 0 | 12 | 36 | 0 | 12 | 36 | 0 | 12 | 36 | 0 | 12 | 36 | 0 | 12 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5620 |  | 0 | 3046 | 1858 | 536 | 180 | 0 | 0 | 0 | 0 |  | 5620 |  | 610 | 3130 | 1470 | 278 | 132 | 0 | 0 | 0 | 0 |  | 5620
Summary by Staff Name
1 | Dan Dean | QA Project Manager | 154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
8 | Timothy King | QA PMO Specialist | 114 | 0 | 24 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 280 | 280 | 0 | 200 | 80 | 0 | 0 | 0 | 0 | 0 | 0 |  | 280 |  | 56 | 192 | 32 | 0 | 0 | 0 | 0 | 0 | 0 |  | 280
9 | TBD 1 | QA Technical Lead (OCAT) |  | 0 | 4 | 160 | 160 | 168 | 144 | 160 | 168 | 152 | 176 | 168 | 152 | 160 | 168 | 168 | 160 | 160 | 160 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3468 | 3468 | 0 | 1772 | 1376 | 320 | 0 | 0 | 0 | 0 | 0 |  | 3468 |  | 324 | 1944 | 1120 | 80 | 0 | 0 | 0 | 0 | 0 |  | 3468
10 | TBD 2 | QA Specialist (OCAT) |  | 0 | 4 | 72 | 82 | 84 | 72 | 80 | 84 | 94 | 90 | 56 | 76 | 40 | 40 | 40 | 40 | 40 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1074 | 1074 | 0 | 834 | 240 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1074 |  | 158 | 796 | 120 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1074
11 | Wendy Battermann | QA Executive | 154 | 0 | 2 | 8 | 4 | 2 | 2 | 2 | 4 | 8 | 6 | 4 | 6 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | 92 | 0 | 52 | 32 | 8 | 0 | 0 | 0 | 0 | 0 |  | 92 |  | 14 | 50 | 26 | 2 | 0 | 0 | 0 | 0 | 0 |  | 92
12 | Frank Ono | QA Executive | 154 | 0 | 0 | 6 | 14 | 14 | 6 | 6 | 6 | 6 | 6 | 6 | 2 | 2 | 2 | 2 | 2 | 2 | 6 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 110 | 0 | 74 | 28 | 8 | 0 | 0 | 0 | 0 | 0 |  | 110 |  | 20 | 60 | 28 | 2 | 0 | 0 | 0 | 0 | 0 |  | 110
22 | Julie Hereth | QA Sr. Administrative Assistant |  | 0 | 4 | 18 | 16 | 12 | 4 | 4 | 8 | 16 | 8 | 8 | 12 | 4 | 4 | 4 | 4 | 8 | 8 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 164 |  | 0 | 114 | 42 | 8 | 0 | 0 | 0 | 0 | 0 |  | 164 | IFG | 38 | 88 | 36 | 2 | 0 | 0 | 0 | 0 | 0 |  | 164 | [7 empty] | IFG
23 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
24 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
25 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
26 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
27 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
28 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
29 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| Total |  |  | 0 | 38 | 280 | 292 | 296 | 244 | 268 | 286 | 292 | 302 | 258 | 264 | 226 | 234 | 234 | 226 | 230 | 272 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5188 |  | 0 | 3046 | 1798 | 344 | 0 | 0 | 0 | 0 | 0 | 0 | 5188 |  | 610 | 3130 | 1362 | 86 | 0 | 0 | 0 | 0 | 0 |  | 5188
Summary by QA Role
1 |  | QA Project Manager |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
2 |  | QA PMO Specialist |  | 0 | 24 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 280 | 0 | 0 | 200 | 80 | 0 | 0 | 0 | 0 | 0 | 0 |  | 280 |  | 56 | 192 | 32 | 0 | 0 | 0 | 0 | 0 | 0 |  | 280
3 |  | QA Technical Lead (OCAT) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
4 |  | QA Specialist (OCAT) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
5 |  | QA Executive |  | 0 | 2 | 14 | 18 | 16 | 8 | 8 | 10 | 14 | 12 | 10 | 8 | 6 | 6 | 6 | 6 | 6 | 8 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 202 | 0 | 0 | 126 | 60 | 16 | 0 | 0 | 0 | 0 | 0 |  | 202 |  | 34 | 110 | 54 | 4 | 0 | 0 | 0 | 0 | 0 |  | 202
6 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
7 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
8 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
9 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
10 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
11 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
12 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
13 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
14 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
15 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
16 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
17 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| Total |  |  | 0 | 26 | 30 | 34 | 32 | 24 | 24 | 26 | 30 | 28 | 26 | 24 | 22 | 22 | 22 | 22 | 22 | 24 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 482 | 0 | 0 | 326 | 140 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 482 |  | 90 | 302 | 86 | 4 | 0 | 0 | 0 | 0 | 0 | 988 | 482
0
#DIV/0!
IFG Work Percentage Calculations
[65 empty] | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | IFG
[65 empty] | SFY | SFY | SFY | SFY | SFY | SFY | Involved
[65 empty] | 18/19 | 19/20 | 20/21 | 21/22 | 22/23 | 23/24 | Deliverable
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #3 - QA Monthly Status Report (Monthly)
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #6 - QA Testing Plan
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #7 - QA Test Monthly Report (Monthly)
[65 empty] | 0% | 13.64% | 0% | 0% | 0% | 0% | DEL #8 - UAT Weekly Report (Weekly)
[65 empty] | 0% | 81.82% | 0% | 0% | 0% | 0% | DEL #9 - QA Security Review Plan
[65 empty] | 0% | 88.1% | 13.33% | 16.67% | 17.78% | 0% | DEL #10 - Quarterly QA Security Report (Quarterly)
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #13 - Assessment of DD&I Vendor CalSAWS General Design
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #14 - Assessment of DD&I Vendor CalACES Master Conversion Plan
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #15 - Assessment of DD&I Vendor Application Development Preparation and Installation Plan
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #17 - Assessment of DD&I Vendor CalSAWS Business Architecture Design
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #18 - Assessment of DD&I Vendor CalSAWS General Design
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #19 - Assessment of DD&I Vendor CalSAWS General Design
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #20 - Assessment of DD&I Vendor C-IV Master Training Plan
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #21 - Assessment of DD&I Vendor CalWIN/CalSAWS Master Conversion Plan
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #23 - Assessment of DD&I Vendor CalSAWS General Design (Page/Report/Correspondence Changes per Requirement)
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #24 - Assessment of DD&I Vendor C-IV Deployment Readiness Plan
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #26 - Assessment of DD&I Vendor CalSAWS General Design
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #27 - Assessment of DD&I Vendor CalWIN/CalSAWS Master Conversion Plan - Update 1
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #28 - Assessment of DD&I Vendor CalSAWS General Design
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #31 - Assessment of DD&I Vendor CalSAWS General Design
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #33 - Assessment of DD&I Vendor C-IV Change Management Plan
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #35 - Assessment of DD&I Vendor CalSAWS General Design
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #38 - Assessment of DD&I Vendor CalSAWS UAT Support Plan
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #40 - Assessment of DD&I Vendor CalSAWS (C-IV) UAT Readiness Report/Milestone
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #42 - Assessment of DD&I Vendor CalSAWS (CalWIN) UAT Readiness Report/Milestone
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #46 - Assessment of DD&I Vendor CalACES Migration Final Acceptance Certification
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #47 - Assessment of DD&I Vendor CalSAWS Deployment Complete Milestone/Report - CalWIN Wave 1
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #49 - Assessment of DD&I Vendor CalSAWS Deployment Complete Milestone/Report - CalWIN Wave 2
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #50 - Assessment of DD&I Vendor CalSAWS Deployment Complete Milestone/Report - CalWIN Wave 3
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #51 - Assessment of DD&I Vendor CalSAWS Deployment Complete Milestone/Report - CalWIN Wave 4
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #52 - Assessment of DD&I Vendor CalSAWS Deployment Complete Milestone/Report - CalWIN Wave 5
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #53 - Assessment of DD&I Vendor CalSAWS Deployment Complete Milestone/Report - CalWIN Wave 6
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #60 - Assessment of CalWIN Implementation Support Vendor CalWIN Master Training Plan
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #61 - Assessment of CalWIN Implementation Support Vendor CalWIN Deployment Readiness Plan
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #62 - Assessment of CalWIN Implementation Support Vendor CalWIN Change Management Plan
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #63 - Assessment of CalWIN Implementation Support Vendor CalWIN ILT Training Material
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #64 - Assessment of CalWIN Implementation Support Vendor CalWIN WBT Training Material
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #65 - QA Status Report (Monthly)
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #67 - QA M&O Monthly Test Report (Monthly)
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #68 - Quarterly QA Security Report (Quarterly)
[65 empty] | 0% | 0% | 0% | 0% | 0% | 0% | DEL #69 - Monthly SLA & Performance Review Report (Monthly)
[65 empty] | 0 | 114 | 42 | 8 | 0 | 0
[65 empty] | #DIV/0! | 34.97% | 30% | 50% | #DIV/0! | #DIV/0!

## Sch 4 - Deliverables (OCAT) old (hidden)
Schedule 4 - Deliverable Detail (OCAT) |  |  |  |  | <This entire tab should not be manually updated>
# | Deliverable | Position | Hourly Rate | Total Hours | Cost
DEL #1 - QA Monthly Status Report (OCAT)
1 | Dan Dean | QA Project Manager | 154 | 0 | 0
2 | Timothy King | QA PMO Specialist | 114 | 204 | 23256
3 | TBD 1 |  |  | 1758 | 0
4 | TBD 2 |  |  | 586 | 0
5 | Wendy Battermann | QA Executive | 154 | 32 | 4928
6 | Frank Ono | QA Executive | 154 | 32 | 4928
7 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 64 | 2880
8 |  |  |  | 0 | 0
9 |  |  |  | 0 | 0 | 30
10 |  |  |  | 0 | 0
11 |  |  |  | 0 | 0
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 2676 | 35992
DEL #2 - Assessment of OCAT Project Control Document
1 | Dan Dean | QA Project Manager | 154 | 0 | 0
2 | Timothy King | QA PMO Specialist | 114 | 24 | 2736
3 | TBD 1 |  |  | 0 | 0
4 | TBD 2 |  |  | 8 | 0
5 | Wendy Battermann | QA Executive | 154 | 2 | 308
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 4 | 180
7 |  |  |  | 0 | 0
8 |  |  |  | 0 | 0
9 |  |  |  | 0 | 0
10 |  |  |  | 0 | 0
11 |  |  |  | 0 | 0
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 38 | 3224
DEL #3 - QA Assessment of OCAT Work Plan
1 | Dan Dean | QA Project Manager | 154 | 0 | 0
2 | Timothy King | QA PMO Specialist | 114 | 16 | 1824
3 | TBD 1 |  |  | 4 | 0
4 | TBD 2 |  |  | 4
5 | Wendy Battermann | QA Executive | 154 | 2 | 308
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 4 | 180
7 |  |  |  | 0 | 0
8 |  |  |  | 0 | 0
9 |  |  |  | 0 | 0
10 |  |  |  | 0 | 0
11 |  |  |  | 0 | 0
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 30 | 2312
DEL #4 - QA Assessment of OCAT RTM
1 | Dan Dean | QA Project Manager | 154 | 0 | 0
2 | Timothy King | QA PMO Specialist | 114 | 0 | 0
3 | TBD 1 |  |  | 30 | 0
4 | TBD 2 |  |  | 20 | 0
5 | Wendy Battermann | QA Executive | 154 | 2 | 308
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 4 | 180
7 |  |  |  | 0 | 0
8 |  |  |  | 0 | 0
9 |  |  |  | 0 | 0
10 |  |  |  | 0 | 0
11 |  |  |  | 0 | 0
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 56 | 488
DEL #5 - QA Assessment of OCAT General Design Document
1 | Dan Dean | QA Project Manager | 154 | 0 | 0
2 | Timothy King | QA PMO Specialist | 114 | 4 | 456
3 | TBD 1 |  |  | 120 | 0
4 | TBD 2 |  |  | 60 | 0
5 | Frank Ono | QA Executive | 154 | 12 | 1848
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 6 | 270
7 |  |  |  | 0 | 0
8 |  |  |  | 0 | 0
9 |  |  |  | 0 | 0
10 |  |  |  | 0 | 0
11 |  |  |  | 0 | 0
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 202 | 2574
DEL #6 - Technical Design Document
1 | Dan Dean | QA Project Manager | 154 | 0 | 0
2 | Timothy King | QA PMO Specialist | 114 | 4 | 456
3 | TBD 1 |  |  | 120 | 0
4 | TBD 2 |  |  | 0 | 0
5 | Frank Ono | QA Executive | 154 | 8 | 1232
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 8 | 360
7 |  |  |  | 0 | 0
8 |  |  |  | 0 | 0
9 |  |  |  | 0 | 0
10 |  |  |  | 0 | 0
11 |  |  |  | 0 | 0
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 140 | 2048
DEL #7 - QA Assessment of OCAT Application SAWS Interfaces
1 | Dan Dean | QA Project Manager | 154 | 0 | 0
2 | Timothy King | QA PMO Specialist | 114 | 4 | 456
3 | TBD 1 |  |  | 300 | 0
4 | TBD 2 |  |  | 0 | 0
5 | Frank Ono | QA Executive | 154 | 32 | 4928
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 8 | 360
7 |  |  |  | 0 | 0
8 |  |  |  | 0 | 0
9 |  |  |  | 0 | 0
10 |  |  |  | 0 | 0
11 |  |  |  | 0 | 0
12 |  |  |  | 0 | 0
13 |  | 0 |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 344 | 5744
DEL #8 - QA Assessment of OCAT Master Test Plan
1 | Dan Dean | QA Project Manager | 154 | 0 | 0
2 | Timothy King | QA PMO Specialist | 114 | 4 | 456
3 | TBD 1 |  |  | 16 | 0
4 | TBD 2 |  |  | 56 | 0
5 | Wendy Battermann | QA Executive | 154 | 4 | 616
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 8 | 360
7 |  |  |  | 0 | 0
8 |  |  |  | 0 | 0
9 |  |  |  | 0 | 0
10 |  | 0 |  | 0 | 0
11 |  |  |  | 0 | 0
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 88 | 1432
DEL #9 - QA Assessment of OCAT Training Plan
1 | Dan Dean | QA Project Manager | 154 | 0 | 0
2 | Timothy King | QA PMO Specialist | 114 | 4 | 456
3 | TBD 1 |  |  | 0 | 0
4 | TBD 2 |  |  | 72 | 0
5 | Wendy Battermann | QA Executive | 154 | 4 | 616
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 8 | 360
7 |  |  |  | 0 | 0
8 |  |  |  | 0 | 0
9 |  |  |  | 0 | 0
10 |  |  |  | 0 | 0
11 |  |  |  | 0 | 0
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 88 | 1432
DEL #10 - QA Assessment of OCAT Training Materials
1 | Dan Dean | QA Project Manager | 154 | 0 | 0
2 | Timothy King | QA PMO Specialist | 114 | 4 | 456
3 | TBD 1 |  |  | 0 | 0
4 | TBD 2 |  |  | 148 | 0
5 | Wendy Battermann | QA Executive | 154 | 8 | 1232
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 8 | 360
7 |  |  |  | 288 | 0
8 |  |  |  | 72 | 0
9 |  |  |  | 72 | 0
10 |  |  |  | 0 | 0
11 |  |  |  | 0 | 0
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 600 | 2048
DEL #11 - QA Assessment of OCAT System Documentation
1 | Dan Dean | QA Project Manager | 154 | 0 | 0
2 | Timothy King | QA PMO Specialist | 114 | 4 | 456
3 | TBD 1 |  |  | 80 | 0
4 | TBD 2 |  |  | 80 | 0
5 | Wendy Battermann | QA Executive | 154 | 4 | 616
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 8 | 360
7 |  |  |  | 0 | 0
8 |  |  |  | 0 | 0
9 |  |  |  | 0 | 0
10 |  |  |  | 0 | 0
11 |  |  |  | 0 | 0
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 176 | 1432
DEL #12 - QA Assessment of OCAT Final Acceptance
1 | Dan Dean | QA Project Manager | 154 | 0 | 0
2 | Timothy King | QA PMO Specialist | 114 | 4 | 456
3 | TBD 1 |  |  | 120 | 0
4 | TBD 2 |  |  | 0 | 0
5 | Wendy Battermann | QA Executive | 154 | 12 | 1848
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 8 | 360
7 |  |  |  | 0 | 0
8 |  |  |  | 0 | 0
9 |  |  |  | 0 | 0
10 |  |  |  | 0 | 0
11 |  |  |  | 0 | 0
12 |  |  |  | 0 | 0
13 |  |  |  | 0 | 0
14 |  |  |  | 0 | 0
15 |  |  |  | 0 | 0
16 |  |  |  | 0 | 0
17 |  |  |  | 0 | 0
18 |  |  |  | 0 | 0
19 |  |  |  | 0 | 0
20 |  |  |  | 0 | 0
| Total |  |  | 144 | 2664
DEL #13 - QA Assessment of OCAT M&O Transition Plan
1 | Dan Dean | QA Project Manager | 154 | 0 | 0
2 | Timothy King | QA PMO Specialist | 114 | 4 | 456
3 | TBD 1 |  |  | 40 | 0
4 | TBD 2 |  |  | 40 | 0
5 | Frank Ono | QA Executive | 154 | 4 | 616
6 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 4 | 180
7 |  | 0 |  | 0 | 0
8 |  | 0 |  | 0 | 0
9 |  | 0 |  | 0 | 0
10 |  | 0 |  | 0 | 0
11 |  | 0 |  | 0 | 0
12 |  | 0 |  | 0 | 0
13 |  | 0 |  | 0 | 0
14 |  | 0 |  | 0 | 0
15 |  | 0 |  | 0 | 0
16 |  | 0 |  | 0 | 0
17 |  | 0 |  | 0 | 0
18 |  | 0 |  | 0 | 0
19 |  | 0 |  | 0 | 0
20 |  | 0 |  | 0 | 0
| Total |  |  | 92 | 1252
DEL #14 - QA M&O Monthly Status Report (OCAT)
1 | Dan Dean | QA Project Manager | 154 | 0 | 0
2 | Timothy King | QA PMO Specialist | 114 | 0 | 0
3 | TBD 1 |  |  | 880 | 0
4 | TBD 2 |  |  | 0 | 0
5 | Wendy Battermann | QA Executive | 154 | 22 | 3388
6 | Frank Ono | QA Executive | 154 | 22 | 3388
7 | Julie Hereth | QA Sr. Administrative Assistant | 45 | 22 | 990
8 |  | 0 |  | 0 | 0
9 |  | 0 |  | 0 | 0
10 |  | 0 |  | 0 | 0
11 |  | 0 |  | 0 | 0
12 |  | 0 |  | 0 | 0
13 |  | 0 |  | 0 | 0
14 |  | 0 |  | 0 | 0
15 |  | 0 |  | 0 | 0
16 |  | 0 |  | 0 | 0
17 |  | 0 |  | 0 | 0
18 |  | 0 |  | 0 | 0
19 |  | 0 |  | 0 | 0
20 |  | 0 |  | 0 | 0
| Total |  |  | 946 | 7766
0
1 |  | 0 |  | 0 | #VALUE!
2 |  | 0 |  | 0 | 0
3 |  | 0 |  | 0 | 0
4 |  | 0 |  | 0 | 0
5 |  | 0 |  | 0 | 0
6 |  | 0 |  | 0 | 0
7 |  | 0 |  | 0 | 0
8 |  | 0 |  | 0 | 0
9 |  | 0 |  | 0 | 0
10 |  | 0 |  | 0 | 0
11 |  | 0 |  | 0 | 0
12 |  | 0 |  | 0 | 0
13 |  | 0 |  | 0 | 0
14 |  | 0 |  | 0 | 0
15 |  | 0 |  | 0 | 0
16 |  | 0 |  | 0 | 0
17 |  | 0 |  | 0 | 0
18 |  | 0 |  | 0 | 0
19 |  | 0 |  | 0 | 0
20 |  | 0 |  | 0 | 0
| Total |  |  | 0 | #VALUE!
0
1 |  | 0 |  | 0 | #VALUE!
2 |  | 0 |  | 0 | 0
3 |  | 0 |  | 0 | 0
4 |  | 0 |  | 0 | 0
5 |  | 0 |  | 0 | 0
6 |  | 0 |  | 0 | 0
7 |  | 0 |  | 0 | 0
8 |  | 0 |  | 0 | 0
9 |  | 0 |  | 0 | 0
10 |  | 0 |  | 0 | 0
11 |  | 0 |  | 0 | 0
12 |  | 0 |  | 0 | 0
13 |  | 0 |  | 0 | 0
14 |  | 0 |  | 0 | 0
15 |  | 0 |  | 0 | 0
16 |  | 0 |  | 0 | 0
17 |  | 0 |  | 0 | 0
18 |  | 0 |  | 0 | 0
19 |  | 0 |  | 0 | 0
20 |  | 0 |  | 0 | 0
| Total |  |  | 0 | #VALUE!
0
1 |  | 0 |  | 0 | #VALUE!
2 |  | 0 |  | 0 | 0
3 |  | 0 |  | 0 | 0
4 |  | 0 |  | 0 | 0
5 |  | 0 |  | 0 | 0
6 |  | 0 |  | 0 | 0
7 |  | 0 |  | 0 | 0
8 |  | 0 |  | 0 | 0
9 |  | 0 |  | 0 | 0
10 |  | 0 |  | 0 | 0
11 |  | 0 |  | 0 | 0
12 |  | 0 |  | 0 | 0
13 |  | 0 |  | 0 | 0
14 |  | 0 |  | 0 | 0
15 |  | 0 |  | 0 | 0
16 |  | 0 |  | 0 | 0
17 |  | 0 |  | 0 | 0
18 |  | 0 |  | 0 | 0
19 |  | 0 |  | 0 | 0
20 |  | 0 |  | 0 | 0
| Total |  |  | 0 | #VALUE!
0
1 |  | 0 |  | 0 | #VALUE!
2 |  | 0 |  | 0 | 0
3 |  | 0 |  | 0 | 0
4 |  | 0 |  | 0 | 0
5 |  | 0 |  | 0 | 0
6 |  | 0 |  | 0 | 0
7 |  | 0 |  | 0 | 0
8 |  | 0 |  | 0 | 0
9 |  | 0 |  | 0 | 0
10 |  | 0 |  | 0 | 0
11 |  | 0 |  | 0 | 0
12 |  | 0 |  | 0 | 0
13 |  | 0 |  | 0 | 0
14 |  | 0 |  | 0 | 0
15 |  | 0 |  | 0 | 0
16 |  | 0 |  | 0 | 0
17 |  | 0 |  | 0 | 0
18 |  | 0 |  | 0 | 0
19 |  | 0 |  | 0 | 0
20 |  | 0 |  | 0 | 0
| Total |  |  | 0 | #VALUE!
0
1 |  | 0 |  | 0 | #VALUE!
2 |  | 0 |  | 0 | 0
3 |  | 0 |  | 0 | 0
4 |  | 0 |  | 0 | 0
5 |  | 0 |  | 0 | 0
6 |  | 0 |  | 0 | 0
7 |  | 0 |  | 0 | 0
8 |  | 0 |  | 0 | 0
9 |  | 0 |  | 0 | 0
10 |  | 0 |  | 0 | 0
11 |  | 0 |  | 0 | 0
12 |  | 0 |  | 0 | 0
13 |  | 0 |  | 0 | 0
14 |  | 0 |  | 0 | 0
15 |  | 0 |  | 0 | 0
16 |  | 0 |  | 0 | 0
17 |  | 0 |  | 0 | 0
18 |  | 0 |  | 0 | 0
19 |  | 0 |  | 0 | 0
20 |  | 0 |  | 0 | 0
| Total |  |  | 0 | #VALUE!
0
1 |  | 0 |  | 0 | #VALUE!
2 |  | 0 |  | 0 | 0
3 |  | 0 |  | 0 | 0
4 |  | 0 |  | 0 | 0
5 |  | 0 |  | 0 | 0
6 |  | 0 |  | 0 | 0
7 |  | 0 |  | 0 | 0
8 |  | 0 |  | 0 | 0
9 |  | 0 |  | 0 | 0
10 |  | 0 |  | 0 | 0
11 |  | 0 |  | 0 | 0
12 |  | 0 |  | 0 | 0
13 |  | 0 |  | 0 | 0
14 |  | 0 |  | 0 | 0
15 |  | 0 |  | 0 | 0
16 | Julie Hereth | 0 |  | 0 | 0
17 |  | 0 |  | 0 | 0
18 |  | 0 |  | 0 | 0
19 |  | 0 |  | 0 | 0
20 |  | 0 |  | 0 | 0
| Total |  |  | 0 | #VALUE!
|  |  | OCAT DD&I Total | 4850 | 64074
|  |  | OCAT M&O Total | 946 | 7766
|  |  | OCAT Total | 5620 | 71840

## Cost Assumptions
# | Cost Assumptions
1 | Started costs for Deliverables #16 and #17 in June 2019 (instead of the published May 2019) based on projected contract start date.
2 | Assumed 10% travel for QA PMO Lead and QA PMO Specialist between North and South locations.
3 | Assumed 35%-50% travel for QA Testing Manager, QA UAT Lead, and QA Independent Tester/UAT Leaders between North and South locations.
4 | Assumed 20% travel for QA Functional Manager and QA Business Analyst/Tester between North and South locations.
5 | Assumed 50% travel for QA Project Manager, QA Technical Manager, QA Technical Leads, QA Conversion Lead, QA Implementation Manager, and QA Implementation Leads
6 | Formula Update - Sch 5 - Summary - To calculate invoice month for recurring deliverables on Sch 5 - Summary, added formulas to columns CL through CR on Sch 3 - QA Staff Loading schedule (hidden).
7 | Formula Update - Sch 5 - Summary - For non-recurring deliverable payments, added formulas and date row (hidden row 80) on Sch 5 - Summary schedule to calculate SFY totals based on invoice month and linked recurring cost calculations from Sch 3 - QA Staff Loading.
8 | Formula Update - Corrected Total Costs by SFY formulas on Sch 5 - Summary for the DD&I and M&O.
9 | Formula Update - Corrected SFY and FFY calculations in hidden columns on Sch 3 - Staff Loading so that all rows were not included in summary totals to support the additional calculation of subcontractor percentages by SFY. Added subcontractor percentage calculations in BN1521-BX1769 (hidden).
10 | BAFO - Removed one QA Independent Tester/UAT Leader.
11 | BAFO - Reduced rates across team by $1/hr.
12 | Contract Negotiations - Shifted the start of all project activities to July 1, 2019 and adjusted the time and due dates of initial deliverables appropriately (i.e., continuing to allow for certain designated deliverables to be reviewed within 45 days of contract start).
13 | Contract Negotiations - Reduced the QA Implementation Team to two team members through April 2020 to support the initial C-IV Implementation effort and increased the QA Implementation Team to the full three team members beginning May 2020 to support the remainder of the C-IV Implementation and the whole of the CalWIN Implementation effort.
14 | Contact Negotiations - Reduced hours and adjusted start dates for some non-key staff while providing sufficient time for them to assimilate to the project and complete assigned deliverables.
15 | Contract Negotiations - Reduced project administrative costs by decreasing the hourly rate and overall hours while still enabling appropriate coverage for the team.