## Slide 1: November 15, 2019
JPA Board of Directors Meeting

## Slide 2: Agenda
Call Meeting to Order
Public Opportunity to speak on items NOT on the Agenda. Public comments are limited to no more than three minutes per speaker, except that a speaker using a translator shall be allowed up to six minutes.
Note: The public may also speak on any Item ON the Agenda by waiting until that item is read, then requesting recognition from the Chair to speak.
Confirmation of Quorum and Agenda Review.

## Slide 3
Action Items

## Slide 4: Action Items
Approval of the Minutes and review of Action Items of the September 13, 2019 CalSAWS JPA Board of Directors meeting.
Approval of the Accenture C-IV Amendment 105 package, which includes requests for:
Approval of C-IV Accenture Change Order CO-113 Online CalWORKs Appraisal Tool (“OCAT”)
Approval of County Purchase
Approval of C-IV Accenture Amendment 105 (References Change Order CO-114 and County Purchases) and updates to Exhibit A.

## Slide 5: Action Items
Approval of Accenture LRS Base Agreement Amendment 17, which includes:
Updates to the Maximum Contract Sum
Updates to Exhibit C for OCAT
Approval of C-IV First Data Contract Amendment No. 66 package, contingent upon Federal approval. The Amendment No. 66 package includes requests for:
Approval of C-IV First Data Change Order CO-021 – First Data Government Solutions Agreement Extension, Revision 2
Approval of C-IV First Data Change Order CO-016 – California Healthcare Eligibility, Enrollment and Retention System (“CalHEERS”), Revision 12
Approval of C-IV First Data Change Order CO-018 – Central Contact Center Platform (“CCP”) Covered California (“CA”) Expansion, Revision 2
Approval of C-IV First Data Change Order CO-032 – SB 1341, Revision 4
Approval of C-IV First Amendment 66 (references Consortium Name Change, Change Order CO-021, Change Order CO-016, Change Order CO-018, and Change Order CO-032) and Updates to Exhibit A

## Slide 6: Action Items
Approval of LRS First Data Contract Amendment No. 2 package, contingent upon Federal approval. The Amendment No. 2 package includes:
Consortium Name Change
Updates to the Agreement – Definitions, Term, and Scope with addition of the “QA Further Extended Term”
Updates to Exhibit A – Addition of “QA Further Extended Term” including extension of QA Management Services and addition of Augmentation Staff to provide Senior Business Analyst/Tester services
Updates to Exhibit B Schedule of Payments

## Slide 7: Action Items
Approval of Group Sales Agreement between the CalSAWS Consortium and Interstate Management Company, LLC (“Operator”), as agent for DiamondRock San Diego Tenant, LLC (“Owner”), dba Westin San Diego, for the CalSAWS Consortium Annual Conference June 24 – 26, 2020, and delegation of authority to the CalSAWAS Executive Director to sign catering and A/V agreements in an amount not to exceed $55,000.
Approval of RGS Amendment 29, which includes
Additional Pay Rate for Existing Position
Updated Administrative and Benefit Costs, Effective January 2020
Revised Terms and Conditions for clarity

## Slide 8: Background
The Imaging Functional Design Sessions were executed June through July 2019 to further define the scope of requirements for the Design and Development phase of the CalSAWS Migration Project. Key Accomplishments:
  Provided a forum for the counties to assist in the development of the solution
    Team visited 5 CalWIN Counties and Los Angeles County.
    Held four-day Session for each CalSAWS Region open to all counties.
    Total of 117 county experts from 42 different counties participated in sessions.
  Clarified system actions needed
  Discovered critical business processes
  Confirmed design objectives for application development
  Established context and validated requirements
  Received agreement and confirmation from all CalSAWS Regions
Consortium provided recommendation for the CalSAWS 58 County Imaging Solution is Hyland hosted in AWS Cloud
  Recommendation based on: County Input, Available Capabilities, Risk, Cost, Timeline
August 2019 JPA
Notes: Remove

## Slide 9: Updates to Imaging Discussions
Round 1 (presented at August JPA)-
  Compared two options: 1)Hyland to 2) Kofax/Documentum
    Discussed 5 year pricing
    Risk and Timeline were additional considerations- AWS credentials
    Both solutions were deemed to meet requirements from Functional Design
  Consortium Recommended Hyland
Round 2 (September/October)- 3 options assessed with Kofax and Documentum no longer combined
  Hyland
  Kofax/CloudDocs
  OpenText (Captiva/Documentum)
Results:
  Met with Vendors
  Vendors improved pricing
  Vendors improved licensing terms
  Consortium confirmed all options can meet requirements from Functional Design
September/October 2019 Working Sessions
Notes: Remove

## Slide 10: Summary Comparison of Imaging Solutions
 | Hyland | Kofax/CloudDocs | OpenText
Price- 5 yr. Total * | $ | $$ | $
Contract | Fixed SaaS Fixed Services | Fixed SaaS Fixed Services | Fixed SaaS T&M ROM Services
Capture/ Repository | Joint/Single Software: Preceptive Content | Separate: Kofax Capture and CloudDocs (Acquired May 2019) | Separate: OpenText Captiva and OpenText Documentum
References | AWS SaaS credential confirmed with proposed configuration. | AWS SaaS credential not confirmed. | AWS SaaS credential not confirmed.
User Licensing | Capture - Unlimited Intelligent Capture - Unlimited Repository - Unlimited | Capture - 4,020 concurrent users Intelligent Capture: 440 Million/Yr Repository -Unlimited | Capture - Unlimited Intelligent Capture - Unlimited Repository - Unlimited
Reporting Analytics | Unlimited | 40 Admin/Unlimited Consumers | Unlimited
Recommendation for the CalSAWS 58 County Imaging Solution remains Hyland hosted in AWS Cloud as concurred by ClearBest and a 3rd party reviewer.
* Imaging Vendor, SI, AWS, WAN, HW/SW

## Slide 11: Action Items
Confirmation of CalSAWS Imaging Solution recommendation.

## Slide 12
Informational Items

## Slide 13
Debrief/Status of LRS Migration to the Cloud

## Slide 14: Cutover –
Sat. Oct 12
6:00 AM
12:00 PM
6:00 PM
12:00 AM
6:00 AM
Sun. Oct 13
12:00 PM
6:00 PM
12:00 AM
Mon. Oct 14 –
County Holiday
6:00 AM
12:00 PM
6:00 PM
12:00 AM
Tues. Oct 15
Tech
Validation
Functional
Validation
6:00 AM
Users Log in
Informational
Touch point call #1 @ 6 pm
Mandatory/Go-No Go Decision
Touch point call #3 @ 6pm
11:00 AM
LRS Read-Only / YBN Offline
YBN Online @ 8PM
LRS URL Updated
Email communications were sent every four hours through out the cut over weekend.
Informational
Touch point call #1 @ 6 pm
Partner Cut Over and Validation
Collaborative effort across multiple external partners to complete the cut over.
Thank You

## Slide 15: Post Cutover
Week One
Day 1:
A
Users encountered login errors during morning ramp up and afternoon ramp up
Challenge - Impact
Action Taken
Removed DPSS Active Directory from the rotation and modified settings in security software to handle the load.
Day 2:
CalSAWS WAN
(Extranet VRF)
CalSAWS Exchange LA3
(primary)
AWS Transit
Gateway
CalSAWS Exchange SV1
(secondary)
LA County
us-west-2
E-Cloud
ISD Active Directory
Auxiliary Systems (LA Hosted)
LA County Offices
DPSS Active Directory
Webservers
Application Servers
Security
Dashboards
Docs- SaaS
Web Services
Reports
Database
https://calsaws.net
A
A
A
B
B
Users encounter login errors and experienced performance degradation post morning ramp up
Security software services were restarted. Additional tuning was applied in the evening.
Day 4:
Users experienced performance degradation for approximately a two hour period in the morning.
Security software services were restarted.
Daily restart scheduled and additional capacity added to security services to support the load.
CalSAWS Active Directory
C
B

## Slide 16: Lessons
Minimize potential differences between testing processes/transactions and real user behavior
Mitigate potential risks with each release by enhancing test cycles and readiness criteria to minimize disruption to business operations.
Continue hosting County User testing. County Validation test and System Test efforts prove effectiveness of testing.
Continue collaboration to maintain high degree of cross communication across stakeholders ( business, external partners, service providers (Oracle, AWS))
Applying Continuous Improvement

## Slide 17
CalSAWS Notice of Deficiency and Non-Compliance to Cambria Solutions

## Slide 18
CalSAWS Staffing and Statistics

## Slide 19: Staffing Update
Project Management Office (PMO)
  Fiscal/Contract Manager (1 long-term)
  Fiscal/Contract Analyst (2 long-term)
  PMO Analysts (2 long-term)
Common Services/PMO
  Procurement Manager (1 long-term)
  Procurement Analysts (2 long-term)
  Procurement Analysts (2 limited-term through January 2023)
Technical & Operations
  Cloud Analyst (1 long-term)
  Conversion Analyst (4 limited-term through January 2023)
Application Development & Test
  Release Coordinator (1 long-term)
  Release Coordinator (1 limited-term through January 2023)
Policy, Design & Application Development
  Business Analysts (4 limited-term through September 2021 or January 2023 depending on specific assignment)
Customer Engagement
  Implementation Manager (1 limited-term through January 2023)
  Implementation Coordinators (3 limited-term through January 2023)
  Trainers (3 limited-term through January 2023)
CIT 0084-19 Recruitment of CalSAWS Project Staff Closing Friday, Nov. 29, 2019

## Slide 20
M&O Application and Operations Update

## Slide 21: Policy Update
Cal-OAR
Policy Effective Date & State Policy Reference | C-IV/LRS Status | CalWIN Status | Implementation Details
7/1/2019 ACL 19-40 | SCRs CIV-103934; CA-208030 Phase I New Release October 2019 SCRs CIV-104230; CA-208720 Implemented Release 19.07 Priority 7/25/19 SCRs CIV-102191; CA-204569 Phase II New Release 20.05 | PPM #51772 Phase 1 October 2019 PPM #52398 Design Phase II R60 (2/20) PPM #52368 Phase II (BI) R61 (5/20) | The CDSS/CWDA/SAWS automation group continues to meets bi-weekly. CalSAWS Update: Manual Phase I – Manually send the files to CDSS, which will include the priority variables that already exist in SAWS. The process of manually sending the files to CDSS will begin in October 2019. The design for this effort will be reviewed and approved by CalSAWS consortium staff. October files were sent to CDSS on the 11th. CDSS is in the process of validating the file. Two case flags have been created for the counties to track the Home Visiting Initiative (HVI), HVI Offered and HVI Received. The cases flag data will be included in Phase I. Automated Phase II and III – Automate the process to send the files to CDSS. This will include the priority variables from Phase I, 2 and 3 above. The project will work with the WTW Committee on this effort. CalSAWS County Business Impact: Educate staff on how the system data collection page information will populate the Cal-OAR reports. Train staff to use the HVI case flags - HVI Offered and HVI Received. For more information on the HVI case flags, refer to CIT 0057-19. -Continued on Next Slide-

## Slide 22: Policy Update
Cal-OAR
Policy Effective Date & State Policy Reference | C-IV/LRS Status | CalWIN Status | Implementation Details
7/1/2019 ACL 19-40 | SCRs CIV-103934; CA-208030 Phase I New Release October 2019 SCRs CIV-104230; CA-208720 Implemented Release 19.07 Priority 7/25/19 SCRs CIV-102191; CA-204569 Phase II New Release 20.05 | PPM #51772 Phase 1 October 2019 PPM #52398 Design Phase II R60 (2/20) PPM #52368 Phase II (BI) R61 (5/20) | CalWIN Update: Manual Phase I – Manually send the Phase 1 data files to CDSS beginning October 2019. The design for this effort includes input and data validation from a group of volunteer project action team counties: Fresno, Orange, Placer, Sacramento, San Luis Obispo, Solano and Sonoma The following case special indicators were added to the system and allow counties to track HVI at the case level: HVI Offered HVI Received The first files have been sent to CDSS; counties will validate on an individual basis now that the files are being routinely generated. Automated Phase II - Automate the process to send the files to CDSS and use a business intelligence solution to create the files. CalWIN County Business Impact: CalWIN is conducting CalWIN SME meetings to review the data fields that must be completed to capture the required data elements outlined in ACL 19-40 and in the Cal-OAR trainings facilitated by CDSS.

## Slide 23: Policy Update
CalWORKs Stage One Child Care Continuous Eligibility
Policy Effective Date & State Policy Reference | C-IV/LRS Status | CalWIN Status | Implementation Details
10/1/2019 ACL 19-99 Draft ACL CW Stage One Child Care Notice of Action Forms 10/9/19 | SCRs CIV-104597; CA-209488 Design Release 20.01 SCR CA-209408 New Release TBD SCRs CIV-105397; CA-211332 New Release TBD | PPM # 52483 Pending Release TBD | SB 80 increases access to child care services for CalWORKs participants by authorizing CalWORKs Stage One Child Care immediately and continuously for 12 months or until the participants are transferred to Stage Two. Effective 10/1/19, counties shall authorize CalWORKs Stage One Child Care services immediately for 12 months or until participants are transferred to Stage Two. Participants will receive a Stage One Child Care authorization the day they are deemed eligible for CalWORKs. Beginning no later than 1/1/21, counties shall provide limited, read-only, online access through SAWS database to local contractors providing CalWORKs child care services. Access shall include a single summary page that contains current individual family data needed to enroll a family in CalWORKs child care services or transfer a family between stages. CalSAWS Update: SCRs CIV-104597 and CA-209488 are SPG approved and design has just started. Until the updated CCP 7 and CCP 8 forms are implemented, counties can use the version on the CDSS website. CalSAWS County Business Impact: Manually complete and send the updated CCP 7 and CCP 8 forms. -Continued on Next Slide-

## Slide 24: Policy Update
CalWORKs Stage One Child Care Continuous Eligibility
Policy Effective Date & State Policy Reference | C-IV/LRS Status | CalWIN Status | Implementation Details
10/1/2019 ACL 19-99 Draft ACL CW Stage One Child Care Notice of Action Forms 10/9/19 | SCRs CIV-104597; CA-209488 Design Release 20.01 SCR CA-209408 New Release TBD SCRs CIV-105397; CA-211332 New Release TBD | PPM #52483- Pending Release TBD PPM #53070- Pending Release TBD PPM #53366- Pending Release TBD | CalWIN Update: Stage 1 is administered using CalWIN by 9 of the 18 counties. The system does not place a limit in the number of Stage 1 months that can be administered to a post-aid case. Counties are able to continue Stage 1 child care for the 12 months outlined by SB 80 ensuring there is no break in child care when transitioning to Stage 2. CCP7 will be updated when final draft is posted-TBD. Upon release of final ACL project will be opened to address read-only access for a summary page for child care contractors. Proposal initiated for a Child Care Provider access - screen design. Reporting component: A workgroup consisting of representatives from CDSS, CWDA, and Parent Voices, in consultation with CWDs and SAWS, will design the report. CalWIN County SMEs developing a BENDS until automation can be implemented. CalWIN County Business Impact Counties will continue to follow established business processes.

## Slide 25: Policy Update
Able-Bodied Adults Without Dependents (ABAWD)
Policy Effective Date & State Policy Reference | C-IV/LRS Status | CalWIN Status | Implementation Details
1/1/2017 Fixed Clock 8/31/2019 Waiver Expires ACIN I-11-16 ACIN I-88-16 ACL 18-08 ABAWD Handbook ACL 19-93 ABAWD Handbook 2.0 | SCRs CIV-7215; CA-57971 Phase II Implemented Release 19.09 | PPM #46539- Implemented 8/2018 PPM #47411- Implemented 8/2018 PPM #51360 Implemented 8/19 PPM #52397 Design R60 (2/20) | ABAWD implementation began in September 2018 for San Francisco, San Mateo, and Santa Clara. The remaining counties are on waiver until 8/31/2019. In September, CDSS submitted another ABAWD waiver request to FNS for the time period 9/1/2018-8/31/2019. FNS approved the waiver and only the three additional counties (Alameda, Contra Costa, and Marin) are required to implement the ABAWD policy effective September 2019. This waiver is valid 9/1/19-8/31/20. The ABAWD Handbook version 2.0 was published on 9/12/19. CalSAWS Update: Marin County staff will attend an ABAWD functionality demo and click through at the CalSAWS North location on 8/12/19. A CIV functional presentation is being created for the changes being introduced in the September release. Phase II changes include the following: Updates to ABAWD exemption logic Updates to Count persons as ABAWD in a partial month Provide a manual way for case workers to indicate whether the ABAWD work requirement was met Add a task and batch EDBC closure for ABAWD that does not meet work requirement and has no other exemption, good cause, etc. Provide a way to track whether an ABAWD regained eligibility by meeting the work requirement -Continued on Next Slide-

## Slide 26: Policy Update
Able-Bodied Adults Without Dependents (ABAWD)
Policy Effective Date & State Policy Reference | C-IV/LRS Status | CalWIN Status | Implementation Details
1/1/2017 Fixed Clock 8/31/2019 Waiver Expires ACIN I-11-16 ACIN I-88-16 ACL 18-08 ABAWD Handbook ACL 19-93 ABAWD Handbook 2.0 | SCRs CIV-7215; CA-57971 Phase II Implemented Release 19.09 | PPM #46539- Implemented 8/2018 PPM #47411- Implemented 8/2018 PPM #51360 Implemented 8/19 PPM #52397 Design R60 (2/20) | Add new ABAWD MEDS codes, calendar, and transactions Updates to Time Limit data collection pages New NOAs and forms Update the Stat 47 report CalSAWS County Business Impact: Train staff on changes to system functionality. CalWIN Update: •ABAWD functionality enabled for Alameda and Contra Costa as of 9/1/2019. •Suppress the FX60 transactions until new criteria for starting the ABAWD time clock is programmed. •Modify CalWIN to start the ABAWD time clock for non-exempt ABAWD individuals. Run special job to re-transmit FX20 and FX60 MEDS transactions once change is implemented. CalWIN County Business Impact Counties will not have ABAWD information in MEDS when FX60 is suppressed. Receiving ABAWD counties will have to obtain Countable/Consecutive clock information from sending counties for ICTs.

## Slide 27: Policy Update
Increase Threshold for CalFresh Overissuances
Policy Effective Date & State Policy Reference | C-IV/LRS Status | CalWIN Status | Implementation Details
6/1/2019 ACL 19-50 | SCRs CIV-104217; CA-208685 System Test Release 19.11 | PPM #52311- Interim Testing R59 (11/19) PPM #52396- Design R60 (2/20) | Effective 6/1/19, the CalFresh claims establishment threshold will be $400 for closed CalFresh cases with an overissuance (OI) caused by an Administrative Error (AE) or Inadvertent Household Error (IHE). The new threshold does not apply to OIs arising from an IPV or from QC reviews. As a reminder, per current claims reporting policy, a claim that is not established (i.e. under $400) must not be reported on the FNS 209 form. CalSAWS Updates: Update the Recovery Account Detail page Update the Recovery Account batch job Update the FNS 209 Report Provide the counties a list of CalFresh recovery accounts established on or after June 1st, 2019 with status code ‘Active’, ‘Pending Agreement’, or ‘Suspended’ - but should have been terminated based on the new threshold policy. CalSAWS County Business Impact: Refer to CIT 0045-19, which was published on 6/14/19 for the interim process. -Continued on Next Slide-

## Slide 28: Policy Update
Increase Threshold for CalFresh Overissuances
Policy Effective Date & State Policy Reference | C-IV/LRS Status | CalWIN Status | Implementation Details
6/1/2019 ACL 19-50 | SCRs CIV-104217; CA-208685 System Test Release 19.11 | PPM #52311- Interim Testing R59 (11/19) PPM #52396- Design R60 (2/20) | CalWIN Update: Until automation can be implemented BENDS (workaround) instructions issued 6/19. Interim solution to run SQL to suspend CalFresh over-issuance for claims $400 or under if the CalFresh is discontinuing. Full automation change: •Modify CalWIN to not establish a CalFresh over-issuance for claims $400 or under if the CalFresh is discontinuing. •Modify CalWIN to open claims $400 or under if the CalFresh is rescinded/restored. CalWIN County Business Impact Users need to suspend/terminate CalFresh claims $400 or under if the CalFresh is discontinuing. Counties to follow BENDS (workaround) instructions.

## Slide 29: Policy Update
Medi-Cal Expansion for Young Adults
Policy Effective Date & State Policy Reference | C-IV/LRS Status | CalWIN Status | Implementation Details
1/1/2020 Draft ACWDL Received on 6/7/19 Draft NOAs Received on 7/1/19 | SCRs CIV-103662; CA-206941 Implemented Release 19.09 SCRs CIV-104022; CA-208241 System Test Release 19.09 Priority SCRs CIV-103874; CA-207950 Build Release 19.11 Priority | PPM #51191- Phase 1 Design R58B (9/19) PPM #51703- Phase 2 Design R59 (11/19) | The effort to turn on young adult expansion eHIT functionality and process a one-time batch EDBC run is tentatively scheduled to run on 11/22/2019. System down time is not required for this process. Batch EDBC memorandum call with the counites was held on 11/6/19. The batch EDBC memorandum provides details on the batch EDBC process, timeline, and list with county action for cases not processed by batch EDBC. The on-going monthly batch process will re-evaluate individuals for Medi-Cal due to aging out of young adult expansion aid codes. The first time this batch needs to run will be in January 2020 for February 2020 benefit month. CalSAWS County Business Impact: Train staff on changes to system functionality Manually process the cases not processed in the batch EDBC -Continued on Next Slide-

## Slide 30: Policy Update
Medi-Cal Expansion for Young Adults
Policy Effective Date & State Policy Reference | C-IV/LRS Status | CalWIN Status | Implementation Details
1/1/2020 Draft ACWDL Received on 6/7/19 Draft NOAs Received on 7/1/19 | SCRs CIV-103662; CA-206941 System Test Release 19.09 SCRs CIV-104022; CA-208241 Build Release 19.09 SCRs CIV-103874; CA-207950 Committee Review Release 19.11 Priority | PPM #51191- Phase 1 Design R58B (9/19) PPM #51703- Phase 2 Design R59 (11/19) | CalWIN Update: Phase 1: Notice of action changes Aid code rule changes to account for the increased age limit Batch triggers inserted for applicable cases for 1/2020 effective date Phase 2: Batch EDBC run will be scheduled for early November to identify individuals meeting the new criteria and grant full scope eligibility. Notice of Action snippets for Non-MAGI, such as MC 239P, MC 239Q and MC 239S CalWIN County Business Impact Exception lists will be provided for county action for cases not processed by the batch run.

## Slide 31: Policy Update
Social Security Admin (SSA) Cost of Living
Policy Effective Date & State Policy Reference | C-IV/LRS Status | CalWIN Status | Implementation Details
1/1/2020 Draft ACWDL Received 11/4/19 Draft ACIN Received on 11/4/19 | CIV-100451/CA-200824 Design Release 19.11 CIV-105046/CA-210439 Design Release 19.11 CIV-105301/CA-211064 New Release 20.02 CIV-105302/CA-211066 New Release 20.02 | PPM #53121 Design December 2019 | Social Security Administration has approved a 1.6 percent Cost of Living Adjustment (COLA) for 2020. Based on the increase in the Consumer Price Index (CPI-W) from the third quarter of 2018 through the third quarter of 2019, Social Security and Supplemental Security Income (SSI) beneficiaries will receive a 1.6 percent increase. On 11/4/19, SAWS met with DHCS to discuss streamlining the release of policy guidance for the Social Security Administration cost of living adjustment and the annual changes to the federal poverty limits. DHCS is going to publish ACWDL as updates become available. CalSAWS Update: The project has begun planning for these efforts. Once we receive draft ACLs and can confirm with DCHS that the values will be the same in the Final ACL, we will update the values in the systems and run batch EDBC. CalSAWS County Business Impact: Manually process the cases not processed in the batch EDBC -Continued on next slide-

## Slide 32: Policy Update
Social Security Admin (SSA) Cost of Living
Policy Effective Date & State Policy Reference | C-IV/LRS Status | CalWIN Status | Implementation Details
1/1/2020 Draft ACWDL Received 11/4/19 Draft ACIN Received on 11/4/19 | CIV-100451/CA-200824 Design Release 19.11 CIV-105046/CA-210439 Design Release 19.11 CIV-105301/CA-211064 New Release 20.02 CIV-105302/CA-211066 New Release 20.02 | PPM #53121 Design December 2019 | CalWIN Update: CalWIN COLA process targeting to be run December 7, 2019 for SSA COLA. Related a CAPI COLA will be run December 14, 2019 (PPM# 53122). To minimize the impact to county workers, CalWIN will apply the Social Security increase by updating all cases with SSA income by the percent of the increase. All programs, all cases where at least one individual is receiving Social Security benefits. CalWIN will not run the SSA COLA on MAGI-Only Medi-Cal and Mixed (APTC/MAGI) Medi-Cal cases. CalWIN County Business Impact Manually process the cases not processed in the batch EDBC.

## Slide 33
Functional Design Sessions Outcomes
Task Management Update
GA/GR Update
Non-State Forms Update
APIs Update
Functional Design Sessions Roadmap

## Slide 34: Functional Design Sessions
Task Management
Task requirements were updated to reflect business needs as noted by participants
Create Tasks
Assign Tasks
Reassign Tasks
Work Tasks
Oversee Tasks
Manual Task Creation
Automated Actions
Image Based Tasks
Other Task Creation Methods
Program Worker
Worker Schedule
Office Distribution
Task Banks
Manual Reassignment
Bulk Reassignment
Program Reassignment
My Tasks and Task Search Pages
Worklist Pages
Get Next Button
Task Reports
  On Request
  Extracts
Dashboard
Subscription
Quality Sampling

## Slide 35: Functional Design Sessions
GA GR
Existing LA County GR functionality will continue to be unchanged and part of CalSAWS
Leveraging existing Consortia assets and solutions, where possible
  Existing CalWIN rules and client correspondence
  Existing C-IV managed GA program functionality
Add functionality to support existing 57 Counties GA/GR programs, including data collection, eligibility rules where appropriate, fiscal processing, periodic reporting, and employment services programs
Consortium analysis of the proposed solution is in progress and includes:
  Accenture and DXC working together to refine the technical solution for eligibility and correspondence requirements
  Consortium and partners are reviewing and assessing the proposed technical solution and potential alternate solutions. This includes not only the DD&I scope but ongoing maintenance of the solution

## Slide 36: Functional Design Sessions
Non State Forms
Overarching goal was to develop one set of Non-State Forms for all 58 counties where possible
Reviewed 246 most frequently generated Non-State Forms across the three SAWS Systems. Forms were mapped across the three systems e.g. New Worker Letter, Appointment Letter
Agreed to retain 161 forms with the overarching agreement to use a single Non-State Form where similar forms existed across the three SAWS Systems

## Slide 37: Functional Design Sessions
Application Programming Interfaces (APIs)
Long Term Goal is to provide access to CalSAWS data via APIs
Full integration of the APIs will be a phased approach
Initial Data Access will be provided via APIs for targeted needs and supplemented with the Enhanced Data Reporting (EDR) solution
EDR is a copy of the production schema that is refreshed on a nightly basis and made available within the CalSAWS cloud infrastructure
Initial API implementation will focus on near real-time needs for:
  Lobby Management
  Appointments
  Worker Schedule
  Employment Services
  Program and Person Information
  Other needs
Counties will continue to be provided access to read-only schemas for ad-hoc reporting
APIs will provide counties access to near real-time data for specific needs as business domain objects or as raw data

## Slide 38: Functional Design Sessions
CalWIN Ancillary Systems Conversions
Facilitated functional Design Sessions with each of the CalWIN Counties to discuss core capabilities and conversion needs of the Collections, Fraud, and QA/QC Ancillary Systems
The Conversion Team is defining a common extract file format for each of the areas (Collections, Fraud, QA/QC and Task Management) to be used by the Counties to format and provide their ancillary system data for automated conversion into CalSAWS
Collections
  2 Ancillary Systems across 12 Counties Opting-In to the CalSAWS capabilities
  12 additional CalWIN County Conversion sources for this data
Fraud
  18 Ancillary Systems across 16 Counties Opting-In to the CalSAWS capabilities
  18 additional CalWIN County Conversion sources for this data
QA/QC
  13 Ancillary Systems across 10 Counties Opting-In to the CalSAWS capabilities
  13 additional CalWIN County Conversion sources for this data
Note: The 18 CalWIN counties Task Management ancillary systems have been added representing an additional 18 sources for this data

## Slide 39: Functional Design Sessions
Requirements Summary
Functional Design Session | Total
Imaging | 42
Task Management | 32
Non State Forms | 114
GA/GR | 28
APIs | 37
Ancillary Systems Conversion | 50
Total New Requirements* | 303
The 303 FDS requirements are in addition to the existing ~600 requirements

## Slide 40: Functional Design Sessions
Migration DD&I Schedule and Additional FDS Scope
The FDS represent approximately 250,000 hours of additional application, technical and conversion changes to the CalSAWS system
The expected start date is March 2020, assuming all State, Federal and governance approvals are obtained by mid February, 2020
By March 2020, Release 3 will be ready for deployment, Release 4 will be ready to start System Test, Release 5 will be ready for development and Release 6 in design. This would mean that Releases 7 and 8 are extremely large – likely over 100,000 hours each
This also has downstream impacts on when the conversion and training teams can start their development efforts, especially as it relates to the C-IV counties cutover
Alternate deployment approaches and schedules are being assessed

## Slide 42
Procurement Update
Portal/Mobile RFP timeline
CalWIN OCM & Training RFP timeline

## Slide 43: CalSAWS Statewide Portal/Mobile Application
Strategy and Scope
  Conduct an open procurement to acquire vendor services to design, develop, test and implement the statewide portal and mobile infrastructure and applications according to the CalSAWS Migration Schedule by September 2021, as an integral part of the overall migration strategy.
Key Objectives
  Minimize the burden of the overall eligibility process for enrollment and retention of benefits for low-income Californians and streamlining interactions for both clients and eligibility workers.
  Achieve the policy and business outcomes in a dynamic, intuitive, user friendly manner based on a robust User Centered Design (UCD) process to provide the best streamlined and responsive user experience possible within the existing policy framework.
  Move from the traditional forms completion model to an approach which is intuitive for the user, where answers to questions are used to inform subsequent questions and where forms are automatically and seamlessly completed.
  Engage stakeholders, advocates and clients in the design, development and test tasks through the UCD and test processes.
  Enhance the user interface and quality of the user experience to improve program outcomes; capture, analyze and apply data about how all users are interacting with the system with the goal of continuous improvement.
  Determine the extent to which the existing SAWS portal designs, source code and/or system documentation can be leveraged while not compromising the UCD principles required to modernize and maximize the use of the CalSAWS Portal.
  Employ an approach that recognizes: (1) that policy change is continuous; and (2) will enable the Portal to adjust quickly, to program changes, some of which will occur prior to go-live.
  Establish a framework to streamline maintenance through configurability, expedite implementation of future changes and facilitate future program, practice and technology innovation.
Strategy, Scope and Timeline

## Slide 44: CalSAWS Statewide Portal/Mobile Application
Strategy, Scope and Timeline
Timeline
Procurement Event | Date
Final Review by State Sponsors, Counties and Advocate Community | September 25 – October 2, 2019
Final Revisions to RFP Based on State and Stakeholder Feedback | October 3 – 7, 2019
Federal RFP Review and Approval | October 8 – October 31, 2019
Update RFP based on Federal Review | October 31 – November 1, 2019
Release RFP | November 4, 2019
Conduct Bidder’s Conference Sacramento County Department of Human Assistance 1825 Bell Street, Suite 200 Room 256 Sacramento, CA | November 20, 2019 10:30am-12:00pm
Contractor Proposal Due Date | January 22, 2020
Evaluate Proposals and Prepare Vendor Selection Report | January 23 – April 22, 2020
Contract Negotiations | April 27 – May 5, 2020
State, Federal and JPA BOD Approval of Agreement | May 7 – August 7, 2020
Start Date of Statewide Portal/Mobile App Vendor | August 10, 2020
Portal/Mobile App Go-Live | September 2021

## Slide 45: CalWIN Training, OCM & Implementation Support
Strategy
  Conduct an open procurement to acquire vendor services to provide Training, OCM and Implementation Support for the 18 CalWIN counties.
  CalWIN to CalSAWS migration is expected in 6 waves beginning January 2022 and continuing through January 2023
  CalWIN to CalSAWS migration must address multiple combinations of ancillary systems and business processes.
Scope and Key Objectives
  The Consortium is seeking a Contractor to apply innovative strategies, approaches, and methods for leading the cultural and organizational changes the CalWIN Counties will experience in transforming from their existing state and assimilating into the CalSAWS environment. This effort includes completing the transition from the CalWIN decentralized County-based support model to the CalSAWS regional structure for governance and ongoing system support.
  Prepare the CalWIN Counties to transition from using the CalWIN application and supporting business processes to using the CalSAWS application.
  Ensure each County’s As-Is business processes are documented and analyzed in order to prepare for changes, To-Be business processes, resulting from adoption of the CalSAWS application.
  Conduct a county-specific As-Is and To-Be gap analysis to create a foundation for OCM and communication with internal stakeholders including labor organizations and other County departments.
  Support county-specific business process change resulting from ancillary system choices.
  Ensure county-specific Training is developed to address changes in business processes.
  Where possible, leverage and adopt standard CalSAWS application Training as the target for transition.
Strategy, Scope and Timeline

## Slide 46: CalWIN Training, OCM & Implementation Support
Strategy, Scope and Timeline
PROCUREMENT EVENT | DATE
County, Consortium and State RFP Review | September 27 – October 15, 2019
Update RFP Based on Reviews | October 15 – October 20, 2019
Federal RFP Review and Approval | October 20 – December 13, 2019
RFP Release | December 17, 2019
Bidder’s Conference | January 7, 2020, 10:30am – 12:00pm
Contractor Proposal Due Date | February 19, 2020
Evaluate Proposals and Prepare Vendor Selection Report | February 20 – May 18, 2020
Consortium Issues Notice of Intent to Award | May 19, 2020
Contract Negotiation Period | May 21 – June 2, 2020
Federal, State and Consortium JPA Board of Directors Approval of Agreement | June 5 – August 28, 2020
Planned Start Date of CalWIN Contractor | August 31, 2020

## Slide 47
Adjourn Meeting