## North - CCB Approved
No. | SCR | Summary | Change Type (SCR) | SPG Priority | Status | Release | Minor Version | Other Agency Cross Reference | Committee / WorkGroup
1 | CIV-105460 | Enhance Replacement CalFresh Issuances to be replaceable up to Original Issuance Amount | Enhancement | High | New | TBD |  |  | Fiscal
2 | CIV-105067 | Update Kern County IP Address | Operational Enhancement | Medium | Test Complete | 19.09 | 19.09.13 |  | Fiscal
3 | CIV-104168 | Automated Regression Test - Execution and Maintenance - 19.09 Release Cycle | Operational Enhancement | Medium | System Test | 19.09 | 19.11.XX | CA-208531 | Other
4 | CIV-104415 | Add Full/Restricted Scope verbiage for Young Adult Expansion MAGI NOAs (CH-139211) | New Policy | High | System Test | 19.09 | 19.11.14 | CA-209109; CH-139211 | Correspondence
5 | CIV-104457 | Add Full/Restricted Scope Verbiage for Young Adult Expansion Non-MAGI NOAs | New Policy | High | System Test | 19.09 | 19.11.14 | CA-209232; CH-139211 | Correspondence
6 | CIV-104022 | CalHEERS eHIT: One-time Batches to Transition Young Adults from Restricted Scope to Full Scope Medi-Cal | Enhancement | High | System Test | 19.09 | 19.11.22 | CA-208241; CH-139211 | Medi-Cal/CMSP
7 | CIV-105087 | Update Lassen County Rush Warrant Template | Operational Enhancement | Medium | Test Complete | 19.09 | 19.11.14 | CA-210618 | Correspondence
8 | CIV-105053 | Update the BRM address for the Riverside County Administration office | Operational Enhancement | Medium | In Assembly Test | 19.09 | 19.11.14
9 | CIV-103087 | ACIN I-55-19 - 2020 State Minimum Wage | New Policy | High | In Assembly Test | 19.09 | 19.11.14 | CA-206223 | CalWORKs/CalFresh
10 | CIV-104997 | Automated Regression Test - Execution and Maintenance - 19.11 Release Cycle | Operational Enhancement | Medium | In Development | 19.11 | 20.01.XX | CA-210328 | Other
11 | CIV-104615 | Add office 2A Los Banos Eligibility Office in Merced to C4Y | Operational Enhancement | Low | System Test | 19.11 |  |  | C4Yourself
12 | CIV-103773 | Re-name Office/Agency '01' in Mariposa County | Operational Enhancement | Low | Test Complete | 19.11 |  |  | Usability
13 | CIV-103669 | Migrate Yuba County IVR to Amazon Connect | Enhancement | High | In Development | 19.11 | 20.01.23
14 | CIV-103667 | Migrate Kern County IVR to Amazon Connect | Enhancement | High | In Development | 19.11 | 20.01.09
15 | CIV-103668 | Migrate Sutter County IVR to Amazon Connect | Enhancement | High | Design in Progress | 19.11 | 20.01.23
16 | CIV-102209 | ABAWD: Update MEDS Transactions for the 36-month rollover process | New Policy | Critical | System Test | 19.11 |  | CA-204599 | MEDS
17 | CIV-102560 | ACL 18-107, ACL 18-108 - SNB/TNB Forms and Notices - Threshold Languages Phase 1 | New Policy | Critical | System Test | 19.11 |  | CA-205319 | Correspondence
18 | CIV-100482 | 2019/2020 Family Member Base Allocation Amount | New Policy | High | Test Complete | 19.11 |  | CA-200840 | Medi-Cal/CMSP
19 | CIV-12021 | ACL 18-121 Changes to Income and Eligibility Verification System (IEVS) Management Report (DPA 482) | New Policy | High | System Test | 19.11 |  | CA-58588 | State/Fiscal Reports
20 | CIV-104577 | Update Issuance Thresholds for 2020 (CRFI 19-026) | Enhancement | Medium | System Test | 19.11 |  | CA-209407 | Fiscal
21 | CIV-100074 | Update the Treatment of Veterans Income | New Policy | Medium | Test Complete | 19.11 |  | CA-59263 | CalWORKs/CalFresh
22 | CIV-104159 | Stop benefit offsets on CalFresh Administrative Error Recovery Accounts | Policy Re-Design | Critical | System Test | 19.11 |  | CA-202330 | Collections
23 | CIV-9838 | ACL 17-61 - Achieving a Better Life Experience (ABLE) Accounts | New Policy | Medium | System Test | 19.11 |  | CA-203060 | CalWORKs/CalFresh, Foster Care/Kin GAP/AAP, Medi-Cal/CMSP
24 | CIV-7419 | Update San Bernardino Financial Accounting Software interface file to SAP | Operational Enhancement | Medium | System Test | 19.11 |  |  | Fiscal
25 | CIV-102151 | Add/Update Non-MAGI Screening Packets | New Policy | High | System Test | 19.11 |  | CA-203981 | Correspondence, Medi-Cal/CMSP
26 | CIV-104608 | ACIN I-41-19 STAT 47 - Exclude CFAP Participants | New Policy | High | Approved | 19.11 | 19.12.12 | CA-209498 | State/Fiscal Reports
27 | CIV-104094 | CFL 18/19-79 Update Electronic Theft replacement and reporting | New Policy | High | System Test | 19.11 |  | CA-208374 | Fiscal, State/Fiscal Reports
28 | CIV-103874 | CalHEERS eHIT: Young Adult Expansion - Age Reevaluation Updates | New Policy | High | Approved | 19.11 | 20.01.10 | CA-207950; CH-139211 | Medi-Cal/CMSP
29 | CIV-104861 | Additional ABAWD Updates | Policy Re-Design |  | System Test | 19.11 |  | CA-210031 | CalWORKs/CalFresh
30 | CIV-104217 | ACL 19-50 - Increase Threshold For CalFresh Overissuances | New Policy | High | System Test | 19.11 |  | CA-208685 | Collections, State/Fiscal Reports
31 | CIV-8054 | ACL 17-05 CalFresh Student Eligibility | New Policy | Critical | System Test | 19.11 |  | CA-51457 | CalWORKs/CalFresh
32 | CIV-8775 | ACL 17-30 Allow Second Active CF Program for Victims of Domestic Violence | New Policy | High | Test Complete | 19.11 |  | CA-53457 | CalWORKs/CalFresh
33 | CIV-103539 | Migrate Marin County IVR to Amazon Connect | Enhancement | High | System Test | 19.11 |  | CA-207026 | IVR & Contact Center
34 | CIV-103540 | Create Customized Call Control Panel for Amazon Connect | Enhancement | High | System Test | 19.11 |  | CA-208919 | IVR & Contact Center
35 | CIV-102308 | Clean-up of MC Program Block for Individuals Active on CW | Enhancement | Critical | In Development | 19.11 | 20.01.10 | CA-49736 | Medi-Cal/CMSP
36 | CIV-103671 | Migrate Shasta County IVR to Amazon Connect | Enhancement | High | In Development | 20.01 | 20.01.31
37 | CIV-103670 | Migrate Butte County IVR to Amazon Connect | Enhancement | High | In Development | 20.01 | 20.01.31
38 | CIV-102946 | Update CW EDBC to Remove Stepsibling or Half-Sibling Excluded from CalWORKs in the CalFresh Budget | Policy Re-Design | Critical | In Development | 20.01 |  | CA-205982 | CalWORKs/CalFresh
39 | CIV-100733 | Enhance the Employment Summation and Employment Summation Detail Reports | Enhancement | Medium | In Development | 20.01 |  | CA-51131 | Management Reports
40 | CIV-101987 | Update SAR7 Sent Text Message for Tutorial | Enhancement | Medium | In Assembly Test | 20.01 |  |  | IVR & Contact Center
41 | CIV-541 | Update WDTIP Outbound file writer to not allow LD02 transactions to be generated for WTW supportive services participation records | Enhancement | Critical | In Development | 20.01 |  | CA-204814 | Time Limits
42 | CIV-105458 | Automated Regression Test - Execution and Maintenance - 20.01 Release Cycle | Operational Enhancement | Medium | Approved | 20.01 | 20.03.XX | CA-211451 | Other
43 | CIV-104036 | ACL 18-107, ACL 18-108 - SNB/TNB Forms and Notices - Threshold Languages Phase 2 | New Policy | Critical | In Development | 20.01 |  | CA-208258 | Correspondence
44 | CIV-101430 | CF - FTP INS Document, Income of FRE should be prorated | Policy Re-Design | High | In Development | 20.01 |  | CA-201575 | CalWORKs/CalFresh
45 | CIV-105048 | Update Lake County Warrant Print template | Operational Enhancement | Medium | Approved | 20.01 |  |  | Correspondence
46 | CIV-101423 | Update Office Location on system generated Benefit Reductions and Offset Transactions | Enhancement | High | In Development | 20.01 |  | CA-205512 | Collections
47 | CIV-100500 | ACL 18-15 Last Date of Payment for Extended Foster Care, ARC and Kin-GAP | Policy Re-Design | Medium | In Development | 20.01 |  | CA-201036 | Foster Care/Kin GAP/AAP
48 | CIV-102404 | Transitional CalFresh Eligibility Updates | Enhancement | Medium | In Development | 20.01 |  | CA-204326 | CalWORKs/CalFresh
49 | CIV-104929 | Lobby Management: Reception Log: Update Number Generated Logic for Reception Log Visits | Enhancement | High | Approved | 20.01 |  | CA-201772 | Lobby Management
50 | CIV-104902 | Update CalHEERS Outbound Mappings for 'Educational, Student' Income Category | Enhancement | High | Approved | 20.01 |  | CA-210148 | Medi-Cal/CMSP
51 | CIV-103674 | Migrate Stanislaus County IVR to Amazon Connect | Enhancement | High | Design in Progress | 20.02 | 20.03.05
52 | CIV-103675 | Migrate Monterey County IVR to Amazon Connect | Enhancement | High | Design in Progress | 20.02 | 20.03.19
53 | CIV-103673 | Migrate Humboldt County IVR to Amazon Connect | Enhancement | High | Design in Progress | 20.02 | 20.03.05
54 | CIV-103672 | Migrate San Bernardino County IVR to Amazon Connect | Enhancement | High | Design in Progress | 20.02 | 20.02.20
55 | CIV-103599 | CalHEERS eHIT: Add Spousal Support Agreement/Modification Date | Enhancement | Medium | In Development | 20.02 |  | CA-206994; CH-138728 | Medi-Cal/CMSP
56 | CIV-104268 | Enhance Refused Verification functionality to send failed Admin Verif | Enhancement | Medium | Approved | 20.02 |  | CA-209076 | Medi-Cal/CMSP
57 | CIV-105016 | CalHEERS eHIT: Update Interface Schema to version 14 | Enhancement | High | In Development | 20.02 |  | CA-210381; CH-140031 | Medi-Cal/CMSP
58 | CIV-103677 | Migrate Regional Contact Center IVR to Amazon Connect | Enhancement | High | Design in Progress | 20.03 | 20.04.09
59 | CIV-103676 | Migrate Kings County IVR to Amazon Connect | Enhancement | High | Design in Progress | 20.03 | 20.03.26
60 | CIV-103679 | Migrate Non-Contact Center County IVRs to Amazon Connect | Enhancement | High | Design in Progress | 20.03 | 20.03.XX
61 | CIV-103666 | Migrate Riverside County IVR to Amazon Connect | Enhancement | High | In Development | 20.03 | 20.03.XX
62 | CIV-9947 | Change Recovery Account Cause Code editing logic | Enhancement | High | Approved | 20.03 |  | CA-205652 | Collections
63 | CIV-104671 | Update Previous Potential Benefit Calculation Logic | Enhancement | High | Design in Progress | 20.03 |  | CA-209661 | Collections, State/Fiscal Reports
64 | CIV-10075 | Add Need Categories for Family Stabilization and Housing Support to Needs Detail page | Enhancement | High | In Development | 20.03 |  | CA-205441 | Fiscal
65 | CIV-103387 | Modify Existing Report | Enhancement | High | Approved | 20.05 |  | CA-211200 | Other
66 | CIV-101733 | Move Voice Prints between Counties | Enhancement | Medium | In Development | 20.07 |  |  | IVR & Contact Center
67 | CIV-103678 | Migrate Outbound Calling Campaigns to Amazon Connect | Enhancement | High | New | 20.07

## North - SPG Approved
No. | SCR | Summary | Change Type (SCR) | SPG Priority | Status | Other Agency Cross Reference | Committee / WorkGroup
1 | CIV-66 | Aligning Status Begin Date of Associated Programs With Primary Cash Aid Programs or EDBC Run Date, whichever is later | Enhancement | High | Ready for Committee | CA-58934 | Welfare to Work/WPR
2 | CIV-272 | Add additional field for known CIN (40067) | Enhancement | High | New |  | MEDS
3 | CIV-331 | Update Event Logic when Moving the BDA or Logging a Rescind | Enhancement | High | New | CIV-200895 | CalWORKs/CalFresh
4 | CIV-391 | Add Edit Functionality to a Service Arrangement | Enhancement | Critical | Design in Progress | CA-204582 | Welfare to Work/WPR
5 | CIV-430 | Count CalWORKs clock when Extender is added | Enhancement | High | New | CA-53782, CA-53784 | Time Limits
6 | CIV-533 | Update WEX/CS WorkSheet Detail Page | Enhancement | Medium | Design in Progress | CA-55200 and CIV-5340 | Welfare to Work/WPR
7 | CIV-593 | OBIEE: Apply Oracle Patch to OBIEE (47550) | Enhancement | Medium | New | CA-201657 | Management Reports
8 | CIV-661 | Time Limit: Automate the creation of months for Supportive Service recipients (48917) | Enhancement | Critical | Design in Progress | CA-210580 | Time Limits
9 | CIV-675 | OBIEE: Caseload Inventory Report Program Persons (49407) | Enhancement | High | New | CA-201656 | Management Reports
10 | CIV-714 | Create Password Reset Self-Service functionality for C-IV Users (50123) | Enhancement | Medium | New |  | Security
11 | CIV-1068 | CalHEERS eHIT: Married Filing Jointly and Out-of-State Residence Address | Enhancement | High | Design in Progress | CA-208863 ; CH-142899 | Medi-Cal/CMSP
12 | CIV-1082 | CO-068: Enhance the Medi-Cal Caseload Report (56781) | Enhancement | Medium | New | CA-200975 | Medi-Cal/CMSP, State/Fiscal Reports
13 | CIV-4108 | CO-xxx: Online CalWORKs Appraisal Tool (OCAT) Integration | Enhancement | High | Design in Progress | CA-50302
14 | CIV-4400 | County Funded: Add 'Notice of Action' Functionality to the General Assistance (Managed) Program | Enhancement | Critical | New | C-IV Specific | Other
15 | CIV-5165 | Add Medi-Cal Negative Action Reason 'Worker Initiated-Skip CalHEERS' | Enhancement | Medium | Committee Review | CA-209381 | Medi-Cal/CMSP
16 | CIV-6081 | DDCR 10000: Update C-IV Envelopes to Match LRS | Enhancement | Critical | New | None | Correspondence
17 | CIV-8583 | Time Limit Months for Immediate Need program | Enhancement | Critical | New | CA-204823 | Time Limits
18 | CIV-10044 | Add Subscription Functionality to the Employment Services Program Assignment Report | Enhancement | Medium | New | CA-201443 | Management Reports
19 | CIV-10045 | Add Subscription Functionality to the Pending Recovery Account Report | Enhancement | Medium | New | CA-201441 | Management Reports
20 | CIV-11257 | Place Holder SCR to update the Imprest Cash functionality in Issued Valuable Inventory Report | Enhancement | High | New | CA-201569 | State/Fiscal Reports
21 | CIV-11609 | IEVS: Do not process Abstracts for PVS records without income | Enhancement | High | New | None | IEVS
22 | CIV-11725 | Add functionality to manage Conditionally Eligible status in MAGI Determinations | Enhancement | High | Committee Review | CA-203824 | Medi-Cal/CMSP
23 | CIV-11907 | Flip ICT Status to Manually Complete | Enhancement | High | New | 49021 | ICT
24 | CIV-11988 | Automate Medi-Cal Discontinuance for Individual Turning 65 for Failure to Return MC 604 IPS | Enhancement | High | New | CA-49841 | Medi-Cal/CMSP
25 | CIV-12446 | CA 812 Collection Reports Claim Adjustments | Enhancement | High | Design in Progress | CA-52597 | State/Fiscal Reports
26 | CIV-100260 | IEVS: Do not create tasks for IEVS abstracts that have been automatically closed. | Enhancement | High | New | CIV Specific | IEVS
27 | CIV-100502 | Update Outbound WIS Interface for 2020 STS Calendar Cycle Numbers | Enhancement | Medium | Design in Progress |  | Tax Intercept
28 | CIV-100504 | Update Bank Routing Information for Direct Deposit | Enhancement | High | New |  | Fiscal
29 | CIV-100575 | CalACES.org: Make updates | Enhancement | Medium | New | ca-207614 | C4Yourself
30 | CIV-100589 | Enhance Business Intelligence navigation tab to handle user session timeout. | Enhancement | Medium | New |  | Usability
31 | CIV-100748 | CalFresh Churn Trends Report for District Offices | Enhancement | High | New | CA-54520 | Management Reports
32 | CIV-100845 | CF 296 - Changes in logic for Line 10 - Overdue Recertifications (CWD Caused) during the month | Enhancement | Medium | New | CA-201742 | State/Fiscal Reports
33 | CIV-101131 | CES 2018-035: Add Language to Text Notifications if appointments are in Person or by Telephone | Enhancement | Medium | New |  | IVR & Contact Center
34 | CIV-101174 | Update 206-Cal-Learn Time Limit Exemption to not apply to WTW time clock | Enhancement | High | New | CA-202482 | Welfare to Work/WPR
35 | CIV-101447 | CF 387 CalFresh Request for Information for Residency | Enhancement | High | Ready for Committee | CA-49633
36 | CIV-101649 | Task Management: Update the Task Reassignment Detail page to include a Task Bundling option | Enhancement | Low | New
37 | CIV-102056 | WTW 25/WTW25A State Reports Modifications | Enhancement | Critical | New | CA-202110 | State/Fiscal Reports
38 | CIV-102098 | Do not Create an Offset Transaction for Overpayment/Overissuances Adjustments | Enhancement | Critical | New | CA-204762 | Collections, State/Fiscal Reports
39 | CIV-102291 | WTW 24 MTC - Update WTW 24 MTC from Verified Actual Hours (Priority 10) | Enhancement | Critical | New | CA-53786 | Welfare to Work/WPR
40 | CIV-102305 | WTW 24 MTC - Update Tracking of Voc Ed (Priority 11) | Enhancement | Critical | New | CA-53787 | Welfare to Work/WPR
41 | CIV-102312 | Separate Penalties for "Assign Support Rights" Non-Compliance | Enhancement | High | New |  | CalWORKs/CalFresh
42 | CIV-102360 | CalHEERS eHIT: Add Medi-Cal Deemed Infant and Medi-Cal Access Infant Program FunctionalityÂ (CH-122183) | Enhancement | High | New | CH-122183, CA-204952 | Medi-Cal/CMSP
43 | CIV-102423 | Redesign FC Facility Ratios page ? Need to store historical ratio info based on the eff. date for Group Home and Foster Family Agency type | Enhancement | High | New | CA-55206 | RDB
44 | CIV-102606 | Add State PINs to Integrated Service Payment / Valuable Detail Claiming Report | Enhancement | Medium | Design in Progress | CA-209221 CA-208814 CIV-104015 | State/Fiscal Reports
45 | CIV-103498 | Add Family Size 11 and 12 to FPL Code Table | Enhancement | Medium | New | CA-206805 | Medi-Cal/CMSP
46 | CIV-103772 | Automate SAWS 30 - IEVS Employment and Income Verification Form | Enhancement | High | Pending Approval | CA-206520 | IEVS
47 | CIV-103887 | Create State Agency Accounts for Designated DHCS and CDSS Staff | Enhancement | Low | Design in Progress | CA-209032
48 | CIV-104299 | CalHEERS eHIT: Budget Periods and Individual-Level Eligibility | Enhancement | Critical | New | CA-208864; CH-151332 | Medi-Cal/CMSP
49 | CIV-104321 | eICT: Updates for eICT (EHIT, ABAWD, SB 380) | Enhancement | High | New | CA-208889 | ICT
50 | CIV-104322 | New data elements to be added to the EICT Outbound file to indicate CalFresh SSI/SSP Reversal. | Enhancement | Critical | Ready for Committee | CA-208888 | ICT
51 | CIV-104665 | Add Threshold Languages for FC/KG CNI NOA Fragment | Enhancement | High | Design in Progress | CA-209638 | Correspondence
52 | CIV-104670 | Update the NA 791 to the most current state version | Enhancement | Medium | Committee Review | CA-203787 | Correspondence, Foster Care/Kin GAP/AAP
53 | CIV-104826 | Add threshold language translations for the newly added MAGI and Non-MAGI YAE fragments | Enhancement | High | Design in Progress | CA-209956
54 | CIV-104947 | Updates to Restaurant Meals Batch EDBC Sweep | Enhancement | High | New |  | CalWORKs/CalFresh
55 | CIV-105065 | NB Application Future Application Date | Enhancement | High | Ready for Committee | CA-210498 | CalWORKs/CalFresh
56 | CIV-572 | Update MEDS to Send Prior FC / KG Aid Code to MEDS for NMD's Minor Infant Child (47096) | New Policy | High | Design in Progress | CA-203208 | MEDS
57 | CIV-632 | ACL 12-67, ACL 13-19, ACL 13-37, ACL 13-59 Welfare to Work (WTW) 24-Month Time Clock- Phase 3 (48176) | New Policy | High | New |  | Time Limits
58 | CIV-832 | ACL 14-64: Add CalWORKs Family Stabilization (FS) Program Quarterly Status Report - FSP 14 (53467) | New Policy | Critical | New | CA-56913 | State/Fiscal Reports
59 | CIV-966 | ACL 15-03: Transitioning from WTW 24 MTC Participation to Post WTW 24 MTC CW Federal Standards (55674) | New Policy | High | New |  | Welfare to Work/WPR
60 | CIV-3094 | ACL 14-28 - Expansion of the Definition of Relative for the Kin-GAP Program | New Policy | High | New | None | Foster Care/Kin GAP/AAP
61 | CIV-7522 | Update EDBC to process mid-period TCF programs via eICT | New Policy | High | New | CA-200800 | CalWORKs/CalFresh, ICT
62 | CIV-7564 | Revised Medi-Cal Hierarchy | New Policy | Critical | Design in Progress | CA-202778 | Medi-Cal/CMSP
63 | CIV-7859 | ACL 16-98: Add M44-211A and M44-211D and update CW 42 on the Template Repository; Limit HA Manual EDBC drop down values | New Policy | Medium | Committee Review | CA-50686 and CA-51882 | CalWORKs/CalFresh
64 | CIV-8576 | Update special needs to issue current state amounts | New Policy | Medium | New | None | CalWORKs/CalFresh
65 | CIV-8633 | ACWDL 17-12: Changes to the Designation and Responsibilities of the Medi-Cal Authorized Representative | New Policy | Critical | New | CA-208191 | Medi-Cal/CMSP
66 | CIV-8975 | NFC 17-023: Update SAR 2 to latest state revision | New Policy | High | New | CA-202463 | Correspondence
67 | CIV-9259 | ACL 17-31 Application Procedures for CAPI | New Policy | Low | New | None | CalWORKs/CalFresh
68 | CIV-9741 | ACIN I-33-17 - Temporary absence in CalWORKs for hospital stay remains CWs eligible for duration of hospital stay | New Policy | Low | New | CA-49414 | CalWORKs/CalFresh
69 | CIV-9943 | CO-100: Consolidate Foster Care Issuances | New Policy | High | New | CA-200413, CIV-9697, CIV-101451, CA-206015 | Fiscal
70 | CIV-10156 | CalFresh E&T Reporting | New Policy | High | New | CA-204858 | State/Fiscal Reports
71 | CIV-10179 | ACL 17-53: ESAP Notices Threshold Languages | New Policy | Medium | New | LRS 52758, 54952 | Correspondence
72 | CIV-10791 | Prevent Advancing Medi-Cal Renewal with a Soft Pause Individual | New Policy | Critical | Committee Review | CA-58123 | Medi-Cal/CMSP
73 | CIV-10972 | ACL 17-87 -CalWORKs update to immunization penalty | New Policy | Medium | New | CA-201440 | CalWORKs/CalFresh
74 | CIV-12023 | ACWDL 17-36 - NOA snippets for Medi-Cal Inmate Program | New Policy | Medium | New | CA-200866 | Correspondence
75 | CIV-100213 | ACL 18-07 - SUSPENSION, REINSTATEMENT AND TERMINATION OF AND REAPPLICATION FOR CASH ASSISTANCE PROGRAM FOR IMMIGRANTS (CAPI) BENEFITS; TRANSMISSION OF UPDATED CAPI NOTICE OF CHANGE (NA 692) | New Policy | High | New |  | Correspondence
76 | CIV-100451 | 2020 Social Security Title II and Title XVI Cost of Living Adjustments (SSA COLA) | New Policy | High | Design in Progress | CA-200824 | CalWORKs/CalFresh, Foster Care/Kin GAP/AAP, Medi-Cal/CMSP
77 | CIV-100535 | ACL 18-16 - CalFresh Exclusion of Funeral Agreement from Resources | New Policy | Low | New |  | CalWORKs/CalFresh
78 | CIV-100580 | ACL 18-XX CW & CF: Partial Revision of State Automated Welfare Systems (SAWS) 2 PLUS Application Forms | New Policy | High | New | CA-202458 | Correspondence
79 | CIV-100752 | ACL 17-34 - CFR 273.2 Create monthly/annual report for Non-Assistance CalFresh Elderly Simplified Application Project (ESAP) Waiver Approval for Elderly/Disabled (E/D) Households (HHs) with no earned income | New Policy | Medium | New | CA-56341 | State/Fiscal Reports
80 | CIV-100774 | Updates to the GEN 1365 Form and Form Generation | New Policy | High | Design in Progress | CA-202307 | Correspondence
81 | CIV-100878 | ACL 18-117: Implement CalFresh Churn Report - CF 18 | New Policy | High | Design in Progress | CA-201836 | State/Fiscal Reports
82 | CIV-101282 | Transitional Medi-Cal, Four Month Continuing Eligibility, and CalWORKs Denials and Discontinuances | New Policy | Critical | New | CA-202682 | Medi-Cal/CMSP
83 | CIV-101796 | ACWDL 18-17: Translations â€“ MC 604 MDV Doctorâ€™s Verification (Reference All County Welfare Directors Letter No. 17-25) | New Policy | High | New | CA-203671 | Correspondence
84 | CIV-101980 | CalHEERS eHIT: IAP Transition Enhancement | New Policy | High | New | CA-204030; CH-124914 | Medi-Cal/CMSP
85 | CIV-102263 | ACL 18-99 CF OI Collection Period | New Policy | Critical | New | CA-204863 | Collections
86 | CIV-102568 | ACL 18-92, ACL 18-107 Transitional Nutrition Benefit Program Recertification | New Policy | Critical | Ready for Committee | CA-205328 | CalWORKs/CalFresh
87 | CIV-102757 | ACL 18-75 Phase IV-Long Term Funding for Emergency Caregivers with Placements Prior to RFA Approval | New Policy | Critical | New | CA-205633 | Foster Care/Kin GAP/AAP
88 | CIV-102761 | CalHEERS eHIT: BREfS Phase C, Part 2 Override Eligibility Determination Functionality | New Policy | High | New | CA-205642, CH-109747 | Medi-Cal/CMSP
89 | CIV-102912 | Add 5L Aid Code for FC Emergency Assistance EC Ineligible Cases | New Policy | High | Design in Progress | CA-205913 | Foster Care/Kin GAP/AAP
90 | CIV-103015 | ACL 18-141 CF REVISED SUPPLEMENTAL FORM FOR EXCESS MEDICAL DEDUCTIONS (CF 31) | New Policy | High | New | CA-206080 | Correspondence
91 | CIV-103088 | ACIN I-55-19- 2020 State Minimum Wage Run Batch EDBC | New Policy | High | Ready for Committee | CA-206224 | CalWORKs/CalFresh
92 | CIV-103743 | ACL 18-08 - ABAWD - Phase III | New Policy | Critical | New | CA-207637 | CalWORKs/CalFresh
93 | CIV-103983 | MEDIL I 19-12: Update on Asset Verification Reports | New Policy | High | New | CA - 208130 | IEVS
94 | CIV-104011 | ACL 19-34 Update Kin-GAP Beginning Date of Aid Rules to Accept Mid-Month Application Date | New Policy | High | Design in Progress | CA-208184 | Foster Care/Kin GAP/AAP
95 | CIV-104019 | ACL 19-31and CFL 19/20-14 - Re-Entry into Extended Foster Care for Youth Receiving SSI | New Policy | High | New | CA-208203 | Foster Care/Kin GAP/AAP
96 | CIV-104040 | ACL 18-107, ACL 18-108 - SNB/TNB Forms and Notices - Threshold Languages Phase 3 | New Policy | Critical | Committee Review | CA-208261 | Correspondence
97 | CIV-104043 | ACL 18-107, ACL 18-108 - SNB/TNB Forms and Notices - Threshold Languages Phase 4 | New Policy | Critical | Committee Review | CA-208268 | Correspondence
98 | CIV-104383 | ACL 19-76 - CalWORKs Change in Earned Income Disregard (EID) and Income Reporting Thresholds Tiers (IRTs) | New Policy | High | New | CA-209033 | CalWORKs/CalFresh
99 | CIV-104559 | ACL 19-67 - CalWORKs: Changes to Asset and Vehicle Value Limits | New Policy | High | New | CA-209360 | CalWORKs/CalFresh
100 | CIV-104574 | ACL 19-59 Revise DFA 358F and DFA 358S | New Policy | High | Design in Progress | CA 209404 | State/Fiscal Reports
101 | CIV-104584 | Update Medi-Cal Auto-Discontinuance Batch for Failure to Complete RE to process at an Individual Level | New Policy | High | Design in Progress | CA-209422 | Medi-Cal/CMSP
102 | CIV-104597 | ACL 19-99 Child Care Immediate and Continuous Eligibility to Stage One | New Policy | Medium | Design in Progress | CA 209488 | Child Care
103 | CIV-104703 | ACL 19-75 Revisions to ABCD 350 | New Policy | High | Design in Progress | CA 209709 | State/Fiscal Reports
104 | CIV-104707 | Add NOAs and Forms for Electronic Theft | New Policy | High | Design in Progress | CA-209721 | Correspondence
105 | CIV-104848 | ACL 19-77 New and Revised Homeless Assistance Forms and Notices of Action | New Policy | High | New | CA-209996 | Correspondence
106 | CIV-104986 | Deactivating Pre-ACA Aid Codes | New Policy | High | Design in Progress | CA-210307 | Medi-Cal/CMSP
107 | CIV-105046 | Batch EDBC to apply 2020 SSA Cost of Living Adjustments (COLA) | New Policy | High | Design in Progress | CA-210439 | CalWORKs/CalFresh, Foster Care/Kin GAP/AAP, Medi-Cal/CMSP
108 | CIV-443 | MEDS: Calculate CIN Check Digit (43880) | Operational Enhancement | Medium | New | CA-202312 | MEDS
109 | CIV-101296 | CalACES.org: Update the Web Portal link on CalACES.org | Operational Enhancement | Medium | New |  | C4Yourself
110 | CIV-102289 | Quarterly release testing for EBT vendor FIS - January 2020 | Operational Enhancement | Medium | New |  | Fiscal
111 | CIV-102290 | Quarterly release testing for EBT vendor FIS - April 2020 | Operational Enhancement | Medium | New |  | Fiscal
112 | CIV-102442 | CO-1072-2018 -Update Address for Chico Office in IVR & C4Yourself | Operational Enhancement | Medium | Design in Progress |  | IVR & Contact Center
113 | CIV-436 | NOA: Over Property NOA does not list property (43735) | Policy Re-Design | High | New |  | Correspondence
114 | CIV-604 | Update the Kin-Gap/Foster Care EDBC to Add SCI Prior to Subtracting Income (47717) | Policy Re-Design | High | New |  | Foster Care/Kin GAP/AAP
115 | CIV-644 | Update Incomplete CF Recertification Status (48318) | Policy Re-Design | High | New | CA-207798 | Correspondence
116 | CIV-676 | CW: Special Needs for Therapeutic Diets Returning Conflicting Values (49436) | Policy Re-Design | Low | New |  | CalWORKs/CalFresh
117 | CIV-789 | ACL 14-12, CFL 13/14-35 FAMILY STABILIZATION PROGRAM for CalWORKs (51903) | Policy Re-Design | High | Committee Review | CA-51700, CA-57298 | Welfare to Work/WPR
118 | CIV-818 | CalWORKs clock is ticking for parent who is under 18 years old (52832) | Policy Re-Design | High | Committee Review | CA-204747 | Time Limits
119 | CIV-960 | Update Child In Foster Care on 18th Birthday Check (55621) | Policy Re-Design | High | New |  | Foster Care/Kin GAP/AAP
120 | CIV-1131 | ACL 11-51: Update FC Education Travel Reimbursement NOAs (57200) | Policy Re-Design | Medium | New | CA-209231 | Correspondence
121 | CIV-1207 | CW Treatment of Motor Vehicles (57833) | Policy Re-Design | Medium | New |  | CalWORKs/CalFresh
122 | CIV-3551 | Update Most Beneficial Logic for Add Person Mid-Period (SAR) | Policy Re-Design | High | New | None | CalWORKs/CalFresh
123 | CIV-5849 | ACL 18-50 - Implement Redesigned CalFresh Overissuance NOAs | Policy Re-Design | High | New | CA-202684 | Correspondence
124 | CIV-7278 | Apply Minimum Allotment Logic to CFAP Budget | Policy Re-Design | Low | New | None | CalWORKs/CalFresh
125 | CIV-7358 | CO-091: ACIN I-88-16 - Tracking Deleted Database Records for ABAWD Determination | Policy Re-Design | Medium | New | CA-56918 | CalWORKs/CalFresh
126 | CIV-8657 | Updates to CW Change NOA due to Overpayment Adjustment | Policy Re-Design | High | Design in Progress | CA-50293
127 | CIV-8850 | ACL 11-01, ACL 11-01E - Reimplement QNA File NA960X/NA960Y Reason Codes as Timed Out instead of Terminated | Policy Re-Design | High | New | LRS SCR 48771 | CalWORKs/CalFresh
128 | CIV-8950 | Active $0 CF grants removed from Negative Univers File transfer to Suspend (S) | Policy Re-Design | High | New | LRS SCR 48771 | CalWORKs/CalFresh
129 | CIV-9009 | STAT 47 - Updates to Design | Policy Re-Design | Medium | New | CA-51987 | State/Fiscal Reports
130 | CIV-9916 | Prevent MAGI-only Mode EDBC for a beneficiary on Non-MAGI Medi-Cal | Policy Re-Design | Medium | New | CA-203116 | Medi-Cal/CMSP
131 | CIV-10060 | Update CA1037 State report Revise line 8a logic | Policy Re-Design | High | New | CA-47600 | State/Fiscal Reports
132 | CIV-10385 | ACL 17-70 CAPI Clarification of the Indigence Exception Expiration Policy for Sponsor Immigrants | Policy Re-Design | Low | New | CA-51119 | CalWORKs/CalFresh
133 | CIV-10690 | C4Y: Update C4Yourself with latest SAWS 2 Plus form and appendices | Policy Re-Design | Medium | New | None | C4Yourself
134 | CIV-11690 | Update to Indicator 12 of the DHCS CMS Performance Indicators Master Data Request report in the C-IV System. | Policy Re-Design | Critical | New | CA-55584 | State/Fiscal Reports
135 | CIV-100039 | ACL 17-70E CAPI Indigence Exception Expiration Policy | Policy Re-Design | Medium | New | CA-51119 | Correspondence
136 | CIV-100174 | Update Medicare Savings Program (MSP) NOAs | Policy Re-Design | High | Design in Progress | CA-202460 | Correspondence
137 | CIV-100246 | Automate EDR processing for MAGI Customer Turning 65 | Policy Re-Design | Low | New | C-IV Specific | Medi-Cal/CMSP
138 | CIV-100432 | Update Cash Aid Time Limit Extender clock counts for Welfare to Work and CalWORKs | Policy Re-Design | High | New | CA-53782 CA-53784 | Time Limits
139 | CIV-100919 | Add Sample SAR7 to Template Respository and RE Packets | Policy Re-Design | High | New | CA-207892 | Correspondence
140 | CIV-101159 | Update Expedited Service Determination, Postponed Verification and Batch Discontinuance Process | Policy Re-Design | High | Design in Progress | CA-53789 | CalWORKs/CalFresh
141 | CIV-101397 | Phase I - Change CalFresh Notice of Actions - New CF 286 Budget Cont. Page and Remove CF Text on CW NOA | Policy Re-Design | High | New | CA-50316 | Correspondence
142 | CIV-101513 | ACL 16-79 Add a drop down menu for out of state short-term residential therapeutic program (STRTP) placements | Policy Re-Design | High | New | CA-203392 | Foster Care/Kin GAP/AAP
143 | CIV-101570 | ACL 18-43 - CALIFORNIA WORK OPPORTUNITY AND RESPONSIBILITY TO KIDS (CalWORKs): REVISED NOTICE OF ACTION MESSAGES: M40-107(C), M40-107(D) AND M40-107(G) | Policy Re-Design | Medium | New | CA-204115 | Correspondence
144 | CIV-102306 | Time Limit should not be counted for Non-Cal-Learn 19 Year old Custodial Parents | Policy Re-Design | High | New | CA-54665 | Welfare to Work/WPR
145 | CIV-103104 | Include ARC When Determining if a Non Minor Dependent was in FC on their 18th Birthday | Policy Re-Design | Critical | New |  | Foster Care/Kin GAP/AAP
146 | CIV-103252 | Remove the HEAR 302 CIV and replace with the DPA 315 | Policy Re-Design | Medium | New |  | Correspondence
147 | CIV-103281 | Separate Case & Issuance for CAPI Couple Case | Policy Re-Design | Critical | Design in Progress | CA-202055 | CalWORKs/CalFresh
148 | CIV-103745 | NOMI - Interview Completion Due date to be 30 days from application date | Policy Re-Design | High | Ready for Committee | CA-201756 | Correspondence
149 | CIV-105185 | Split â€œUnfit For Employmentâ€ and â€œPhysically/Mentally Incapacitatedâ€ Work Registration Exempt Status Reasons | Policy Re-Design | High | Ready for Committee | CA-210813 | CalWORKs/CalFresh

## Key
SCR Status Key |  | SCR Change Type Key
System Change Request (SCR) Status | Definition | SCR Change Type | Definition
New | Default status when an Issue is created | Data Change | This change type is selected for data change that impacts high volume of cases
Design in Progress | Indicates that the Team/Consortium Staff are working on the Design | Enhancement | This change type is selected for changes to existing design that are not new policy or policy re design.
Ready for Committee | Indicates the Design is ready for Committee to review/approve | Individual Data Change | This change tyhpe is selected for data changes that impacts low volumne of cases (less than 20)
Committee Review | Indicates the Committee is reviewing for approval | New Policy | This change type is selected for SCRs that have references to regulations or state policy letters that have not yet been integrated in the system.
Pending Approval | Indicates that the Issue is pending the approval of CCB. | Operational Enhancement | This change type is selcted for changes to the system that are county specific, impact a specific technology upgrade (ie. New EBT Printer, New Warrant Stock, FTP changes, DB Upgrade, etc.), or are only operational in nature (IP address change, configurational file changes, etc.)
Approved | Indicates that the Issue has been Accepted by the CCB and/or has been given Expedited Approval and build may begin. | Policy Re-Design | This change type is selected of the SCRs is requesting a change to existing design with a regualtion or state policy letter reference.
In Development | Indicates that the Issue is in the development phase
Development Complete | Indicates that the development team has completed development of the Issue
In Assembly Test | Indicates the development team has completed development of the Issue and Assembly Test is in progress
System Test | Indicates that the Issue is currently in System Test and all Test Conditions are being validated in System Test
Test Complete | Indicates that the Issue has been validated in System Test and all Test Conditions have passed System Test