## Slide 1: December 13, 2019
JPA Board of Directors Meeting

## Slide 2: Agenda
Call Meeting to Order
Public Opportunity to speak on items NOT on the Agenda. Public comments are limited to no more than three minutes per speaker, except that a speaker using a translator shall be allowed up to six minutes.
Note: The public may also speak on any Item ON the Agenda by waiting until that item is read, then requesting recognition from the Chair to speak.
Confirmation of Quorum and Agenda Review.

## Slide 3
Action Items

## Slide 4: Action Items
Approval of the Minutes and review of Action Items from the November 15, 2019 CalSAWS JPA Board of Directors meeting.

## Slide 5
Informational Items

## Slide 6
CalSAWS Schedule Impact Resulting from Functional Design Sessions Outcomes

## Slide 7: Revised CalSAWS DD&I Project Schedule
Background
Overview
Revised Schedule
Functional Area Overview
Next Steps
Agenda

## Slide 8: Revised CalSAWS DD&I Project Schedule
Background
As discussed at the September and November JPA and PSC meetings, the project team has been analyzing the outputs of the Functional Design Sessions and assessing options for integrating this new scope into the CalSAWS DD&I Project Schedule
In addition, the project team identified a risk related to the impact of adding this additional scope to the existing project schedule. Specifically, the risk is associated with implementing a large volume of changes in a short timeframe to meet the current deadlines, and the resulting impact on LA County users, the down steam migration activities (conversion, training, change management) and the quality of future releases.

## Slide 9: Revised CalSAWS DD&I Project Schedule
Overview
Develop a project schedule that:
Allows the 39 C-IV Counties to cutover to CalSAWS in September 2021
Provides CalSAWS functionality, including new requirements defined by the Functional Design Sessions, that meets the current business needs of the C-IV Counties
Allows for the development and implementation of additional capabilities needed for the CalWIN Counties after C-IV counties go-live
Incrementally builds out the CalSAWS requirements for the 57 counties, minimizing any throw away code
Completes CalWIN Counties rollout no later than December 2023
Assumptions:
Imaging will begin work in January, 2020 (pending JPA approval)
All other work begins in March, 2020 for the new scope required by the Functional Design Sessions and Foster Care
No changes to the LRS Agreement end date

## Slide 10: Revised CalSAWS DD&I Project Schedule
The following slide highlights a revised project schedule that assumes:
The 39 C-IV Counties cutover to CalSAWS in September 2021 (no change to this date)
  There would be no functional release during this cutover month
  There would be no technical release during the month after cutover
A phased approach, where appropriate, for the outstanding Functional Design Session scope:
  Focus on implementing requirements needed by the C-IV Counties to align CalSAWS functionality with current C-IV functionality prior to cutover (referred to as “Phase 1”)
  Phase in other features/functions needed by the CalWIN counties that may also be used by C-IV counties and LA County in the future. These would be developed and implemented prior to CalWIN UAT (referred to as “Phase 2”)
Revised Schedule

## Slide 11: Revised CalSAWS DD&I Project Schedule
Revised Schedule continued
Impacts to CalWIN Implementation Dates:
Shifts the first CalWIN wave from January 2022 to October 2022. All subsequent waves are adjusted accordingly
  No changes to the number of CalWIN waves was contemplated or requested at this time
  Adjustment to the timing of the second wave to avoid a cutover in a holiday month e.g. (November, December)

## Slide 12: Revised CalSAWS DD&I Project Schedule
Refer to Handout

## Slide 13: Revised CalSAWS DD&I Project Schedule
Functional Area Overview
The following slides will provide additional details for:
58 County Imaging
Task Management
Non State Forms
GA/GR
APIs
Ancillary Systems Conversions
Analytics: BIP/State Report Replatforming
Foster Care

## Slide 14: Revised CalSAWS DD&I Project Schedule
Functional Area Overview: Requirements Summary
Functional Design Session | Total Pre FDS | Total Post FDS | Estimated Total Effort+
Imaging | 24 | 42 | 87,000
Task Management | 39 | 32 | 39,500
Non State Forms | 2 | 114 | 38,000
GA/GR++ | 11 | 28 | 77,700
APIs | 3 | 37 | 15,800
Ancillary Systems Conversion | 4 | 50 | 37,000
Total New Requirements* | 83 | 303 | 295,000
The 303 FDS requirements are in addition to the existing ~600 requirements
+ Estimate is under review. Estimate includes the design, build, test, training, tech, and conversion activities as appropriate
++ Final solution is still under review

## Slide 15: Revised CalSAWS DD&I Project Schedule
Functional Area Overview: 58 County Imaging
Category | Description
Phase 1 | Deploy integrated imaging solution to the 39 C-IV Counties at go-live LA County continues to use EDMS interface (already integrated with CalSAWS)
Phase 2 | Deploy the integrated imaging solution to LA County prior to the CalWIN Wave 1 cutover Deploy the integrated imaging solution to each CalWIN County at their respective CalSAWS Cutover
Dependencies | Integration with task management and APIs

## Slide 16: Revised CalSAWS DD&I Project Schedule
Functional Area Overview: Task Management
Category | Description
Phase 1 | Core CalSAWS requirements to create a unified task management approach, inclusive of C-IV tasks and automated actions, along with integration with the 58 counties imaging solution (Releases 20.09-21.03)
Phase 2 | Additional capabilities (needed for the CalWIN counties and that will be available for all counties) will be implemented post C-IV cutover (Releases 21.05-22.01)
Dependencies | Integration with imaging. Downstream impacts to both conversion and training

## Slide 17: Revised CalSAWS DD&I Project Schedule
Functional Area Overview: Non State Forms
Category | Description
Phase 1 | Non State Forms in English and Spanish (Releases 20.11-21.05)
Phase 2 | Non State Forms in 13 threshold languages (Releases 21.07-22.07)
Dependencies | An approved English version of a form is required prior to obtaining translations

## Slide 18: Revised CalSAWS DD&I Project Schedule
Functional Area Overview: GA/GR
Category | Description
Phase 1 | Implement C-IV managed and non managed solution Generate the GA 237 for the 39 counties Send GA transactions to MEDS (Releases 20.11-21.03)
Phase 2 | Implement CalWIN Counties rules and integrate with GA Correspondence service (Releases 21.05-22.01)
Dependencies | Downstream impacts to both conversion and training
No changes to the LA County GA/GR program already integrated with the CalSAWS system

## Slide 19: Revised CalSAWS DD&I Project Schedule
Functional Area Overview: APIs
Category | Description
Phase 1 | Implement APIs related to task management and imaging (Releases 20.11-21.01)
Phase 2 | All other APIs (Releases 21.03-22.01)
Dependencies | Integration with task management and imaging
Functional Design Sessions were targeted at the 18 CalWIN Counties

## Slide 20: Revised CalSAWS DD&I Project Schedule
Functional Area Overview: Ancillary Systems Conversion
Category | Description
Phase 1 | N/A
Phase 2 | N/A
Dependencies | Extracts from source legacy systems by the counties in accordance with the target schema and conversion team schedule
Functional Design Sessions were targeted at the 18 CalWIN Counties for the following systems: Collections, Fraud, and QA/QC

## Slide 21: Revised CalSAWS DD&I Project Schedule
Functional Area Overview :
Analytics – BIP/State reports replatforming
Pending results of POC in late December 2019
Replatforming of reports may be prioritized based on:
Performance of the existing report with 40 county volumes
Legacy system reports that currently do not exist in LRS and must be ported from C-IV counties
Underlying application changes driving a reporting change

## Slide 22: Revised CalSAWS DD&I Project Schedule
Functional Area Overview:
Foster Care
Category | Description
Phase 1 | Update CalSAWS with additional data collection elements, eligibility rules, NOAs, State forms, reports, and fiscal processing One way, inbound interface with CWS. Replaces LA/LRS datamart with a direct interface from CWS to CalSAWS (Still being discussed)
Phase 2 | Integration with CWS-CARES System
Dependencies | Timing of the CWS-CARES System go-live. Downstream impact on training

## Slide 23: Revised CalSAWS DD&I Project Schedule
Other Consortium Decision Points
Decision | Description
58 County Portal Solution | Procurement pending. If the new 58 County portal is not available by September 2021, C4Yourself would need to be integrated with CalSAWS for the 39 C-IV Counties. YBN is already integrated with the CalSAWS system.
58 County Contact Center Solution | Pending Consortium decision on the solution. If the new 58 County Contact Center solution is not available by September 2021, integrate the C-IV Counties AWS Connect Contact Center solution with CalSAWS. The LA County Contact Center is already integrated with the CalSAWS system.

## Slide 24: Revised CalSAWS DD&I Project Schedule
Other Consortium Decision Points
Decision | Description
Central Print solution | Procurement pending for central print services for 56 of 58 counties. If the central print solution is not operational by September 2021, integrate existing C-IV Central Print services with the CalSAWS system LA County Central Print Services are already integrated with the CalSAWS system

## Slide 25: Revised CalSAWS DD&I Project Schedule
Next Steps
Review revised schedule with approval and funding entities (December 2019)
Finalize amendment documentation and budget documentation (December 2019)
Seek State and Federal approval of the Amendment for Functional Design Sessions and revised schedule (January/February 2020)
Seek JPA Board approval for the Amendment (February/March 2020)

## Slide 26
Status of Cambria Solutions Corrective Action Plan

## Slide 27: Status of Corrective Action Plan
Completed remediation of all impacted deliverables
General Design Document | Submitted on 11/27
Technical Design Document | Submitted on 12/4
Project Control Document | Submitted on 12/2
Work Plan | Submitted on 12/2
Master Test Plan | Submitted on 12/2
Proposal Supplement | Submitted on 12/3
Requirements Traceability Matrix | No Findings
Status Reports | No Findings
Other Work Products | No Findings
Walkthroughs have been conducted with the Consortium and QA Vendor

## Slide 28: Status of Corrective Action Plan
Trained all Cambria staff on developing of original content and citing where needed
Improved internal deliverable review and QA processes
Added use of tools to scan/check all documents
Require peer reviews
Added a QA Director
Cambria executives approval/submittal of deliverables
Quality Improvement steps

## Slide 29: Status of Corrective Action Plan
Tasks were added for CAP remediation work
Tasks for deliverable completion and resources allocations were impacted by remediation effort
Critical schedule milestones (e.g., UAT and Go-Live) remain unchanged
Technical Design Document
  Updates continue in collaboration with the Consortium and QA Vendor; DDEL will be submitted on 12/20
Schedule

## Slide 30
CalSAWS Quarterly Fiscal Update

## Slide 31: CalSAWS Financial Report – December 2019
Overview
Actuals to Date
Based on Vendor Invoices & County Claims
Projections (Estimates to Complete)
Estimated Costs for Future Months
Estimate at Completion (EAC)
Actual Costs Plus Estimated
Total Allocation/Budget
Amount Allocated by Line Item for the Approved Budget
Balance
Difference Between EAC and Budget
Positive balance is under budget Negative balance is over budget
% Expended to Date (Actuals)
Percent of Actuals to Date Divided by the Budget
% EAC to Budget
Percent of EAC Divided by the Budget
1
5
3
7
4
2
6
LRS M&O and Premise for 1 County
C-IV M&O and Premise for 39 Counties
CalWIN M&O and Premise for 18 Counties
CalSAWS DD&I and Premise for 58 Counties
(OCAT & Undocumented 19-25)

## Slide 33: CalSAWS Financial Report – December 2019
1Includes only Consortium Staff, does not include County Support Staff
2Includes RGS and CSAC employees
3Includes RGS, CSAC, and First Data Staff (Non-Employees)

## Slide 34: CalSAWS Financial Report – December 2019
1Includes only Consortium Staff, does not include County Support Staff
2Includes RGS and CSAC employees
3Includes RGS, CSAC, and First Data Staff (Non-Employees)
4Does not account for backfill considerations

## Slide 35: CalSAWS Financial Report – December 2019

## Slide 36: CalSAWS Financial Report – December 2019

## Slide 37
CalSAWS Staffing Update

## Slide 38: CalSAWS Staffing Update
Project Management Office (PMO)
  Fiscal/Contract Manager (1 long-term)
  Fiscal/Contract Analyst (2 long-term)
  PMO Analysts (2 long-term)
Common Services/PMO
  Procurement Manager (1 long-term)
  Procurement Analysts (2 long-term)
  Procurement Analysts (2 limited-term through January 2023)
Technical & Operations
  Cloud Analyst (1 long-term)
  Conversion Analyst (4 limited-term through January 2023)
Application Development & Test
  Release Coordinator (1 long-term)
  Release Coordinator (1 limited-term through January 2023)
Policy, Design & Application Development
  Business Analysts (4 limited-term through September 2021 or January 2023 depending on specific assignment)
Customer Engagement
  Implementation Manager (1 limited-term through January 2023)
  Implementation Coordinators (3 limited-term through January 2023)
  Trainers (3 limited-term through January 2023)
CIT 0084-19 Recruitment of CalSAWS Project Staff Closed Friday Nov. 29, 2019

## Slide 39: CalSAWS Staffing Update
Applicants
Team | Position | Applicants
Policy, Design, Governance and Application Development | Business Analyst | 16
Application Development | Release Coordinator | 18
Customer Engagement | Trainer | 18
 | Implementation Manager | 8
 | Implementation Coordinator | 12
Technical Operations | Cloud Analyst | 8
 | Conversion Analyst | 14
PMO/Common Services | Fiscal/Contract Analyst | 8
 | Procurement Analyst | 8
 | PMO Analyst | 17
 | Fiscal/Contract Manager | 2
 | Procurement Manager | 3
 | Total | 132
Note: 47 individual candidates applied for multiple positions

## Slide 40: CalSAWS Staffing Update
Select Candidates to Interview and Schedule Interviews 12/2 – 12/6
Interviews – 12/9 through 12/19
Identify selections 12/20
Notify Directors and Receive Director Confirmation 12/23 – 1/3
Notify Candidates 1/6 – 1/10
Candidates Accept/Reject 1/13-1/17
Contingency 1/20 - 1/31
Next Steps

## Slide 41
M&O Application and Policy Update
SSA COLA

## Slide 42: Policy Update
Able-Bodied Adults Without Dependents (ABAWD)
Policy Effective Date & State Policy Reference | C-IV/LRS Status | CalWIN Status | Implementation Details
1/1/2017 Fixed Clock 8/31/2019 Waiver Expires ACIN I-11-16 ACIN I-88-16 ACL 18-08 ABAWD Handbook ACL 19-93 ABAWD Handbook 2.0 | SCRs CIV-7215; CA-57971 Phase II Implemented Release 19.09 | PPM #46539- Implemented 8/2018 PPM #47411- Implemented 8/2018 PPM #51360 Implemented 8/19 PPM #52397 Design R60 (2/20) | FNS is working with the Western Region to discuss planning and preparation for the publication of the final rule on ABAWDs. FNS did not provide any information specific to what changes will be implemented in the final rule, but they did share that the Administration still has a December release date on the rulemaking calendar. When released, a relatively aggressive implementation timeline may be required by States. FNS mentioned that this timeline could be as little as 60-90 days from release of the final rule. This means that States could be expected to be in compliance as early as March 2020. California may be required to submit an updated waiver request under new waiver criteria. FNS has confirmed that our current waiver will be valid until final approval of the new waiver is received. If this is the case, CDSS will take the lead on submitting an updated waiver and will keep impacted counties in the loop. CDSS encourages counties to begin planning for implementation, but would limit these activities to planning that can occur ahead of a final rule as additional details will only come to light once the rule is finalized. -Continued on Next Slide-

## Slide 43: Policy Update
Medi-Cal Expansion for Young Adults
Policy Effective Date & State Policy Reference | C-IV/LRS Status | CalWIN Status | Implementation Details
1/1/2020 ACWDL 19-23 | SCRs CIV-103662; CA-206941 Implemented Release 19.09 SCRs CIV-104022; CA-208241 Implemented Release 19.09 Priority SCRs CIV-103874; CA-207950 Build Release 19.11 Priority SCRs CIV-104826;CA-209956 Design Release 20.03 | PPM #51191- Phase 1 Implemented R58B (9/19) PPM #51703- Phase 2 Implemented R59 (11/19) | CalSAWS Updates: The effort to turn on young adult expansion eHIT functionality and process a one-time batch EDBC run is tentatively scheduled to run on 11/27/2019. System down time is not required for this process. Batch EDBC memorandum call with the counites was held on 11/6/19. The batch EDBC memorandum provides details on the batch EDBC process, timeline, and list with county action for cases not processed by batch EDBC. The on-going monthly batch process will re-evaluate individuals for Medi-Cal due to aging out of young adult expansion aid codes. The first time this batch will run is in January 2020 for February 2020 benefit month. CIT 0098-19- CA-208241 ¦ CIV-104022: Posted List for Young Adult Expansion (YAE) Batch was posted to the CalSAWS web portal on 12/2/19. The purpose of this CIT was to inform the counties of posted lists associated to CA-208241¦CIV-104022 (One-time Batches to Transition Young Adults from Restricted Scope to Full Scope Medi-Cal). Three one-time lists have been posted to the CalSAWS Web Portal for County follow-up of the Young Adult Expansion population who remain in restricted scope Medi-Cal after the automated transition batch processing is complete or where a program or person were discontinued. -Continued on Next Slide-

## Slide 44: Policy Update
Medi-Cal Expansion for Young Adults
Policy Effective Date & State Policy Reference | C-IV/LRS Status | CalWIN Status | Implementation Details
1/1/2020 ACWDL 19-23 | SCRs CIV-103662; CA-206941 System Test Release 19.09 SCRs CIV-104022; CA-208241 Build Release 19.09 SCRs CIV-103874; CA-207950 Committee Review Release 19.11 Priority SCRs CIV-104826;CA-209956 Design Release 20.03 | PPM #51191- Phase 1 Implemented R58B (9/19) PPM #51703- Phase 2 Implemented R59 (11/19) | CalSAWS County Business Impact: Train staff on changes to system functionality Manually process the cases not processed in the batch EDBC CalWIN Update: Phase 1: Notice of action changes Aid code rule changes to account for the increased age limit Batch triggers inserted for applicable cases for 1/2020 effective date Phase 2: Batch EDBC run will be scheduled for late November to identify individuals meeting the new criteria and grant full scope eligibility. Notice of Action snippets for Non-MAGI, such as MC 239P, MC 239Q and MC 239S. Client Correspondence maintenance Service Requests (SRs) opened for translations to be implemented. MAGI – SR #626668 and Non-MAGI – SR #627578. CalWIN County Business Impact Exception lists will be provided for county action for cases not processed by the batch run.

## Slide 45: Policy Update
Social Security Admin (SSA) Cost of Living
Policy Effective Date & State Policy Reference | C-IV/LRS Status | CalWIN Status | Implementation Details
1/1/2020 ACWDL 19-24 ACIN I-67-19 | CIV-100451/CA-200824 Test Release 19.11 CIV-105046/CA-210439 Build Release 19.11 | PPM #53339 Design/testing December 2019 | Social Security Administration has approved a 1.6 percent Cost of Living Adjustment (COLA) for 2020. Based on the increase in the Consumer Price Index (CPI-W) from the third quarter of 2018 through the third quarter of 2019, Social Security and Supplemental Security Income (SSI) beneficiaries will receive a 1.6 percent increase. On 11/14/19, SAWS met with DHCS to discuss streamlining the release of policy guidance for the Social Security Administration cost of living adjustment and the annual changes to the federal poverty limits. DHCS is going to publish ACWDL as updates become available. On 12/6/19, CDSS provided the following guidance: For the county to take a “county initiated action” there must be enough information available for the county to accurately take action on the CalFresh (CF) budget. Because SAWS does not maintain each household’s standard SSI income amount (i.e. the SSI income amount before any deductions or other adjustments are made) or the household’s most recent SSI income amount paid per SSA, there is not enough available information for the county to accurately apply the SSI COLA increase to the CF budget. Therefore, CDSS has instructed SAWS to not take any action on CalFresh cases as a result of the 1/1/20 SSI COLA. -Continued on next slide-

## Slide 46: Policy Update
Social Security Admin (SSA) Cost of Living
Policy Effective Date & State Policy Reference | C-IV/LRS Status | CalWIN Status | Implementation Details
1/1/2020 ACWDL 19-24 ACIN I-67-19 | CIV-100451/CA-200824 Test Release 19.11 CIV-105046/CA-210439 Build Release 19.11 | PPM #53339 Design/testing December 2019 | CDSS, SAWS and DHCS are meeting on December 10, 2019 to explore whether it would be possible to act on the updated SSI payment information that is received from SSA. This SSI payment information is only in available MEDs. CDSS is working thought the details of the QC error risk and will get information out the counties as is becomes available. On 12/5/19, SCR CIV-100451 added/updated the SSI/SSP and SSI Only Other Program Assistance (OPA) records for CF participants to bring the SSI amount to the payment standard for the C-IV counties. Due to the CDSS guidance, SCR CIV-105832 (Reverse the Data Changes applied to OPA Detail SSI Amount) was created to reverse the OPA updates. This change is targeted for implementation on 12/12/19. A CIT with a list of CalFresh cases where EDBC has been processed between 12/5/2019 and implementation date of this SCR will be made available to the counties. The CIT will include county action for processing cases on the list. -Continued on next slide-

## Slide 47: Policy Update
Social Security Admin (SSA) Cost of Living
Policy Effective Date & State Policy Reference | C-IV/LRS Status | CalWIN Status | Implementation Details
1/1/2020 ACWDL 19-24 ACIN I-67-19 | CIV-100451/CA-200824 Test Release 19.11 CIV-105046/CA-210439 Build Release 19.11 | PPM #53339 Design/testing December 2019 | CalSAWS Update: The following changes were implemented 12/12/19: Added the new SSA income amount effective 1/1/2020. Updated the value of the 'Backout Multiplier' to match the rate increase. Updated the Pickle values to match the 'Pickle Disregard Computation Chart' effective 1/1/2020. Updated the SSI/SSP payment standards Updated the Medicare Part B Premium amounts in the system to the new values. Created a Journal entry to document the data changes for SSA Income and Medicare Part B Premium amounts. This journal entry was applied to all applicable cases. The batch EDBC process to apply the SSA COLA change to the applicable cases will run for LA and the C-IV counties on 12/14/19. CalFresh cases with SSI/SSP or SSI only income will NOT be included in the batch process on 12/14/19. The C-IV System will be available until 5pm on 12/14/19. CalSAWS County Business Impact: All Counties, refer to CIT XX-19 to manually process the cases not processed in the batch EDBC. This CIT is scheduled to the published on 12/16/19. -Continued on next slide-

## Slide 48: Policy Update
Social Security Admin (SSA) Cost of Living
Policy Effective Date & State Policy Reference | C-IV/LRS Status | CalWIN Status | Implementation Details
1/1/2020 ACWDL 19-24 ACIN I-67-19 | CIV-100451/CA-200824 Test Release 19.11 CIV-105046/CA-210439 Build Release 19.11 | PPM #53339 Design/testing December 2019 | CalWIN Update: CalWIN COLA process targeting to be run December 14th and 15th, 2019 for SSA COLA. Related a CAPI COLA will be run December 14, 2019 (PPM# 53122). To minimize the impact to county workers, CalWIN will apply the Social Security increase by updating all cases with SSA income by the percent of the increase, to all programs and all cases where at least one individual is receiving Social Security benefits. The SSI increase will not be applied. CalWIN will not run the SSA COLA on MAGI-Only Medi-Cal and Mixed (APTC/MAGI) Medi-Cal cases. CalWIN County Business Impact Manually process the cases not processed in the batch EDBC.

## Slide 49
Imaging Solution Benchmarks, Performance Standards, and Testing Standards/Phases

## Slide 50
2021
2023
Today
Feb
May
Aug
Nov
Feb
May
Aug
Nov
Feb
C-IV Go-Live
Sep 1
LRS Go-Live
Nov 1
CalWIN Wave 1 Go-Live
Feb 1
CalWIN Wave 2 Go-Live
May 1
CalWIN Wave 3 Go-Live
Aug 1
CalWIN Wave 4 Go-Live
Oct 1
CalWIN Wave 5 Go-Live
Dec 1
CalWIN Wave 6 Go-Live
Feb 1
Performance Test 1
Feb 14
Performance Test 2
Jul 15
Performance Test 3
Dec 15
Performance Test 4
Mar 15
Performance Test 5
Jun 15
Performance Test 6
Nov 15
Test # | County Volume Included in Test
1 | C-IV & LRS
2 | C-IV, LRS & CalWIN Wave 1, 2, 3, 4, 5 & 6
3 | C-IV, LRS & CalWIN Wave 1, 2, 3, 4, 5 & 6
4 | C-IV, LRS & CalWIN Wave 1, 2, 3, 4, 5 & 6
5 | C-IV, LRS & CalWIN Wave 1, 2, 3, 4, 5 & 6
6 | C-IV, LRS & CalWIN Wave 1, 2, 3, 4, 5 & 6
NOTE: Document migration activities will kick off once the amendment is approved. Testing the performance of importing documents will be completed during this time.

## Slide 51: Service Level Agreements – Performance SLAs
Hyland | 
Monthly Uptime: (Percentage) | 99.90%
Document View: (Percentage) | 90% < = 2 seconds per page
Database Transactions: (Percentage) | 90% <= 1 seconds per transaction
Intelligent Capture Document Processing: (Pages per Hour) | 90,000 Pages Processed
Assumptions:
SLAs do not account for failures due to faults (such as availability, performance or security) with the Amazon Web Services (“AWS”) or Telecommunication providers (including Cloud Exchange providers).
The SLAs in the table below are the responsibility of Hyland.

## Slide 52: Service Level Credits
Hyland |  | 
Monthly Uptime Percentage Service Level Credits | Monthly Uptime Percentage Service Credit Ranges and Applicable Credit Determinations | 99.89-99.00% 10% of the Monthly SaaS Fees
 |  | Less than 99.00% 20% of the Monthly SaaS Fees
Monthly Page View Percentage Target | Page View Service Level Credit | 3.5% of the Monthly SaaS Fees
Monthly Database Transaction Percentage Target | Database Transaction Service Level Credit | 3.5% of the Monthly SaaS Fees
Monthly Intelligent Capture Document Processing Percentage Target | Intelligent Capture Document Processing Service Level Credit | 3.5% of the Monthly SaaS Fees
The credits in the table below are the responsibility of Hyland.
(SaaS is “Software as a Service”.)

## Slide 53: Imaging Solution
Bottomline: Accenture as prime contractor is responsible for delivery of the Imaging solution. To receive payment, Accenture must first receive acceptance and approval of the work. Acceptance requires that the solution meet the Requirements, including performance requirements, that are included in the contract. In addition, timely delivery is enforced by liquidated damages that may be imposed on Accenture if the overall Implementation dates are delayed.
Exhibit Z expressly provides that “all Work performed pursuant to Exhibit Z shall be subject to the terms and conditions of the Agreement, unless otherwise expressly stated in this Exhibit Z.” Thus, the Imaging Project has become part of the Work required of Contractor to deliver the CalSAWS System.
Consortium Approval of Work (Section 4.2)
  “All Deliverables, M&O Services, M&E Services and work on the CalSAWS Project provided by CONTRACTOR must have the approval of CONSORTIUM Executive Director…”
Right to Reject (Section 4.7)
  “CONSORTIUM reserves the right to reject any Tasks, Subtasks, Deliverables, goods, or services not approved by CONSORTIUM pursuant to Subparagraph 4.2 or other provisions of this Agreement.”
LEADER Replacement System and CalSAWS System (Section 4.4)
  “CONTRACTOR shall provide the LEADER Replacement System and CalSAWS System to CONSORTIUM in accordance with the terms and conditions set forth in this Agreement.” The definition of CalSAWS System (1.4.19) notes that “Reference to the CalSAWS System may include one or more components thereof or the entire CalSAWS System.”
Contract Protections

## Slide 54
Procurement Update
Portal/Mobile RFP
CalWIN OCM & Training RFP

## Slide 55: CalSAWS Statewide Portal/Mobile Application
Strategy, Scope and Timeline
Timeline
Procurement Event | Date
Released RFP | November 4, 2019
Conducted Bidder’s Conference Sacramento County Department of Human Assistance | November 20, 2019 10:30am-12:00pm
Published RFP Addendum 1 Based on 14 Vendor Questions and Answers | November 26, 2019
Received 136 Additional Vendor Questions | December 3, 2019
Publish RFP Addendum 2 and Responses to All Vendor Questions | By December 16, 2019
Contractor Proposal Due Date | January 22, 2020
Evaluate Proposals and Prepare Vendor Selection Report | January 23 – April 22, 2020
Contract Negotiations | April 27 – May 5, 2020
State, Federal and JPA BOD Approval of Agreement | May 7 – August 7, 2020
Start Date of Statewide Portal/Mobile App Vendor | August 10, 2020
Portal/Mobile App Go-Live | September 2021

## Slide 56: CalWIN Training, OCM & Implementation Support
Strategy
  Conduct an open procurement to acquire vendor services to provide Training, OCM and Implementation Support for the 18 CalWIN counties.
  CalWIN to CalSAWS migration is expected in 6 waves beginning January 2022 and continuing through January 2023
  CalWIN to CalSAWS migration must address multiple combinations of ancillary systems and business processes.
Scope and Key Objectives
  The Consortium is seeking a Contractor to apply innovative strategies, approaches, and methods for leading the cultural and organizational changes the CalWIN Counties will experience in transforming from their existing state and assimilating into the CalSAWS environment. This effort includes completing the transition from the CalWIN decentralized County-based support model to the CalSAWS regional structure for governance and ongoing system support.
  Prepare the CalWIN Counties to transition from using the CalWIN application and supporting business processes to using the CalSAWS application.
  Ensure each County’s As-Is business processes are documented and analyzed in order to prepare for changes, To-Be business processes, resulting from adoption of the CalSAWS application.
  Conduct a county-specific As-Is and To-Be gap analysis to create a foundation for OCM and communication with internal stakeholders including labor organizations and other County departments.
  Support county-specific business process change resulting from ancillary system choices.
  Ensure county-specific Training is developed to address changes in business processes.
  Where possible, leverage and adopt standard CalSAWS application Training as the target for transition.
Strategy, Scope and Timeline

## Slide 57: CalWIN Training, OCM & Implementation Support
Strategy, Scope and Timeline
PROCUREMENT EVENT | DATE
Federal RFP Review and Approval | October 20 – December 13, 2019
RFP Release | December 17, 2019
Bidder’s Conference Sacramento County Department of Human Assistance 4450 East Commerce Way Sacramento, CA | January 7, 2020, 10:30am – 12:00pm
Contractor Proposal Due Date | February 19, 2020
Evaluate Proposals and Prepare Vendor Selection Report | February 20 – May 18, 2020
Consortium Issues Notice of Intent to Award | May 19, 2020
Contract Negotiation Period | May 21 – June 2, 2020
Federal, State and Consortium JPA Board of Directors Approval of Agreement | June 5 – August 28, 2020
Planned Start Date of CalWIN Contractor | August 31, 2020

## Slide 58
Adjourn Meeting