## South - CCB Approved
No. | SCR | Summary | Change Type (SCR) | Priority | Status | Release | Minor Version | Other Agency Cross Reference | Committee / WorkGroup
1 | CA-209290 | Mobile App Issue Due to iOS 13 Release in Fall 2019 | Operational Enhancement | High | Approved | RWR
2 | CA-209151 | Enforce Data Integrity during Accept EDBC | Enhancement | Medium | New | TBD |  |  | Medi-Cal/CMSP
3 | CA-212039 | Update YBN downtime message page with external links and phone numbers | Operational Enhancement | High | New | TBD |  | CIV-105722
4 | CA-208817 | App Server storage issues, change temp file storage location | Operational Enhancement |  | In Development | 19.09 | 19.XX.XX |  | Tech
5 | CA-208841 | Automated Regression Test - Transaction Backlog - Phase 3 | Operational Enhancement | Medium | In Development | 19.11 | 19.12.XX |  | Other
6 | CA-212015 | ACIN X-XX-19 2020 CAPI COLA - Batch EDBC | New Policy | Medium | Design in Progress | 19.11 | 20.01.10 |  | CalWORKs/CalFresh
7 | CA-200882 | ACIN X-XX-19 2020 CAPI COLA | New Policy | Medium | Design in Progress | 19.11 | 20.01.10 |  | CalWORKs/CalFresh
8 | CA-49736 | Clean-up of MC Program Block for Individuals Active on CW | Enhancement | Critical | Development Complete | 19.11 | 20.01.10 | CIV-102308 | Medi-Cal/CMSP
9 | CA-211697 | ACL 19-50 FNS 209 and FNS 209 Line 3b Backup Report Enhancement | New Policy | High | Design in Progress | 19.11 | x | CIV-105596 | State/Fiscal Reports
10 | CA-210328 | Automated Regression Test - Execution and Maintenance - 19.11 Release Cycle | Operational Enhancement | Medium | System Test | 19.11 | 20.01.XX | CIV-104997 | Other
11 | CA-207950 | CalHEERS eHIT: Young Adult Expansion - Age Reevaluation Updates | New Policy | High | Development Complete | 19.11 | 20.01.10 | CIV-103874; CH-139211 | Medi-Cal/CMSP
12 | CA-200824 | 2020 Social Security Title II and Title XVI Cost of Living Adjustments (SSA COLA) | New Policy | High | Development Complete | 19.11 | 19.12.12 | CIV-100451 | CalWORKs/CalFresh, Foster Care/Kin GAP/AAP, Medi-Cal/CMSP
13 | CA-204417 | ACL 07-16 Direct Certification (DC) for a New Local Education Agency (LEA) Snowline Joint Unified School District | New Policy | High | System Test | 19.11 | 19.12.05 | N/A
14 | CA-209498 | ACIN I-41-19 STAT 47 - Exclude CFAP Participants | New Policy | High | Development Complete | 19.11 | 19.12.12 | CIV-104608 | State/Fiscal Reports
15 | CA-211992 | Update the NA 840A Page Generation Logic | Enhancement | Critical | System Test | 19.11 | 19.12.05 |  | Correspondence
16 | CA-210439 | Batch EDBC to apply 2020 SSA Cost of Living Adjustments (COLA) | New Policy | High | Development Complete | 19.11 | 19.12.14 | CIV-105046 | CalWORKs/CalFresh, Foster Care/Kin GAP/AAP, Medi-Cal/CMSP
17 | CA-211223 | CalFresh $0 Allotment Discontinuance Batch Run/List | Enhancement | High | System Test | 19.11 | 19.12.07 |  | CalWORKs/CalFresh
18 | CA-212038 | 2020 MEDS Renewal and Recon Schedule | Operational Enhancement | Medium | New | 19.11 | 19.12.12 | CIV-105719 | MEDS
19 | CA-206224 | ACIN I-55-19 - 2020 State Minimum Wage Run Batch EDBC | New Policy | High | Development Complete | 19.11 | 19.12.14 | CIV-103088 | CalWORKs/CalFresh
20 | CA-211451 | Automated Regression Test - Execution and Maintenance - 20.01 Release Cycle | Operational Enhancement | Medium | Approved | 20.01 | 20.03.XX | CIV-105458 | Other
21 | CA-210148 | Update CalHEERS Outbound Mappings for 'Educational, Student' Income Category | Enhancement | High | System Test | 20.01 |  | CIV-104902 | Medi-Cal/CMSP
22 | CA-210591 | Update LA County Accounting String Information for Refunds from FC Trust Fund Accounts | Operational Enhancement | Medium | System Test | 20.01 |  |  | Fiscal
23 | CA-208930 | Outbound Text - Inbound Reader Interface | Enhancement | Low | System Test | 20.01 |  | N/A | IVR & Contact Center
24 | CA-49308 | DCFS: Create a task when child goes from AAP to FC | Enhancement | Medium | System Test | 20.01 |  | N/A | Foster Care/Kin GAP/AAP, Task Management
25 | CA-204814 | Update WDTIP Outbound file writer to not allow LD02 transactions to be generated for WTW supportive services participation records | Enhancement | Critical | System Test | 20.01 |  | CIV-541 | Time Limits
26 | CA-49842 | Change all outbound calls data file format to accommodate participant appointment date/time. | Enhancement | Medium | System Test | 20.01 |  | N/A | IVR & Contact Center
27 | CA-57044 | Add IHSS and In-Kind Earned income to the IFDS (IFD115) Quarterly Outbound file (C-IV SIR #9156) | Enhancement | Medium | System Test | 20.01 |  | CCM-9156 | IEVS
28 | CA-211614 | Enhance Architecture LDAP (Lightweight Directory Access Protocol) framework to support OID (Oracle Internet Directory) interaction independent of OVD (Oracle Virtual Directory) | Operational Enhancement | Medium | System Test | 20.01
29 | CA-204326 | Transitional CalFresh Eligibility Updates | Enhancement | Medium | System Test | 20.01 |  | CIV-102404 | CalWORKs/CalFresh
30 | CA-201575 | CF - FTP INS Document, Income of FRE should be prorated | Policy Re-Design | High | System Test | 20.01 |  | CIV-101430 | CalWORKs/CalFresh
31 | CA-205982 | Update CW EDBC to Remove Stepsibling or Half-Sibling Excluded from CalWORKs in the CalFresh Budget | Policy Re-Design | Critical | System Test | 20.01 |  | CIV-102946 | CalWORKs/CalFresh
32 | CA-205286 | Updates to the MEDS Critical and ZZZ Alerts Reports | New Policy | High | In Development | 20.01 |  |  | Management Reports
33 | CA-211801 | Upgrade OAM to version 11.1.2.3 and upgrade OHS and OAM to RHEL7 | Operational Enhancement |  | System Test | 20.01
34 | CA-209050 | Add MC Annual Renewal NOA Variable Threshold Population | Enhancement | High | System Test | 20.01 |  |  | Correspondence
35 | CA-208258 | ACL 18-107, ACL 18-108 - SNB/TNB Forms and Notices - Threshold Languages Phase 2 | New Policy | Critical | System Test | 20.01 |  | CIV-104036 | Correspondence
36 | CA-51131 | Enhance the Employment Summation and Employment Summation Detail Reports | Enhancement | Medium | Development Complete | 20.01 |  | CIV-100733 | Management Reports
37 | CA-206520 | Automate SAWS 30 - IEVS Employment and Income Verification Form | Enhancement | High | System Test | 20.01 |  | CIV-103772 | IEVS
38 | CA-201036 | ACL 18-15 Last Date of Payment for Extended Foster Care, ARC and Kin-GAP | New Policy | High | System Test | 20.01 |  | CIV -100500 | Foster Care/Kin GAP/AAP
39 | CA-207080 | Eliminate EDD Registration Requirements for General Relief Program | Enhancement | High | System Test | 20.01 |  |  | GA/GR
40 | CA-205512 | Update Office Location on system generated Benefit Reductions and Offset Transactions | Enhancement | High | Development Complete | 20.01 |  | CIV-101423 | Collections
41 | CA-209076 | Enhance Refused Verification functionality to send failed Admin Verif | Enhancement | Medium | System Test | 20.02 |  | CIV-104268 | Medi-Cal/CMSP
42 | CA-210381 | CalHEERS eHIT: Update Interface Schema to version 14 | Enhancement | High | System Test | 20.02 |  | CIV-105016; CH-140031 | Medi-Cal/CMSP
43 | CA-206994 | CalHEERS eHIT: Add Spousal Support Agreement/Modification Date | Enhancement | Medium | System Test | 20.02 |  | CH-138728; CIV-103599 | Medi-Cal/CMSP
44 | CA-209661 | Update Previous Potential Benefit Calculation logic | Enhancement | High | Committee Review | 20.03 |  | CIV-104671 | Collections, State/Fiscal Reports
45 | CA-204496 | SB 1341 All County Solution Phase 2 - Updates to the flow of mixed Non-MAGI/MAGI NOAs | Enhancement | Medium | Approved | 20.03 |  |  | Correspondence, Medi-Cal/CMSP
46 | CA-205441 | Add Need Categories for Family Stabilization and Housing Support to Needs Detail page | Enhancement | High | Approved | 20.03 |  | CIV-10075 | Fiscal
47 | CA-209381 | Add Medi-Cal Negative Action Reason 'Worker Initiated-Skip CalHEERS' | Enhancement | Medium | Approved | 20.03 |  | CIV-5165 | Medi-Cal/CMSP
48 | CA-205652 | Change Recovery Account Cause Code editing logic | Enhancement | High | Approved | 20.03 |  | CIV-9947 | Collections
49 | CA-57298 | ACL 14-12, CFL 13/14-35 Family Stabilization Program for CalWORKs | New Policy | High | In Development | 20.03 |  | CIV-789 and CIV-10075 | Welfare to Work/WPR
50 | CA-205328 | ACL 18-92, ACL 18-107 Transitional Nutrition Benefit Program Recertification | New Policy | Critical | Approved | 20.03 |  | CIV-102568 | CalWORKs/CalFresh
51 | CA-208261 | ACL 18-107, ACL 18-108 - SNB/TNB Forms and Notices - Threshold Languages Phase 3 | New Policy | Critical | In Development | 20.03 |  | CIV-104040 | Correspondence
52 | CA-54659 | Update WIS Establishment Logic for CalFresh Recovery Accounts | Operational Enhancement | High | New | 20.05 |  | CIV-5503 implemented Release 17.11 | Collections
53 | CA-58934 | Aligning Status Begin Date of Associated Programs With Primary Cash Aid Programs or EDBC Run Date, whichever is later | Enhancement | High | Approved | 20.05 |  | CIV-66 | Welfare to Work/WPR
54 | CA-211200 | Modify Existing Report | Enhancement | High | Approved | 20.05 |  | CIV-103387 | Other
55 | CA-58123 | Prevent Advancing Medi-Cal Renewal with a Soft Pause Individual | New Policy | Critical | Committee Review | 20.06 |  | CIV-10791 | Medi-Cal/CMSP
56 | CA-208386 | Content Development on CalSAWS.org | Operational Enhancement |  | Approved | 20.06 | 20.06.30 |  | Other

## South - SPG Approved
No. | SCR | Summary | Change Type (SCR) | SPG Priority | Status | Other Agency Cross Reference | Committee / WorkGroup
1 | CA-210580 | Automate the creation of months for Supportive Service recipients | Enhancement | Critical | Design in Progress | CIV-661
2 | CA-209638 | Add Threshold Languages for FC/KG CNI NOA Fragment | Enhancement | High | Design in Progress | CIV-104665 | Correspondence
3 | CA-202920 | Strategic Plan -Case Alignment Phase III- All Active Eligibility Programs (GR/CF/MC) with multiple program blocks in all districts will be aligned under a single worker | Enhancement | High | New |  | Usability
4 | CA-202482 | Update 206-Cal-Learn Time Limit Exemption to apply to WTW time clock | Enhancement | High | New | CIV-101174 | Time Limits
5 | CA-201709 | Updates to Change Reason Mid-period addition of Individual | Enhancement | High | New |  | CalWORKs/CalFresh
6 | CA-201742 | CF 296 - Changes in logic for Line 10 - Overdue Recertifications (CWD Caused) during the month. | Enhancement | High | Design in Progress | CIV-100845 | State/Fiscal Reports
7 | CA-201569 | Place Holder SCR to update the Imprest Cash functionality in Issued Valuable Inventory Report | Enhancement | High | New | CIV-11257 | State/Fiscal Reports
8 | CA-202110 | WTW 25/25A State Reports - Modifications | Enhancement | Critical | New | CIV-102056 | State/Fiscal Reports
9 | CA-201656 | OBIEE: Caseload Inventory Report Program Persons | Enhancement | High | New | CIV-675 | Management Reports
10 | CA-200895 | Update the Rescind Logic to accommodate for overlapping rescinded periods | Enhancement | Medium | New | C-IV 450, C-IV 331 | CalWORKs/CalFresh
11 | CA-50782 | Enhance the Initial Search Screen of the Audit Tool | Enhancement | High | Design in Progress | Specific to LRS | Other
12 | CA-201250 | YBN External Mobile App - add Analytics | Enhancement | Medium | New |  | Tech
13 | CA-48755 | Child care Task Assignment Addendum | Enhancement | High | New |  | Child Care
14 | CA-50780 | Additional Detail for Audit Application Report | Enhancement | High | Ready for Committee | Specific to LRS | Other
15 | CA-53607 | Add Form Trigger Reasons for the CL 3 and CL 4 / NA 290 - Cal-Learn and replace TEMP CL1 Spanish with CL1 Spanish | Enhancement | High | Design in Progress
16 | CA-58455 | Data Change Request - Void Pending Approval Recovery Accounts | Enhancement | High | New |  | Collections
17 | CA-51448 | Add Time Tracking Report to CalACES Audit Application | Enhancement | High | Design in Progress |  | Other, Tech
18 | CA-49410 | Allow Users to Authorize Multiple Transportation Types for Overlapping Periods | Enhancement | Medium | Design in Progress | CA-50300 | Welfare to Work/WPR
19 | CA-53787 | WTW 24 MTC - Update Tracking of Voc Ed (Priority 11) | Enhancement | Critical | New |  | Time Limits
20 | CA-52880 | Additions to Person, Vendor, Invoice Search Criteria; Modifications on the Money Management Resource Detail Page and On the on the Select Service and Provider Page | Enhancement | Medium | Design in Progress | LA County request for GA/GR program | Fiscal
21 | CA-50543 | IEVS Criminal Assignment and processing | Enhancement | High | Design in Progress | CIV-102716 | IEVS
22 | CA-58124 | LRS Dashboard Applications Report to include (CBO) Agency code for each DPSS program | Enhancement | Medium | New | CIV-100782 | Management Reports
23 | CA-47600 | Update CA1037 State report Revise line 8a logic | Enhancement | High | New | CIV-10060 | State/Fiscal Reports
24 | CA-52597 | CA 812 Collections Enhancement Report | Enhancement | High | Design in Progress | CIV-12446 | Collections, State/Fiscal Reports
25 | CA-53786 | WTW 24 MTC - Update WTW 24 MTC from Verified Actual Hours (Priority 10) | Enhancement | Critical | New | CIV-102291 | Time Limits
26 | CA-48348 | Extension of Time-Period for Dropping the Worker on Discontinued Eligibility Programs | Enhancement | Critical | Design in Progress |  | CalWORKs/CalFresh
27 | CA-52872 | Jail Match Interface for All Programs | Enhancement | Medium | Design in Progress | LA County Specific | Other
28 | CA-56515 | Stop Benefit Reductions/Offsets on Zero or Negative Recovery Accounts | Enhancement | High | New |  | CalWORKs/CalFresh, Collections
29 | CA-51876 | LRS Ancillary Pages: Modify the LRS Service Arrangement Detail Page, Service Type Description box to allow for the itemization of ancillary items requested under the Ancillary-Education category, instead of the current text box. | Enhancement | Medium | Design in Progress |  | Welfare to Work/WPR
30 | CA-55206 | Redesign FC Facility Ratios page ? Need to store historical ratio info based on the eff. date for Group Home and Foster Family Agency type | Enhancement | High | New | CIV-102423 | RDB
31 | CA-57104 | GR Self-Employment Expense Calculations | Enhancement | Medium | New |  | GA/GR
32 | CA-55200 | Update WEX/CS WorkSheet Detail Page | Enhancement | Medium | Design in Progress | CIV-533 | Welfare to Work/WPR
33 | CA-53326 | Add process for all WebService Interfaces to queue up when partner's system is down, for both scheduled and unscheduled downtime. | Enhancement | High | New |  | ICT, Imaging
34 | CA-48412 | IHSS IPW Referrals/Auto Generate MEDI-CAL Application | Enhancement | Medium | Design in Progress |  | Medi-Cal/CMSP
35 | CA-55693 | Create an additional CalHEERs column for the Medi-Cal Pending Applications Report in Business Intelligence/DPSSTATS | Enhancement | High | New | CIV-100785 | Management Reports
36 | CA-54848 | Phase III- Change CalFresh NOAs add ineligible person names in Term NOAs, Add TCF NOA for Fleeing Felon | Enhancement | High | New | LA County Specific-Transitional CF fleeing felon NOA already exist in CIV | Correspondence
37 | CA-54520 | CIV-100748 CalFresh Churn Trends Report for District Offices | Enhancement | High | New | CIV-100748 | Management Reports
38 | CA-58963 | Revisions to the Medicare Savings Programs (MSP) Notices of Action (NOAs) 1 of 1 | Enhancement | High | New |  | Correspondence
39 | CA-51884 | Reports - Resource Data Bank - Service Providers with a Status of Close or an end date within the next 6 months. | Enhancement | Medium | New |  | RDB
40 | CA-56693 | DCFS - Enhance the MEDS Journal Detail Exception Report | Enhancement | Medium | New | LA County Specific | Management Reports
41 | CA-55208 | Changes to the Child Care Requests page | Enhancement | High | New |  | Child Care
42 | CA-58777 | Create BI Dashboard that identifies entry source for SAR 7, QR-7, Recertification/Redetermination/Renewal/Reevaluation (RC/RD/RN/RE) | Enhancement | Medium | New | CIV-100783 | Management Reports
43 | CA-53456 | DCFS: LRS to accommodate various licensing statuses per license number, instead of per vendor number. | Enhancement | High | New | CIV-102416 | RDB
44 | CA-52756 | Modify duplicate payment logic | Enhancement | High | New |  | Foster Care/Kin GAP/AAP
45 | CA-50091 | SB 1147 - Juvenile Probation Interface | Enhancement | Low | Design in Progress | LA County Specific | Medi-Cal/CMSP
46 | CA-51491 | Modify LRS Functionality to Not Require Adding a Homeless Temp or Homeless Perm Program When Processing Supplemental Housing Assistance Programs. | Enhancement | High | New |  | CalWORKs/CalFresh
47 | CA-47915 | DCFS: Send Medi-Cal to MEDS for AAP with $0 Authorized Amount 01/14/16 AA - Priority confirmed by RE | Enhancement | Medium | New |  | MEDS
48 | CA-55143 | Phase III - Modify and Add Validations to run EDBC for the Correct RE/SAR/QR Submit Month | Enhancement | High | New | CIV-702 | CalWORKs/CalFresh
49 | CA-51726 | Modifications to Benefit Recovery Management Report | Enhancement | Medium | Design in Progress |  | State/Fiscal Reports
50 | CA-57647 | Monthly CalFresh New Applications District Office, Your Benefits Now (YBN) and Customer Service Center | Enhancement | High | New |  | Management Reports
51 | CA-58006 | LRS mapping for domestic abuse/child abuse to LRS case from eapp screen. | Enhancement | Medium | New | LA County Specific | C4Yourself, Usability
52 | CA-54164 | Update Sanctions Dashboard Reports/Data in DPSSTATS Data Warehouse Homepage | Enhancement | Medium | Design in Progress |  | Management Reports
53 | CA-52751 | Create a daily outbound file for Families and Children's Index (FCI) | Enhancement | Medium | Design in Progress |  | CalWORKs/CalFresh, Medi-Cal/CMSP
54 | CA-49841 | Automate Medi-Cal Discontinuance for Individual turning age 65 for failure to return MC 604 IPS | Enhancement | High | New | CIV-11988 | Correspondence, Medi-Cal/CMSP
55 | CA-54527 | Modify the TTC Interface File | Enhancement | Medium | Design in Progress | LA County Specific | Tax Intercept
56 | CA-57452 | ACWDL 17-32 - NOA Requirements for Failure to Respond - Compliance with Settlement of Korean Community Center of the East Bay | Enhancement | High | Design in Progress | CIV-10892 | Correspondence
57 | CA-208864 | CalHEERS eHIT: Budget Periods and Individual-Level Eligibility | Enhancement | Critical | New | CIV-104299; CH-151332 | Medi-Cal/CMSP
58 | CA-208889 | eICT: Updates for eICT (EHIT, ABAWD, SB 380) | Enhancement | High | New | CIV-104321 | ICT
59 | CA-208925 | Text to Opt out of Text Messages | Enhancement | Medium | Design in Progress |  | IVR & Contact Center
60 | CA-206598 | Your Benefits Now Online Medi-Cal Renewal Process form MC 262LTC in all Threshold Language | Enhancement | High | New |  | C4Yourself
61 | CA-206602 | Your Benefits Now Online Medi-Cal Renewal Process form MC14A MSP in all Threshold Language | Enhancement | High | New |  | C4Yourself
62 | CA-206394 | Add Threshold for MC RE/Restore Notice | Enhancement | Medium | Design in Progress |  | Correspondence
63 | CA-206805 | Add Family Size 11 and 12 to FPL Code Table | Enhancement | Medium | New | CIV-103498 | Medi-Cal/CMSP
64 | CA-204582 | Add Edit Functionality to a Service Arrangement (42700) | Enhancement | Critical | Design in Progress | CIV-391 | Welfare to Work/WPR
65 | CA-204553 | CalWORKs/RCA Adults by Welfare-to-Work Category Report | Enhancement | High | New |  | Management Reports
66 | CA-204494 | SB 1341 All County Solution Phase 4 - Letter Format Mixed Non-MAGI/MAGI NOAs | Enhancement | Medium | New |  | Correspondence, Medi-Cal/CMSP
67 | CA-204952 | CalHEERS eHIT: Add Medi-Cal Deemed Infant and Medi-Cal Access Infant Program Functionality | Enhancement | High | New | CH-122183, CIV-102360 | Medi-Cal/CMSP
68 | CA-204499 | SB 1341 All County Solution Phase 5 - Mixed Non-MAGI/MAGI Text updates and update to Skip Report | Enhancement | Medium | New |  | Correspondence, Medi-Cal/CMSP
69 | CA-204497 | SB 1341 All County Solution Phase 3 - Updates to the mixed Non-MAGI/MAGI NOAs to allow for mixed actions | Enhancement | Medium | Design in Progress |  | Correspondence, Medi-Cal/CMSP
70 | CA-205642 | CalHEERS eHIT: BREfS Phase C, Part 2 Override Eligibility Determination Functionality | Enhancement | High | New | CIV-102761, CH-109747 | Medi-Cal/CMSP
71 | CA-204823 | Time Limit Months for Immediate Need program | Enhancement | Critical | New | CIV-8583 | CalWORKs/CalFresh
72 | CA-204030 | CalHEERS eHIT: IAP Transition Enhancement | Enhancement | Medium | New | CIV-101980; CH-124914 | Medi-Cal/CMSP
73 | CA-203485 | Update to LRS database for intake applications source/program history | Enhancement | Low | New |  | Usability
74 | CA-203421 | Your Benefits Now (YBN) SAWS II Plus/GR SAWS II plus/CW RD form(also the SAWS II Plus) to remove all default mapping. | Enhancement | Medium | New |  | C4Yourself, Tech
75 | CA-209221 | Add State PINs to Integrated Service Payment / Valuable Detail Claiming Report | Enhancement | Medium | Committee Review | CIV-102606, CIV-104015, CA-208814 | State/Fiscal Reports
76 | CA-49633 | CF 387 CalFresh Request for Information for Residency | Enhancement | High | Pending Approval | CIV-101447 | CalWORKs/CalFresh, Correspondence
77 | CA-208863 | CalHEERS eHIT: Married Filing Jointly and Out-of-State Residence Address | Enhancement | High | Design in Progress | CIV-1068; CH-153970 | Medi-Cal/CMSP
78 | CA-202177 | Modifications to the Medi-Cal Renewal E-Hit Dashboard and DPSS Performance Measures Dashboard - Medi-Cal Renewals | Enhancement | High | Design in Progress |  | Management Reports
79 | CA-203824 | Add Functionality to Manage Conditionally Eligible Status in MAGI Determinations | Enhancement | High | Committee Review | CIV-11725 | Medi-Cal/CMSP
80 | CA-210926 | Add EDBC Validation to Force Completion of Customer Report | Enhancement | High | Pending Approval |  | CalWORKs/CalFresh
81 | CA-210498 | NB Application Future Application Date | Enhancement | High | Pending Approval | CIV-105065 | CalWORKs/CalFresh
82 | CA-50302 | OCAT - Upcoming Premise Item | Enhancement | High | Committee Review | CIV-4108 | Welfare to Work/WPR
83 | CA-50800 | CalWORKs Denial NOA - correct the 30-day date inserted on the NOA | Enhancement | High | Design in Progress |  | Correspondence
84 | CA-206168 | Customer Reporting Page Updates | Enhancement | High | Design in Progress |  | CalWORKs/CalFresh
85 | CA-209721 | Add NOAs and Forms for Electronic Theft | New Policy | High | Design in Progress | CIV-104707 | Correspondence
86 | CA-209709 | ACL 19-75 Revisions to ABCD 350 | New Policy | High | Design in Progress | CIV 104703 | State/Fiscal Reports
87 | CA-203208 | Update MEDS to Send Prior FC or KG Aid Code to MEDS for NMD's Minor Infant Child | New Policy | High | Design in Progress | CIV-572 | MEDS
88 | CA-202054 | Suspend/Discontinue/Reinstate for CAPI case | New Policy | High | New | CIV-100213
89 | CA-202682 | Transitional Medi-Cal, Four Month Continuing Eligibility, and CalWORKs Denials and Discontinuances | New Policy | Critical | New | CIV-101282 | Medi-Cal/CMSP
90 | CA-202463 | NFC 17-023 Update SAR 2 to the latest State version | New Policy | High | New | CIV-8975 | Correspondence
91 | CA-202684 | ACL 18-50 - Implement Redesigned CalFresh Overissuance NOAs | New Policy | High | New | CIV-5849 | Correspondence
92 | CA-56341 | ACL 17-34 - CFR 273.2 Create monthly/annual report for Non-Assistance CalFresh Elderly Simplified Application Project (ESAP) Waiver Approval for Elderly/Disabled (E/D) Households (HHs) with no earned income | New Policy | Medium | New | CIV-100752 | Management Reports
93 | CA-200866 | ACWDL 17-36 NOA snippets for Medi-Cal Inmate Program | New Policy | Medium | New | CIV-12023 | Correspondence
94 | CA-51987 | ACL 14-91 - Track Workfare and 15% Exemptions on Stat 47 Quarterly Report (see SCR CA-50766) | New Policy | Medium | New | CIV-9009 | State/Fiscal Reports
95 | CA-50787 | ACL 16-120 - Create a Report that Identifies Overpayments that were created as a result of a Mandatory Mid-Period Change that was Reported Timely and the County was unable to provide a 10-Day Notice of Action. Addendum to SCR BPP-CWs-GPD-139 | New Policy | High | New |  | Management Reports
96 | CA-56913 | ACL 14-64: Add CalWORKs Family Stabilization (FS) Program Quarterly Status Report - FSP 14 (dependent on SCR CA-57298: Creating Family Stabilization Pages) | New Policy | Critical | New | CIV-832 | State/Fiscal Reports
97 | CA-53617 | ACWDL 17-14: Update the "Medi-Cal General Property Limitations" (MC 007) form in LRS and the LRS code tables with the Statewide Average Private Pay Rate (APPR) for 2019. | New Policy | High | New | CIV-104975 | Medi-Cal/CMSP
98 | CA-48513 | Change EDBC logic to auto-test for 4M when youth 18 years or older exits FC | New Policy | Medium | New | LA County Specific | Foster Care/Kin GAP/AAP, Medi-Cal/CMSP
99 | CA-58236 | Add Translations of Revised Forms to LRS: ABP SSI 1, ABP SSI 3, and ABP SSI 4 | New Policy | Medium | New | LA County Forms for General Relief | Correspondence
100 | CA-49617 | ACL 16-45: Automate the CW 2219 for Non-Needy Caretaker application instead of the SAWS 2 Plus application | New Policy | Medium | Design in Progress | CIV-9772 | Correspondence
101 | CA-54311 | ACL 18-18 CalFresh Changes to Reporting Requirements | New Policy | Critical | New | CIV SCR# 100532 | CalWORKs/CalFresh
102 | CA-58579 | ACWDL 17-31 Revisions to the NA Back 9 for all Medi-Cal Notices of Action | New Policy | Critical | Design in Progress | CIV-10665 | Correspondence
103 | CA-56916 | Modify the ABAWD super trigger functionality to detect deleted data to update the ABAWD status | New Policy | High | New |  | CalWORKs/CalFresh
104 | CA-209360 | ACL 19-67 - CalWORKs: Changes to Asset and Vehicle Value Limits | New Policy | High | Design in Progress | CIV-104559 | CalWORKs/CalFresh
105 | CA-209033 | ACL 19-76 - CalWORKs Change in Earned Income Disregard (EID) and Income Reporting Thresholds Tiers (IRTs) | New Policy | High | Design in Progress | CIV-104383 | CalWORKs/CalFresh
106 | CA-209404 | ACL 19-59 Revise DFA 358F and DFA 358S | New Policy | High | Design in Progress | CIV 104574 | State/Fiscal Reports
107 | CA-208988 | ACWDL June 11, 2019; CFL NO. 18/19-26 Add Functionality for Housing Support Program (HSP) | New Policy | Critical | Design in Progress | CA-208109; CIV-104367 | CalWORKs/CalFresh
108 | CA-208203 | ACL 19-31and CFL 19/20-14- Re-Entry into Extended Foster Care for Youth Receiving SSI | New Policy | High | New | CIV-104019 | Foster Care/Kin GAP/AAP
109 | CA-208268 | ACL 18-107, ACL 18-108 - SNB/TNB Forms and Notices - Threshold Languages Phase 4 | New Policy | Critical | Committee Review | CIV-104043 | Correspondence
110 | CA-208191 | ACWDL 17-12: Changes to the Designation and Responsibilities of the Medi-Cal Authorized Representative | New Policy | High | New | CIV-8633 | Medi-Cal/CMSP
111 | CA-208184 | ACL 19-34 Update Kin-GAP Beginning Date of Aid Rules to Accept Mid-Month Application Date | New Policy | High | Committee Review | CIV 104011 | Foster Care/Kin GAP/AAP
112 | CA-207637 | ACL 18-08 - ABAWD - Phase III | New Policy | Critical | Design in Progress | CIV-103743 | CalWORKs/CalFresh
113 | CA-208030 | ACL 19-40 Cal-OAR - Phase I - Automation Alternative | New Policy | High | New | CIV-103934 | Welfare to Work/WPR
114 | CA-205633 | ACL 18-75 Phase IV-Long Term Funding for Emergency Caregivers with Placements Prior to RFA Approval | New Policy | Critical | New | CIV-102757 | Foster Care/Kin GAP/AAP
115 | CA-204863 | ACL 18-99 CF OI Collection Period | New Policy | Critical | New | CIV-102263 | Collections
116 | CA-204858 | ACWDL CalFresh Employment & Training (E&T) Compliance with New Federal Reporting Requirements | New Policy | High | New | CIV-10156 | State/Fiscal Reports
117 | CA-203671 | ACWDL 18-17 and 17-25: Add MC 604 MDV Doctorâ€™s Verification to Template Repository | New Policy | High | New | CIV-101796 | Correspondence
118 | CA-208155 | CFL 18/19-49 Create one new Pay Code for CalWORKs Home Visiting Program (HVP) | New Policy | Medium | Design in Progress | CIV-103989
119 | CA-201836 | ACL 18-117: Implement CalFresh Churn Report - CF 18 | New Policy | High | Design in Progress | CIV-100878 | State/Fiscal Reports
120 | CA-208265 | ACL 19-42 Implement the Automation of CalWORKs Home Visiting Program (HVP) | New Policy | High | Design in Progress | CIV-104042 | CalWORKs/CalFresh, Welfare to Work/WPR
121 | CA-205913 | ACL 18-75 Add 5L Aid Code for FC Emergency Assistance EC Ineligible Cases | New Policy | High | Design in Progress | CIV-102912 | Foster Care/Kin GAP/AAP
122 | CA-210307 | Deactivating Pre-ACA Aid Codes | New Policy | High | Design in Progress | CIV-104986 | Medi-Cal/CMSP
123 | CA-209422 | Update Medi-Cal Auto-Discontinuance Batch for Failure to Complete RE to process at an Individual Level | New Policy | High | Design in Progress | CIV-104584 | Medi-Cal/CMSP
124 | CA-211216 | Income Disregard for the Aged, Blind & Disabled Federal Poverty Level Program | New Policy | High | Design in Progress | CIV-105339 | Medi-Cal/CMSP
125 | CA-208130 | MEDIL I 19-12: Update on Asset Verification Reports | New Policy | High | New | CIV-103983 | IEVS
126 | CA-202778 | Revised Medi-Cal Hierarchy | New Policy | Critical | Design in Progress | CIV-7564 | Medi-Cal/CMSP
127 | CA-209996 | ACL 19-77 New and Revised Homeless Assistance Forms and Notice of Action | New Policy | High | New | CIV - 104848 | Correspondence
128 | CA-206080 | ACL 18-141 CF REVISED SUPPLEMENTAL FORM FOR EXCESS MEDICAL DEDUCTIONS (CF 31) | New Policy | High | New | CIV-103015 | Correspondence
129 | CA-50293 | ACL 11-80 - CalWORKs New & Revised Overpayment Notice of Action Messages | New Policy | High | Design in Progress | CIV-8657
130 | CA-209488 | ACL 19-99 Child Care Immediate and Continuous Eligibility to Stage One | New Policy | Medium | Design in Progress | CIV-104597 | Child Care
131 | CA-204569 | ACL 19-40 CalWORKs Outcome and Accountability Review (Cal-OAR) Phase II | New Policy | High | Design in Progress | CIV-102191 | Welfare to Work/WPR
132 | CA-201657 | OBIEE: Apply Oracle Patch to OBIEE | Operational Enhancement | Medium | New | CIV-593 | IVR & Contact Center
133 | CA-202347 | LRS: Automate e-app status update from Data Transfer to Transfer to LRS once the case is processed (Active, Denied etc) and DCR to update Data transfer to Transfer to LRS status. | Operational Enhancement | Medium | New |  | C4Yourself, Usability
134 | CA-201214 | Add Business Reply Mail (BRM) to MC 355 Form | Operational Enhancement | High | New |  | Correspondence
135 | CA-54663 | Suppress WTW/REP/GROW forms when the Provider Resources are in house | Operational Enhancement | High | New | CIV-102421 | RDB
136 | CA-55990 | No Cost SCR: Update EDBC Run Date with latest Authorization Date | Operational Enhancement | High | New |  | CalWORKs/CalFresh, Foster Care/Kin GAP/AAP, Medi-Cal/CMSP
137 | CA-53434 | Selective Address Normalization (Tech) | Operational Enhancement | Medium | Design in Progress |  | Tech
138 | CA-209492 | Refactor: Medi-Cal NOA Regulations | Operational Enhancement | Medium | New |  | Correspondence
139 | CA-206525 | YBN - Create CalSAWS mail server to change all YBN and outbound related email to calSAWS email address | Operational Enhancement | Medium | New |  | C4Yourself
140 | CA-205523 | Add Scheduled Report to Track FC/KG/AAP Minors Aging Out at 18 or 21 Years of Age | Operational Enhancement | Medium | New |  | Management Reports
141 | CA-205562 | 2019 Bicsuite Batch Schedule Calendar Update | Operational Enhancement | Critical | Design in Progress | CIV-105160 | Other
142 | CA-205454 | LRS only change: remove DPSS-at-a-glance link from LRS Business Intelligence dashboard. | Operational Enhancement | High | New |  | Management Reports
143 | CA-205535 | Add Monthly Report to Track Non-Federal Cases from CWS/CMS Special Project Page and ID Num Page | Operational Enhancement | Medium | New |  | Management Reports
144 | CA-209032 | Create State Agency Accounts for Designated DHCS and CDSS Staff | Operational Enhancement | Low | Ready for Committee | CIV-103887
145 | CA-203787 | Auto Discontinue of AAP When Youth Turn 18/21 | Operational Enhancement | Medium | Committee Review | CIV-104670 | Foster Care/Kin GAP/AAP
146 | CA-211827 | Automated Regression Test - Execution and Maintenance - 20.03 Release Cycle | Operational Enhancement | Medium | Pending Approval |  | Other
147 | CA-201226 | Phase II - Provide Internal Services Department (ISD) LMRS/SFV lobby app, lobby monitor and lobby check in app web services & database for SFV office. | Operational Enhancement | High | Pending Approval |  | Lobby Management
148 | CA-209754 | Add Threshold Languages for GN 6050 RP and GN 6053-R | Policy Re-Design | Medium | New |  | Correspondence
149 | CA-201756 | NOMI - Interview Completion Due date to be 30 days from application date | Policy Re-Design | High | Design in Progress | CIV-103745
150 | CA-200800 | Update EDBC to process mid-period TCF programs via eICT | Policy Re-Design | High | New | CIV-7522 | ICT
151 | CA-50303 | Update LRS to have WTW/REP/Cal-Learn sanctions, GR sanction and GR Time Limit at a person level instead of the program level, so the sanction will follow the person if they are moved to another case. | Policy Re-Design | High | New |  | Time Limits
152 | CA-50316 | Phase I - Change CalFresh Notice of Actions - New CF 286 Budget Cont. Page | Policy Re-Design | High | New | CIV-101397 | Correspondence
153 | CA-56887 | Phase III-B- Change CalFresh NOAs to include the name of the individuals on change and denial NOAs | Policy Re-Design | High | New |  | Correspondence
154 | CA-49396 | ACL 15-96 â€“ Add and automate ARC Forms NA 1281, NA 1280, NA 1279, and NA 1278 | Policy Re-Design | High | New |  | Correspondence
155 | CA-51882 | ACL 16-98: Change HA Eligibility From 12-Month to 365-Day Period; Limit HA Manual and Override EDBC drop down values | Policy Re-Design | High | Design in Progress | CIV-7859 | CalWORKs/CalFresh
156 | CA-50776 | CalFresh Work Requirement Changes | Policy Re-Design | Medium | New |  | CalWORKs/CalFresh
157 | CA-54665 | Time Limit should not be counted for Non-Cal-Learn 19 Year old Custodial Parents | Policy Re-Design | High | New | CIV-102306 | Time Limits
158 | CA-50801 | Phase I - ACL 15-62 changes: NA 816, NA 817 with the latest versions in all threshold languages. | Policy Re-Design | Medium | New |  | Correspondence
159 | CA-50297 | Permit Concurrent Activity For Participants With Good Cause Status | Policy Re-Design | Critical | New |  | Welfare to Work/WPR
160 | CA-202055 | Separate Case & Issuance for CAPI Couple Case | Policy Re-Design | Critical | Design in Progress | CIV-103281 | CalWORKs/CalFresh
161 | CA-209231 | ACL 11-51: FC Education Travel Reimbursement NOAs | Policy Re-Design | Medium | New | CIV-1131 | Correspondence
162 | CA-208415 | Monthly Batch Job - Case Purge - Discontinued/Inactive Cases | Policy Re-Design | High | New | CIV-105446 | Other
163 | CA-207892 | Add Sample SAR7 to Template Respository and RE Packets | Policy Re-Design | High | New | CIV-100919 | Correspondence
164 | CA-207798 | Update Incomplete CF Recertification Status (48318) | Policy Re-Design | High | New | CIV-644 | Correspondence
165 | CA-206740 | YourBenefitsNow YBN and LEADER Replacement Systems LRS electronic notification and paperless option logic update. | Policy Re-Design | High | New |  | Usability
166 | CA-206415 | ACL 13-02 Good Cause Reason 407 - Lack of Supportive Services should not impact WTW 24 Month Clock. | Policy Re-Design | Critical | New | C-IV 12392 | Time Limits
167 | CA-204762 | Do not Create an Offset Transaction for Overpayment/Overissuances Adjustments | Policy Re-Design | Critical | Design in Progress | CIV-102098 | Collections, State/Fiscal Reports
168 | CA-205448 | ACL 14-20 - CalFresh Recertification Appointment Letter Revisions/Additions | Policy Re-Design | Medium | New |  | Correspondence
169 | CA-204747 | CalWORKs clock is ticking for parent who is under 18 years old | Policy Re-Design | High | Committee Review | CIV-818 | Time Limits
170 | CA-203392 | ACL 16-79 Add a drop down menu for out of state short-term residential therapeutic program (STRTP) placements | Policy Re-Design | High | New | CIV-101513 | Foster Care/Kin GAP/AAP
171 | CA-210813 | Update CFWR Work Registration Exempt Status Reason Replace â€œPhysically/Mentally Incapacitatedâ€ with â€œUnfit For Employment-Medically Verifiedâ€ | Policy Re-Design | High | Pending Approval | CIV-105185 | CalWORKs/CalFresh
172 | CA-53789 | Update Expedited Service Determination, Postponed Verification and Batch Discontinuance Process | Policy Re-Design | High | Committee Review | CIV-101159 | CalWORKs/CalFresh
173 | CA-208888 | New data elements to be added to the eICT Outbound file to indicate CalFresh SSI/SSP Reversal. | Policy Re-Design | Critical | Pending Approval | CIV-104322 | ICT
174 | CA-204115 | ACL 18-43 - Revise CalWORKs M40-107 Time Limit NOAs in the C, D, and G Series | Policy Re-Design | Medium | New | CIV 101570 | Correspondence
175 | CA-200879 | ACL 19-95 Automate Disaster CalFresh | Policy Re-Design | Medium | Design in Progress |  | CalWORKs/CalFresh
176 | CA-55584 | Updates the DHCS CMS Performance Indicator Report | Policy Re-Design | Critical | New | CIV-11690 | State/Fiscal Reports
177 | CA-205414 | ACL 14-20 -CF 29A (2/14) - CalFresh Initial Appointment Letter | Policy Re-Design | High | Committee Review | CIV-102600 | Correspondence
178 | CA-202460 | Update Verbiage for Medical Savings Program (MSP) NOAs | Policy Re-Design | High | Design in Progress | CIV-100174 | Correspondence
179 | CA-202307 | Updates to the GEN 1365 Form and Form Generation | Policy Re-Design | High | Design in Progress | CIV-100774
180 | CA-49395 | ACL: Update ARC1 and ARC1A Forms | Policy Re-Design | Medium | Design in Progress | C-IV SCR 3915 (CCM)
181 | CA-55378 | Require the Immunizations page is updated when a child in the Assistance Unit is under age 6 and not in school | Policy Re-Design | Medium | Design in Progress | CIV-Counties to adopt LRS Functionality | CalWORKs/CalFresh

## Key
SCR Status Key |  | SCR Change Type Key
System Change Request (SCR) Status | Definition | SCR Change Type | Definition
New | Default status when an Issue is created | Data Change | This change type is selected for data change that impacts high volume of cases
Design in Progress | Indicates that the Team/Consortium Staff are working on the Design | Enhancement | This change type is selected for changes to existing design that are not new policy or policy re design.
Ready for Committee | Indicates the Design is ready for Committee to review/approve | Individual Data Change | This change tyhpe is selected for data changes that impacts low volumne of cases (less than 20)
Committee Review | Indicates the Committee is reviewing for approval | New Policy | This change type is selected for SCRs that have references to regulations or state policy letters that have not yet been integrated in the system.
Pending Approval | Indicates that the Issue is pending the approval of CCB. | Operational Enhancement | This change type is selcted for changes to the system that are county specific, impact a specific technology upgrade (ie. New EBT Printer, New Warrant Stock, FTP changes, DB Upgrade, etc.), or are only operational in nature (IP address change, configurational file changes, etc.)
Approved | Indicates that the Issue has been Accepted by the CCB and/or has been given Expedited Approval and build may begin. | Policy Re-Design | This change type is selected of the SCRs is requesting a change to existing design with a regualtion or state policy letter reference.
In Development | Indicates that the Issue is in the development phase
Development Complete | Indicates that the development team has completed development of the Issue
In Assembly Test | Indicates the development team has completed development of the Issue and Assembly Test is in progress
System Test | Indicates that the Issue is currently in System Test and all Test Conditions are being validated in System Test
Test Complete | Indicates that the Issue has been validated in System Test and all Test Conditions have passed System Test