## CalSAWS DD&I
| 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024
| SFY 2018/19 | [5 empty] | SFY 2019/20 | [11 empty] | SFY 2020/21 | [11 empty] | SFY 2021/22 | [11 empty] | SFY 2022/23 | [11 empty] | SFY 2023/24 | [11 empty] | SFY 2024/25
 | time axis 2019-01-01 to 2024-12-01
CalSAWS Application Releases
CalSAWS Technical Releases
Current Schedule
CalSAWS DD&I | 2019-03-01: CalSAWS 58 County Design, Development, Test, Conversion and Implementation; 2023-02-01: CalSAWS Stabilization
CalSAWS Application Releases
[24 empty] | C-IV: |  | CDT |  |  | UAT
[25 empty] | CalWIN: |  | CDT | [5 empty] | UAT
Revised Schedule
|  |  | CalSAWS 58 County Design, Development, Test, Conversion and Implementation | [55 empty] | CalSAWS Stabilization
CalSAWS Migration Releases
(integrated with CalSAWS Application Releases)
CalSAWS Analytics Releases
(Dashboards)
[24 empty] | C-IV: |  | CDT |  |  | UAT
[34 empty] | CalWIN: |  | CDT | [5 empty] | UAT
[5 empty] | CalWIN OCM, Training & Implementation Support Procurement | [15 empty] | CalWIN Business Process Alignment, Organizational Change Management, Training & Implementation Support
[5 empty] | Prepare, Approve & Release RFP | [7 empty] | Proposal Preparation, Submission & Evaluation |  |  |  |  | Negotiate & Approve Contract
Additional Scope:
|  |  | 58 County Imaging | [9 empty] | 58 County Centralized Imaging | [20 empty] | Post Deployment Support, LA County and CalWIN Counties Document Migration and Support
|  |  | Task Management: | [11 empty] | Phase 1
Phase 2
|  |  | Non State Forms (NSF) | [11 empty] | Phase 1
Phase 2
|  |  | GA/GR | [11 empty] | Phase 1
Phase 2
|  |  | APIs | [11 empty] | APIs
|  |  | Ancillary Systems Conversions | [11 empty] | CalWIN Ancillary Systems Conversions (QA/QC, Fraud, Collections) | [30 empty] | Cutover
Analytics: BIP/State Reports replatforming - Pending POC completion (target December (end) 2019)
Phase 1 - State Reports not rendering at a 40 County data volumes
Phase 2 - High Usage C-IV Management Reports not in LRS (Scheduled and Online)
Phase 3 - High Usage LRS Management Reports (Scheduled and Online)
Phase 4 - Other State reports and Management Reports
|  |  | Foster Care | [11 empty] | Phase 1
Other Consortium Decision Points:
1) 58 County Portal Solution; 2) 58 County Contact Center Solution; 3) Print Center Procurement; 4) Foster Care CARES Integration
39-County Go-live
on CalSAWS
9/2021
Wave 6
CalSAWS
Migration Complete
1/2023
CalWIN Wave 1
Go-live
1/2022
LRS ---> AWS Cloud
10/2019
Final Acceptance
6/2023
Wave 6
CalSAWS
Migration Complete
10/2023
CalWIN Wave 1
Go-live
10/2022
LRS ---> AWS Cloud
10/2019
Final Acceptance
3/2024
39-County Go-live
on CalSAWS
9/2021
OCAT go-live
06/2020 & CH release
Application changes
for imaging
39-County Go-live
on CalSAWS 9/2021
CalHEERS
Release
CalHEERS
Release
CalHEERS
Release
CalHEERS
Release
CalHEERS
Release
CalHEERS
Release
CalHEERS
Release
CalHEERS
Release
Wave 2
Wave 3
Wave 4
Wave 5
Wave 2
Wave 3
Wave 4
Wave 5
CalWIN OCM, Training, Implementation Support End
Start of CalWIN UAT
APIs for Imaging and Task Management