## Slide 1
CalSAWS Risk & Issues Executive Summary
Legend
Risk 102: Lack of Annual Project Funding may cause schedule delay or reduction in scope for CalSAWS M&O, and all existing projects
Risk 104: Functionality gaps between the 3 systems may result in a loss of functionality for some counties during migration to CalSAWS
Risk 201: Pace of Policy Changes may exceed capacity of App-Dev team, resulting in less automation
Risk 202 (Retired): Not all of the estimates related to Functional Design Sessions have been completed yet. Until the FDS estimates have been completed, cost and schedule impacts to CalSAWS are not known.
Risk 203: Project communications must be enhanced, otherwise stakeholder / audience needs will not be met
Risk 204: Volume of changes to baseline code may cause degradation in quality & increase in defects
Risk 206: Delays in staffing the Consortium and/or Accenture teams may delay the project schedule Risk 208: CalHEERS release readiness delays may negatively impact CalSAWS delivery timelines, slowing critical updates to counties
Risk 209: CalWIN Counties may not be adequately supported for change readiness prior to August 2020 until the CalWIN Change Management Procurement vendor starts Risk 211: Delay in consolidated portal procurement and implementation may impact C-IV and CalWIN go-live dates Risk 214: If counties are not able to adapt to the regional governance structure, the project schedule is at risk regarding decision making Risk 219: Facilitation across Committees is inconsistent, which may impact the project schedule and quality of decisions
Risk 221: The instability of two 3rd party software products from Oracle causes LRS production performance degradation.
Risk 222 (Retired): The alignment in FCED approach and FCED governance approval must be completed by March 27th, otherwise the project schedule and costs may be impacted.
Risk 223: CalSAWS DD&I / LRS Technology Operations ability to manage, maintain, monitor, and deliver a scalable and sustainable 58 county CalSAWS.
Risk 224: The implementation of ForgeRock may delay the OCAT Schedule Risk 225: The ForgeRock solution may not perform as expected, causing LRS production performance degradation.
Risk 226 (New): COVID-19 relief efforts may impact CalSAWS DD&I schedule. ---------------------------------------------------------------------------------------------------------------------------------------------------------------------------------- Issue 118: Some non-production environments using Delphix software do not have the desired responsiveness
P
Overall Project
High = 9 DD&I = 15
Med = 7 M&O= 2
Low = 1
____________
Risk Total: 17
Issue Total: 1
Retired Total: 1 Avg Project Exposure: 2.24
Legend
Risk 102: Lack of Annual Project Funding may cause schedule delay or reduction in scope for CalSAWS M&O, and all existing projects
Risk 104: Functionality gaps between the 3 systems may result in a loss of functionality for some counties during migration to CalSAWS
Risk 201: Pace of Policy Changes may exceed capacity of App-Dev team, resulting in less automation
Risk 202: Not all of the estimates related to Functional Design Sessions have been completed yet. Until the FDS estimates have been completed, cost and schedule impacts to CalSAWS are not known.
Risk 203: Project communications must be enhanced, otherwise stakeholder / audience needs will not be met
Risk 204: Volume of changes to baseline code may cause degradation in quality & increase in defects
Risk 206: Delays in staffing the Consortium and/or Accenture teams may delay the project schedule Risk 208: CalHEERS release readiness delays may negatively impact CalSAWS delivery timelines, slowing critical updates to counties
Risk 209: CalWIN Counties may not be adequately supported for change readiness prior to August 2020 until the CalWIN Change Management Procurement vendor starts Risk 211: Delay in consolidated portal procurement and implementation may impact C-IV and CalWIN go-live dates Risk 214: If counties are not able to adapt to the regional governance structure, the project schedule is at risk regarding decision making Risk 219: Facilitation across Committees is inconsistent, which may impact the project schedule and quality of decisions
Risk 221: The instability of two 3rd party software products from Oracle causes LRS production performance degradation.
Risk 222 (Retired): The alignment in FCED approach and FCED governance approval must be completed by March 27th, otherwise the project schedule and costs may be impacted.
Risk 223: CalSAWS DD&I / LRS Technology Operations ability to manage, maintain, monitor, and deliver a scalable and sustainable 58 county CalSAWS.
Risk 224: The implementation of ForgeRock may delay the OCAT Schedule Risk 225: The ForgeRock solution may not perform as expected, causing LRS production performance degradation.
Risk 226 (New): COVID-19 relief efforts may impact CalSAWS DD&I schedule. ---------------------------------------------------------------------------------------------------------------------------------------------------------------------------------- Issue 118: Some non-production environments using Delphix software do not have the desired responsiveness
Notes: General Definitions
What is a risk, what is an issue what is a contingency or mitigation plan,
Level of control, qualitative assessment of the risk (what is impacting, scheduling cost, stakeholder communication.
Impact and category of impact, level of control (what is it, what are the different levels)
What is our definition of issues. If a risk is identified and validated, then it becomes an issue

## Slide 2: CalSAWS Project Issue and High Risks Update
Risk Trend Legend
Remains same
Trending to Issue
Trending to Low
Retired Risk
Realized into an Issue
Trending to Medium
Risk/ Issue # | Risk/Issue Name | Risk Status | Risk Trend
Issue 118 | Some non-production environments using Delphix software do not have the desired responsiveness | A quantitative analysis for Delphix performance was completed. Although results were positive, it was decided due to the impact of remote work to the user experience, to keep 3 non-prod environments on full disk and re-evaluate the decision in a couple of months | N/A
201 | Pace of Policy Changes may exceed capacity of the project teams, resulting in less automation | Closely monitor specific policy changes, such as ABAWD, and escalate into separate issues as necessary. | 
202 | Not all of the estimates related to Functional Design Sessions have been completed yet. Until the FDS estimates have been completed, cost and schedule impacts to CalSAWS are not known | The Analytics Exhibit and As-Needed IAPDU received conditional approval at the JPA Board meeting on March 27, 2020, contingent on receiving an approval letter from CMS. This risk will be retired once the approval letter is received from CMS. | 
203 | Project communications must be enhanced, otherwise stakeholder / audience needs will not be met | The YBN and C4Yourself broadcast is being planned as a new feature / future enhancement. The Quarterly Communications Plan assessment is included in the March PSC materials related to key communication milestones from the Project teams. | 
204 | Volume of changes to baseline code may cause degradation in quality & increase in defects | Mitigation measures include: Increased Automated Regression Testing (ART), Future ART enhancements, Enforcing SCR Freeze Dates, Improving Design Documentation, reducing late content revisions, Code quality checks and impact analysis | 
211 | Delay in consolidated portal procurement and implementation may impact C-IV and CalWIN go-live dates | The CalWIN OCM RFP was released on December 17, 2019; vendor responses were due on February 19, 2020. The C-IV and CalWIN go-live dates remain at risk until the vendor commences work. | 
221 | The instability of two 3rd party software products from Oracle causes LRS production performance degradation | Work to deploy Oracle patch has been suspended and the project direction is to focus on the Oracle OAM replacement work with ForgeRock. Refer to the new ForgeRock Risk #225 | 
224 | The implementation of ForgeRock may delay the OCAT Schedule | The OCAT Work Plan has been updated and re-baselined. ForgeRock implementation tasks and dependencies have been planned and communicated between Cambria, Accenture, and the Consortium. | 
225 | The ForgeRock solution may not perform as expected, causing LRS production performance degradation | ForgeRock (FR) deployed into the test environments and ready for OCAT testing. FR and OCAT integration is in progress, and performance testing of FR APIs has started. Operational readiness planning activities for delivery of FR are in progress. | 
226 | COVID-19 relief efforts may impact CalSAWS DD&I schedule | Mitigation strategies for consideration include: prioritization of SCRs, existing staff working overtime, slow ramp to add new staff and providing orientation remotely. |