## 1. Summary
Exhibit D - Price Proposal Schedules
Schedule 1
Summary of OCAT D&I and 1st 12 Months of M&O Project Price
OCAT D&I and M&O Project Overall Price Total |  | SFY 2018/19 | SFY 2019/20 | SFY 2020/21 | SFY 2021/22 | OCAT Maximum Amount
| OCAT Deliverables Price | 0 | 3028818.36 | 521353.98 | 587557.66 | 4137730
| OCAT Facilities Price | 0 | 142545 | 0 | 0 | 142545
| OCAT Hardware and Software Price | 0 | 117506 | 111904 | 44260 | 273670
OCAT: D&I Price Subtotal |  | 0 | 3288869.36 | 633257.98 | 631817.66 | 4553945
| OCAT Maintenance & Operations Price: 1st 12 Months | 0 | 0 | 703890 | 703890 | 1407780
OCAT: M&O Price Subtotal |  | 0 | 0 | 703890 | 703890 | 1407780
OCAT Maximum Price |  | 0 | 3288869.36 | 1337147.98 | 1335707.66 | 5961725
Assumptions
1 | The Consortium will pay the Amazon Web Services (AWS) hosting costs
2 | Consortium staff will only be at the OCAT facility for workshops and design sessions as documented in the OCAT Work Plan.
3 | User Acceptance Testing will be conducted after Cambria System Testing has been completed for all components of the OCAT solution.
4 | Pre-configured components and pre-developed deliverables provided by Cambria can be used to keep the project on schedule.
5 | There will be thirty (30) days time between contract award and project start to establish the facility and it's infrastructure.
6 | Pricing includes Conversational User Interface chatbot technology integrated with the Jira Help Desk Solution.
7 | Pricing includes Jira project manager, Jira test manager, Jira Help Desk, and SharePoint licenses.
8 | SAWS is available to develop, test, and implement interfaces for the duration of the development project.
9 | Deliverables and Deliverable Expectation Documents will be review/approved by the Consortium in five (5) days.
10

## 2. Deliverables
Schedule 2
OCAT Project Deliverables
Number | WBS | Deliverable Name | Category | Review Period (Business Days) | Deliverable Due Date (Month/Year) | Target Invoice Date (Month/Year) | Total Deliverables Maximum Price (Inclusive of Holdback) | Holdback Amount | SFY 2018/19 Total | SFY 2019/20 Total | SFY 2020/21 Total | SFY 2021/22 Total
1 |  | OCAT Project Control Document Initial (plus annual updates) | Project Management | 5 | 2019-08-05 | 2019-09-01 | 496527.6 | 49652.76 |  | 446874.84
2 |  | OCAT Work Plan Initial (plus monthly updates) | Project Management | 5 | 2019-08-05 | 2019-09-01 | 496527.6 | 49652.76 |  | 446874.84
3 |  | OCAT Monthly Status Reports | Project Management | 5 | 2019-08-05 | 2019-09-01 | 496527.6 | 49652.76 |  | 446874.84
4 |  | OCAT Requirements Traceability Matrix (plus updates at key milestones) | Application Development & Test | 5 | 2019-08-13 | 2019-09-01 | 496527.6 | 49652.76 |  | 446874.84
5 |  | OCAT General Design | Application Development & Test | 5 | 2019-10-09 | 2019-11-01 | 496527.6 | 49652.76 |  | 446874.84
6 |  | OCAT Technical Design | Application Development & Test | 5 | 2020-03-27 | 2020-04-01 | 496527.6 | 49652.76 |  | 446874.84
7 |  | OCAT Application/SAWS Interfaces | Application Development & Test | 5 | 2020-10-31 | 2020-11-01 | 193094.0667 | 19309.4067 |  |  | 173784.66
8 |  | OCAT Master Test Plan | Application Development & Test | 5 | 2019-09-12 | 2019-10-01 | 193094.0667 | 19309.4067 |  | 173784.66
9 |  | CalACES Training Plan | Training | 5 | 2020-02-21 | 2020-03-01 | 193094.0667 | 19309.4067 |  | 173784.66
10 |  | CalACES Training Materials (WBT) | Training | 5 | 2020-09-30 | 2020-10-01 | 193094.0667 | 19309.4067 |  |  | 173784.66
11 |  | OCAT System Documentation | Implementation | 5 | 2020-10-31 | 2020-11-01 | 193094.0667 | 19309.4067 |  |  | 173784.66
12 |  | OCAT Performance Verification Report & Final Acceptance | Implementation | 5 | 2021-10-14 | 2021-11-01 | 193094.0667 | 19309.4067 |  |  |  | 173784.66
|  | Holdback Release | Holdback Release |  |  | 2021-11-01 | [5 empty] | 413773
|  | Total OCAT Project Deliverables Price / Maximum Price |  |  |  |  | 4137730 | 413773 | 0 | 3028818.36 | 521353.98 | 587557.66
Holdback Release
|  | Milestone |  | % Released | % Released | Amount | Target Invoice Date | State Fiscal Year
|  | OCAT Final Acceptance Certification |  | 100% | 100% | 413773 | 2021-11-01 | SFY 21/22
| Assumptions | Assumptions
1 | Deliverables and DEDs have a 5 business day review period.
2 | Cambria would lilke to discuss an accelerated delivery and submission schedule with the Consortium
3
4
5

## 3. Facilities
Schedule 3
OCAT Project Facilities Price
| Facility Line Items | SFY 2018/19 | SFY 2019/20 | SFY 2020/21 | SFY 2021/22 | Total Facilities Price
Application Development & Test Facility
| Cambria OCAT Office |  | 142545 | 0 | 0 | 142545
| Total OCAT Project Facilities Price | 0 | 142545 | 0 | 0 | 142545
Assumptions
1 | Office, furniture, Internet connectivity for the OCAT Office.
2 | The Consortium is not expected to work in this office, other than for workshops and meetings.
3
4
5

## 4. HW & SW
Schedule 4
OCAT Project Hardware and Software Price
| Hardware and Software Line Items | SFY 2018/19 | SFY 2019/20 | SFY 2020/21 | SFY 2021/22 | Total Hardware & Software Price
Hardware
| Development Hardware | 0 | 0 | 0 | 0 | 0
| Central Hardware |  | 5680 | 0 | 0 | 5680
| Training Central Hardware | 0 | 0 | 0 | 0 | 0
| Hardware Subtotal | 0 | 5680 | 0 | 0 | 5680
Hardware Support
| Development Hardware Support | 0 | 0 | 0 | 0 | 0
| Central Hardware Support | 0 | 0 | 0 | 0 | 0
| Hardware Support Subtotal | 0 | 0 | 0 | 0 | 0
| Hardware and Hardware Support Total | 0 | 5680 | 0 | 0 | 5680
Software
| Development Software | 0 | 0 | 0 | 0 | 0
| Central Software |  | 50076 | 54646 | 19260 | 123982
| Training Central Software | 0 | 0 | 0 | 0 | 0
| Software Subtotal | 0 | 50076 | 54646 | 19260 | 123982
Software Support
| Development Software Support | 0 | 0 | 0 | 0 | 0
| Central Software Support |  | 61750 | 57258 | 25000 | 144008
| Training Central Software Maintenance | 0 | 0 | 0 | 0 | 0
| Software Support Subtotal | 0 | 61750 | 57258 | 25000 | 144008
| Software and Software Support Total | 0 | 111826 | 111904 | 44260 | 267990
| Total OCAT Project Hardware and Software Price | 0 | 117506 | 111904 | 44260 | 273670
Assumptions
1 | Central software includes JIRA, SharePoint, and Blazemeter
2 | Central support software includes costs for a Helpdesk Chatbot
3
4
5

## 6. Hourly Rate Card
Schedule 6
OCAT Project Hourly Rate Card: D&I Phase
Staff Description | Hourly Rate
Project Manager | 195
Technical Lead | 195
Application Development Manager | 195
Implementation / Training Lead | 165
Database Administrator | 185
Business Analyst | 165
Developer | 165
Interface Developer | 165
Tester | 165
Average Hourly Rate | 177.2222

## 5. M&O
Schedule 5
OCAT Project Maintenance & Operations Price: 1st 12 Months
| Maintenance & Operations | SFY 2018/19 | SFY 2019/20 | SFY 2020/21 | SFY 2021/22 | Total OCAT M&O Price
| Application Enhancements & Releases |  |  | 703890 | 703890 | 1407780
| WAN Administration |  | 0 |  |  | 0
| Cloud Infrastructure |  | 0 | 0 | 0 | 0
| Total OCAT Project M&O Price | 0 | 0 | 703890 | 703890 | 1407780
Assumptions
1 | The Consortium will pay for the Cloud infrastructure and WAN costs
2
3
4
5

## 7. Change Order Rate Card
Schedule 7
OCAT Project Change Order Hourly Rate Card
Staff Description | SFY 2018/19 Hourly Rate | SFY 2019/20 Hourly Rate | SFY 2020/21 Hourly Rate | SFY 2021/22 Hourly Rate
Project Manager | 225 | 225 | 225 | 225
Technical Lead | 225 | 225 | 225 | 225
Application Development Manager | 225 | 225 | 225 | 225
Implementation / Training Lead | 195 | 195 | 195 | 195
Database Administrator | 215 | 215 | 215 | 215
Business Analyst | 195 | 195 | 195 | 195
Developer | 195 | 195 | 195 | 195
Interface Developer | 195 | 195 | 195 | 195
Tester | 195 | 195 | 195 | 195

## 8. Staff Loading by Task
ID | Key Task | Task Description | Position | Hourly Rate | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | Total OCAT D&I Hours | Total OCAT D&I Price
[5 empty] | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01
[5 empty] | 160 | 160 | 168 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160
1 | Project Management |  |  |  | 0 | 248 | 306 | 322 | 290 | 290 | 290 | 254 | 254 | 254 | 254 | 254 | 254 | 254 | 254 | 286 | 270 | 156 | 4998 | 937470
1.1 |  | Project Management |  |  |  | 128 | 212 | 228 | 204 | 204 | 204 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 96 | 3276 | 621660
|  |  | Project Manager | 195 |  | 28 | 112 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 32 | 1964 | 382980
|  |  | Technical Lead | 195 |  | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 476 | 92820
|  |  | Implementation / Training Lead | 165 |  | 56 | 56 | 56 | 32 | 32 | 32 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 572 | 94380
|  |  | Application Development Manager | 195 |  | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 264 | 51480
1.2 |  | Deliverable Management |  |  |  | 104 | 80 | 72 | 64 | 64 | 64 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 64 | 48 | 39 | 855 | 149865
|  |  | Project Manager | 195 |  | 32 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 160 | 31200
|  |  | Technical Lead | 195 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 68 | 13260
|  |  | Implementation / Training Lead | 165 |  | 16 | 16 | 16 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 40 | 24 | 24 | 224 | 36960
|  |  | Business Analyst | 165 |  | 48 | 48 | 40 | 40 | 40 | 40 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 2 | 338 | 55770
|  |  | Application Development Manager | 195 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 1 | 65 | 12675
1.3 |  | OCAT Work Plan Management |  |  |  | 16 | 14 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 21 | 359 | 69045
|  |  | Project Manager | 195 |  | 16 | 8 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 264 | 51480
|  |  | Technical Lead | 195 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 32 | 6240
|  |  | Implementation / Training Lead | 165 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 32 | 5280
|  |  | Application Development Manager | 195 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 31 | 6045
1.4 |  | Project Status Reporting |  |  |  | 62 | 36 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 18 | 508 | 96900
|  |  | Project Manager | 195 |  | 46 | 24 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 302 | 58890
|  |  | Technical Lead | 195 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 68 | 13260
|  |  | Implementation / Training Lead | 165 |  | 8 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 72 | 11880
|  |  | Application Development Manager | 195 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 66 | 12870
2 | Confirm Requirements |  |  |  | 0 | 436 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 636 | 114220
2.1 |  | Confirm System Requirements |  |  | 0 | 436 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 636 | 114220
|  |  | Technical Lead | 195 | 2019-07-01: 90; 2019-08-01: 48 | 138 | 26910
|  |  | Database Administrator | 185 | 2019-07-01: 76; 2019-08-01: 40 | 116 | 21460
|  |  | Tester | 165 | 2019-07-01: 72; 2019-08-01: 16 | 88 | 14520
|  |  | Implementation / Training Lead | 165 | 2019-07-01: 56; 2019-08-01: 16 | 72 | 11880
|  |  | Business Analyst | 165 | 2019-07-01: 72; 2019-08-01: 56 | 128 | 21120
|  |  | Application Development Manager | 195 | 2019-07-01: 70; 2019-08-01: 24 | 94 | 18330
3 | Design |  |  |  | 0 | 0 | 44 | 614 | 477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1135 | 197895
3.1 |  | Develop General Design Document |  |  | 0 | 0 | 44 | 450 | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 606 | 104270
|  |  | Technical Lead | 195 | 2019-08-01: 4; 2019-09-01: 40; 2019-10-01: 8 | 52 | 10140
|  |  | Database Administrator | 185 | 2019-08-01: 4; 2019-09-01: 64; 2019-10-01: 8 | 76 | 14060
|  |  | Tester | 165 | 2019-08-01: 8; 2019-09-01: 88; 2019-10-01: 32 | 128 | 21120
|  |  | Developer | 165 | 2019-08-01: 8; 2019-09-01: 64; 2019-10-01: 8 | 80 | 13200
|  |  | Business Analyst | 165 | 2019-08-01: 16; 2019-09-01: 92; 2019-10-01: 40 | 148 | 24420
|  |  | Application Development Manager | 195 | 2019-08-01: 2; 2019-09-01: 30; 2019-10-01: 8 | 40 | 7800
|  |  | Interface Developer | 165 | 2019-08-01: 2; 2019-09-01: 72; 2019-10-01: 8 | 82 | 13530
3.2 |  | Develop Technical Design Document |  |  | 0 | 0 | 0 | 164 | 365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 529 | 93625
|  |  | Technical Lead | 195 | 2019-09-01: 32; 2019-10-01: 64 | 96 | 18720
|  |  | Database Administrator | 185 | 2019-09-01: 26; 2019-10-01: 54 | 80 | 14800
|  |  | Developer | 165 | 2019-09-01: 32; 2019-10-01: 66 | 98 | 16170
|  |  | Business Analyst | 165 | 2019-09-01: 30; 2019-10-01: 77 | 107 | 17655
|  |  | Application Development Manager | 195 | 2019-09-01: 20; 2019-10-01: 42 | 62 | 12090
|  |  | Interface Developer | 165 | 2019-09-01: 24; 2019-10-01: 62 | 86 | 14190
4 | Application Development |  |  |  | 0 | 0 | 478 | 303 | 471 | 652 | 661 | 672 | 522 | 436 | 293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4488 | 805420
4.1 |  | Install and Configure System Software |  |  | 0 | 0 | 198 | 105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 303 | 54765
|  |  | Application Development Manager | 195 | 2019-08-01: 32; 2019-09-01: 10 | 42 | 8190
|  |  | Database Administrator | 185 | 2019-08-01: 92; 2019-09-01: 13 | 105 | 19425
|  |  | Developer | 165 | 2019-08-01: 20; 2019-09-01: 28 | 48 | 7920
|  |  | Interface Developer | 165 | 2019-08-01: 14; 2019-09-01: 27 | 41 | 6765
|  |  | Technical Lead | 195 | 2019-08-01: 40; 2019-09-01: 7 | 47 | 9165
|  |  | Tester | 165 | 2019-09-01: 20 | 20 | 3300
4.2 |  | Develop Baseline OCAT Application and SAWS Interfaces |  |  | 0 | 0 | 280 | 198 | 471 | 652 | 661 | 672 | 522 | 436 | 293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4185 | 750655
|  |  | Application Development Manager | 195 | 2019-08-01: 4; 2019-09-01: 44; 2019-10-01: 84; 2019-11-01: 65; 2019-12-01: 115; 2020-01-01: 119; 2020-02-01: 104; 2020-03-01: 76; 2020-04-01: 52 | 663 | 129285
|  |  | Database Administrator | 185 | 2019-08-01: 16; 2019-09-01: 40; 2019-10-01: 109; 2019-11-01: 163; 2019-12-01: 150; 2020-01-01: 148; 2020-02-01: 120; 2020-03-01: 122; 2020-04-01: 112 | 980 | 181300
|  |  | Developer | 165 | 2019-08-01: 120; 2019-09-01: 56; 2019-10-01: 112; 2019-11-01: 130; 2019-12-01: 114; 2020-01-01: 119; 2020-02-01: 152; 2020-03-01: 156; 2020-04-01: 64 | 1023 | 168795
|  |  | Interface Developer | 165 | 2019-08-01: 124; 2019-09-01: 42; 2019-10-01: 102; 2019-11-01: 166; 2019-12-01: 154; 2020-01-01: 158; 2020-02-01: 82; 2020-03-01: 2; 2020-04-01: 1 | 831 | 137115
|  |  | Technical Lead | 195 | 2019-08-01: 16; 2019-09-01: 16; 2019-10-01: 64; 2019-11-01: 128; 2019-12-01: 128; 2020-01-01: 128; 2020-02-01: 64; 2020-03-01: 80; 2020-04-01: 64 | 688 | 134160
5 | Testing |  |  |  | 0 | 0 | 128 | 86 | 128 | 464 | 340 | 292 | 372 | 428 | 454 | 632 | 330 | 0 | 0 | 0 | 0 | 0 | 3654 | 617100
5.1 |  | Develop Master Test Plan |  |  | 0 | 0 | 128 | 86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 214 | 38250
|  |  | Application Development Manager | 195 | 2019-08-01: 56; 2019-09-01: 42 | 98 | 19110
|  |  | Tester | 165 | 2019-08-01: 72; 2019-09-01: 44 | 116 | 19140
5.2 |  | Conduct System Test |  |  | 0 | 0 | 0 | 0 | 120 | 368 | 340 | 292 | 372 | 428 | 454 | 320 | 0 | 0 | 0 | 0 | 0 | 0 | 2694 | 448050
|  |  | Application Development Manager | 195 | 2019-11-01: 20; 2020-01-01: 20; 2020-02-01: 16; 2020-03-01: 4; 2020-04-01: 42; 2020-05-01: 16 | 118 | 23010
|  |  | Business Analyst | 165 | 2019-11-01: 124; 2019-12-01: 124; 2020-01-01: 64; 2020-02-01: 40; 2020-03-01: 24; 2020-04-01: 24; 2020-05-01: 24 | 424 | 69960
|  |  | Developer | 165 | 2019-11-01: 52; 2019-12-01: 32; 2020-01-01: 48; 2020-02-01: 48; 2020-03-01: 36; 2020-04-01: 72; 2020-05-01: 48 | 336 | 55440
|  |  | Interface Developer | 165 | 2019-11-01: 24; 2019-12-01: 24; 2020-01-01: 24; 2020-02-01: 80; 2020-03-01: 188; 2020-04-01: 172; 2020-05-01: 112 | 624 | 102960
|  |  | Tester | 165 | 2019-10-01: 120; 2019-11-01: 148; 2019-12-01: 160; 2020-01-01: 136; 2020-02-01: 188; 2020-03-01: 176; 2020-04-01: 144; 2020-05-01: 120 | 1192 | 196680
5.3 |  | Support User Acceptance Test |  |  | 0 | 0 | 0 | 0 | 8 | 96 | 0 | 0 | 0 | 0 | 0 | 312 | 330 | 0 | 0 | 0 | 0 | 0 | 746 | 130800
|  |  | Application Development Manager | 195 | 2019-11-01: 56; 2020-05-01: 120; 2020-06-01: 81 | 257 | 50115
|  |  | Developer | 165 | 2020-05-01: 80; 2020-06-01: 65 | 145 | 23925
|  |  | Interface Developer | 165 | 2020-05-01: 48; 2020-06-01: 104 | 152 | 25080
|  |  | Tester | 165 | 2019-10-01: 8; 2019-11-01: 40; 2020-05-01: 64; 2020-06-01: 80 | 192 | 31680
6 | Training |  |  |  | 0 | 0 | 0 | 48 | 140 | 140 | 88 | 216 | 236 | 260 | 264 | 266 | 306 | 132 | 72 | 0 | 0 | 0 | 2168 | 357720
6.1 |  | Develop Master Training Plan |  |  | 0 | 0 | 0 | 48 | 140 | 140 | 88 | 216 | 148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 780 | 128700
|  |  | Business Analyst | 165 | 2020-01-01: 120; 2020-02-01: 74 | 194 | 32010
|  |  | Implementation / Training Lead | 165 | 2019-09-01: 48; 2019-10-01: 140; 2019-11-01: 140; 2019-12-01: 88; 2020-01-01: 96; 2020-02-01: 74 | 586 | 96690
6.2 |  | Develop Training Materials |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88 | 260 | 264 | 124 | 0 | 0 | 0 | 0 | 0 | 0 | 736 | 121440
|  |  | Business Analyst | 165 | 2020-02-01: 36; 2020-03-01: 140; 2020-04-01: 136; 2020-05-01: 80 | 392 | 64680
|  |  | Implementation / Training Lead | 165 | 2020-02-01: 52; 2020-03-01: 120; 2020-04-01: 128; 2020-05-01: 44 | 344 | 56760
6.3 |  | Provide Training |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 142 | 306 | 132 | 72 | 0 | 0 | 0 | 652 | 107580
|  |  | Business Analyst | 165 | 2020-05-01: 70; 2020-06-01: 162; 2020-07-01: 32; 2020-08-01: 32 | 296 | 48840
|  |  | Implementation / Training Lead | 165 | 2020-05-01: 72; 2020-06-01: 144; 2020-07-01: 100; 2020-08-01: 40 | 356 | 58740
7 | Performance Verification & Final Acceptance |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 182 | 158 | 0 | 256 | 632 | 1092 | 1172 | 1196 | 1237 | 324 | 6249 | 1107905
7.1 |  | Provide System Documentation |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156 | 29860
|  |  | Application Development Manager | 195 | 2020-02-01: 8; 2020-03-01: 24 | 32 | 6240
|  |  | Database Administrator | 185 | 2020-02-01: 28; 2020-03-01: 28 | 56 | 10360
|  |  | Technical Lead | 195 | 2020-02-01: 36; 2020-03-01: 32 | 68 | 13260
7.1 |  | Provide System Maintenance Plan |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 184 | 35300
|  |  | Application Development Manager | 195 | 2020-02-01: 24; 2020-03-01: 24 | 48 | 9360
|  |  | Database Administrator | 185 | 2020-02-01: 38; 2020-03-01: 20 | 58 | 10730
|  |  | Technical Lead | 195 | 2020-02-01: 48; 2020-03-01: 30 | 78 | 15210
7.2 |  | Transition to Production Environment |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 256 | 632 | 76 | 0 | 0 | 0 | 0 | 964 | 176560
|  |  | Application Development Manager | 195 | 2020-05-01: 24; 2020-06-01: 80; 2020-07-01: 34 | 138 | 26910
|  |  | Database Administrator | 185 | 2020-05-01: 160; 2020-06-01: 164; 2020-07-01: 2 | 326 | 60310
|  |  | Developer | 165 | 2020-05-01: 16; 2020-06-01: 116; 2020-07-01: 2 | 134 | 22110
|  |  | Project Manager | 195 | 2020-07-01: 16 | 16 | 3120
|  |  | Technical Lead | 195 | 2020-05-01: 40; 2020-06-01: 152; 2020-07-01: 20 | 212 | 41340
|  |  | Tester | 165 | 2020-05-01: 16; 2020-06-01: 120; 2020-07-01: 2 | 138 | 22770
7.3 |  | Conduct Performance Verification |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1016 | 1172 | 1196 | 1237 | 324 | 4945 | 866185
|  |  | Application Development Manager | 195 | 2020-07-01: 96; 2020-08-01: 140; 2020-09-01: 156; 2020-10-01: 171; 2020-11-01: 44 | 607 | 118365
|  |  | Business Analyst | 165 | 2020-07-01: 100; 2020-08-01: 140; 2020-09-01: 140; 2020-10-01: 155; 2020-11-01: 36 | 571 | 94215
|  |  | Database Administrator | 185 | 2020-07-01: 164; 2020-08-01: 172; 2020-09-01: 172; 2020-10-01: 163; 2020-11-01: 36 | 707 | 130795
|  |  | Developer | 165 | 2020-07-01: 164; 2020-08-01: 164; 2020-09-01: 164; 2020-10-01: 171; 2020-11-01: 36 | 699 | 115335
|  |  | Implementation / Training Lead | 165 | 2020-07-01: 40; 2020-08-01: 80; 2020-09-01: 80; 2020-10-01: 95; 2020-11-01: 10 | 305 | 50325
|  |  | Interface Developer | 165 | 2020-07-01: 156; 2020-08-01: 156; 2020-09-01: 164; 2020-10-01: 171; 2020-11-01: 44 | 691 | 114015
|  |  | Technical Lead | 195 | 2020-07-01: 124; 2020-08-01: 148; 2020-09-01: 148; 2020-10-01: 143; 2020-11-01: 34 | 597 | 116415
|  |  | Tester | 165 | 2020-07-01: 172; 2020-08-01: 172; 2020-09-01: 172; 2020-10-01: 168; 2020-11-01: 84 | 768 | 126720
|  | Total Prime Contractor Hours: | [20 empty] | 23328 | 4137730
|  | Total Subcontractor Hours | [20 empty] | 0 | 0
|  | Total Hours: |  |  | 0 | 684 | 1156 | 1373 | 1506 | 1546 | 1379 | 1434 | 1566 | 1536 | 1265 | 1408 | 1522 | 1478 | 1498 | 1482 | 1507 | 480 | 23328 | 4137730
[5 empty] | 2020-11-01: Average Hourly Rate |  | 177.3718

## 9. AWS IaaS Resources
Schedule 9. AWS IaaS Resources
Instructions: 1 - Using the AWS pricing calulator found here: https://calculator.s3.amazonaws.com/index.html 2 - Select "US West (Oregon)" for the region 3 - Create your resources as needed from the pricing calculator 4 - Be sure to include storage and data transfer costs 5 - Use "On-Demand" for the billing option 6 - Enter each resource on a row below. Add new rows as needed. 7 - Do NOT include support costs 8 - Remove the two example rows
AWS Resource List |  | Resource Type | Quantity | Monthly Cost | Total Monthly Cost | Notes
1 | RDS PostgreSQL Database - Dev | db.t2.xlarge | 1 | 164 | 164
2 | RDS PostgreSQL Database - Non-Production (Train, Test) | db.t2.xlarge | 2 | 164 | 328
3 | RDS PostgreSQL Database - Non-Production (UAT) | db.m5.2xlarge | 1 | 1210 | 1210
4 | RDS PostgreSQL Database - Production | db.m5.4xlarge | 1 | 2356 | 2356
5 | EC2 Web Server | a1.large | 11 | 37 | 407
6 | Amazon Cloud Watch |  |  | 250 | 250
7 | AWS CloudTrail |  |  | 2 | 2
8 | Simple Email Service |  |  | 20 | 20
9 | Simple Storage Service |  |  | 60 | 60
10 | Elastic File System |  |  | 5 | 5
11 | ElastiCache |  |  | 63 | 63
12 | EC2 Container Service - Not in estimator |  |  | 43 | 43
13 | EC2 Container Registry (ECR) - Not in estimator |  |  | 7 | 7
14 | AWS Config |  |  | 31 | 31
15 | API Gateway - Not in estimator |  |  | 10 | 10
16 | AWS Key Management Service |  |  | 1.67 | 1.67
17 | Route 53 |  |  | 2 | 2
18 | AWS Data Transfer |  |  | 15 | 15
19 | Amazon Elastic Load Balancer |  |  | 200 | 200
20 | Amazon WorkDocs |  |  | 75 | 75
21 | Glacier |  |  | 15 | 15
22 | VPC Services |  | 3 | 300 | 300
Totals |  |  | 16 |  | 5564.67