## 1. M&E SFY Summary
Attachment B13 - M&E Staffing Schedules
Schedule 1
M&E Staffing Assumptions Summary
No Price related information should be included within the M&E Staffing Assumptions
ONLY UPDATE THE ASSUMPTIONS TABLE ON THIS TAB.
Assumptions
1 | Updated all associated sheets herin to the latest Key Task updates contained in Schedule B5
2
3
4
5
6
7
8
9
10

## 2. Transition-In Staff Loading
Schedule 2
M&E Transition-In Staff Loading: May 2024 - April 2025
|  |  | Service Month | [11 empty] | Total M&E Transition-In Hours | Average Monthly Hours Constant
ID | Key Task | Position <From Tab 6> | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |  |  | Average Monthly FTEs | Average Monthly Hours
|  |  | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01
|  |  | 176 | 160 | 176 | 176 | 160 | 176 | 144 | 168 | 168 | 152 | 168 | 176 | 2000 | 166.6667
1 | Project Management
1.1 | Project Management | M&E Project Management Office (PMO) Lead | 176 | 160 | 176 | 176 | 160 | 176 | 144 | 168 | 168 | 152 | 168 | 176 | 2000 |  | 1 | 166.6667
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
| Project Management Subtotal |  | 176 | 160 | 176 | 176 | 160 | 176 | 144 | 168 | 168 | 152 | 168 | 176 | 2000 |  | 1 | 166.6667
1.2 | Work Plan/Schedule Management | M&E Project Scheduler | 176 | 160 | 176 | 176 | 160 | 176 | 144 | 168 | 168 | 152 | 168 | 176 | 2000 |  | 1 | 166.6667
|  | PMO Analyst | 528 | 480 | 528 | 528 | 480 | 528 | 432 | 504 | 504 | 456 | 504 | 528 | 6000 |  | 3 | 500
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
| Work Plan/Schedule Management Subtotal |  | 704 | 640 | 704 | 704 | 640 | 704 | 576 | 672 | 672 | 608 | 672 | 704 | 8000 |  | 4 | 666.6667
1.3 | PMO Support | PMO Analyst | 880 | 800 | 880 | 880 | 800 | 880 | 720 | 840 | 840 | 760 | 840 | 880 | 10000 |  | 5 | 833.3333
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
| PMO Support Subtotal |  | 880 | 800 | 880 | 880 | 800 | 880 | 720 | 840 | 840 | 760 | 840 | 880 | 10000 |  | 5 | 833.3333
| Project Management Subtotal |  | 1760 | 1600 | 1760 | 1760 | 1600 | 1760 | 1440 | 1680 | 1680 | 1520 | 1680 | 1760 | 20000 |  | 10 | 1666.6667
2 | SCRs
2.1 | SCR Team Management | Functional Lead | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152 | 168 | 176 | 496 |  | 0.248 | 41.3333
|  | M&E Application Manager | 176 | 160 | 176 | 176 | 160 | 176 | 144 | 168 | 168 | 152 | 168 | 176 | 2000 |  | 1 | 166.6667
|  | M&E Delivery Integration Office Manager | 176 | 160 | 176 | 176 | 160 | 176 | 144 | 168 | 168 | 152 | 168 | 176 | 2000 |  | 1 | 166.6667
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
| SCR Team Mgmt Subtotal |  | 352 | 320 | 352 | 352 | 320 | 352 | 288 | 336 | 336 | 456 | 504 | 528 | 4496 |  | 2.248 | 374.6667
2.2 | SCR Prep, Requirements & Design | Business Analyst | 176 | 160 | 176 | 176 | 160 | 176 | 144 | 168 | 168 | 152 | 168 | 528 | 2352 |  | 1.176 | 196
|  | M&E Transition SME | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 608 | 672 | 704 | 1984 |  | 0.992 | 165.3333
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
| SCR Prep, Requirements & Design Subtotal |  | 176 | 160 | 176 | 176 | 160 | 176 | 144 | 168 | 168 | 760 | 840 | 1232 | 4336 |  | 2.168 | 361.3333
2.3 | SCR Build & Test | Database Administrator | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176 | 176 |  | 0.088 | 14.6667
|  | DevOps Engineer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 304 | 336 | 352 | 992 |  | 0.496 | 82.6667
|  | Functional Lead | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 304 | 336 | 352 | 992 |  | 0.496 | 82.6667
|  | M&E Transition SME | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1056 | 1056 |  | 0.528 | 88
|  | Senior QA Analyst | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152 | 168 | 176 | 496 |  | 0.248 | 41.3333
| SCR Build & Test Subtotal |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 760 | 840 | 2112 | 3712 |  | 1.856 | 309.3333
2.4 | SCR Release Management | M&E Project Manager | 176 | 160 | 176 | 176 | 160 | 176 | 144 | 168 | 168 | 152 | 168 | 176 | 2000 |  | 1 | 166.6667
|  | M&E Technical Manager | 176 | 160 | 176 | 176 | 160 | 176 | 144 | 168 | 168 | 152 | 168 | 176 | 2000 |  | 1 | 166.6667
|  | M&E Transition SME | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152 | 168 | 528 | 848 |  | 0.424 | 70.6667
|  | Trainer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176 | 176 |  | 0.088 | 14.6667
[15 empty] | 0 |  | 0 | 0
| SCR Release Management Subtotal |  | 352 | 320 | 352 | 352 | 320 | 352 | 288 | 336 | 336 | 456 | 504 | 1056 | 5024 |  | 2.512 | 418.6667
2.5 | SIRFRA/ SCERFRA/ External Inquiries | M&E Transition SME | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 456 | 504 | 528 | 1488 |  | 0.744 | 124
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
| SIRFRA/ SCERFRA/ External Inquiries Subtotal |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 456 | 504 | 528 | 1488 |  | 0.744 | 124
| SCR Subtotal |  | 880 | 800 | 880 | 880 | 800 | 880 | 720 | 840 | 840 | 2888 | 3192 | 5456 | 19056 |  | 9.528 | 1588
3 | Tier 3 Service Desk Support
3.1 | Tier 3 Service Desk Support | M&E Transition SME | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 456 | 504 | 528 | 1488 |  | 0.744 | 124
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
| Tier 3 Service Desk Support Subtotal |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 456 | 504 | 528 | 1488 |  | 0.744 | 124
| Tier 3 Service Desk Supoort Subtotal |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 456 | 504 | 528 | 1488 |  | 0.744 | 124
4 | CalHEERS SCRs
4.1 | CalHEERS SCRs | Business Analyst | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 352 | 352 |  | 0.176 | 29.3333
|  | Functional Lead | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 704 | 704 |  | 0.352 | 58.6667
|  | M&E Test Manager | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176 | 176 |  | 0.088 | 14.6667
|  | M&E Transition SME | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1760 | 1760 |  | 0.88 | 146.6667
|  | Senior QA Analyst | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176 | 176 |  | 0.088 | 14.6667
| CalHEERS SCRs Subtotal |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3168 | 3168 |  | 1.584 | 264
| CalHEERS SCRs Subtotal |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3168 | 3168 |  | 1.584 | 264
5 | GA/GR
5.1 | GA/GR | M&E Transition SME | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176 | 176 |  | 0.088 | 14.6667
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
| GA/GR Subtotal |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176 | 176 |  | 0.088 | 14.6667
| GA/GR Subtotal |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176 | 176 |  | 0.088 | 14.6667
6 | Security
6.1 | Security Team Management | M&E Deputy Project Manager | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 168 | 168 | 304 | 336 | 352 | 1472 |  | 0.736 | 122.6667
|  | M&E Security Manager | 176 | 160 | 176 | 176 | 160 | 176 | 144 | 168 | 168 | 152 | 168 | 176 | 2000 |  | 1 | 166.6667
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
| Security Subtotal |  | 176 | 160 | 176 | 176 | 160 | 176 | 288 | 336 | 336 | 456 | 504 | 528 | 3472 |  | 1.736 | 289.3333
6.2 | Application Security | Security Analyst | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152 | 168 | 352 | 672 |  | 0.336 | 56
|  | Security Tester | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176 | 176 |  | 0.088 | 14.6667
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
| Application Security Subtotal |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152 | 168 | 528 | 848 |  | 0.424 | 70.6667
5.3 | Security Monitoring | [13 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
| Security Monitoring Subtotal |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
6.3 | Security Support | Functional Lead | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176 | 176 |  | 0.088 | 14.6667
|  | Security Analyst | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176 | 176 |  | 0.088 | 14.6667
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
| Security Support Subtotal |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 352 | 352 |  | 0.176 | 29.3333
| Security Subtotal |  | 176 | 160 | 176 | 176 | 160 | 176 | 288 | 336 | 336 | 608 | 672 | 1408 | 4672 |  | 2.336 | 389.3333
7 | Application/Architecture Evolution
7.1 | App/Arch Team Management | Functional Lead | 176 | 160 | 176 | 176 | 160 | 176 | 144 | 168 | 168 | 152 | 168 | 176 | 2000 |  | 1 | 166.6667
|  | M&E Enterprise Architect | 176 | 160 | 176 | 176 | 160 | 176 | 144 | 168 | 168 | 152 | 168 | 176 | 2000 |  | 1 | 166.6667
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
| App/Arch Team Management Subtotal |  | 352 | 320 | 352 | 352 | 320 | 352 | 288 | 336 | 336 | 304 | 336 | 352 | 4000 |  | 2 | 333.3333
7.2 | App/Arch Dev/Testing/Deployment | Business Analyst | 0 | 0 | 0 | 0 | 160 | 528 | 432 | 504 | 504 | 456 | 504 | 528 | 3616 |  | 1.808 | 301.3333
|  | Human Centric Design Lead | 176 | 160 | 176 | 176 | 160 | 176 | 144 | 168 | 168 | 152 | 168 | 176 | 2000 |  | 1 | 166.6667
|  | M&E Transition SME | 0 | 0 | 0 | 0 | 0 | 352 | 288 | 336 | 336 | 304 | 336 | 352 | 2304 |  | 1.152 | 192
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
| App/Arch Dev/Testing/Deployment Subtotal |  | 176 | 160 | 176 | 176 | 320 | 1056 | 864 | 1008 | 1008 | 912 | 1008 | 1056 | 7920 |  | 3.96 | 660
7.3 | Performance | M&E Transition SME | 0 | 0 | 0 | 0 | 0 | 528 | 432 | 504 | 504 | 456 | 504 | 528 | 3456 |  | 1.728 | 288
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
| Performance Subtotal |  | 0 | 0 | 0 | 0 | 0 | 528 | 432 | 504 | 504 | 456 | 504 | 528 | 3456 |  | 1.728 | 288
| Application/Architecture Evolution Subtotal |  | 528 | 480 | 528 | 528 | 640 | 1936 | 1584 | 1848 | 1848 | 1672 | 1848 | 1936 | 15376 |  | 7.688 | 1281.3333
8 | Innovation
8.1 | Innovation Team Management | M&E innovation Lead | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 168 | 168 | 152 | 168 | 176 | 976 |  | 0.488 | 81.3333
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
| Innovation Team Management Subtotal |  | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 168 | 168 | 152 | 168 | 176 | 976 |  | 0.488 | 81.3333
8.2 | Prepare Innovation Proposal | M&E Transition SME | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 168 | 168 | 152 | 168 | 176 | 976 |  | 0.488 | 81.3333
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
| Prepare Innovation Proposal Subtotal |  | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 168 | 168 | 152 | 168 | 176 | 976 |  | 0.488 | 81.3333
8.3 | Conduct POC/Pilot | Functional Lead | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 168 | 168 | 152 | 168 | 176 | 976 |  | 0.488 | 81.3333
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
| Conduct POC/Pilot Subtotal |  | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 168 | 168 | 152 | 168 | 176 | 976 |  | 0.488 | 81.3333
8.4 | Implement Innovation | M&E Transition SME | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152 | 168 | 176 | 496 |  | 0.248 | 41.3333
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
| Implement Innovation Subtotal |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152 | 168 | 176 | 496 |  | 0.248 | 41.3333
| Innovation Subtotal |  | 0 | 0 | 0 | 0 | 0 | 0 | 432 | 504 | 504 | 608 | 672 | 704 | 3424 |  | 1.712 | 285.3333
9 | Production Operations
9.1 | Production Operations Management | Business Analyst | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 168 | 168 | 152 | 168 | 176 | 976 |  | 0.488 | 81.3333
|  | Functional Lead | 0 | 0 | 0 | 0 | 0 | 176 | 144 | 168 | 168 | 152 | 168 | 176 | 1152 |  | 0.576 | 96
|  | M&E Release Manager | 176 | 160 | 176 | 176 | 160 | 176 | 144 | 168 | 168 | 152 | 168 | 176 | 2000 |  | 1 | 166.6667
|  | M&E Transition Manager | 176 | 160 | 176 | 176 | 160 | 176 | 144 | 168 | 168 | 152 | 168 | 176 | 2000 |  | 1 | 166.6667
[15 empty] | 0 |  | 0 | 0
| Production Operations Management Subtotal |  | 352 | 320 | 352 | 352 | 320 | 528 | 576 | 672 | 672 | 608 | 672 | 704 | 6128 |  | 3.064 | 510.6667
9.2 | Daily Ops/Production Ops | Business Analyst | 176 | 160 | 176 | 176 | 160 | 176 | 144 | 168 | 168 | 152 | 168 | 176 | 2000 |  | 1 | 166.6667
|  | Functional Lead | 176 | 160 | 176 | 176 | 160 | 176 | 144 | 168 | 168 | 152 | 168 | 176 | 2000 |  | 1 | 166.6667
|  | M&E Transition SME | 352 | 320 | 352 | 352 | 320 | 352 | 576 | 672 | 672 | 912 | 1008 | 1232 | 7120 |  | 3.56 | 593.3333
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
| Daily Ops/Production Operations Subtotal |  | 704 | 640 | 704 | 704 | 640 | 704 | 864 | 1008 | 1008 | 1216 | 1344 | 1584 | 11120 |  | 5.56 | 926.6667
9.3 | Batch & Interfaces | M&E Transition SME | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 168 | 168 | 304 | 336 | 352 | 1472 |  | 0.736 | 122.6667
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
| Batch & Interfaces Subtotal |  | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 168 | 168 | 304 | 336 | 352 | 1472 |  | 0.736 | 122.6667
9.4 | Tier 3 Contact Center | Contact Center Lead | 176 | 160 | 176 | 176 | 160 | 176 | 144 | 168 | 168 | 152 | 168 | 176 | 2000 |  | 1 | 166.6667
|  | M&E Transition SME | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 168 | 168 | 456 | 504 | 528 | 1968 |  | 0.984 | 164
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
| Tier 3 Contact Center Subtotal |  | 176 | 160 | 176 | 176 | 160 | 176 | 288 | 336 | 336 | 608 | 672 | 704 | 3968 |  | 1.984 | 330.6667
9.5 | Performance Monitoring | Database Administrator | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152 | 168 | 176 | 496 |  | 0.248 | 41.3333
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
| Performance Monitoring Subtotal |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152 | 168 | 176 | 496 |  | 0.248 | 41.3333
9.6 | Technology Recovery | M&E Transition SME | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152 | 168 | 176 | 496 |  | 0.248 | 41.3333
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
| Technology Recovery Subtotal |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152 | 168 | 176 | 496 |  | 0.248 | 41.3333
| Production Operations Subtotal |  | 1232 | 1120 | 1232 | 1232 | 1120 | 1408 | 1872 | 2184 | 2184 | 3040 | 3360 | 3696 | 23680 |  | 11.84 | 1973.3333
| M&E Staff Loading Total |  | 4576 | 4160 | 4576 | 4576 | 4320 | 6160 | 6336 | 7392 | 7392 | 10792 | 11928 | 18832 | 91040 |  | 45.52 | 7586.6667

## 3. M&E Staff Loading
Schedule 3
M&E Annual Staff Loading: May 2025 - April 2026
Average Monthly Hours Constant
Service Month
ID | Key Task | Position <From Tab 6> | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | Total M&E Year 1: Hours |  | Average Monthly FTEs | Average Monthly Hours
|  |  | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01
|  |  | 168 | 168 | 176 | 168 | 168 | 168 | 144 | 160 | 160 | 152 | 176 | 176 | 1984 | 165.3333
1 | Project Management
1.1 | Project Management | M&E Project Management Office (PMO) Lead | 168 | 168 | 176 | 168 | 168 | 168 | 144 | 160 | 160 | 152 | 176 | 176 | 1984 |  | 1 | 165.3333
|  | PMO Analyst | 168 | 168 | 176 | 168 | 168 | 168 | 144 | 160 | 160 | 152 | 176 | 176 | 1984 |  | 1 | 165.3333
|  | M&E Deputy Project Manager | 67 | 67 | 70 | 67 | 67 | 67 | 58 | 64 | 64 | 61 | 70 | 70 | 792 |  | 0.39919 | 66
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
| Project Management Subtotal |  | 403 | 403 | 422 | 403 | 403 | 403 | 346 | 384 | 384 | 365 | 422 | 422 | 4760 |  | 2.3992 | 396.6667
1.2 | Work Plan/Schedule Management | M&E Project Scheduler | 168 | 168 | 176 | 168 | 168 | 168 | 144 | 160 | 160 | 152 | 176 | 176 | 1984 |  | 1 | 165.3333
|  | PMO Analyst | 504 | 504 | 528 | 504 | 504 | 504 | 432 | 480 | 480 | 456 | 528 | 528 | 5952 |  | 3 | 496
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
| Work Plan/Schedule Management Subtotal |  | 672 | 672 | 704 | 672 | 672 | 672 | 576 | 640 | 640 | 608 | 704 | 704 | 7936 |  | 4 | 661.3333
1.3 | PMO Support | PMO Analyst | 840 | 840 | 880 | 840 | 840 | 840 | 720 | 800 | 800 | 760 | 880 | 880 | 9920 |  | 5 | 826.6667
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
| PMO Support Subtotal |  | 840 | 840 | 880 | 840 | 840 | 840 | 720 | 800 | 800 | 760 | 880 | 880 | 9920 |  | 5 | 826.6667
| Project Management Subtotal |  | 1915 | 1915 | 2006 | 1915 | 1915 | 1915 | 1642 | 1824 | 1824 | 1733 | 2006 | 2006 | 22616 |  | 11.3992 | 1884.6667
2 | SCRs
2.1 | SCR Team Management | Functional Lead | 336 | 336 | 352 | 336 | 336 | 336 | 288 | 320 | 320 | 304 | 352 | 352 | 3968 |  | 2 | 330.6667
|  | M&E Application Manager | 168 | 168 | 176 | 168 | 168 | 168 | 144 | 160 | 160 | 152 | 176 | 176 | 1984 |  | 1 | 165.3333
|  | M&E Delivery Integration Office Manager | 168 | 168 | 176 | 168 | 168 | 168 | 144 | 160 | 160 | 152 | 176 | 176 | 1984 |  | 1 | 165.3333
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
| SCR Team Management Subtotal |  | 672 | 672 | 704 | 672 | 672 | 672 | 576 | 640 | 640 | 608 | 704 | 704 | 7936 |  | 4 | 661.3333
2.2 | SCR Prep, Requirements & Design | Business Analyst | 1008 | 1008 | 1056 | 1008 | 1008 | 1008 | 864 | 960 | 960 | 912 | 1056 | 1056 | 11904 |  | 6 | 992
|  | Human Centric Design Analyst | 1008 | 1008 | 1056 | 1008 | 1008 | 1008 | 864 | 960 | 960 | 912 | 1056 | 1056 | 11904 |  | 6 | 992
|  | Human Centric Design Lead | 168 | 168 | 176 | 168 | 168 | 168 | 144 | 160 | 160 | 152 | 176 | 176 | 1984 |  | 1 | 165.3333
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
| SCR Prep, Requirements & Design Subtotal |  | 2184 | 2184 | 2288 | 2184 | 2184 | 2184 | 1872 | 2080 | 2080 | 1976 | 2288 | 2288 | 25792 |  | 13 | 2149.3333
2.3 | SCR Build & Test | Database Administrator | 504 | 504 | 528 | 504 | 504 | 504 | 432 | 480 | 480 | 456 | 528 | 528 | 5952 |  | 3 | 496
|  | DevOps Engineer | 336 | 336 | 352 | 336 | 336 | 336 | 288 | 320 | 320 | 304 | 352 | 352 | 3968 |  | 2 | 330.6667
|  | Functional Lead | 672 | 672 | 704 | 672 | 672 | 672 | 576 | 640 | 640 | 608 | 704 | 704 | 7936 |  | 4 | 661.3333
|  | Programmer Analyst | 3696 | 3696 | 3872 | 3696 | 3696 | 3696 | 3168 | 3520 | 3520 | 3344 | 3872 | 3872 | 43648 |  | 22 | 3637.3333
|  | QA Analyst | 2184 | 2184 | 2288 | 2184 | 2184 | 2184 | 1872 | 2080 | 2080 | 1976 | 2288 | 2288 | 25792 |  | 13 | 2149.3333
|  | Senior Programmer Analyst | 2016 | 2016 | 2112 | 2016 | 2016 | 2016 | 1728 | 1920 | 1920 | 1824 | 2112 | 2112 | 23808 |  | 12 | 1984
|  | Senior QA Analyst | 672 | 672 | 704 | 672 | 672 | 672 | 576 | 640 | 640 | 608 | 704 | 704 | 7936 |  | 4 | 661.3333
|  | Perf. Tester | 336 | 336 | 352 | 336 | 336 | 336 | 288 | 320 | 320 | 304 | 352 | 352 | 3968 |  | 2 | 330.6667
| SCR Build & Test Subtotal |  | 10416 | 10416 | 10912 | 10416 | 10416 | 10416 | 8928 | 9920 | 9920 | 9424 | 10912 | 10912 | 123008 |  | 62 | 10250.6667
2.4 | SCR Release Management | Training Developer | 168 | 168 | 176 | 168 | 168 | 168 | 144 | 160 | 160 | 152 | 176 | 176 | 1984 |  | 1 | 165.3333
|  | Training Manager | 168 | 168 | 176 | 168 | 168 | 168 | 144 | 160 | 160 | 152 | 176 | 176 | 1984 |  | 1 | 165.3333
|  | M&E Project Manager | 168 | 168 | 176 | 168 | 168 | 168 | 144 | 160 | 160 | 152 | 176 | 176 | 1984 |  | 1 | 165.3333
|  | M&E Technical Manager | 168 | 168 | 176 | 168 | 168 | 168 | 144 | 160 | 160 | 152 | 176 | 176 | 1984 |  | 1 | 165.3333
|  | Programmer Analyst | 336 | 336 | 352 | 336 | 336 | 336 | 288 | 320 | 320 | 304 | 352 | 352 | 3968 |  | 2 | 330.6667
|  | Trainer | 168 | 168 | 176 | 168 | 168 | 168 | 144 | 160 | 160 | 152 | 176 | 176 | 1984 |  | 1 | 165.3333
| SCR Release Management Subtotal |  | 1176 | 1176 | 1232 | 1176 | 1176 | 1176 | 1008 | 1120 | 1120 | 1064 | 1232 | 1232 | 13888 |  | 7 | 1157.3333
2.5 | SIRFRA/ SCERFRA/ External Inquiries | Programmer Analyst | 336 | 336 | 352 | 336 | 336 | 336 | 288 | 320 | 320 | 304 | 352 | 352 | 3968 |  | 2 | 330.6667
|  | Senior Programmer Analyst | 168 | 168 | 176 | 168 | 168 | 168 | 144 | 160 | 160 | 152 | 176 | 176 | 1984 |  | 1 | 165.3333
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
| SIRFRA/ SCERFRA/ External Inquiries Subtotal |  | 504 | 504 | 528 | 504 | 504 | 504 | 432 | 480 | 480 | 456 | 528 | 528 | 5952 |  | 3 | 496
| SCR Subtotal |  | 14952 | 14952 | 15664 | 14952 | 14952 | 14952 | 12816 | 14240 | 14240 | 13528 | 15664 | 15664 | 176576 |  | 89 | 14714.6667
3 | Tier 3 Service Desk Support
3.1 | Tier 3 Service Desk Support | Programmer Analyst | 336 | 336 | 352 | 336 | 336 | 336 | 288 | 320 | 320 | 304 | 352 | 352 | 3968 |  | 2 | 330.6667
|  | Senior Programmer Analyst | 504 | 504 | 528 | 504 | 504 | 504 | 432 | 480 | 480 | 456 | 528 | 528 | 5952 |  | 3 | 496
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
| Tier 3 Service Desk Support Subtotal |  | 840 | 840 | 880 | 840 | 840 | 840 | 720 | 800 | 800 | 760 | 880 | 880 | 9920 |  | 5 | 826.6667
| Tier 3 Service Desk Support Subtotal |  | 840 | 840 | 880 | 840 | 840 | 840 | 720 | 800 | 800 | 760 | 880 | 880 | 9920 |  | 5 | 826.6667
4 | CalHEERS SCRs
4.1 | CalHEERS SCRs | Business Analyst | 336 | 336 | 352 | 336 | 336 | 336 | 288 | 320 | 320 | 304 | 352 | 352 | 3968 |  | 2 | 330.6667
|  | Functional Lead | 672 | 672 | 704 | 672 | 672 | 672 | 576 | 640 | 640 | 608 | 704 | 704 | 7936 |  | 4 | 661.3333
|  | Human Centric Design Analyst | 168 | 168 | 176 | 168 | 168 | 168 | 144 | 160 | 160 | 152 | 176 | 176 | 1984 |  | 1 | 165.3333
|  | M&E Test Manager | 168 | 168 | 176 | 168 | 168 | 168 | 144 | 160 | 160 | 152 | 176 | 176 | 1984 |  | 1 | 165.3333
|  | Programmer Analyst | 504 | 504 | 528 | 504 | 504 | 504 | 432 | 480 | 480 | 456 | 528 | 528 | 5952 |  | 3 | 496
|  | QA Analyst | 504 | 504 | 528 | 504 | 504 | 504 | 432 | 480 | 480 | 456 | 528 | 528 | 5952 |  | 3 | 496
|  | Senior Programmer Analyst | 504 | 504 | 528 | 504 | 504 | 504 | 432 | 480 | 480 | 456 | 528 | 528 | 5952 |  | 3 | 496
|  | Senior QA Analyst | 168 | 168 | 176 | 168 | 168 | 168 | 144 | 160 | 160 | 152 | 176 | 176 | 1984 |  | 1 | 165.3333
| CalHEERS SCRs Subtotal |  | 3024 | 3024 | 3168 | 3024 | 3024 | 3024 | 2592 | 2880 | 2880 | 2736 | 3168 | 3168 | 35712 |  | 18 | 2976
| CalHEERS SCRs Subtotal |  | 3024 | 3024 | 3168 | 3024 | 3024 | 3024 | 2592 | 2880 | 2880 | 2736 | 3168 | 3168 | 35712 |  | 18 | 2976
5 | GA/GR
5.1 | GA/GR | Programmer Analyst | 168 | 168 | 176 | 168 | 168 | 168 | 144 | 160 | 160 | 152 | 176 | 176 | 1984 |  | 1 | 165.3333
|  | Senior Programmer Analyst | 336 | 336 | 352 | 336 | 336 | 336 | 288 | 320 | 320 | 304 | 352 | 352 | 3968 |  | 2 | 330.6667
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
| GA/GR Subtotal |  | 504 | 504 | 528 | 504 | 504 | 504 | 432 | 480 | 480 | 456 | 528 | 528 | 5952 |  | 3 | 496
| GA/GR Subtotal |  | 504 | 504 | 528 | 504 | 504 | 504 | 432 | 480 | 480 | 456 | 528 | 528 | 5952 |  | 3 | 496
6 | Security
6.1 | Security Team Management | M&E Deputy Project Manager | 101 | 101 | 106 | 101 | 101 | 101 | 86 | 96 | 96 | 91 | 106 | 106 | 1192 |  | 0.60081 | 99.3333
|  | M&E Security Manager | 168 | 168 | 176 | 168 | 168 | 168 | 144 | 160 | 160 | 152 | 176 | 176 | 1984 |  | 1 | 165.3333
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
| Security Team Management Subtotal |  | 269 | 269 | 282 | 269 | 269 | 269 | 230 | 256 | 256 | 243 | 282 | 282 | 3176 |  | 1.6008 | 264.6667
6.2 | Application Security | Security Tester | 168 | 168 | 176 | 168 | 168 | 168 | 144 | 160 | 160 | 152 | 176 | 176 | 1984 |  | 1 | 165.3333
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
| Application Security Subtotal |  | 168 | 168 | 176 | 168 | 168 | 168 | 144 | 160 | 160 | 152 | 176 | 176 | 1984 |  | 1 | 165.3333
6.3 | Security Monitoring | Security Analyst | 168 | 168 | 176 | 168 | 168 | 168 | 144 | 160 | 160 | 152 | 176 | 176 | 1984 |  | 1 | 165.3333
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
| Security Monitoring Subtotal |  | 168 | 168 | 176 | 168 | 168 | 168 | 144 | 160 | 160 | 152 | 176 | 176 | 1984 |  | 1 | 165.3333
6.4 | Security Support | Security Analyst | 504 | 504 | 528 | 504 | 504 | 504 | 432 | 480 | 480 | 456 | 528 | 528 | 5952 |  | 3 | 496
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
| Security Support Subtotal |  | 504 | 504 | 528 | 504 | 504 | 504 | 432 | 480 | 480 | 456 | 528 | 528 | 5952 |  | 3 | 496
| Security Subtotal |  | 1109 | 1109 | 1162 | 1109 | 1109 | 1109 | 950 | 1056 | 1056 | 1003 | 1162 | 1162 | 13096 |  | 6.6008 | 1091.3333
7 | Application/Architecture Evolution
7.1 | App/Arch Team Management | Functional Lead | 168 | 168 | 176 | 168 | 168 | 168 | 144 | 160 | 160 | 152 | 176 | 176 | 1984 |  | 1 | 165.3333
|  | M&E Enterprise Architect | 168 | 168 | 176 | 168 | 168 | 168 | 144 | 160 | 160 | 152 | 176 | 176 | 1984 |  | 1 | 165.3333
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
| App/Arch Team Management Subtotal |  | 336 | 336 | 352 | 336 | 336 | 336 | 288 | 320 | 320 | 304 | 352 | 352 | 3968 |  | 2 | 330.6667
7.2 | App/Arch Dev/Testing/Deployment | Functional Lead | 168 | 168 | 176 | 168 | 168 | 168 | 144 | 160 | 160 | 152 | 176 | 176 | 1984 |  | 1 | 165.3333
|  | Human Centric Design Analyst | 168 | 168 | 176 | 168 | 168 | 168 | 144 | 160 | 160 | 152 | 176 | 176 | 1984 |  | 1 | 165.3333
|  | Human Centric Design Lead | 168 | 168 | 176 | 168 | 168 | 168 | 144 | 160 | 160 | 152 | 176 | 176 | 1984 |  | 1 | 165.3333
|  | Programmer Analyst | 1176 | 1176 | 1232 | 1176 | 1176 | 1176 | 1008 | 1120 | 1120 | 1064 | 1232 | 1232 | 13888 |  | 7 | 1157.3333
|  | QA Analyst | 504 | 504 | 528 | 504 | 504 | 504 | 432 | 480 | 480 | 456 | 528 | 528 | 5952 |  | 3 | 496
|  | Senior Programmer Analyst | 504 | 504 | 528 | 504 | 504 | 504 | 432 | 480 | 480 | 456 | 528 | 528 | 5952 |  | 3 | 496
| App/Arch Dev/Testing/Deployment Subtotal |  | 2688 | 2688 | 2816 | 2688 | 2688 | 2688 | 2304 | 2560 | 2560 | 2432 | 2816 | 2816 | 31744 |  | 16 | 2645.3333
7.3 | Performance | Data Analyst | 168 | 168 | 176 | 168 | 168 | 168 | 144 | 160 | 160 | 152 | 176 | 176 | 1984 |  | 1 | 165.3333
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
| Performance Subtotal |  | 168 | 168 | 176 | 168 | 168 | 168 | 144 | 160 | 160 | 152 | 176 | 176 | 1984 |  | 1 | 165.3333
| Application/Architecture Evolution Subtotal |  | 3192 | 3192 | 3344 | 3192 | 3192 | 3192 | 2736 | 3040 | 3040 | 2888 | 3344 | 3344 | 37696 |  | 19 | 3141.3333
8 | Innovation
8.1 | Innovation Team Management | M&E innovation Lead | 168 | 168 | 176 | 168 | 168 | 168 | 144 | 160 | 160 | 152 | 176 | 176 | 1984 |  | 1 | 165.3333
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
| Innovation Team Management Subtotal |  | 168 | 168 | 176 | 168 | 168 | 168 | 144 | 160 | 160 | 152 | 176 | 176 | 1984 |  | 1 | 165.3333
8.2 | Prepare Innovation Proposal | Human Centric Design Analyst | 168 | 168 | 176 | 168 | 168 | 168 | 144 | 160 | 160 | 152 | 176 | 176 | 1984 |  | 1 | 165.3333
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
| Prepare Innovation Proposal Subtotal |  | 168 | 168 | 176 | 168 | 168 | 168 | 144 | 160 | 160 | 152 | 176 | 176 | 1984 |  | 1 | 165.3333
8.3 | Conduct POC/Pilot | Functional Lead | 168 | 168 | 176 | 168 | 168 | 168 | 144 | 160 | 160 | 152 | 176 | 176 | 1984 |  | 1 | 165.3333
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
| Conduct POC/Pilot Subtotal |  | 168 | 168 | 176 | 168 | 168 | 168 | 144 | 160 | 160 | 152 | 176 | 176 | 1984 |  | 1 | 165.3333
8.4 | Implement Innovation | Senior Programmer Analyst | 168 | 168 | 176 | 168 | 168 | 168 | 144 | 160 | 160 | 152 | 176 | 176 | 1984 |  | 1 | 165.3333
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
| Implement Innovation Subtotal |  | 168 | 168 | 176 | 168 | 168 | 168 | 144 | 160 | 160 | 152 | 176 | 176 | 1984 |  | 1 | 165.3333
| Innovation Subtotal |  | 672 | 672 | 704 | 672 | 672 | 672 | 576 | 640 | 640 | 608 | 704 | 704 | 7936 |  | 4 | 661.3333
9 | Production Operations
9.1 | Production Operations Management | Business Analyst | 336 | 336 | 352 | 336 | 336 | 336 | 288 | 320 | 320 | 304 | 352 | 352 | 3968 |  | 2 | 330.6667
|  | M&E Release Manager | 168 | 168 | 176 | 168 | 168 | 168 | 144 | 160 | 160 | 152 | 176 | 176 | 1984 |  | 1 | 165.3333
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
| Production Operations Management Subtotal |  | 504 | 504 | 528 | 504 | 504 | 504 | 432 | 480 | 480 | 456 | 528 | 528 | 5952 |  | 3 | 496
9.2 | Daily Ops/Production Ops | Business Analyst | 168 | 168 | 176 | 168 | 168 | 168 | 144 | 160 | 160 | 152 | 176 | 176 | 1984 |  | 1 | 165.3333
|  | Programmer Analyst | 168 | 168 | 176 | 168 | 168 | 168 | 144 | 160 | 160 | 152 | 176 | 176 | 1984 |  | 1 | 165.3333
|  | Framework Lead | 168 | 168 | 176 | 168 | 168 | 168 | 144 | 160 | 160 | 152 | 176 | 176 | 1984 |  | 1 | 165.3333
|  | Senior Programmer Analyst | 1344 | 1344 | 1408 | 1344 | 1344 | 1344 | 1152 | 1280 | 1280 | 1216 | 1408 | 1408 | 15872 |  | 8 | 1322.6667
[15 empty] | 0 |  | 0 | 0
| Daily Ops/Production Operations Subtotal |  | 1848 | 1848 | 1936 | 1848 | 1848 | 1848 | 1584 | 1760 | 1760 | 1672 | 1936 | 1936 | 21824 |  | 11 | 1818.6667
9.3 | Batch & Interfaces | Batch Operations Analyst | 1008 | 1008 | 1056 | 1008 | 1008 | 1008 | 864 | 960 | 960 | 912 | 1056 | 1056 | 11904 |  | 6 | 992
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
| Batch & Interfaces Subtotal |  | 1008 | 1008 | 1056 | 1008 | 1008 | 1008 | 864 | 960 | 960 | 912 | 1056 | 1056 | 11904 |  | 6 | 992
9.4 | Tier 3 Contact Center | Contact Center Lead | 168 | 168 | 176 | 168 | 168 | 168 | 144 | 160 | 160 | 152 | 176 | 176 | 1984 |  | 1 | 165.3333
|  | Senior Programmer Analyst | 504 | 504 | 528 | 504 | 504 | 504 | 432 | 480 | 480 | 456 | 528 | 528 | 5952 |  | 3 | 496
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
| Tier 3 Contact Center Subtotal |  | 672 | 672 | 704 | 672 | 672 | 672 | 576 | 640 | 640 | 608 | 704 | 704 | 7936 |  | 4 | 661.3333
9.5 | Performance Monitoring | Database Administrator | 504 | 504 | 528 | 504 | 504 | 504 | 432 | 480 | 480 | 456 | 528 | 528 | 5952 |  | 3 | 496
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
| Performance Monitoring Subtotal |  | 504 | 504 | 528 | 504 | 504 | 504 | 432 | 480 | 480 | 456 | 528 | 528 | 5952 |  | 3 | 496
9.6 | Technology Recovery | Programmer Analyst | 168 | 168 | 176 | 168 | 168 | 168 | 144 | 160 | 160 | 152 | 176 | 176 | 1984 |  | 1 | 165.3333
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
[15 empty] | 0 |  | 0 | 0
| Technology Recovery Subtotal |  | 168 | 168 | 176 | 168 | 168 | 168 | 144 | 160 | 160 | 152 | 176 | 176 | 1984 |  | 1 | 165.3333
| Production Operations Subtotal |  | 4704 | 4704 | 4928 | 4704 | 4704 | 4704 | 4032 | 4480 | 4480 | 4256 | 4928 | 4928 | 55552 |  | 28 | 4629.3333
| M&E Staff Loading Total |  | 30912 | 30912 | 32384 | 30912 | 30912 | 30912 | 26496 | 29440 | 29440 | 27968 | 32384 | 32384 | 365056 |  | 184 | 30421.3333
Average Hourly Rate
Assumptions

## 4. M&E DB Migration
Schedule 4
M&E Database Migration Price: May 2025 - April 2026
Average Monthly Hours Constant
Service Month
# | Key Task | Position <Must be in Tab 6> | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
|  |  | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01
|  |  | 168 | 168 | 176 | 168 | 168 | 168 | 144 | 160 | 160 | 152 | 176 | 176 | 165.3333
1 | Project Management
1.1 | Project Management | DB Migration Project Manager | 168 | 168 | 176 | 168 | 168 | 168 | 144 | 160 | 160 | 152 | 176 | 176
1.1 | Project Management | DB Migration SME | 430 | 430 | 431 | 430 | 430 | 430 | 430 | 430 | 430 | 430 | 431 | 430
1.2 | PMO/Admin Support | PMO Analyst | 534 | 534 | 534 | 534 | 534 | 534 | 534 | 534 | 534 | 534 | 534 | 534
| Subtotal PM/PMO |  | 1132 | 1132 | 1141 | 1132 | 1132 | 1132 | 1108 | 1124 | 1124 | 1116 | 1141 | 1140
2 | DB Architecture & Requirements Assessment
2.1 | Plan, Prepare, & Conduct Architecture Review | Database Administrator | 2025-05-01: 1688; 2025-06-01: 562
2.1 | Plan, Prepare, & Conduct Architecture Review | Senior Programmer Analyst | 2025-05-01: 1688; 2025-06-01: 562
2.1 | Plan, Prepare, & Conduct Architecture Review | DB Migration SME | 2025-05-01: 3128; 2025-06-01: 1042
2.1 | Plan, Prepare, & Conduct Architecture Review | DB Migration Analyst | 2025-05-01: 992; 2025-06-01: 331
2.2 | Prepare Requirements Matrix, Summary and Recommendations | DB Migration Analyst | 2025-05-01: 3443; 2025-06-01: 1147
2.2 | Prepare Requirements Matrix, Summary and Recommendations | DB Migration SME | 2025-05-01: 2003; 2025-06-01: 667
| Subtotal DB Architecture & Req Assessment |  | 12942 | 4311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | DB Migration Design
3.1 | Plan, Prepare, & Conduct Design Sessions | Database Administrator | 2025-07-01: 2002; 2025-08-01: 668
3.1 | Plan, Prepare, & Conduct Design Sessions | Senior Programmer Analyst | 2025-07-01: 2995; 2025-08-01: 998
3.1 | Plan, Prepare, & Conduct Design Sessions | DB Migration SME | 2025-07-01: 2804; 2025-08-01: 934
3.2 | Prepare Design Specs, Test Plan and Migration Plan | QA Analyst | 2025-07-01: 1116; 2025-08-01: 372
3.2 | Prepare Design Specs, Test Plan and Migration Plan | DB Migration SME | 2025-07-01: 1440; 2025-08-01: 480
3.2 | Prepare Design Specs, Test Plan and Migration Plan | DB Migration Analyst | 2025-07-01: 2002; 2025-08-01: 668
| Subtotal DB Migration Design |  | 0 | 0 | 12359 | 4120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | DB Migration
4.1 | Plan, Prepare, Test & Implement DB Migration | Senior QA Analyst | 2025-10-01: 82; 2025-11-01: 182; 2025-12-01: 700; 2026-01-01: 1090; 2026-02-01: 700; 2026-03-01: 700; 2026-04-01: 182
4.1 | Plan, Prepare, Test & Implement DB Migration | DB Migration SME | 108 | 110 | 110 | 110 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400
4.1 | Plan, Prepare, Test & Implement DB Migration | Perf. Tester | 2025-11-01: 134; 2025-12-01: 534; 2026-01-01: 800; 2026-02-01: 534; 2026-03-01: 534; 2026-04-01: 134
4.1 | Plan, Prepare, Test & Implement DB Migration | QA Analyst | 2025-11-01: 90; 2025-12-01: 364; 2026-01-01: 546; 2026-02-01: 364; 2026-03-01: 364; 2026-04-01: 91
4.1 | Plan, Prepare, Test & Implement DB Migration | Security Tester | 2025-11-01: 132; 2025-12-01: 529; 2026-01-01: 794; 2026-02-01: 529; 2026-03-01: 529; 2026-04-01: 132
4.1 | Plan, Prepare, Test & Implement DB Migration | Programmer Analyst |  | 220 | 220 | 229 | 1334 | 1334 | 1334 | 668 | 334 | 334 | 334 | 334
4.1 | Plan, Prepare, Test & Implement DB Migration | Senior Programmer Analyst |  | 60 | 62 | 62 | 364 | 364 | 364 | 182 | 90 | 90 | 90 | 90
4.2 | Prepare Migration Report | DB Migration Analyst | 150 | 150 | 150 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152 | 152
4.2 | Prepare Migration Report | DB Migration SME | 66 | 66 | 66 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 69
| Subtotal DB Migration |  | 324 | 606 | 608 | 623 | 2320 | 2402 | 2858 | 3599 | 4276 | 3173 | 3173 | 1584
| Total M&E DB Migration Price |  | 14398 | 6049 | 14108 | 5875 | 3452 | 3534 | 3966 | 4723 | 5400 | 4289 | 4314 | 2724
Assumptions
1
2
3
4
5

## 5. M&E Task Management
Schedule 5
M&E Task Management Price: May 2025 - April 2026
Average Monthly Hours Constant
Service Month
# | Key Task | Position <Must be in Tab 6> | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
|  |  | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01
|  |  | 168 | 168 | 176 | 168 | 168 | 168 | 144 | 160 | 160 | 152 | 176 | 176 | 165.3333
1 | Project Management
1.1 | Project Management | Task Management Lead | 2025-05-01: 168; 2025-06-01: 168; 2025-07-01: 176; 2025-08-01: 168; 2025-09-01: 168; 2025-10-01: 168
1.2 | PMO/Admin Support | Task Management SME | 2025-05-01: 168; 2025-06-01: 168; 2025-07-01: 176; 2025-08-01: 168; 2025-09-01: 168; 2025-10-01: 32
| Subtotal PM/PMO |  | 336 | 336 | 352 | 336 | 336 | 200 | 0 | 0 | 0 | 0 | 0 | 0
2 | Task Management Architecture & Process Assessment
2.1 | Plan, Prepare, Schedule & Conduct Assessments in 4 Counties | Functional Lead | 2025-05-01: 504; 2025-06-01: 504; 2025-07-01: 32
2.1 | Plan, Prepare, Schedule & Conduct Assessments in 4 Counties | Human Centric Design Analyst | 2025-05-01: 336; 2025-06-01: 336; 2025-07-01: 48
2.2 | Prepare Recommendations Report | Business Analyst | 2025-05-01: 504; 2025-06-01: 504; 2025-07-01: 32
| Subtotal Task Management Assessment |  | 1344 | 1344 | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Task Management Requirements Analysis
3.1 | Plan, Prepare, Schedule & Conduct Requirements Sessions | Human Centric Design Analyst | 2025-07-01: 280
3.2 | Prepare Requirements Matrix, Summary and Recommendations | Senior Programmer Analyst | 2025-07-01: 1170
| Subtotal Task Management Requirements Analysis |  | 0 | 0 | 1450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Task Management Architecture Design
4.1 | Plan, Prepare, Schedule & Conduct Design Sessions | Human Centric Design Analyst | 2025-08-01: 168; 2025-09-01: 168; 2025-10-01: 64
4.1 | Plan, Prepare, Schedule & Conduct Design Sessions | Human Centric Design Lead | 2025-08-01: 168; 2025-09-01: 72
4.2 | Prepare Design Artifacts, Summary and Recommendations | Task Management SME | 2025-08-01: 504; 2025-09-01: 362
| Subtotal Task Management Design |  | 0 | 0 | 0 | 840 | 602 | 64 | 0 | 0 | 0 | 0 | 0 | 0
| Total M&E Task Management Price |  | 1680 | 1680 | 1914 | 1176 | 938 | 264 | 0 | 0 | 0 | 0 | 0 | 0
Assumptions
1
2
3
4
5

## 6. Staff Roles
Schedule 6
Base M&E Staff Roles
California State Fiscal Year is July through June
# | Staff Position
1 | M&E Project Manager
2 | M&E Project Management Office (PMO) Lead
3 | M&E Delivery Integration Office Manager
4 | M&E Transition Manager
5 | M&E innovation Lead
6 | M&E Enterprise Architect
7 | M&E Technical Manager
8 | M&E Security Manager
9 | M&E Test Manager
10 | M&E Release Manager
11 | M&E Project Scheduler
12 | Batch Operations Analyst
13 | Business Analyst
14 | Contact Center Lead
15 | Data Analyst
16 | Database Administrator
17 | DB Migration Analyst
18 | DB Migration Project Manager
19 | DB Migration SME
20 | DevOps Engineer
21 | Framework Lead
22 | Functional Lead
23 | Human Centric Design Analyst
24 | Human Centric Design Lead
25 | Imaging Architect
26 | Imaging Programmer
27 | Imaging Project Manager
28 | Imaging SME
29 | M&E Application Manager
30 | M&E Deputy Project Manager
31 | M&E Transition SME
32 | Perf. Tester
33 | PMO Analyst
34 | Programmer Analyst
35 | QA Analyst
36 | Security Analyst
37 | Security Tester
38 | Senior Programmer Analyst
39 | Senior QA Analyst
40 | Task Management Lead
41 | Task Management SME
42 | Trainer
43 | Training Developer
44 | Training Manager

## 7. Optional Imaging
Schedule 7
Optional Imaging Services: May 2025 Through April 2031
# | Key Tasks/Items | Position <Must be in Tab 6> | Number of FTEs | Average Monthly Hours | Average Annual Hours | Average Monthly Hours Constant
168
Imaging Tasks
| Imaging Services | Database Administrator | 0.13 | 21.84 | 262.08
| Imaging Services | Imaging Architect | 1 | 168 | 2016
| Imaging Services | Imaging Project Manager | 1 | 168 | 2016
| Imaging Services | Imaging SME | 1.53 | 257.04 | 3084.48
| Imaging Services | Perf. Tester | 1 | 168 | 2016
| Imaging Services | Imaging Programmer | 5.25 | 882 | 10584
| Imaging Services | QA Analyst | 1.63 | 273.84 | 3286.08
| Imaging Tasks Subtotal |  | 11.54 | 1938.72 | 23264.64