## Slide 1: August 18, 2022
CalWIN Wave-1 County Preparation Phase Kickoff

## Slide 2
County Prep Phase Overview
County Prep Packet
County Prep Support Structure & Schedule
County Prep Metrics and Tracking

## Slide 3: County Prep Phase Timeline
The County Prep Phase occurs 6 weeks prior to CalSAWS Go-Live for Wave 1 Counties, September 19-October 31. This phase allows for Counties to access the CalSAWS Production environment and complete the activities listed in the County Prep Phase Packet. Case data will NOT be included with 1A Cutover.

## Slide 4: County Prep Phase Packet
The County Prep Phase Packet was distributed to Wave 1 Counties on August 5th 2022 in CIT 0216-22.
The purpose of the County Prep Phase Packet is to prepare the CalWIN Counties for the activities to be completed during the County Prep Phase (the 6 weeks leading up to go-live).
The intent is for CalWIN Counties to review and understand the instructions for required and optional activities that need to be completed during County Prep Phase.
The 43 County Prep Activities are listed by subcategory:
Access (1)
Appointment Management (2)
Automated Action (4)
Readiness for BenefitsCal (6)
Caseload Management (1)
System Configuration (7)
Correspondence (2)
Fiscal (6)
GA/GR (3)
IEVS (1)
Lobby Management (2)
Medi-Cal (1)
Security (1)
Task Management (6)
Purpose & Organization

## Slide 5: County Prep Overview
All County Prep activities are assigned a Level of Necessity, and a Priority.
Activity Designations
Necessity
Required activities must be completed before go-live in order for the CalSAWS application to align with County business practices.
Required if Applicable activities are specific to optional system functionality and must be completed by Counties who opt-in.
Optional activities are additional configurations that counties can leverage but will not cause negative impacts if not completed by go live.
Priority
High priority activities are important for each county's ability to conduct their work to County specifications as of go-live.
Medium priority activities should be completed during the County Prep Phase but will have less impact on system usability than High Priority items.
Low Priority activities will not impede system functionality after go-live if not completed.

## Slide 6: County Prep Phase Activities Overview
NOTE: As of 09/02/2022 two activities were added, and one was removed.
Notes: There are 13 Required activities that are high priority and an additional 4 Required if Applicable activities that are high priority

## Slide 7: County Prep Related Efforts
33 of the 41 County Prep activities are covered by the Configuration and Process Simulation efforts.
The worksheets and content of Configuration and Process Simulation will directly inform the activities you’ll be expected to complete during the County Prep Phase.
The associated CalSAWS Configuration Guide and CalSAWS Additional Configuration Guide are included with County Prep Materials and linked in the County Prep Packet.
Configuration and Process Simulation

## Slide 8: County Prep Overview
ALL CalSAWS Users are recommended to Login and confirm access to the CalSAWS Application within the first two weeks of the County Prep Phase. Logging in early will help avoid access-related bottlenecks leading up to and after go-live.
The County staff responsible for the completing the remaining County Prep Activities include:
  Primary, Technical and Implementation Points of Contact (PPOCs, TPOCs and IPOCs)
  County Administrators
  Security Administrators
  Other County Staff designated by Counties
Best practice is for the County Points of Contact who have been working on Process Simulation to be responsible for completing, or guiding other County staff in completing, the Configuration related activities.
Who’s Responsible

## Slide 9
County Prep Phase Packet Navigation & Activities

## Slide 10: County Prep Phase Packet
Each activity in the County Prep Phase packet includes the following components:
Type, Priority, Necessity & Level of Effort bar
  Provides an at-a-glance view of the importance and level of effort for each activity.
Overview
  Describes the background information and the action to be taken
Page Location
  Guides the user to the appropriate page location in CalSAWS
Impact Analysis
  Explains how completing the activity or failure to do so impacts the usability of county specific configurations and functionality.
Instructions
  Details how to complete the activity.
Activity Components

## Slide 11: County Prep Phase Packet
Navigation & Examples of Activities
References to other activities in the document that are related or use the same page
Quick overview of activity specs
Where to find the relevant page
How to complete the activity

## Slide 12: County Prep Phase Packet
Navigation & Examples of Activities
Some activities link to an auxiliary document for instruction. These are included in the County Prep Materials and are housed in the same Web Portal Location as the County Prep Packet.

## Slide 13: County Prep Phase Packet
The CalSAWS Project recognizes the importance of users having the appropriate access within the CalSAWS system, so an additional focused guide is being created to assist counties with configuring their county specific access rules, hereafter referred to as Application Security.
Counties are required to complete the Application Security configuration during the County Prep Phase along with the rest of the County Prep activities.
A separate kickoff event will be held to present the additional materials prior to the start of the County Prep Phase. The date will be announced in coming weeks so that Counties have time to prepare.
A Note on Security

## Slide 14
County Prep Support Structure & Schedule

## Slide 15: County Prep Support Structure
Support Structure for County Prep Phase
Daily Debrief
County Prep Office Hours
County POC Support
Self-Support Resources
COUNTY PREP SUPPORT STRUCTURE
04
Daily office hours
03
County Help Desk Support
02
PPOCs, IPOCs, TPOCs, Security Administrators, BPR Leads (Configuration)
01
Self-Support Resources
County office hours 8:00am – 12:00pm for the first 2 weeks, 9:00am – 10:30am thereafter. Project SMEs, Implementation Team(facilitator)
Daily call 4:00 – 5:00 pm; reporting issues or progress towards resolution. County POCs, Project Security SMEs, Help Desk, Other County designated staff as appropriate, Implementation, TOSS/QA, Regional Managers, Implementation Team (facilitator)
Help Desk Support
05
Daily Debrief Call
Validation of CalSAWS credentials
May assist with users logging in. These will otherwise be the staff completing the activities
County Prep Packet, Configuration Guides, Job Aids
Notes: Helpful to show the WHO and the Responsibility of whom in the meetings/support structures. Who is included in the Daily Debrief – who’s leading/facilitating and who is attending from a support structure + attending

## Slide 16: County Prep Support
Daily Office Hours and Daily Debriefs
Daily Office Hours (Teams Call)
8:00am – 12:00pm 9/19 - 9/30
9:00am – 10:30am 10/3 - 10/27
For questions or issues with completing the County Prep Phase Activities, County Points of Contact can call the Project for additional support. Questions will be documented for follow up and trend analysis.
Daily Debrief (Teams Call)
4:00pm – 5:00pm
The Project will provide updates on challenges identified during office hours and resolutions, when applicable to County Points of Contact. The Project will report out on completion progress made on a weekly basis.

## Slide 17: County Prep Support
Teams Call | Time | Purpose | County Audience | Project Attendees
Daily Office Hours | Mornings - 9/19 - 9/30 8:00am – 12:00pm 10/3 - 10/27 9:00am – 10:30 am | If there are questions/issues with completing the County Prep Phase Activities, Counties can call the Project for additional support | Security Administrators, PPOCs, IPOCs, TPOCs | Project Leads & Subject Matter Experts, Implementation Managers
Daily Debrief Call | Daily: 4:00 – 5:00 pm | The Project will provide updates on high-impact challenges (coming out of the office hours) and resolutions, when applicable. The Project will report out on progress made on a weekly basis (utilizing County Prep metrics and reporting). County stakeholders will share County experiences and escalate additional findings | County Stakeholders (IPOCs, TPOCs, PPOCs, others identified by the Counties) | Project Leadership, Project Leads, Implementation Managers, Regional Managers.
Daily Office Hours and Daily Debriefs

## Slide 18: County Prep Support
Supporting the Wave 1 Counties
August |  |  |  |  |  | 
Su | Mo | Tu | We | Th | Fr | Sa
 | 1 | 2 | 3 | 4 | 5 | 6
7 | 8 | 9 | 10 | 11 | 12 | 13
14 | 15 | 16 | 17 | 18 | 19 | 20
21 | 22 | 23 | 24 | 25 | 26 | 27
28 | 29 | 30 | 31 |  |  | 
September |  |  |  |  |  | 
Su | Mo | Tu | We | Th | Fr | Sa
 |  |  |  | 1 | 2 | 3
4 | 5 | 6 | 7 | 8 | 9 | 10
11 | 12 | 13 | 14 | 15 | 16 | 17
18 | 19 | 20 | 21 | 22 | 23 | 24
25 | 26 | 27 | 28 | 29 | 30 | 
October |  |  |  |  |  | 
Su | Mo | Tu | We | Th | Fr | Sa
 |  |  |  |  |  | 1
2 | 3 | 4 | 5 | 6 | 7 | 8
9 | 10 | 11 | 12 | 13 | 14 | 15
16 | 17 | 18 | 19 | 20 | 21 | 22
23 | 24 | 25 | 26 | 27 | 28 | 29
30 | 31 |  |  |  |  | 
County Prep Phase Packet Distribution
County Prep Kickoff
County Prep Support:
Daily Office Hours
9/19/22 - 9/30/22 8:00 am – 12:00 pm
10/3/22 - 10/27/22 9:00am – 10:30am
Daily Debrief 4:00 – 5:00 pm
CalSAWS Go-Live Wave 1
County Prep Phase Cutover 1A
Go-Live Event
County Prep Application Security Kickoff

## Slide 19
Focused Subject Matter & General Sessions
County Help Desk* Ticket
Daily Office Hours
CalSAWS End User
Security Administrator
IPOCs/TPOCs/PPOCs
County Prep Support
*Help Desk Tickets to be logged based on County Process​
For Login Issues & defects
IPOC – Implementation Point of Contact​
TPOC – Technical Point of Contact​
PPOC – Primary Point of Contact
Escalation Flow
Login activity Only

## Slide 20: Help Desk and Office Hours
When to use what
When to Submit a County Help Desk Ticket
When to Raise Questions through the Office Hours
Resources Provided
When encountering issues logging in
When there are environment/ performance issues
When seeing a functional defect, if applicable
When there are questions completing the activities included in the County Prep Phase Packet
County Prep Phase Packet
County Prep Phase Kick-Off
Configuration Documentation
Notes: When to submit a Help Desk ticket (County Help Desk)
  When encountering issues logging in
  When there are environment/performance issues
  When seeing a functional defect, if applicable
When to dial into the Office Hours
  When there are questions completing the activities included in the County Prep Phase Packet
Resources Provided:
  County Prep Phase Packet
  County Prep Phase Kick-Off
  Configuration Documentation

## Slide 21
County Prep Metrics & Tracking

## Slide 22: County Prep Communications
Keeping Track of Challenges
Questions raised at the Daily Office Hours will be tracked to analyze trends and to ensure follow up and resolution to outstanding inquiries.
Challenges and Issue Resolutions will be reported on the Daily Debrief calls from 4:00-5:00pm.

## Slide 23: County Prep Completion
The CalSAWS Project will track the completion of each county’s County Prep Activities as part of Green Light and Readiness monitoring.
These Metrics will be reported weekly on the Debrief Call and will be included on the Readiness Dashboard and Packet.
Getting it Done
As an optional tool to assist counties with tracking their own progress and to report back, we’ve included a simplified checklist of all the County Prep activities.

## Slide 24: County Prep Completion
Optional Checklist Tool Preview

## Slide 25
Questions?