## 1. Transition-In Staff Loading
Schedule 1
QA Transition-In Staff Loading: December 2026 - January 2027
|  |  | Service Month |  | Total QA Transition-In Hours | Average Monthly Hours Constant
ID | Key Task | Position <From Tab 3> | 1 | 2 |  |  | Average Monthly FTEs | Average Monthly Hours
|  |  | 2026-12-01 | 2027-01-01
|  |  | 152 | 168 | 320 | 160
1 | Management
1.1 | Quality Assurance Management | QA Project Manager | 80 | 24 | 104 |  | 0.325 | 52
|  | QA PMO Manager | 60 | 24 | 84 |  | 0.2625 | 42
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
| Quality Assurance Management Subtotal |  | 140 | 48 | 188 |  | 0.5875 | 94
1.2 | Work Plan/Schedule Management | QA PMO Manager | 60 | 16 | 76 |  | 0.2375 | 38
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
| Work Plan/Schedule Management Subtotal |  | 60 | 16 | 76 |  | 0.2375 | 38
1.3 | Project Management Support | QA PMO Specialist | 50 | 50 | 100 |  | 0.3125 | 50
|  | QA Project Administrator | 12 | 12 | 24 |  | 0.075 | 12
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
| Project Management Support Subtotal |  | 62 | 62 | 124 |  | 0.3875 | 62
| Management Subtotal |  | 262 | 126 | 388 |  | 1.2125 | 194
2 | Quality Assurance
2.1 | Project Management - QA |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
| Project Management - QA Subtotal |  | 0 | 0 | 0 |  | 0 | 0
2.2 | SCR Prep, Requirements & Design - QA |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
| SCR Prep, Requirements & Design - QA Subtotal |  | 0 | 0 | 0 |  | 0 | 0
2.3 | SCR Build/Test - QA |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
| SCR Build Subtotal |  | 0 | 0 | 0 |  | 0 | 0
2.4 | SCR Release Management/Training/OCM - QA |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
| SCR Release Management/Training/OCM - QA Subtotal |  | 0 | 0 | 0 |  | 0 | 0
2.5 | Marketing and Public Communications Support - QA |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
| Marketing and Public Communications Support - QA Subtotal |  | 0 | 0 | 0 |  | 0 | 0
2.6 | Enhancement and Innovation - QA |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
| Enhancement and Innovation - QA Subtotal |  | 0 | 0 | 0 |  | 0 | 0
2.7 | Operations - QA |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
| Operations - QA Subtotal |  | 0 | 0 | 0 |  | 0 | 0
2.8 | Security - QA |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
| Security - QA Subtotal |  | 0 | 0 | 0 |  | 0 | 0
| Quality Assurance Subtotal |  | 0 | 0 | 0 |  | 0 | 0
3 | Independent Test Planning, Executing, and Reporting
3.1 | Independent Test Plan/Management | QA Test Manager | 80 | 40 | 120 |  | 0.375 | 60
|  | QA Test Lead | 96 | 58 | 154 |  | 0.48125 | 77
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
| Independent Test Plan/Management Subtotal |  | 176 | 98 | 274 |  | 0.85625 | 0
3.2 | Independent Test Development |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
| Independent Test Development Subtotal |  | 0 | 0 | 0 |  | 0 | 137
3.3 | Independent Test Execution |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
| Independent Test Execution Subtotal |  | 0 | 0 | 0 |  | 0 | 0
| Independent Test Planning, Executing, and Reporting Subtotal |  | 176 | 98 | 274 |  | 0.85625 | 137
| QA Staff Loading Total |  | 438 | 224 | 662 |  | 2.0687 | 331
Assumptions
1 | Since no significant transition is required, transition in effort is only required to complete the new deliverables. All other ClearBest activities will be included under its existing contract.
2
3
4
5
6
7
8
9
10
Note on K5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Updated the formulas in Column K to average hours over two months instead of six months.

## 2. Staff Loading
Schedule 2
QA Average Annual Staff Loading: February 2027 - January 2033
Average Monthly Hours Constant
Service Year
ID | Key Task | Position <From Tab 3> | Base Year 1 | Base Year 2 | Base Year 3 | Base Year 4 | Base Year 5 | Base Year 6 |  | QA Total: Hours |  | Average Monthly FTEs | Average Monthly Hours
|  |  | February 27 - January 28 | February 28 - January 29 | February 29 - January 30 | February 30 - January 31 | February 31 - January 32 | February 32 - January 33
|  |  | 1920 | 1920 | 1920 | 1920 | 1920 | 1920 |  | 11520 | 160
1 | Management
1.1 | Quality Assurance Management | QA Project Executive | 192 | 192 | 192 | 192 | 192 | 192 |  | 1152 |  | 0.1 | 16
|  | QA Project Manager | 480 | 480 | 480 | 480 | 480 | 480 |  | 2880 |  | 0.25 | 40
|  | QA PMO Manager | 960 | 960 | 960 | 960 | 960 | 960 |  | 5760 |  | 0.5 | 80
[10 empty] | 0 |  | 0 | 0
[10 empty] | 0 |  | 0 | 0
| Quality Assurance Management Subtotal |  | 1632 | 1632 | 1632 | 1632 | 1632 | 1632 | 0 | 9792 |  | 0.85 | 136
1.2 | Work Plan/Schedule Management | QA PMO Manager | 384 | 384 | 384 | 384 | 384 | 384 |  | 2304 |  | 0.2 | 32
|  | QA PMO Specialist | 384 | 384 | 384 | 384 | 384 | 384 |  | 2304 |  | 0.2 | 32
[10 empty] | 0 |  | 0 | 0
[10 empty] | 0 |  | 0 | 0
[10 empty] | 0 |  | 0 | 0
| Work Plan/Schedule Management Subtotal |  | 768 | 768 | 768 | 768 | 768 | 768 | 0 | 4608 |  | 0.4 | 64
1.3 | Project Management Support | QA PMO Manager | 576 | 576 | 576 | 576 | 576 | 576 |  | 3456 |  | 0.3 | 48
|  | QA PMO Specialist | 1536 | 1536 | 1536 | 1536 | 1536 | 1536 |  | 9216 |  | 0.8 | 128
|  | QA Project Administrator | 960 | 960 | 960 | 960 | 960 | 960 |  | 5760 |  | 0.5 | 80
[10 empty] | 0 |  | 0 | 0
[10 empty] | 0 |  | 0 | 0
| Project Management Support Subtotal |  | 3072 | 3072 | 3072 | 3072 | 3072 | 3072 | 0 | 18432 |  | 1.6 | 256
| Management Subtotal |  | 5472 | 5472 | 5472 | 5472 | 5472 | 5472 | 0 | 32832 |  | 2.85 | 456
2 | Quality Assurance
2.1 | Project Management - QA | QA Project Manager | 1440 | 1440 | 1440 | 1440 | 1440 | 1440 |  | 8640 |  | 0.75 | 120
|  | QA Functional Manager | 1920 | 1920 | 1920 | 1920 | 1920 | 1920 |  | 11520 |  | 1 | 160
|  | QA Technical Manager | 480 | 480 | 480 | 480 | 480 | 480 |  | 2880 |  | 0.25 | 40
[10 empty] | 0 |  | 0 | 0
[10 empty] | 0 |  | 0 | 0
| Project Management - QA Subtotal |  | 3840 | 3840 | 3840 | 3840 | 3840 | 3840 | 0 | 23040 |  | 2 | 320
2.2 | SCR Prep, Requirements & Design - QA | QA Enhancements & Innovation Lead | 1440 | 1440 | 1440 | 1440 | 1440 | 1440 |  | 8640 |  | 0.75 | 120
|  | QA Business Analyst Lead | 1920 | 1920 | 1920 | 1920 | 1920 | 1920 |  | 11520 |  | 1 | 160
[10 empty] | 0 |  | 0 | 0
[10 empty] | 0 |  | 0 | 0
[10 empty] | 0 |  | 0 | 0
| SCR Prep, Requirements & Design - QA Subtotal |  | 3360 | 3360 | 3360 | 3360 | 3360 | 3360 | 0 | 20160 |  | 1.75 | 280
2.3 | SCR Build/Test - QA | QA Business Analyst/Tester | 480 | 480 | 480 | 480 | 480 | 480 |  | 2880 |  | 0.25 | 40
|  | QA Business Analyst/Tester | 480 | 480 | 480 | 480 | 480 | 480 |  | 2880 |  | 0.25 | 40
|  | QA Business Analyst/Tester | 480 | 480 | 480 | 480 | 480 | 480 |  | 2880 |  | 0.25 | 40
[10 empty] | 0 |  | 0 | 0
[10 empty] | 0 |  | 0 | 0
| SCR Build Subtotal |  | 1440 | 1440 | 1440 | 1440 | 1440 | 1440 | 0 | 8640 |  | 0.75 | 120
2.4 | SCR Release Management/Training/OCM - QA | QA Business Analyst/Tester | 480 | 480 | 480 | 480 | 480 | 480 |  | 2880 |  | 0.25 | 40
|  | QA Business Analyst/Tester | 480 | 480 | 480 | 480 | 480 | 480 |  | 2880 |  | 0.25 | 40
|  | QA Business Analyst/Tester | 480 | 480 | 480 | 480 | 480 | 480 |  | 2880 |  | 0.25 | 40
[10 empty] | 0 |  | 0 | 0
[10 empty] | 0 |  | 0 | 0
| SCR Release Management/Training/OCM - QA Subtotal |  | 1440 | 1440 | 1440 | 1440 | 1440 | 1440 | 0 | 8640 |  | 0.75 | 120
2.5 | Marketing and Public Communications Support - QA | QA Project Executive | 553 | 553 | 553 | 553 | 553 | 553 |  | 3318 |  | 0.28802 | 46.0833
[10 empty] | 0 |  | 0 | 0
[10 empty] | 0 |  | 0 | 0
[10 empty] | 0 |  | 0 | 0
[10 empty] | 0 |  | 0 | 0
| Marketing and Public Communications Support - QA Subtotal |  | 553 | 553 | 553 | 553 | 553 | 553 | 0 | 3318 |  | 0.28802 | 46.0833
2.6 | Enhancement and Innovation - QA | QA Technical Manager | 480 | 480 | 480 | 480 | 480 | 480 |  | 2880 |  | 0.25 | 40
|  | QA Enhancements & Innovation Lead | 480 | 480 | 480 | 480 | 480 | 480 |  | 2880 |  | 0.25 | 40
[10 empty] | 0 |  | 0 | 0
[10 empty] | 0 |  | 0 | 0
[10 empty] | 0 |  | 0 | 0
| Enhancement and Innovation - QA Subtotal |  | 960 | 960 | 960 | 960 | 960 | 960 | 0 | 5760 |  | 0.5 | 80
2.7 | Operations - QA | QA Technical Manager | 480 | 480 | 480 | 480 | 480 | 480 |  | 2880 |  | 0.25 | 40
|  | QA Technical Lead | 1920 | 1920 | 1920 | 1920 | 1920 | 1920 |  | 11520 |  | 1 | 160
[10 empty] | 0 |  | 0 | 0
[10 empty] | 0 |  | 0 | 0
[10 empty] | 0 |  | 0 | 0
| Operations - QA Subtotal |  | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 0 | 14400 |  | 1.25 | 200
2.8 | Security - QA | QA Technical Manager | 480 | 480 | 480 | 480 | 480 | 480 |  | 2880 |  | 0.25 | 40
|  | QA Technical Lead | 1920 | 1920 | 1920 | 1920 | 1920 | 1920 |  | 11520 |  | 1 | 160
[10 empty] | 0 |  | 0 | 0
[10 empty] | 0 |  | 0 | 0
[10 empty] | 0 |  | 0 | 0
| Security - QA Subtotal |  | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 0 | 14400 |  | 1.25 | 200
0
| Quality Assurance Subtotal |  | 16393 | 16393 | 16393 | 16393 | 16393 | 16393 | 0 | 98358 |  | 8.538 | 1366.0833
3 | Independent Test Planning, Executing, and Reporting
3.1 | Independent Test Plan/Management | QA Test Manager | 1920 | 1920 | 1920 | 1920 | 1920 | 1920 |  | 11520 |  | 1 | 160
|  | QA Test Lead | 1920 | 1920 | 1920 | 1920 | 1920 | 1920 |  | 11520 |  | 1 | 160
[10 empty] | 0 |  | 0 | 0
[10 empty] | 0 |  | 0 | 0
[10 empty] | 0 |  | 0 | 0
| Independent Test Plan/Management Subtotal |  | 3840 | 3840 | 3840 | 3840 | 3840 | 3840 | 0 | 23040 |  | 2 | 320
3.2 | Independent Test Development | QA Business Analyst/Tester | 480 | 480 | 480 | 480 | 480 | 480 |  | 2880 |  | 0.25 | 40
|  | QA Business Analyst/Tester | 480 | 480 | 480 | 480 | 480 | 480 |  | 2880 |  | 0.25 | 40
|  | QA Business Analyst/Tester | 480 | 480 | 480 | 480 | 480 | 480 |  | 2880 |  | 0.25 | 40
[10 empty] | 0 |  | 0 | 0
[10 empty] | 0 |  | 0 | 0
| Independent Test Development Subtotal |  | 1440 | 1440 | 1440 | 1440 | 1440 | 1440 | 0 | 8640 |  | 0.75 | 120
3.3 | Independent Test Execution | QA Business Analyst/Tester | 480 | 480 | 480 | 480 | 480 | 480 |  | 2880 |  | 0.25 | 40
|  | QA Business Analyst/Tester | 480 | 480 | 480 | 480 | 480 | 480 |  | 2880 |  | 0.25 | 40
|  | QA Business Analyst/Tester | 480 | 480 | 480 | 480 | 480 | 480 |  | 2880 |  | 0.25 | 40
[10 empty] | 0 |  | 0 | 0
[10 empty] | 0 |  | 0 | 0
| Independent Test Execution Subtotal |  | 1440 | 1440 | 1440 | 1440 | 1440 | 1440 | 0 | 8640 |  | 0.75 | 120
| Independent Test Planning, Executing, and Reporting Subtotal |  | 6720 | 6720 | 6720 | 6720 | 6720 | 6720 | 0 | 40320 |  | 3.5 | 560
| QA Staff Loading Total |  | 28585 | 28585 | 28585 | 28585 | 28585 | 28585 | 0 | 171510 |  | 14.888 | 2382.0833
Assumptions
1
2
3
4
5
6
7
8
9
10
Note on C5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Linked Staff Positions from Base QA Staff tab into Column C.
Note on K5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Added SUM formulas to Column K to total Columns D-I.
Note on P5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Updated formulas in Column P to match the same updates made in the corrected Price Proposal sheet to calculate Average Monthly Hours by 72 instead of 65.
Note on O80: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Added in O66 since it was not included in the SUM formula here.

## 3. Base QA Staff
Schedule 3
Base QA Staff
California State Fiscal Year is July through June
# | Staff Position
1 | QA Specialist V
2 | QA Specialist IV
3 | QA Project Executive
4 | QA Project Manager
5 | QA Specialist III
6 | QA Functional Manager
7 | QA Technical Manager
8 | QA Test Manager
9 | QA PMO Manager
10 | QA Specialist II
11 | QA Technical Lead
12 | QA Enhancements & Innovation Lead
13 | QA Specialist I
14 | QA Business Analyst Lead
15 | QA Test Lead
16 | QA Technical Analyst
17 | QA Business Analyst/Tester
18 | QA PMO Specialist
19 | QA Analyst II
20 | QA Analyst I
21 | QA Project Administrator
Assumptions
1
2
3
4
5
6
7
8
9
10