## 1. Transition-In Staff Loading
Schedule 1
QA Transition-In Staff Loading: December 2026 - January 2027
|  |  | Service Month |  | Total QA Transition-In Hours | Average Monthly Hours Constant
ID | Key Task | Position <From Tab 3> | 1 | 2 |  |  | Average Monthly FTEs | Average Monthly Hours
|  |  | 2026-12-01 | 2027-01-01
|  |  | 152 | 168 | 320 | 160
1 | Management
1.1 | Quality Assurance Management |  |  |  | 0 |  | 0 | 0
|  | Project Executive | 10 | 10 | 20 |  | 0.0625 | 10
|  | Project Manager | 30.4 | 33.6 | 64 |  | 0.2 | 32
|  | Functional Manager | 22.8 | 25.2 | 48 |  | 0.15 | 24
|  | Technical Manager | 22.8 | 25.2 | 48 |  | 0.15 | 24
|  | Test Manager | 22.8 | 25.2 | 48 |  | 0.15 | 24
| Quality Assurance Management Subtotal |  | 108.8 | 119.2 | 228 |  | 0.7125 | 114
1.2 | Work Plan/Schedule Management |  |  |  | 0 |  | 0 | 0
|  | Project Executive | 10 | 10 | 20 |  | 0.0625 | 10
|  | Project Manager | 15.2 | 16.8 | 32 |  | 0.1 | 16
|  | Functional Manager | 15.2 | 16.8 | 32 |  | 0.1 | 16
|  | Technical Manager | 15.2 | 16.8 | 32 |  | 0.1 | 16
|  | Test Manager | 15.2 | 16.8 | 32 |  | 0.1 | 16
| Work Plan/Schedule Management Subtotal |  | 70.8 | 77.2 | 148 |  | 0.4625 | 74
1.3 | Project Management Support |  |  |  | 0 |  | 0 | 0
|  | Project Manager | 15.2 | 16.8 | 32 |  | 0.1 | 16
|  | Functional Manager | 7.6 | 8.4 | 16 |  | 0.05 | 8
|  | Technical Manager | 7.6 | 8.4 | 16 |  | 0.05 | 8
|  | Test Manager | 7.6 | 8.4 | 16 |  | 0.05 | 8
|  | PMO Manager | 76 | 84 | 160 |  | 0.5 | 80
|  | PMO Specialist | 76 | 84 | 160 |  | 0.5 | 80
|  | Project Administrator | 76 | 84 | 160 |  | 0.5 | 80
| Project Management Support Subtotal |  | 266 | 294 | 560 |  | 1.75 | 280
| Management Subtotal |  | 445.6 | 490.4 | 936 |  | 2.925 | 468
2 | Quality Assurance
2.1 | Project Management - QA |  |  |  | 0 |  | 0 | 0
|  | Project Manager | 15.2 | 16.8 | 32 |  | 0.1 | 16
|  | Functional Manager | 15.2 | 16.8 | 32 |  | 0.1 | 16
|  | Technical Manager | 15.2 | 16.8 | 32 |  | 0.1 | 16
|  | Technical Lead - AWS | 15.2 | 16.8 | 32 |  | 0.1 | 16
|  | Security Lead | 10.64 | 11.76 | 22.4 |  | 0.07 | 11.2
|  | Test Manager | 15.2 | 16.8 | 32 |  | 0.1 | 16
|  | PMO Manager | 76 | 84 | 160 |  | 0.5 | 80
|  | PMO Specialist | 76 | 84 | 160 |  | 0.5 | 80
|  | Project Administrator | 76 | 84 | 160 |  | 0.5 | 80
| Project Management - QA Subtotal |  | 314.64 | 347.76 | 662.4 |  | 2.07 | 331.2
2.2 | SCR Prep, Requirements & Design - QA |  |  |  | 0 |  | 0 | 0
|  | Project Manager | 7.6 | 8.4 | 16 |  | 0.05 | 8
|  | Functional Manager | 15.2 | 16.8 | 32 |  | 0.1 | 16
|  | Business Analyst 1 | 31.92 | 35.28 | 67.2 |  | 0.21 | 33.6
|  | Business Analyst 2 |  | 35.28 | 35.28 |  | 0.11025 | 17.64
|  | Business Analyst 3 |  | 35.28 | 35.28 |  | 0.11025 | 17.64
|  | Test Manager | 18.24 | 20.16 | 38.4 |  | 0.12 | 19.2
|  | Tester 1 | 3.04 | 3.36 | 6.4 |  | 0.02 | 3.2
|  | Tester 2 | 3.04 | 3.36 | 6.4 |  | 0.02 | 3.2
|  | Tester 3 | 3.04 | 3.36 | 6.4 |  | 0.02 | 3.2
|  | Tester 4 |  | 3.36 | 3.36 |  | 0.0105 | 1.68
|  | Tester 5 |  | 3.36 | 3.36 |  | 0.0105 | 1.68
|  | Tester 6 |  | 3.36 | 3.36 |  | 0.0105 | 1.68
|  | Technical Manager | 15.2 | 16.8 | 32 |  | 0.1 | 16
|  | Security Lead | 9.12 | 10.08 | 19.2 |  | 0.06 | 9.6
|  | Technical Lead - AWS | 45.6 | 50.4 | 96 |  | 0.3 | 48
| SCR Prep, Requirements & Design - QA Subtotal |  | 152 | 248.64 | 400.64 |  | 1.252 | 200.32
2.3 | SCR Build/Test - QA |  |  |  | 0 |  | 0 | 0
|  | Project Manager | 7.6 | 8.4 | 16 |  | 0.05 | 8
|  | Functional Manager | 15.2 | 16.8 | 32 |  | 0.1 | 16
|  | Business Analyst 1 | 53.2 | 58.8 | 112 |  | 0.35 | 56
|  | Business Analyst 2 |  | 58.8 | 58.8 |  | 0.18375 | 29.4
|  | Business Analyst 3 |  | 58.8 | 58.8 |  | 0.18375 | 29.4
|  | Test Manager | 15.2 | 16.8 | 32 |  | 0.1 | 16
|  | Tester 1 | 3.04 | 3.36 | 6.4 |  | 0.02 | 3.2
|  | Tester 2 | 3.04 | 3.36 | 6.4 |  | 0.02 | 3.2
|  | Tester 3 | 3.04 | 3.36 | 6.4 |  | 0.02 | 3.2
|  | Tester 4 |  | 3.36 | 3.36 |  | 0.0105 | 1.68
|  | Tester 5 |  | 3.36 | 3.36 |  | 0.0105 | 1.68
|  | Tester 6 |  | 3.36 | 3.36 |  | 0.0105 | 1.68
|  | Technical Manager | 15.2 | 16.8 | 32 |  | 0.1 | 16
|  | Technical Lead - AWS | 15.2 | 16.8 | 32 |  | 0.1 | 16
|  | Security Lead | 9.12 | 10.08 | 19.2 |  | 0.06 | 9.6
| SCR Build Subtotal |  | 139.84 | 282.24 | 422.08 |  | 1.319 | 211.04
2.4 | SCR Release Management/Training/OCM - QA |  |  |  | 0 |  | 0 | 0
|  | Project Manager | 7.6 | 8.4 | 16 |  | 0.05 | 8
|  | Functional Manager | 15.2 | 16.8 | 32 |  | 0.1 | 16
|  | Business Analyst 1 | 15.2 | 16.8 | 32 |  | 0.1 | 16
|  | Business Analyst 2 |  | 16.8 | 16.8 |  | 0.0525 | 8.4
|  | Business Analyst 3 |  | 16.8 | 16.8 |  | 0.0525 | 8.4
|  | Test Manager | 15.2 | 16.8 | 32 |  | 0.1 | 16
|  | Technical Manager | 6.08 | 6.72 | 12.8 |  | 0.04 | 6.4
|  | Technical Lead - AWS | 15.2 | 16.8 | 32 |  | 0.1 | 16
|  | Security Lead | 3.04 | 3.36 | 6.4 |  | 0.02 | 3.2
| SCR Release Management/Training/OCM - QA Subtotal |  | 77.52 | 119.28 | 196.8 |  | 0.615 | 98.4
2.5 | Marketing and Public Communications Support - QA |  |  |  | 0 |  | 0 | 0
|  | Project Manager | 7.6 | 8.4 | 16 |  | 0.05 | 8
|  | Functional Manager | 3.04 | 3.36 | 6.4 |  | 0.02 | 3.2
|  | Business Analyst 1 | 4.56 | 5.04 | 9.6 |  | 0.03 | 4.8
|  | Business Analyst 2 |  | 5.04 | 5.04 |  | 0.01575 | 2.52
|  | Business Analyst 3 |  | 5.04 | 5.04 |  | 0.01575 | 2.52
|  | Technical Manager | 7.6 | 8.4 | 16 |  | 0.05 | 8
|  | Test Manager | 7.6 | 8.4 | 16 |  | 0.05 | 8
| Marketing and Public Communications Support - QA Subtotal |  | 30.4 | 43.68 | 74.08 |  | 0.2315 | 37.04
2.6 | Enhancement and Innovation - QA |  |  |  | 0 |  | 0 | 0
|  | Project Manager | 15.2 | 16.8 | 32 |  | 0.1 | 16
|  | Functional Manager | 4.56 | 5.04 | 9.6 |  | 0.03 | 4.8
|  | Technical Manager | 15.2 | 16.8 | 32 |  | 0.1 | 16
|  | Technical Lead - AWS | 15.2 | 16.8 | 32 |  | 0.1 | 16
|  | Security Lead | 7.6 | 8.4 | 16 |  | 0.05 | 8
| Enhancement and Innovation - QA Subtotal |  | 57.76 | 63.84 | 121.6 |  | 0.38 | 60.8
2.7 | Operations - QA |  |  |  | 0 |  | 0 | 0
|  | Project Manager | 7.6 | 8.4 | 16 |  | 0.05 | 8
|  | Functional Manager | 7.6 | 8.4 | 16 |  | 0.05 | 8
|  | Business Analyst 1 | 7.6 | 8.4 | 16 |  | 0.05 | 8
|  | Business Analyst 2 |  | 8.4 | 8.4 |  | 0.02625 | 4.2
|  | Business Analyst 3 |  | 8.4 | 8.4 |  | 0.02625 | 4.2
|  | Test Manager | 7.6 | 8.4 | 16 |  | 0.05 | 8
|  | Technical Manager | 7.6 | 8.4 | 16 |  | 0.05 | 8
|  | Technical Lead - AWS | 7.6 | 8.4 | 16 |  | 0.05 | 8
|  | Security Lead | 4.56 | 5.04 | 9.6 |  | 0.03 | 4.8
| Operations - QA Subtotal |  | 50.16 | 72.24 | 122.4 |  | 0.3825 | 61.2
2.8 | Security - QA |  |  |  | 0 |  | 0 | 0
|  | Technical Manager | 7.6 | 8.4 | 16 |  | 0.05 | 8
|  | Technical Lead - AWS | 30.4 | 33.6 | 64 |  | 0.2 | 32
|  | Security Lead | 101.84 | 112.56 | 214.4 |  | 0.67 | 107.2
| Security - QA Subtotal |  | 139.84 | 154.56 | 294.4 |  | 0.92 | 147.2
| Quality Assurance Subtotal |  | 962.16 | 1332.24 | 2294.4 |  | 7.17 | 1147.2
3 | Independent Test Planning, Executing, and Reporting
3.1 | Independent Test Plan/Management |  |  |  | 0 |  | 0 | 0
|  | Project Manager | 22.8 | 25.2 | 48 |  | 0.15 | 24
|  | Functional Manager | 22.8 | 25.2 | 48 |  | 0.15 | 24
|  | Business Analyst 1 | 15.2 | 16.8 | 32 |  | 0.1 | 16
|  | Business Analyst 2 |  | 16.8 | 16.8 |  | 0.0525 | 8.4
|  | Business Analyst 3 |  | 16.8 | 16.8 |  | 0.0525 | 8.4
|  | Test Manager | 22.8 | 25.2 | 48 |  | 0.15 | 24
|  | Tester 1 | 18.24 | 20.16 | 38.4 |  | 0.12 | 19.2
|  | Tester 2 | 18.24 | 20.16 | 38.4 |  | 0.12 | 19.2
|  | Tester 3 | 18.24 | 20.16 | 38.4 |  | 0.12 | 19.2
|  | Tester 4 |  | 20.16 | 20.16 |  | 0.063 | 10.08
|  | Tester 5 |  | 20.16 | 20.16 |  | 0.063 | 10.08
|  | Tester 6 |  | 20.16 | 20.16 |  | 0.063 | 10.08
|  | Technical Manager | 16.72 | 18.48 | 35.2 |  | 0.11 | 17.6
|  | Security Lead | 6.08 | 6.72 | 12.8 |  | 0.04 | 6.4
|  | Technical Lead - AWS | 7.6 | 8.4 | 16 |  | 0.05 | 8
| Independent Test Plan/Management Subtotal |  | 168.72 | 280.56 | 449.28 |  | 1.404 | 224.64
3.2 | Independent Test Development |  |  |  | 0 |  | 0 | 0
|  | Functional Manager | 7.6 | 8.4 | 16 |  | 0.05 | 8
|  | Business Analyst 1 | 16.72 | 18.48 | 35.2 |  | 0.11 | 17.6
|  | Business Analyst 2 |  | 18.48 | 18.48 |  | 0.05775 | 9.24
|  | Business Analyst 3 |  | 18.48 | 18.48 |  | 0.05775 | 9.24
|  | Test Manager | 4.56 | 5.04 | 9.6 |  | 0.03 | 4.8
|  | Tester 1 | 56.24 | 62.16 | 118.4 |  | 0.37 | 59.2
|  | Tester 2 | 56.24 | 62.16 | 118.4 |  | 0.37 | 59.2
|  | Tester 3 | 56.24 | 62.16 | 118.4 |  | 0.37 | 59.2
|  | Tester 4 |  | 62.16 | 62.16 |  | 0.19425 | 31.08
|  | Tester 5 |  | 62.16 | 62.16 |  | 0.19425 | 31.08
|  | Tester 6 |  | 62.16 | 62.16 |  | 0.19425 | 31.08
| Independent Test Development Subtotal |  | 197.6 | 441.84 | 639.44 |  | 1.9983 | 319.72
3.3 | Independent Test Execution |  |  |  | 0 |  | 0 | 0
|  | Business Analyst 1 | 7.6 | 8.4 | 16 |  | 0.05 | 8
|  | Business Analyst 2 |  | 8.4 | 8.4 |  | 0.02625 | 4.2
|  | Business Analyst 3 |  | 8.4 | 8.4 |  | 0.02625 | 4.2
|  | Tester 1 | 71.44 | 78.96 | 150.4 |  | 0.47 | 75.2
|  | Tester 2 | 71.44 | 78.96 | 150.4 |  | 0.47 | 75.2
|  | Tester 3 | 71.44 | 78.96 | 150.4 |  | 0.47 | 75.2
|  | Tester 4 |  | 78.96 | 78.96 |  | 0.24675 | 39.48
|  | Tester 5 |  | 78.96 | 78.96 |  | 0.24675 | 39.48
|  | Tester 6 |  | 78.96 | 78.96 |  | 0.24675 | 39.48
| Independent Test Execution Subtotal |  | 221.92 | 498.96 | 720.88 |  | 2.2527 | 360.44
| Independent Test Planning, Executing, and Reporting Subtotal |  | 588.24 | 1221.36 | 1809.6 |  | 5.655 | 712.16
| QA Staff Loading Total |  | 1996 | 3044 | 5040 |  | 15.75 | 2327.36
Assumptions
1 | None
2
3
4
5
6
7
8
9
10

## 2. Staff Loading
Schedule 2
QA Average Annual Staff Loading: February 2027 - January 2033
Average Monthly Hours Constant
Service Year
ID | Key Task | Position <From Tab 3> | Base Year 1 | Base Year 2 | Base Year 3 | Base Year 4 | Base Year 5 | Base Year 6 |  | QA Total: Hours |  | Average Monthly FTEs | Average Monthly Hours
|  |  | February 27 - January 28 | February 28 - January 29 | February 29 - January 30 | February 30 - January 31 | February 31 - January 32 | February 32 - January 33
|  |  | 1920 | 1920 | 1920 | 1920 | 1920 | 1920 |  | 11520 | 160
1 | Management
1.1 | Quality Assurance Management | [10 empty] | 0 | 0
|  | Project Executive | 19.2 | 19.2 | 19.2 | 19.2 | 19.2 | 19.2 |  | 115.2 |  | 0.01 | 1.6
|  | Project Manager | 345.6 | 345.6 | 345.6 | 345.6 | 345.6 | 345.6 |  | 2073.6 |  | 0.18 | 28.8
|  | Functional Manager | 259.2 | 259.2 | 259.2 | 259.2 | 259.2 | 259.2 |  | 1555.2 |  | 0.135 | 21.6
|  | Technical Manager | 259.2 | 259.2 | 259.2 | 259.2 | 259.2 | 259.2 |  | 1555.2 |  | 0.135 | 21.6
|  | Test Manager | 259.2 | 259.2 | 259.2 | 259.2 | 259.2 | 259.2 |  | 1555.2 |  | 0.135 | 21.6
| Quality Assurance Management Subtotal |  | 1142.4 | 1142.4 | 1142.4 | 1142.4 | 1142.4 | 1142.4 | 0 | 6854.4 |  | 0.595 | 95.2
1.2 | Work Plan/Schedule Management | [10 empty] | 0 | 0
|  | Project Executive | 19.2 | 19.2 | 19.2 | 19.2 | 19.2 | 19.2 |  | 115.2 |  | 0.01 | 1.6
|  | Project Manager | 172.8 | 172.8 | 172.8 | 172.8 | 172.8 | 172.8 |  | 1036.8 |  | 0.09 | 14.4
|  | Functional Manager | 172.8 | 172.8 | 172.8 | 172.8 | 172.8 | 172.8 |  | 1036.8 |  | 0.09 | 14.4
|  | Technical Manager | 172.8 | 172.8 | 172.8 | 172.8 | 172.8 | 172.8 |  | 1036.8 |  | 0.09 | 14.4
|  | Test Manager | 172.8 | 172.8 | 172.8 | 172.8 | 172.8 | 172.8 |  | 1036.8 |  | 0.09 | 14.4
| Work Plan/Schedule Management Subtotal |  | 710.4 | 710.4 | 710.4 | 710.4 | 710.4 | 710.4 | 0 | 4262.4 |  | 0.37 | 59.2
1.3 | Project Management Support | [10 empty] | 0 | 0
|  | Project Manager | 172.8 | 172.8 | 172.8 | 172.8 | 172.8 | 172.8 |  | 1036.8 |  | 0.09 | 14.4
|  | Functional Manager | 86.4 | 86.4 | 86.4 | 86.4 | 86.4 | 86.4 |  | 518.4 |  | 0.045 | 7.2
|  | Technical Manager | 86.4 | 86.4 | 86.4 | 86.4 | 86.4 | 86.4 |  | 518.4 |  | 0.045 | 7.2
|  | Test Manager | 86.4 | 86.4 | 86.4 | 86.4 | 86.4 | 86.4 |  | 518.4 |  | 0.045 | 7.2
|  | PMO Manager | 912 | 912 | 912 | 912 | 912 | 912 |  | 5472 |  | 0.475 | 76
|  | PMO Specialist | 912 | 912 | 912 | 912 | 912 | 912 |  | 5472 |  | 0.475 | 76
|  | Project Administrator | 480 | 480 | 480 | 480 | 480 | 480 |  | 2880 |  | 0.25 | 40
| Project Management Support Subtotal |  | 2736 | 2736 | 2736 | 2736 | 2736 | 2736 | 0 | 16416 |  | 1.425 | 228
| Management Subtotal |  | 4588.8 | 4588.8 | 4588.8 | 4588.8 | 4588.8 | 4588.8 | 0 | 27532.8 |  | 2.39 | 382.4
2 | Quality Assurance
2.1 | Project Management - QA | [10 empty] | 0 | 0
|  | Project Manager | 172.8 | 172.8 | 172.8 | 172.8 | 172.8 | 172.8 |  | 1036.8 |  | 0.09 | 14.4
|  | Functional Manager | 172.8 | 172.8 | 172.8 | 172.8 | 172.8 | 172.8 |  | 1036.8 |  | 0.09 | 14.4
|  | Technical Manager | 172.8 | 172.8 | 172.8 | 172.8 | 172.8 | 172.8 |  | 1036.8 |  | 0.09 | 14.4
|  | Test Manager | 172.8 | 172.8 | 172.8 | 172.8 | 172.8 | 172.8 |  | 1036.8 |  | 0.09 | 14.4
|  | PMO Manager | 912 | 912 | 912 | 912 | 912 | 912 |  | 5472 |  | 0.475 | 76
|  | PMO Specialist | 912 | 912 | 912 | 912 | 912 | 912 |  | 5472 |  | 0.475 | 76
|  | Project Administrator | 480 | 480 | 480 | 480 | 480 | 480 |  | 2880 |  | 0.25 | 40
|  | Technical Lead - AWS | 182.4 | 182.4 | 182.4 | 182.4 | 182.4 | 182.4 |  | 1094.4 |  | 0.095 | 15.2
|  | Security Lead | 94.08 | 94.08 | 94.08 | 94.08 | 94.08 | 94.08 |  | 564.48 |  | 0.049 | 7.84
| Project Management - QA Subtotal |  | 3271.68 | 3271.68 | 3271.68 | 3271.68 | 3271.68 | 3271.68 | 0 | 19630.08 |  | 1.704 | 272.64
2.2 | SCR Prep, Requirements & Design - QA | [10 empty] | 0 | 0
|  | Project Manager | 86.4 | 86.4 | 86.4 | 86.4 | 86.4 | 86.4 |  | 518.4 |  | 0.045 | 7.2
|  | Functional Manager | 172.8 | 172.8 | 172.8 | 172.8 | 172.8 | 172.8 |  | 1036.8 |  | 0.09 | 14.4
|  | Business Analyst 1 | 383.04 | 383.04 | 383.04 | 383.04 | 383.04 | 383.04 |  | 2298.24 |  | 0.1995 | 31.92
|  | Business Analyst 2 | 383.04 | 383.04 | 383.04 | 383.04 | 383.04 | 383.04 |  | 2298.24 |  | 0.1995 | 31.92
|  | Business Analyst 3 | 383.04 | 383.04 | 383.04 | 383.04 | 383.04 | 383.04 |  | 2298.24 |  | 0.1995 | 31.92
|  | Test Manager | 207.36 | 207.36 | 207.36 | 207.36 | 207.36 | 207.36 |  | 1244.16 |  | 0.108 | 17.28
|  | Tester 1 | 36.48 | 36.48 | 36.48 | 36.48 | 36.48 | 36.48 |  | 218.88 |  | 0.019 | 3.04
|  | Tester 2 | 36.48 | 36.48 | 36.48 | 36.48 | 36.48 | 36.48 |  | 218.88 |  | 0.019 | 3.04
|  | Tester 3 | 36.48 | 36.48 | 36.48 | 36.48 | 36.48 | 36.48 |  | 218.88 |  | 0.019 | 3.04
|  | Tester 4 | 36.48 | 36.48 | 36.48 | 36.48 | 36.48 | 36.48 |  | 218.88 |  | 0.019 | 3.04
|  | Tester 5 | 36.48 | 36.48 | 36.48 | 36.48 | 36.48 | 36.48 |  | 218.88 |  | 0.019 | 3.04
|  | Tester 6 | 36.48 | 36.48 | 36.48 | 36.48 | 36.48 | 36.48 |  | 218.88 |  | 0.019 | 3.04
|  | Technical Manager | 172.8 | 172.8 | 172.8 | 172.8 | 172.8 | 172.8 |  | 1036.8 |  | 0.09 | 14.4
|  | Security Lead | 80.64 | 80.64 | 80.64 | 80.64 | 80.64 | 80.64 |  | 483.84 |  | 0.042 | 6.72
|  | Technical Lead - AWS | 547.2 | 547.2 | 547.2 | 547.2 | 547.2 | 547.2 |  | 3283.2 |  | 0.285 | 45.6
| SCR Prep, Requirements & Design - QA Subtotal |  | 2635.2 | 2635.2 | 2635.2 | 2635.2 | 2635.2 | 2635.2 | 0 | 15811.2 |  | 1.3725 | 219.6
2.3 | SCR Build/Test - QA | [10 empty] | 0 | 0
|  | Project Manager | 86.4 | 86.4 | 86.4 | 86.4 | 86.4 | 86.4 |  | 518.4 |  | 0.045 | 7.2
|  | Functional Manager | 172.8 | 172.8 | 172.8 | 172.8 | 172.8 | 172.8 |  | 1036.8 |  | 0.09 | 14.4
|  | Business Analyst 1 | 638.4 | 638.4 | 638.4 | 638.4 | 638.4 | 638.4 |  | 3830.4 |  | 0.3325 | 53.2
|  | Business Analyst 2 | 638.4 | 638.4 | 638.4 | 638.4 | 638.4 | 638.4 |  | 3830.4 |  | 0.3325 | 53.2
|  | Business Analyst 3 | 638.4 | 638.4 | 638.4 | 638.4 | 638.4 | 638.4 |  | 3830.4 |  | 0.3325 | 53.2
|  | Test Manager | 172.8 | 172.8 | 172.8 | 172.8 | 172.8 | 172.8 |  | 1036.8 |  | 0.09 | 14.4
|  | Tester 1 | 36.48 | 36.48 | 36.48 | 36.48 | 36.48 | 36.48 |  | 218.88 |  | 0.019 | 3.04
|  | Tester 2 | 36.48 | 36.48 | 36.48 | 36.48 | 36.48 | 36.48 |  | 218.88 |  | 0.019 | 3.04
|  | Tester 3 | 36.48 | 36.48 | 36.48 | 36.48 | 36.48 | 36.48 |  | 218.88 |  | 0.019 | 3.04
|  | Tester 4 | 36.48 | 36.48 | 36.48 | 36.48 | 36.48 | 36.48 |  | 218.88 |  | 0.019 | 3.04
|  | Tester 5 | 36.48 | 36.48 | 36.48 | 36.48 | 36.48 | 36.48 |  | 218.88 |  | 0.019 | 3.04
|  | Tester 6 | 36.48 | 36.48 | 36.48 | 36.48 | 36.48 | 36.48 |  | 218.88 |  | 0.019 | 3.04
|  | Technical Manager | 172.8 | 172.8 | 172.8 | 172.8 | 172.8 | 172.8 |  | 1036.8 |  | 0.09 | 14.4
|  | Security Lead | 80.64 | 80.64 | 80.64 | 80.64 | 80.64 | 80.64 |  | 483.84 |  | 0.042 | 6.72
|  | Technical Lead - AWS | 182.4 | 182.4 | 182.4 | 182.4 | 182.4 | 182.4 |  | 1094.4 |  | 0.095 | 15.2
| SCR Build Subtotal |  | 3001.92 | 3001.92 | 3001.92 | 3001.92 | 3001.92 | 3001.92 | 0 | 18011.52 |  | 1.5635 | 250.16
2.4 | SCR Release Management/Training/OCM - QA | [10 empty] | 0 | 0
|  | Project Manager | 86.4 | 86.4 | 86.4 | 86.4 | 86.4 | 86.4 |  | 518.4 |  | 0.045 | 7.2
|  | Functional Manager | 172.8 | 172.8 | 172.8 | 172.8 | 172.8 | 172.8 |  | 1036.8 |  | 0.09 | 14.4
|  | Business Analyst 1 | 182.4 | 182.4 | 182.4 | 182.4 | 182.4 | 182.4 |  | 1094.4 |  | 0.095 | 15.2
|  | Business Analyst 2 | 182.4 | 182.4 | 182.4 | 182.4 | 182.4 | 182.4 |  | 1094.4 |  | 0.095 | 15.2
|  | Business Analyst 3 | 182.4 | 182.4 | 182.4 | 182.4 | 182.4 | 182.4 |  | 1094.4 |  | 0.095 | 15.2
|  | Test Manager | 172.8 | 172.8 | 172.8 | 172.8 | 172.8 | 172.8 |  | 1036.8 |  | 0.09 | 14.4
|  | Technical Manager | 69.12 | 69.12 | 69.12 | 69.12 | 69.12 | 69.12 |  | 414.72 |  | 0.036 | 5.76
|  | Security Lead | 26.88 | 26.88 | 26.88 | 26.88 | 26.88 | 26.88 |  | 161.28 |  | 0.014 | 2.24
|  | Technical Lead - AWS | 182.4 | 182.4 | 182.4 | 182.4 | 182.4 | 182.4 |  | 1094.4 |  | 0.095 | 15.2
| SCR Release Management/Training/OCM - QA Subtotal |  | 1257.6 | 1257.6 | 1257.6 | 1257.6 | 1257.6 | 1257.6 | 0 | 7545.6 |  | 0.655 | 104.8
2.5 | Marketing and Public Communications Support - QA | [10 empty] | 0 | 0
|  | Project Manager | 86.4 | 86.4 | 86.4 | 86.4 | 86.4 | 86.4 |  | 518.4 |  | 0.045 | 7.2
|  | Functional Manager | 34.56 | 34.56 | 34.56 | 34.56 | 34.56 | 34.56 |  | 207.36 |  | 0.018 | 2.88
|  | Business Analyst 1 | 54.72 | 54.72 | 54.72 | 54.72 | 54.72 | 54.72 |  | 328.32 |  | 0.0285 | 4.56
|  | Business Analyst 2 | 54.72 | 54.72 | 54.72 | 54.72 | 54.72 | 54.72 |  | 328.32 |  | 0.0285 | 4.56
|  | Business Analyst 3 | 54.72 | 54.72 | 54.72 | 54.72 | 54.72 | 54.72 |  | 328.32 |  | 0.0285 | 4.56
|  | Test Manager | 86.4 | 86.4 | 86.4 | 86.4 | 86.4 | 86.4 |  | 518.4 |  | 0.045 | 7.2
|  | Technical Manager | 86.4 | 86.4 | 86.4 | 86.4 | 86.4 | 86.4 |  | 518.4 |  | 0.045 | 7.2
| Marketing and Public Communications Support - QA Subtotal |  | 457.92 | 457.92 | 457.92 | 457.92 | 457.92 | 457.92 | 0 | 2747.52 |  | 0.2385 | 38.16
2.6 | Enhancement and Innovation - QA | [10 empty] | 0 | 0
|  | Project Manager | 172.8 | 172.8 | 172.8 | 172.8 | 172.8 | 172.8 |  | 1036.8 |  | 0.09 | 14.4
|  | Functional Manager | 51.84 | 51.84 | 51.84 | 51.84 | 51.84 | 51.84 |  | 311.04 |  | 0.027 | 4.32
|  | Technical Manager | 172.8 | 172.8 | 172.8 | 172.8 | 172.8 | 172.8 |  | 1036.8 |  | 0.09 | 14.4
|  | Security Lead | 67.2 | 67.2 | 67.2 | 67.2 | 67.2 | 67.2 |  | 403.2 |  | 0.035 | 5.6
|  | Technical Lead - AWS | 182.4 | 182.4 | 182.4 | 182.4 | 182.4 | 182.4 |  | 1094.4 |  | 0.095 | 15.2
| Enhancement and Innovation - QA Subtotal |  | 647.04 | 647.04 | 647.04 | 647.04 | 647.04 | 647.04 | 0 | 3882.24 |  | 0.337 | 53.92
2.7 | Operations - QA | [10 empty] | 0 | 0
|  | Project Manager | 86.4 | 86.4 | 86.4 | 86.4 | 86.4 | 86.4 |  | 518.4 |  | 0.045 | 7.2
|  | Functional Manager | 86.4 | 86.4 | 86.4 | 86.4 | 86.4 | 86.4 |  | 518.4 |  | 0.045 | 7.2
|  | Business Analyst 1 | 91.2 | 91.2 | 91.2 | 91.2 | 91.2 | 91.2 |  | 547.2 |  | 0.0475 | 7.6
|  | Business Analyst 2 | 91.2 | 91.2 | 91.2 | 91.2 | 91.2 | 91.2 |  | 547.2 |  | 0.0475 | 7.6
|  | Business Analyst 3 | 91.2 | 91.2 | 91.2 | 91.2 | 91.2 | 91.2 |  | 547.2 |  | 0.0475 | 7.6
|  | Test Manager | 86.4 | 86.4 | 86.4 | 86.4 | 86.4 | 86.4 |  | 518.4 |  | 0.045 | 7.2
|  | Technical Manager | 86.4 | 86.4 | 86.4 | 86.4 | 86.4 | 86.4 |  | 518.4 |  | 0.045 | 7.2
|  | Security Lead | 40.32 | 40.32 | 40.32 | 40.32 | 40.32 | 40.32 |  | 241.92 |  | 0.021 | 3.36
|  | Technical Lead - AWS | 91.2 | 91.2 | 91.2 | 91.2 | 91.2 | 91.2 |  | 547.2 |  | 0.0475 | 7.6
| Operations - QA Subtotal |  | 750.72 | 750.72 | 750.72 | 750.72 | 750.72 | 750.72 | 0 | 4504.32 |  | 0.391 | 62.56
2.8 | Security - QA | [10 empty] | 0 | 0
|  | Technical Manager | 86.4 | 86.4 | 86.4 | 86.4 | 86.4 | 86.4 |  | 518.4 |  | 0.045 | 7.2
|  | Security Lead | 900.48 | 900.48 | 900.48 | 900.48 | 900.48 | 900.48 |  | 5402.88 |  | 0.469 | 75.04
|  | Technical Lead - AWS | 364.8 | 364.8 | 364.8 | 364.8 | 364.8 | 364.8 |  | 2188.8 |  | 0.19 | 30.4
| Security - QA Subtotal |  | 1351.68 | 1351.68 | 1351.68 | 1351.68 | 1351.68 | 1351.68 | 0 | 8110.08 |  | 0.704 | 112.64
0
| Quality Assurance Subtotal |  | 13373.76 | 13373.76 | 13373.76 | 13373.76 | 13373.76 | 13373.76 | 0 | 80242.56 |  | 6.9655 | 1114.48
3 | Independent Test Planning, Executing, and Reporting
3.1 | Independent Test Plan/Management | [10 empty] | 0 | 0
|  | Project Manager | 259.2 | 259.2 | 259.2 | 259.2 | 259.2 | 259.2 |  | 1555.2 |  | 0.135 | 21.6
|  | Functional Manager | 259.2 | 259.2 | 259.2 | 259.2 | 259.2 | 259.2 |  | 1555.2 |  | 0.135 | 21.6
|  | Business Analyst 1 | 182.4 | 182.4 | 182.4 | 182.4 | 182.4 | 182.4 |  | 1094.4 |  | 0.095 | 15.2
|  | Business Analyst 2 | 182.4 | 182.4 | 182.4 | 182.4 | 182.4 | 182.4 |  | 1094.4 |  | 0.095 | 15.2
|  | Business Analyst 3 | 182.4 | 182.4 | 182.4 | 182.4 | 182.4 | 182.4 |  | 1094.4 |  | 0.095 | 15.2
|  | Test Manager | 259.2 | 259.2 | 259.2 | 259.2 | 259.2 | 259.2 |  | 1555.2 |  | 0.135 | 21.6
|  | Tester 1 | 218.88 | 218.88 | 218.88 | 218.88 | 218.88 | 218.88 |  | 1313.28 |  | 0.114 | 18.24
|  | Tester 2 | 218.88 | 218.88 | 218.88 | 218.88 | 218.88 | 218.88 |  | 1313.28 |  | 0.114 | 18.24
|  | Tester 3 | 218.88 | 218.88 | 218.88 | 218.88 | 218.88 | 218.88 |  | 1313.28 |  | 0.114 | 18.24
|  | Tester 4 | 218.88 | 218.88 | 218.88 | 218.88 | 218.88 | 218.88 |  | 1313.28 |  | 0.114 | 18.24
|  | Tester 5 | 218.88 | 218.88 | 218.88 | 218.88 | 218.88 | 218.88 |  | 1313.28 |  | 0.114 | 18.24
|  | Tester 6 | 218.88 | 218.88 | 218.88 | 218.88 | 218.88 | 218.88 |  | 1313.28 |  | 0.114 | 18.24
|  | Technical Manager | 190.08 | 190.08 | 190.08 | 190.08 | 190.08 | 190.08 |  | 1140.48 |  | 0.099 | 15.84
|  | Security Lead | 53.76 | 53.76 | 53.76 | 53.76 | 53.76 | 53.76 |  | 322.56 |  | 0.028 | 4.48
|  | Technical Lead - AWS | 91.2 | 91.2 | 91.2 | 91.2 | 91.2 | 91.2 |  | 547.2 |  | 0.0475 | 7.6
| Independent Test Plan/Management Subtotal |  | 2973.12 | 2973.12 | 2973.12 | 2973.12 | 2973.12 | 2973.12 | 0 | 17838.72 |  | 1.5485 | 247.76
3.2 | Independent Test Development | [10 empty] | 0 | 0
|  | Functional Manager | 86.4 | 86.4 | 86.4 | 86.4 | 86.4 | 86.4 |  | 518.4 |  | 0.045 | 7.2
|  | Business Analyst 1 | 200.64 | 200.64 | 200.64 | 200.64 | 200.64 | 200.64 |  | 1203.84 |  | 0.1045 | 16.72
|  | Business Analyst 2 | 200.64 | 200.64 | 200.64 | 200.64 | 200.64 | 200.64 |  | 1203.84 |  | 0.1045 | 16.72
|  | Business Analyst 3 | 200.64 | 200.64 | 200.64 | 200.64 | 200.64 | 200.64 |  | 1203.84 |  | 0.1045 | 16.72
|  | Test Manager | 51.84 | 51.84 | 51.84 | 51.84 | 51.84 | 51.84 |  | 311.04 |  | 0.027 | 4.32
|  | Tester 1 | 674.88 | 674.88 | 674.88 | 674.88 | 674.88 | 674.88 |  | 4049.28 |  | 0.3515 | 56.24
|  | Tester 2 | 674.88 | 674.88 | 674.88 | 674.88 | 674.88 | 674.88 |  | 4049.28 |  | 0.3515 | 56.24
|  | Tester 3 | 674.88 | 674.88 | 674.88 | 674.88 | 674.88 | 674.88 |  | 4049.28 |  | 0.3515 | 56.24
|  | Tester 4 | 674.88 | 674.88 | 674.88 | 674.88 | 674.88 | 674.88 |  | 4049.28 |  | 0.3515 | 56.24
|  | Tester 5 | 674.88 | 674.88 | 674.88 | 674.88 | 674.88 | 674.88 |  | 4049.28 |  | 0.3515 | 56.24
|  | Tester 6 | 674.88 | 674.88 | 674.88 | 674.88 | 674.88 | 674.88 |  | 4049.28 |  | 0.3515 | 56.24
| Independent Test Development Subtotal |  | 4789.44 | 4789.44 | 4789.44 | 4789.44 | 4789.44 | 4789.44 | 0 | 28736.64 |  | 2.4945 | 399.12
3.3 | Independent Test Execution | [10 empty] | 0 | 0
|  | Business Analyst 1 | 91.2 | 91.2 | 91.2 | 91.2 | 91.2 | 91.2 |  | 547.2 |  | 0.0475 | 7.6
|  | Business Analyst 2 | 91.2 | 91.2 | 91.2 | 91.2 | 91.2 | 91.2 |  | 547.2 |  | 0.0475 | 7.6
|  | Business Analyst 3 | 91.2 | 91.2 | 91.2 | 91.2 | 91.2 | 91.2 |  | 547.2 |  | 0.0475 | 7.6
|  | Tester 1 | 857.28 | 857.28 | 857.28 | 857.28 | 857.28 | 857.28 |  | 5143.68 |  | 0.4465 | 71.44
|  | Tester 2 | 857.28 | 857.28 | 857.28 | 857.28 | 857.28 | 857.28 |  | 5143.68 |  | 0.4465 | 71.44
|  | Tester 3 | 857.28 | 857.28 | 857.28 | 857.28 | 857.28 | 857.28 |  | 5143.68 |  | 0.4465 | 71.44
|  | Tester 4 | 857.28 | 857.28 | 857.28 | 857.28 | 857.28 | 857.28 |  | 5143.68 |  | 0.4465 | 71.44
|  | Tester 5 | 857.28 | 857.28 | 857.28 | 857.28 | 857.28 | 857.28 |  | 5143.68 |  | 0.4465 | 71.44
|  | Tester 6 | 857.28 | 857.28 | 857.28 | 857.28 | 857.28 | 857.28 |  | 5143.68 |  | 0.4465 | 71.44
| Independent Test Execution Subtotal |  | 5417.28 | 5417.28 | 5417.28 | 5417.28 | 5417.28 | 5417.28 | 0 | 32503.68 |  | 2.8215 | 451.44
| Independent Test Planning, Executing, and Reporting Subtotal |  | 13179.84 | 13179.84 | 13179.84 | 13179.84 | 13179.84 | 13179.84 | 0 | 79079.04 |  | 6.8645 | 1098.32
| QA Staff Loading Total |  | 31142.4 | 31142.4 | 31142.4 | 31142.4 | 31142.4 | 31142.4 | 0 | 186854.4 |  | 16.22 | 2595.2
Assumptions
1 | None
2
3
4
5
6
7
8
9
10

## 3. Base QA Staff
Schedule 3
Base QA Staff
California State Fiscal Year is July through June
# | Staff Position
1 | Project Executive
2 | Project Manager
3 | Functional Manager
4 | Business Analyst 1
5 | Business Analyst 2
6 | Business Analyst 3
7 | Test Manager
8 | Tester 1
9 | Tester 2
10 | Tester 3
11 | Tester 4
12 | Tester 5
13 | Tester 6
14 | Technical Manager
15 | Security Lead
16 | Technical Lead - AWS
17 | PMO Manager
18 | PMO Specialist
19 | Project Administrator
<Add as necessary>
Assumptions
1 | None
2
3
4
5
6
7
8
9
10