## 1. Transition-In Staff Loading
Schedule 1
QA Transition-In Staff Loading: December 2026 - January 2027
|  |  | Service Month |  | Total QA Transition-In Hours | Average Monthly Hours Constant
ID | Key Task | Position <From Tab 3> | 1 | 2 |  |  | Average Monthly FTEs | Average Monthly Hours
|  |  | 2026-12-01 | 2027-01-01
|  |  | 152 | 168 | 320 | 160
1 | Management
1.1 | Quality Assurance Management | Sr.QA Project Manager | 96 | 96 | 192 |  | 0.2 | 32
|  | Jr. QA Project Manager | 35.9333 | 35.9333 | 71.8667 |  | 0.074861 | 11.9778
|  | Senior Sec QA Partner/Market Delivery Leader | 1 | 1 | 2 |  | 0.0020833 | 0.33333
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
| Quality Assurance Management Subtotal |  | 132.9333 | 132.9333 | 265.8667 |  | 0.27694 | 44.3111
1.2 | Work Plan/Schedule Management | Sr.QA Project Manager | 64 | 64 | 128 |  | 0.13333 | 21.3333
|  | Jr. QA Project Manager | 15.4 | 15.4 | 30.8 |  | 0.032083 | 5.1333
|  | Senior Sec QA Partner/Market Delivery Leader | 1 | 1 | 2 |  | 0.0020833 | 0.33333
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
| Work Plan/Schedule Management Subtotal |  | 80.4 | 80.4 | 160.8 |  | 0.1675 | 26.8
1.3 | Project Management Support | PMO Lead | 80 | 80 | 160 |  | 0.16667 | 26.6667
|  | PMO Support Analyst | 80 | 80 | 160 |  | 0.16667 | 26.6667
|  | Jr. PMO Support Analyst | 69.95 | 69.95 | 139.9 |  | 0.14573 | 23.3167
|  | Project Administrator | 163.2167 | 163.2167 | 326.4333 |  | 0.34003 | 54.4056
|  | Senior Sec Account Manager | 8.1667 | 8.1667 | 16.3333 |  | 0.017014 | 2.7222
| Project Management Support Subtotal |  | 401.3333 | 401.3333 | 802.6667 |  | 0.83611 | 133.7778
| Management Subtotal |  | 614.6667 | 614.6667 | 1229.3333 |  | 1.2806 | 204.8889
2 | Quality Assurance
2.1 | Project Management - QA | QA Technical Manager | 160 | 160 | 320 |  | 0.33333 | 53.3333
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
| Project Management - QA Subtotal |  | 160 | 160 | 320 |  | 0.33333 | 53.3333
2.2 | SCR Prep, Requirements & Design - QA | QA Functional Manager | 16 | 16 | 32 |  | 0.033333 | 5.3333
|  | QA Functional Lead | 5.845 | 5.845 | 11.69 |  | 0.012177 | 1.9483
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
| SCR Prep, Requirements & Design - QA Subtotal |  | 21.845 | 21.845 | 43.69 |  | 0.04551 | 7.2817
2.3 | SCR Build/Test - QA | QA Functional Manager | 16 | 16 | 32 |  | 0.033333 | 5.3333
|  | QA Functional Lead | 14.6125 | 14.6125 | 29.225 |  | 0.030443 | 4.8708
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
| SCR Build Subtotal |  | 30.6125 | 30.6125 | 61.225 |  | 0.063776 | 10.2042
2.4 | SCR Release Management/Training/OCM - QA | QA Functional Manager | 96 | 96 | 192 |  | 0.2 | 32
|  | QA Functional Lead | 5.845 | 5.845 | 11.69 |  | 0.012177 | 1.9483
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
| SCR Release Management/Training/OCM - QA Subtotal |  | 101.845 | 101.845 | 203.69 |  | 0.21218 | 33.9483
2.5 | Marketing and Public Communications Support - QA | QA Functional Manager | 32 | 32 | 64 |  | 0.066667 | 10.6667
|  | QA Functional Lead | 2.9225 | 2.9225 | 5.845 |  | 0.0060885 | 0.97417
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
| Marketing and Public Communications Support - QA Subtotal |  | 34.9225 | 34.9225 | 69.845 |  | 0.072755 | 11.6408
2.6 | Enhancement and Innovation - QA | Sr. QA Technical Analyst | 19.4 | 19.4 | 38.8 |  | 0.040417 | 6.4667
|  | QA Automation Analyst | 58.2 | 58.2 | 116.4 |  | 0.12125 | 19.4
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
| Enhancement and Innovation - QA Subtotal |  | 77.6 | 77.6 | 155.2 |  | 0.16167 | 25.8667
2.7 | Operations - QA | QA Functional Lead | 174.5875 | 174.5875 | 349.175 |  | 0.36372 | 58.1958
|  | QA Test Analyst | 174.5875 | 174.5875 | 349.175 |  | 0.36372 | 58.1958
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
| Operations - QA Subtotal |  | 349.175 | 349.175 | 698.35 |  | 0.72745 | 116.3917
2.8 | Security - QA | Security Analyst | 15 | 15 | 30 |  | 0.03125 | 5
|  | Cloud/Application Penetration Test - Sr. | 1.6667 | 1.6667 | 3.3333 |  | 0.0034722 | 0.55556
|  | Application Penetration Test - Jr | 0.58333 | 0.58333 | 1.1667 |  | 0.0012153 | 0.19444
|  | SS Security testing automation & finetuning | 6 | 6 | 12 |  | 0.0125 | 2
[5 empty] | 0 |  | 0 | 0
| Security - QA Subtotal |  | 23.25 | 23.25 | 46.5 |  | 0.048438 | 7.75
| Quality Assurance Subtotal |  | 799.25 | 799.25 | 1598.5 |  | 1.6651 | 266.4167
3 | Independent Test Planning, Executing, and Reporting
3.1 | Independent Test Plan/Management | Independent Test Engineer | 128.3355 | 128.3355 | 256.6709 |  | 0.26737 | 42.7785
|  | Independent Test Engineer | 32 | 32 | 64 |  | 0.066667 | 10.6667
|  | SS 5 Threat modeling update | 1.7333 | 1.7333 | 3.4667 |  | 0.0036111 | 0.57778
[5 empty] | 0 |  | 0.03125 | 5
[5 empty] | 0 |  | 0.0034722 | 0.55556
| Independent Test Plan/Management Subtotal |  | 162.0688 | 162.0688 | 324.1376 |  | 0.37237 | 121.9472
3.2 | Independent Test Development | QA Performance Test Analyst | 96.6471 | 96.6471 | 193.2942 |  | 0.20135 | 32.2157
|  | Independent Test Engineer | 32.0839 | 32.0839 | 64.1677 |  | 0.066841 | 10.6946
|  | Independent Test Engineer | 64 | 64 | 128 |  | 0.13333 | 21.3333
|  | Independent Test Engineer | 140.16 | 140.16 | 280.32 |  | 0.292 | 46.72
|  | Independent Test Engineer | 144 | 144 | 288 |  | 0.3 | 48
|  | SS Security testing automation & finetuning |  | 3 | 3 |  | 0.003125 | 0.5
|  | SS 5 Threat modeling update |  | 2.0833 | 2.0833 |  | 0.0021701 | 0.34722
|  | Security Analyst |  | 7.5 | 7.5 |  | 0.0078125 | 1.25
|  | Cloud/Application Penetration Test Jr. |  | 1.625 | 1.625 |  | 0.0016927 | 0.27083
|  | Cloud/Application Penetration Test - Sr. |  | 1.125 | 1.125 |  | 0.0011719 | 0.1875
|  | Application Penetration Test - Jr |  | 0.5 | 0.5 |  | 0.00052083 | 0.083333
|  | Cloud/Application Penetration Test Jr. |  | 0.5 | 0.5 |  | 0.00052083 | 0.083333
|  | Cloud/Application Penetration Test - Sr. |  | 1.5 | 1.5 |  | 0.0015625 | 0.25
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
| Independent Test Development Subtotal |  | 476.891 | 494.7243 | 971.6153 |  | 1.0121 | 161.9359
3.3 | Independent Test Execution | QA Performance Test Analyst | 63.837 | 63.837 | 127.6739 |  | 0.13299 | 21.279
|  | Independent Test Engineer | 64 | 64 | 128 |  | 0.13333 | 21.3333
|  | Independent Test Engineer | 93.44 | 93.44 | 186.88 |  | 0.19467 | 31.1467
|  | Independent Test Engineer | 96 | 96 | 192 |  | 0.2 | 32
|  | SS Security testing automation & finetuning |  | 3 | 3 |  | 0.003125 | 0.5
|  | SS 5 Threat modeling update |  | 2.0833 | 2.0833 |  | 0.0021701 | 0.34722
|  | Security Analyst |  | 7.5 | 7.5 |  | 0.0078125 | 1.25
|  | Cloud/Application Penetration Test Jr. |  | 1.625 | 1.625 |  | 0.0016927 | 0.27083
|  | Cloud/Application Penetration Test - Sr. |  | 1.125 | 1.125 |  | 0.0011719 | 0.1875
|  | Application Penetration Test - Jr |  | 0.5 | 0.5 |  | 0.00052083 | 0.083333
|  | Cloud/Application Penetration Test Jr. |  | 0.5 | 0.5 |  | 0.00052083 | 0.083333
|  | Cloud/Application Penetration Test - Sr. |  | 1.5 | 1.5 |  | 0.0015625 | 0.25
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
| Independent Test Execution Subtotal |  | 317.277 | 335.1103 | 652.3873 |  | 0.67957 | 108.7312
| Independent Test Planning, Executing, and Reporting Subtotal |  | 956.2367 | 991.9034 | 1948.1401 |  | 2.064 | 270.8615
| QA Staff Loading Total |  | 2370.1534 | 2405.8201 | 4775.9735 |  | 5.0097 | 742.1671
Assumptions
1 | Client will identify the Transition point of contact from the State side
2 | 100% of the IBM Team assumed to start Month 1 of Transition. Resources not supporting Deliverables will not be charged during Transition
3 | Transition managers (1.1 FTEs) will lead Transition phase and is not charged to the State
4 | IBM Executive role is not billed to the State.
5 | Client support effort are not included in the estimate
6 | Only Resources supporting Deliverables will be billed to the State during Transition phase.
7 | Transition-out Vendor will support inflight projects delivery during transition phase
8
9
10

## 2. Staff Loading
Schedule 2
QA Average Annual Staff Loading: February 2027 - January 2033
Average Monthly Hours Constant
Service Year
ID | Key Task | Position <From Tab 3> | Base Year 1 | Base Year 2 | Base Year 3 | Base Year 4 | Base Year 5 | Base Year 6 |  | QA Total: Hours |  | Average Monthly FTEs | Average Monthly Hours
|  |  | February 27 - January 28 | February 28 - January 29 | February 29 - January 30 | February 30 - January 31 | February 31 - January 32 | February 32 - January 33
|  |  | 1920 | 1920 | 1920 | 1920 | 1920 | 1920 |  | 11520 | 160
1 | Management
1.1 | Quality Assurance Management | Sr.QA Project Manager | 1152 | 1120.5378 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0
|  | QA Project Manager | 0 | 0 | 1070.5282 | 1038.6067 | 1018.644 | 1000.7762 |  |  |  | 0 | 0
|  | Jr. QA Project Manager | 431.2 | 419.4235 | 400.7046 | 0 | 0 | 0 |  |  |  | 0 | 0
|  | Jr. QA Project Manager | 0 | 0 | 0 | 388.7562 | 381.2841 | 374.5961 |  |  |  | 0 | 0
|  | Digital Assistant | 0 | 43.2878 | 112.0945 | 156.0143 | 183.4802 | 208.0639 |  |  |  | 0 | 0
|  | Senior Sec QA Partner/Market Delivery Leader | 7 | 7 | 7 | 7 | 7 | 7 |  |  |  | 0 | 0
| Quality Assurance Management Subtotal |  | 1590.2 | 1590.2492 | 1590.3273 | 1590.3772 | 1590.4084 | 1590.4363 | 0 | 0 |  | 0 | 0
1.2 | Work Plan/Schedule Management | Sr.QA Project Manager | 768 | 747.0252 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0
|  | QA Project Manager | 0 | 0 | 713.6854 | 692.4044 | 679.096 | 667.1842 |  |  |  | 0 | 0
|  | Jr. QA Project Manager | 184.8 | 179.7529 | 171.7306 | 0 | 0 | 0 |  |  |  | 0 | 0
|  | Jr. QA Project Manager | 0 | 0 | 0 | 166.6098 | 163.4075 | 160.5412 |  |  |  | 0 | 0
|  | Digital Assistant | 0 | 25.9727 | 67.2567 | 93.6086 | 110.0881 | 124.8384 |  |  |  | 0 | 0
|  | Senior Sec QA Partner/Market Delivery Leader | 5 | 5 | 5 | 5 | 5 | 5 |  |  |  | 0 | 0
| Work Plan/Schedule Management Subtotal |  | 957.8 | 957.7508 | 957.6727 | 957.6228 | 957.5916 | 957.5637 | 0 | 0 |  | 0 | 0
1.3 | Project Management Support | PMO Lead | 960 | 933.7815 | 892.1068 | 865.5055 | 848.87 | 833.9802 |  |  |  | 0 | 0
|  | PMO Support Analyst | 960 | 933.7815 | 892.1068 | 865.5055 | 848.87 | 833.9802 |  |  |  | 0 | 0
|  | Jr. PMO Support Analyst | 839.4 | 680.396 | 520.0239 | 504.5176 | 247.4102 | 243.0705 |  |  |  | 0 | 0
|  | Project Administrator | 1958.6 | 2041.188 | 2080.0957 | 2018.0704 | 2226.6922 | 2187.6343 |  |  |  | 0 | 0
|  | Digital Assistant | 0 | 128.853 | 333.6667 | 464.4009 | 546.1575 | 619.3348 |  |  |  | 0 | 0
|  | Senior Sec Account Manager | 98 | 98 | 98 | 98 | 98 | 98 |  |  |  | 0 | 0
| Project Management Support Subtotal |  | 4816 | 4816 | 4816 | 4816 | 4816 | 4816 | 0 | 0 |  | 0 | 0
| Management Subtotal |  | 7364 | 7364 | 7364 | 7364 | 7364 | 7364 | 0 | 0 |  | 0 | 0
2 | Quality Assurance
2.1 | Project Management - QA | QA Technical Manager | 1920 | 905.5935 | 164.219 | 152.9097 | 144.9829 | 138.466 |  |  |  | 0 | 0
|  | QA Functional Lead | 0 | 905.5935 | 1477.9706 | 1376.1869 | 1304.8459 | 1246.1944 |  |  |  | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
| Project Management - QA Subtotal |  | 1920 | 1811.187 | 1642.1896 | 1529.0966 | 1449.8288 | 1384.6604 | 0 | 0 |  | 0 | 0
2.2 | SCR Prep, Requirements & Design - QA | QA Functional Manager | 192 | 214.2012 | 194.2146 | 0 | 0 | 0 |  |  |  | 0 | 0
|  | QA Functional Lead | 70.14 | 0 | 0 | 361.6791 | 342.9298 | 327.5155 |  |  |  | 0 | 0
|  | Digital Assistant | 0 | 25.7377 | 65.7109 | 92.4609 | 111.2102 | 126.6245 |  |  |  | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
| SCR Prep, Requirements & Design - QA Subtotal |  | 262.14 | 239.9388 | 259.9254 | 454.14 | 454.14 | 454.14 | 0 | 0 |  | 0 | 0
2.3 | SCR Build/Test - QA | QA Functional Manager | 192 | 214.2012 | 194.2146 | 0 | 0 | 0 |  |  |  | 0 | 0
|  | QA Functional Lead | 175.35 | 0 | 0 | 904.1978 | 857.3245 | 818.7886 |  |  |  | 0 | 0
|  | Digital Assistant | 0 | 64.3442 | 164.2771 | 231.1522 | 278.0255 | 316.5614 |  |  |  | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
| SCR Build Subtotal |  | 367.35 | 278.5453 | 358.4917 | 1135.35 | 1135.35 | 1135.35 | 0 | 0 |  | 0 | 0
2.4 | SCR Release Management/Training/OCM - QA | QA Functional Manager | 1152 | 1285.207 | 1165.2874 | 0 | 0 | 0 |  |  |  | 0 | 0
|  | QA Functional Lead | 70.14 | 0 | 0 | 361.6791 | 342.9298 | 327.5155 |  |  |  | 0 | 0
|  | Digital Assistant | 0 | 25.7377 | 65.7109 | 92.4609 | 111.2102 | 126.6245 |  |  |  | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
| SCR Release Management/Training/OCM - QA Subtotal |  | 1222.14 | 1310.9447 | 1230.9983 | 454.14 | 454.14 | 454.14 | 0 | 0 |  | 0 | 0
2.5 | Marketing and Public Communications Support - QA | QA Functional Manager | 384 | 428.4023 | 388.4291 | 0 | 0 | 0 |  |  |  | 0 | 0
|  | QA Functional Lead | 35.07 | 0 | 0 | 180.8396 | 171.4649 | 163.7577 |  |  |  | 0 | 0
|  | Digital Assistant | 0 | 12.8688 | 32.8554 | 46.2304 | 55.6051 | 63.3123 |  |  |  | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
| Marketing and Public Communications Support - QA Subtotal |  | 419.07 | 441.2712 | 421.2846 | 227.07 | 227.07 | 227.07 | 0 | 0 |  | 0 | 0
2.6 | Enhancement and Innovation - QA | Sr. QA Technical Analyst | 232.8 | 219.6064 | 159.2924 | 148.3224 | 140.6334 | 134.3121 |  |  |  | 0 | 0
|  | QA Automation Analyst | 698.4 | 658.8193 | 637.1695 | 593.2895 | 562.5336 | 537.2482 |  |  |  | 0 | 0
|  | Digital Assistant | 0 | 52.7743 | 134.7381 | 189.5882 | 228.033 | 259.6397 |  |  |  | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
| Enhancement and Innovation - QA Subtotal |  | 931.2 | 931.2 | 931.2 | 931.2 | 931.2 | 931.2 | 0 | 0 |  | 0 | 0
2.7 | Operations - QA | QA Functional Lead | 2095.05 | 1976.3163 | 1433.5288 | 1334.8057 | 1265.6099 | 1208.722 |  |  |  | 0 | 0
|  | QA Test Analyst | 2095.05 | 1976.3163 | 1433.5288 | 1334.8057 | 1265.6099 | 1208.722 |  |  |  | 0 | 0
|  | Jr. QA Test Analyst | 0 | 0 | 716.7644 | 667.4029 | 632.805 | 604.361 |  |  |  | 0 | 0
|  | Digital Assistant | 0 | 346.2804 | 884.0883 | 1243.9891 | 1496.2464 | 1703.6347 |  |  |  | 0 | 0
[12 empty] | 0 | 0
| Operations - QA Subtotal |  | 4190.1 | 4298.913 | 4467.9104 | 4581.0034 | 4660.2712 | 4725.4396 | 0 | 0 |  | 0 | 0
2.8 | Security - QA | Security Analyst | 180 | 180 | 180 | 180 | 180 | 180 |  |  |  | 0 | 0
|  | Cloud/Application Penetration Test - Sr. | 20 | 20 | 20 | 20 | 20 | 20 |  |  |  | 0 | 0
|  | Cloud/Application Penetration Test Jr. | 7 | 7 | 7 | 7 | 7 | 7 |  |  |  | 0 | 0
|  | SS Security testing automation & finetuning | 72 | 72 | 72 | 72 | 72 | 72 |  |  |  | 0 | 0
[12 empty] | 0 | 0
| Security - QA Subtotal |  | 279 | 279 | 279 | 279 | 279 | 279 | 0 | 0 |  | 0 | 0
0
| Quality Assurance Subtotal |  | 9591 | 9591 | 9591 | 9591 | 9591 | 9591 | 0 | 0 |  | 0 | 0
3 | Independent Test Planning, Executing, and Reporting
3.1 | Independent Test Plan/Management | QA Test Manager | 0 | 0 | 0 | 871.4939 | 781.981 | 709.2732 |  |  |  | 0 | 0
|  | Independent Test Manager | 1540.0256 | 1354.2601 | 1058.0614 | 0 | 0 | 0 |  |  |  | 0 | 0
|  | Independent Test Engineer | 384 | 384 | 384 | 0 | 0 | 0 |  |  |  | 0 | 0
|  | SS 5 Threat modeling update | 20.8 | 20.8 | 20.8 | 20.8 | 20.8 | 20.8 |  |  |  | 0 | 0
[12 empty] | 0 | 0
| Independent Test Plan/Management Subtotal |  | 1944.8256 | 1759.0601 | 1462.8614 | 892.2939 | 802.781 | 730.0732 | 0 | 0 |  | 0 | 0
3.2 | Independent Test Development | QA Test Manager | 0 | 0 | 0 | 217.8735 | 195.4953 | 177.3183 |  |  |  | 0 | 0
|  | QA Performance Test Analyst | 1159.7653 | 1021.1594 | 800.1555 | 677.074 | 608.6294 | 553.0345 |  |  |  | 0 | 0
|  | QA Automation Analyst | 0 | 0 | 0 | 1665.9349 | 1494.8235 | 1355.8363 |  |  |  | 0 | 0
|  | Jr. QA Test Analyst | 0 | 0 | 0 | 999.561 | 896.8941 | 813.5018 |  |  |  | 0 | 0
|  | Digital Assistant | 0 | 697.796 | 2046.8835 | 2880.5142 | 3289.8717 | 3622.3769 |  |  |  | 0 | 0
|  | Independent Test Manager | 385.0064 | 338.565 | 264.5153 | 0 | 0 | 0 |  |  |  | 0 | 0
|  | Independent Test Engineer | 768 | 768 | 768 | 0 | 0 | 0 |  |  |  | 0 | 0
|  | Independent Test Engineer | 1681.92 | 1436.7838 | 870.5747 | 0 | 0 | 0 |  |  |  | 0 | 0
|  | Independent Test Engineer | 1728 | 1553.2703 | 1213.5448 | 0 | 0 | 0 |  |  |  | 0 | 0
|  | SS Security testing automation & finetuning | 36 | 36 | 36 | 36 | 36 | 36 |  |  |  | 0 | 0
|  | SS 5 Threat modeling update | 25 | 25 | 25 | 25 | 25 | 25 |  |  |  | 0 | 0
|  | Security Analyst | 90 | 90 | 90 | 90 | 90 | 90 |  |  |  | 0 | 0
|  | Cloud/Application Penetration Test Jr. | 19.5 | 19.5 | 19.5 | 19.5 | 19.5 | 19.5 |  |  |  | 0 | 0
|  | Cloud/Application Penetration Test - Sr. | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 |  |  |  | 0 | 0
|  | Application Penetration Test - Jr | 6 | 6 | 6 | 6 | 6 | 6 |  |  |  | 0 | 0
|  | Cloud/Application Penetration Test Jr. | 6 | 6 | 6 | 6 | 6 | 6 |  |  |  | 0 | 0
|  | Cloud/Application Penetration Test - Sr. | 18 | 18 | 18 | 18 | 18 | 18 |  |  |  | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
| Independent Test Development Subtotal |  | 5936.6917 | 6029.5744 | 6177.6738 | 6654.9575 | 6699.714 | 6736.0679 | 0 | 0 |  | 0 | 0
3.3 | Independent Test Execution | QA Preformance Test Analyst | 766.0435 | 673.6396 | 526.3036 | 444.2493 | 398.6196 | 361.5564 |  |  |  | 0 | 0
|  | QA Automation Analyst | 0 | 0 | 0 | 1110.6233 | 996.549 | 903.8909 |  |  |  | 0 | 0
|  | Jr. QA Test Analyst | 0 | 0 | 0 | 666.374 | 597.9294 | 542.3345 |  |  |  | 0 | 0
|  | Digitial worker | 0 | 465.1973 | 1364.589 | 1920.3428 | 2193.2478 | 2414.918 |  |  |  | 0 | 0
|  | Independent Test Engineer | 768 | 768 | 768 | 0 | 0 | 0 |  |  |  | 0 | 0
|  | Independent Test Engineer | 1121.28 | 957.8559 | 580.3831 | 0 | 0 | 0 |  |  |  | 0 | 0
|  | Independent Test Engineer | 1152 | 1035.5135 | 809.0299 | 0 | 0 | 0 |  |  |  | 0 | 0
|  | SS Security testing automation & finetuning | 36 | 36 | 36 | 36 | 36 | 36 |  |  |  | 0 | 0
|  | SS 5 Threat modeling update Medium US DAS B8 300hrs | 25 | 25 | 25 | 25 | 25 | 25 |  |  |  | 0 | 0
|  | Security Analyst | 90 | 90 | 90 | 90 | 90 | 90 |  |  |  | 0 | 0
|  | Cloud/Application Penetration Test Jr. | 19.5 | 19.5 | 19.5 | 19.5 | 19.5 | 19.5 |  |  |  | 0 | 0
|  | Cloud/Application Penetration Test - Sr. | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 |  |  |  | 0 | 0
|  | Application Penetration Test - Jr | 6 | 6 | 6 | 6 | 6 | 6 |  |  |  | 0 | 0
|  | Cloud/Application Penetration Test Jr. | 6 | 6 | 6 | 6 | 6 | 6 |  |  |  | 0 | 0
|  | Cloud/Application Penetration Test - Sr. | 18 | 18 | 18 | 18 | 18 | 18 |  |  |  | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
| Independent Test Execution Subtotal |  | 4021.3235 | 4114.2063 | 4262.3056 | 4355.5894 | 4400.3458 | 4436.6997 | 0 | 0 |  | 0 | 0
| Independent Test Planning, Executing, and Reporting Subtotal |  | 11902.8408 | 11902.8408 | 11902.8408 | 11902.8408 | 11902.8408 | 11902.8408 | 0 | 0 |  | 0 | 0
| QA Staff Loading Total |  | 28857.8408 | 28857.8408 | 28857.8408 | 28857.8408 | 28857.8408 | 28857.8408 | 0 | 0 |  | 0 | 0
Assumptions
1 | Ratio of efforts for QA Management and Workplan/Schedule management is assumed 62%/38%
2 | Security QA effort and price is included in M&O Annual hours and price mentioned in RFP
3 | Key Staff Members will work from client location.
4 | Average Onshore/Remote staffing mix is 30%/70%
5 | IBM Executive role is not billed to the State.
6 | State will allow IBM asset IQP Plus to be deployed in the State Environment ( on Prem or Cloud)
7 | State will provide access to the existing Testing tools at no additional charge
8 | State will accept the Digital Hours Considered in the solution from year 2. This is based on the efficiencies built over time.
9 | IBM will re-estimate the effort and price if there is a change in scope
10 | State will provide access to the existing LLMs for IQPP integration ( if applicable)
11 | IBM staffing will include subcontractors from our Partnership companies who are specialized in Quality Assurance and CalSAWS

## 3. Base QA Staff
Schedule 3
Base QA Staff
California State Fiscal Year is July through June
# | Staff Position
1 | Sr.QA Project Manager
2 | QA Project Manager
3 | Jr. QA Project Manager
4 | PMO Lead
5 | PMO Support Analyst
6 | Jr. PMO Support Analyst
7 | Project Administrator
8 | QA Functional Manager
9 | QA Functional Lead
10 | QA Functional Analyst
11 | QA Test Manager
12 | Independent Test Manager
13 | Independent Test Engineer
14 | QA Test Analyst
15 | Jr. QA Test Analyst
16 | QA Automation Analyst
17 | QA Performance Test Analyst
18 | QA Technical Manager
19 | Sr. QA Technical Analyst
20 | Jr. QA Technical Analyst
21 | Digital Assistant
22 | Senior Sec QA Partner/Market Delivery Leader
23 | Senior Sec Account Manager
24 | Security Analyst
25 | Application/Cloud Penetration Test
26 | SS Security testing automation & finetuning
27 | Cloud/Application Penetration Test Jr.
28 | Cloud/Application Penetration Test - Sr.
29 | Application Penetration Test - Jr
30 | SS 5 Threat modeling update
<Add as necessary>
Assumptions
1
2
3
4
5
6
7
8
9
10