## 1. Transition-In Staff Loading
Schedule 1
QA Transition-In Staff Loading: December 2026 - January 2027
|  |  | Hourly Rate <From Tab 7> | Service Month |  | Total QA Transition-In Hours | Total QA Transition-In Price | Average Monthly Hours Constant
ID | Key Task | Position <From Tab 7> |  | 1 | 2 |  |  |  | Average Monthly FTEs | Average Monthly Hours
|  |  |  | 2026-12-01 | 2027-01-01
|  |  |  | 152 | 168 | 320 |  | 160
1 | Management
1.1 | Quality Assurance Management | QA Project Manager |  | 31.5 | 31.5 | 63 | 0 |  | 0.19687 | 31.5
|  | QA Test Manager |  | 21 | 21 | 42 | 0 |  | 0.13125 | 21
|  | QA Functional Manager |  | 21 | 21 | 42 | 0 |  | 0.13125 | 21
|  | QA Technical Manager |  | 21 | 21 | 42 | 0 |  | 0.13125 | 21
[6 empty] | 0 | 0 |  | 0 | 0
| Quality Assurance Management Subtotal |  |  | 94.5 | 94.5 | 189 | 0 |  | 0.59062 | 94.5
1.2 | Work Plan/Schedule Management | QA Project Manager |  | 25.2 | 30 | 55.2 | 0 |  | 0.1725 | 27.6
|  | QA Test Manager |  | 16.8 | 25 | 41.8 | 0 |  | 0.13062 | 20.9
|  | QA Functional Manager |  | 16.8 | 25 | 41.8 | 0 |  | 0.13062 | 20.9
|  | QA Technical Manager |  | 16.8 | 25 | 41.8 | 0 |  | 0.13062 | 20.9
[6 empty] | 0 | 0 |  | 0 | 0
| Work Plan/Schedule Management Subtotal |  |  | 75.6 | 105 | 180.6 | 0 |  | 0.56437 | 90.3
1.3 | Project Management Support | QA Project Manager |  | 60 | 70 | 130 | 0 |  | 0.40625 | 65
|  | QA Functional Manager |  | 15 | 30 | 45 | 0 |  | 0.14062 | 22.5
|  | QA Test Manager |  | 15 | 20 | 35 | 0 |  | 0.10938 | 17.5
[6 empty] | 0 | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0
| Project Management Support Subtotal |  |  | 90 | 120 | 210 | 0 |  | 0.65625 | 105
| Management Subtotal |  |  | 260.1 | 319.5 | 579.6 | 0 |  | 1.8112 | 289.8
2 | Quality Assurance
2.1 | Project Management - QA | QA Project Manager |  | 20 | 20 | 40 | 0 |  | 0.125 | 20
|  | QA Functional Manager |  | 15 | 15 | 30 | 0 |  | 0.09375 | 15
|  | QA Test Manager |  | 12 | 15 | 27 | 0 |  | 0.084375 | 13.5
|  | Security Lead |  | 12 | 15 | 27 | 0 |  | 0.084375 | 13.5
[6 empty] | 0 | 0 |  | 0 | 0
| Project Management - QA Subtotal |  |  | 59 | 65 | 124 | 0 |  | 0.3875 | 62
2.2 | SCR Prep, Requirements & Design - QA | QA Project Manager |  | 10 | 10 | 20 | 0 |  | 0.0625 | 10
|  | QA Test Manager |  | 15 | 18 | 33 | 0 |  | 0.10312 | 16.5
|  | QA Functional Manager |  | 10 | 10 | 20 | 0 |  | 0.0625 | 10
|  | QA Technical Manager |  | 15 | 18 | 33 | 0 |  | 0.10312 | 16.5
|  | QA SDET |  | 5 | 10 | 15 | 0 |  | 0.046875 | 7.5
|  | QA Tester 1 |  | 5 | 10 | 15 | 0 |  | 0.046875 | 7.5
|  | QA Tester 2 |  | 5 | 10 | 15 | 0 |  | 0.046875 | 7.5
|  | QA Tester 3 |  | 5 | 10 | 15 | 0 |  | 0.046875 | 7.5
|  | QA Tester 4 |  | 5 | 10 | 15 | 0 |  | 0.046875 | 7.5
| SCR Prep, Requirements & Design - QA Subtotal |  |  | 75 | 106 | 181 | 0 |  | 0.56563 | 90.5
2.3 | SCR Build/Test - QA | QA Project Manager |  | 5 | 5 | 10 | 0 |  | 0.03125 | 5
|  | QA Test Manager |  | 15 | 15 | 30 | 0 |  | 0.09375 | 15
|  | QA Functional Manager |  | 10 | 10 | 20 | 0 |  | 0.0625 | 10
|  | QA Technical Manager |  | 15 | 15 | 30 | 0 |  | 0.09375 | 15
|  | QA SDET |  | 20 | 20 | 40 | 0 |  | 0.125 | 20
|  | QA Tester 1 |  | 5 | 10 | 15 | 0 |  | 0.046875 | 7.5
|  | QA Tester 2 |  | 5 | 10 | 15 | 0 |  | 0.046875 | 7.5
|  | QA Tester 3 |  | 5 | 10 | 15 | 0 |  | 0.046875 | 7.5
|  | QA Tester 4 |  | 5 | 10 | 15 | 0 |  | 0.046875 | 7.5
| SCR Build Subtotal |  |  | 85 | 105 | 190 | 0 |  | 0.59375 | 95
2.4 | SCR Release Management/Training/OCM - QA | QA Project Manager |  | 5 | 5 | 10 | 0 |  | 0.03125 | 5
|  | QA Test Manager |  | 10 | 15 | 25 | 0 |  | 0.078125 | 12.5
|  | QA Functional Manager |  | 10 | 15 | 25 | 0 |  | 0.078125 | 12.5
|  | QA Technical Manager |  | 10 | 15 | 25 | 0 |  | 0.078125 | 12.5
|  | QA SDET |  | 10 | 15 | 25 | 0 |  | 0.078125 | 12.5
|  | Security Lead |  | 5 | 5 | 10 | 0 |  | 0.03125 | 5
[6 empty] | 0 | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0
| SCR Release Management/Training/OCM - QA Subtotal |  |  | 50 | 70 | 120 | 0 |  | 0.375 | 60
2.5 | Marketing and Public Communications Support - QA | QA Project Manager |  | 5 | 5 | 10 | 0 |  | 0.03125 | 5
|  | QA Test Manager |  | 10 | 10 | 20 | 0 |  | 0.0625 | 10
|  | QA Functional Manager |  | 10 | 10 | 20 | 0 |  | 0.0625 | 10
|  | QA SDET |  | 10 | 10 | 20 | 0 |  | 0.0625 | 10
[6 empty] | 0 | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0
| Marketing and Public Communications Support - QA Subtotal |  |  | 35 | 35 | 70 | 0 |  | 0.21875 | 35
2.6 | Enhancement and Innovation - QA | QA Project Manager |  | 5 | 5 | 10 | 0 |  | 0.03125 | 5
|  | QA Test Manager |  | 8 | 8 | 16 | 0 |  | 0.05 | 8
|  | QA Technical Manager |  | 20 | 20 | 40 | 0 |  | 0.125 | 20
|  | QA SDET |  | 10 | 10 | 20 | 0 |  | 0.0625 | 10
|  | Security Lead |  | 5 | 6 | 11 | 0 |  | 0.034375 | 5.5
[6 empty] | 0 | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0
| Enhancement and Innovation - QA Subtotal |  |  | 48 | 49 | 97 | 0 |  | 0.30312 | 48.5
2.7 | Operations - QA | QA Project Manager |  | 3 | 3 | 6 | 0 |  | 0.01875 | 3
|  | QA Test Manager |  | 5 | 5 | 10 | 0 |  | 0.03125 | 5
|  | QA Technical Manager |  | 5 | 5 | 10 | 0 |  | 0.03125 | 5
|  | QA SDET |  | 5 | 5 | 10 | 0 |  | 0.03125 | 5
|  | Security Lead |  | 5 | 5 | 10 | 0 |  | 0.03125 | 5
|  | QA Tester 1 |  | 5 | 5 | 10 | 0 |  | 0.03125 | 5
|  | QA Tester 2 |  | 5 | 5 | 10 | 0 |  | 0.03125 | 5
[6 empty] | 0 | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0
| Operations - QA Subtotal |  |  | 33 | 33 | 66 | 0 |  | 0.20625 | 33
2.8 | Security - QA | QA Technical Manager |  | 15 | 15 | 30 | 0 |  | 0.09375 | 15
|  | QA SDET |  | 30 | 30 | 60 | 0 |  | 0.1875 | 30
|  | Security Lead |  | 120 | 140 | 260 | 0 |  | 0.8125 | 130
[6 empty] | 0 | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0
| Security - QA Subtotal |  |  | 165 | 185 | 350 | 0 |  | 1.0938 | 175
| Quality Assurance Subtotal |  |  | 550 | 648 | 1198 | 0 |  | 3.7437 | 599
3 | Independent Test Planning, Executing, and Reporting
3.1 | Independent Test Plan/Management | QA Project Manager |  | 10 | 10 | 20 | 0 |  | 0.0625 | 10
|  | QA Test Manager |  | 40 | 50 | 90 | 0 |  | 0.28125 | 45
|  | QA Technical Manager |  | 40 | 50 | 90 | 0 |  | 0.28125 | 45
|  | QA SDET |  | 60 | 80 | 140 | 0 |  | 0.4375 | 70
|  | QA Functional Manager |  | 40 | 50 | 90 | 0 |  | 0.28125 | 45
|  | QA Tester 1 |  | 30 | 40 | 70 | 0 |  | 0.21875 | 35
|  | QA Tester 2 |  | 30 | 40 | 70 | 0 |  | 0.21875 | 35
|  | QA Tester 3 |  | 30 | 40 | 70 | 0 |  | 0.21875 | 35
|  | QA Tester 4 |  |  | 60 | 60 | 0 |  | 0.1875 | 30
|  | QA Tester 5 |  | 10 | 60 | 70 | 0 |  | 0.21875 | 35
|  | QA Tester 6 |  | 10 | 70 | 80 | 0 |  | 0.25 | 40
[6 empty] | 0 | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0
| Independent Test Plan/Management Subtotal |  |  | 300 | 550 | 850 | 0 |  | 2.6562 | 425
3.2 | Independent Test Development | QA Test Manager |  | 30 | 40 | 70 | 0 |  | 0.21875 | 35
|  | QA SDET |  | 40 | 50 | 90 | 0 |  | 0.28125 | 45
|  | QA Tester 1 |  | 50 | 70 | 120 | 0 |  | 0.375 | 60
|  | QA Tester 2 |  | 50 | 70 | 120 | 0 |  | 0.375 | 60
|  | QA Tester 3 |  | 50 | 70 | 120 | 0 |  | 0.375 | 60
|  | QA Tester 4 |  |  | 70 | 70 | 0 |  | 0.21875 | 35
|  | QA Tester 5 |  | 30 | 70 | 100 | 0 |  | 0.3125 | 50
|  | QA Tester 6 |  | 30 | 70 | 100 | 0 |  | 0.3125 | 50
|  | QA Tester 7 |  | 30 | 70 | 100 | 0 |  | 0.3125 | 50
[6 empty] | 0 | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0
| Independent Test Development Subtotal |  |  | 310 | 580 | 890 | 0 |  | 2.7812 | 445
3.3 | Independent Test Execution | QA Test Manager |  | 25 | 57 | 82 | 0 |  | 0.25625 | 41
|  | QA SDET |  | 25 | 57 | 82 | 0 |  | 0.25625 | 41
|  | QA Tester 1 |  | 40 | 57 | 97 | 0 |  | 0.30312 | 48.5
|  | QA Tester 2 |  | 40 | 75 | 115 | 0 |  | 0.35938 | 57.5
|  | QA Tester 3 |  | 40 | 75 | 115 | 0 |  | 0.35938 | 57.5
|  | QA Tester 4 |  |  | 75 | 75 | 0 |  | 0.23438 | 37.5
|  | QA Tester 5 |  | 30 | 90 | 120 | 0 |  | 0.375 | 60
|  | QA Tester 6 |  | 30 | 90 | 120 | 0 |  | 0.375 | 60
|  | QA Tester 7 |  |  | 90 | 90 | 0 |  | 0.28125 | 45
|  | QA Tester 8 |  |  | 90 | 90 | 0 |  | 0.28125 | 45
|  | QA Tester 9 |  |  | 90 | 90 | 0 |  | 0.28125 | 45
[6 empty] | 0 | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0
| Independent Test Execution Subtotal |  |  | 230 | 846 | 1076 | 0 |  | 3.3625 | 538
| Independent Test Planning, Executing, and Reporting Subtotal |  |  | 840 | 1976 | 2816 | 0 |  | 8.8 | 1408
| QA Staff Loading Total |  |  | 1650.1 | 2943.5 | 4593.6 | 0 |  | 14.355 | 2296.8
| Assumptions |  |  |  |  | Average Hourly Rate | 0
1 | 75% of team will be at Onsite, remaining can be offshore/remote, however we are flexible to make it complete Onsite.
2 | No additional transition fees are proposed for the QA Final Project Closeout Report or Transition-Out documentation, as these are included under governance activities.
3 | Quadrant’s Technical Managers possess cloud-agnostic expertise, ensuring seamless integration, testing, and validation across multiple cloud environments (e.g., AWS, Azure, GCP, or hybrid models).
4 | The QA frameworks, automation pipelines, and performance validation tools proposed are platform-independent, supporting scalable and portable deployments across environments.
5
6
7
8
9
10

## 2. Staff Loading
Schedule 2
QA Average Annual Staff Loading: February 2027 - January 2033
Average Monthly Hours Constant
|  |  | Hourly Rate <From Tab 7> | Service Year
ID | Key Task | Position <From Tab 7> |  | Base Year 1 | Base Year 2 | Base Year 3 | Base Year 4 | Base Year 5 | Base Year 6 |  | QA Total: Hours | QA Total: Price |  | Average Monthly FTEs | Average Monthly Hours
|  |  |  | February 27 - January 28 | February 28 - January 29 | February 29 - January 30 | February 30 - January 31 | February 31 - January 32 | February 32 - January 33
|  |  |  | 1920 | 1920 | 1920 | 1920 | 1920 | 1920 |  | 11520 |  | 160
1 | Management
1.1 | Quality Assurance Management | QA Project Manager |  | 252 | 252 | 252 | 252 | 252 | 252 |  | 1512 | 0 |  | 0.13125 | 21
|  | QA Test Manager |  | 201.6 | 201.6 | 201.6 | 201.6 | 201.6 | 201.6 |  | 1209.6 | 0 |  | 0.105 | 16.8
|  | QA Functional Manager |  | 226.8 | 226.8 | 226.8 | 226.8 | 226.8 | 226.8 |  | 1360.8 | 0 |  | 0.11812 | 18.9
|  | QA Technical Manager |  | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 |  | 1058.4 | 0 |  | 0.091875 | 14.7
[11 empty] | 0 | 0 |  | 0 | 0
| Quality Assurance Management Subtotal |  |  | 856.8 | 856.8 | 856.8 | 856.8 | 856.8 | 856.8 | 0 | 5140.8 | 0 |  | 0.44625 | 71.4
1.2 | Work Plan/Schedule Management | QA Project Manager |  | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 |  | 1058.4 | 0 |  | 0.091875 | 14.7
|  | QA Test Manager |  | 126 | 126 | 126 | 126 | 126 | 126 |  | 756 | 0 |  | 0.065625 | 10.5
|  | QA Functional Manager |  | 126 | 126 | 126 | 126 | 126 | 126 |  | 756 | 0 |  | 0.065625 | 10.5
|  | QA Technical Manager |  | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 |  | 1058.4 | 0 |  | 0.091875 | 14.7
[11 empty] | 0 | 0 |  | 0 | 0
| Work Plan/Schedule Management Subtotal |  |  | 604.8 | 604.8 | 604.8 | 604.8 | 604.8 | 604.8 | 0 | 3628.8 | 0 |  | 0.315 | 50.4
1.3 | Project Management Support | QA Project Manager |  | 201.6 | 201.6 | 201.6 | 201.6 | 201.6 | 201.6 |  | 1209.6 | 0 |  | 0.105 | 16.8
|  | QA Functional Manager |  | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 |  | 1058.4 | 0 |  | 0.091875 | 14.7
|  | QA Test Manager |  | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 |  | 1058.4 | 0 |  | 0.091875 | 14.7
[11 empty] | 0 | 0 |  | 0 | 0
[11 empty] | 0 | 0 |  | 0 | 0
| Project Management Support Subtotal |  |  | 554.4 | 554.4 | 554.4 | 554.4 | 554.4 | 554.4 | 0 | 3326.4 | 0 |  | 0.28875 | 46.2
| Management Subtotal |  |  | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 0 | 12096 | 0 |  | 1.05 | 168
2 | Quality Assurance
2.1 | Project Management - QA | QA Project Manager |  | 252 | 252 | 252 | 252 | 252 | 252 |  | 1512 | 0 |  | 0.13125 | 21
|  | QA Functional Manager |  | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 |  | 1058.4 | 0 |  | 0.091875 | 14.7
|  | QA Test Manager |  | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 |  | 1058.4 | 0 |  | 0.091875 | 14.7
|  | Security Lead |  | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 |  | 1058.4 | 0 |  | 0.091875 | 14.7
[11 empty] | 0 | 0 |  | 0 | 0
| Project Management - QA Subtotal |  |  | 781.2 | 781.2 | 781.2 | 781.2 | 781.2 | 781.2 | 0 | 4687.2 | 0 |  | 0.40687 | 65.1
2.2 | SCR Prep, Requirements & Design - QA | QA Project Manager |  | 126 | 126 | 126 | 126 | 126 | 126 |  | 756 | 0 |  | 0.065625 | 10.5
|  | QA Test Manager |  | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 |  | 1058.4 | 0 |  | 0.091875 | 14.7
|  | QA Functional Manager |  | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 |  | 1058.4 | 0 |  | 0.091875 | 14.7
|  | QA Technical Manager |  | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 |  | 1058.4 | 0 |  | 0.091875 | 14.7
|  | QA SDET |  | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 |  | 1058.4 | 0 |  | 0.091875 | 14.7
|  | QA Tester 1 |  | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 |  | 1058.4 | 0 |  | 0.091875 | 14.7
|  | QA Tester 2 |  | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 |  | 1058.4 | 0 |  | 0.091875 | 14.7
|  | QA Tester 3 |  | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 |  | 1058.4 | 0 |  | 0.091875 | 14.7
|  | QA Tester 4 |  | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 |  | 1058.4 | 0 |  | 0.091875 | 14.7
|  | AI Engineers |  | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 |  | 1058.4 | 0 |  | 0.091875 | 14.7
| SCR Prep, Requirements & Design - QA Subtotal |  |  | 1713.6 | 1713.6 | 1713.6 | 1713.6 | 1713.6 | 1713.6 | 0 | 10281.6 | 0 |  | 0.8925 | 142.8
2.3 | SCR Build/Test - QA | QA Project Manager |  | 126 | 126 | 126 | 126 | 126 | 126 |  | 756 | 0 |  | 0.065625 | 10.5
|  | QA Test Manager |  | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 |  | 1058.4 | 0 |  | 0.091875 | 14.7
|  | QA Functional Manager |  | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 |  | 1058.4 | 0 |  | 0.091875 | 14.7
|  | QA Technical Manager |  | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 |  | 1058.4 | 0 |  | 0.091875 | 14.7
|  | QA SDET |  | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 |  | 1058.4 | 0 |  | 0.091875 | 14.7
|  | QA Tester 1 |  | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 |  | 1058.4 | 0 |  | 0.091875 | 14.7
|  | QA Tester 2 |  | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 |  | 1058.4 | 0 |  | 0.091875 | 14.7
|  | QA Tester 3 |  | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 |  | 1058.4 | 0 |  | 0.091875 | 14.7
|  | QA Tester 4 |  | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 |  | 1058.4 | 0 |  | 0.091875 | 14.7
| SCR Build Subtotal |  |  | 1537.2 | 1537.2 | 1537.2 | 1537.2 | 1537.2 | 1537.2 | 0 | 9223.2 | 0 |  | 0.80062 | 128.1
2.4 | SCR Release Management/Training/OCM - QA | QA Project Manager |  | 126 | 126 | 126 | 126 | 126 | 126 |  | 756 | 0 |  | 0.065625 | 10.5
|  | QA Test Manager |  | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 |  | 1058.4 | 0 |  | 0.091875 | 14.7
|  | QA Functional Manager |  | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 |  | 1058.4 | 0 |  | 0.091875 | 14.7
|  | QA Technical Manager |  | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 |  | 1058.4 | 0 |  | 0.091875 | 14.7
|  | QA SDET |  | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 |  | 1058.4 | 0 |  | 0.091875 | 14.7
|  | Security Lead |  | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 |  | 1058.4 | 0 |  | 0.091875 | 14.7
[11 empty] | 0 | 0 |  | 0 | 0
| SCR Release Management/Training/OCM - QA Subtotal |  |  | 1008 | 1008 | 1008 | 1008 | 1008 | 1008 | 0 | 6048 | 0 |  | 0.525 | 84
2.5 | Marketing and Public Communications Support - QA | QA Project Manager |  | 126 | 126 | 126 | 126 | 126 | 126 |  | 756 | 0 |  | 0.065625 | 10.5
|  | QA Test Manager |  | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 |  | 1058.4 | 0 |  | 0.091875 | 14.7
|  | QA Functional Manager |  | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 |  | 1058.4 | 0 |  | 0.091875 | 14.7
|  | QA SDET |  | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 |  | 1058.4 | 0 |  | 0.091875 | 14.7
[11 empty] | 0 | 0 |  | 0 | 0
| Marketing and Public Communications Support - QA Subtotal |  |  | 655.2 | 655.2 | 655.2 | 655.2 | 655.2 | 655.2 | 0 | 3931.2 | 0 |  | 0.34125 | 54.6
2.6 | Enhancement and Innovation - QA | QA Project Manager |  | 126 | 126 | 126 | 126 | 126 | 126 |  | 756 | 0 |  | 0.065625 | 10.5
|  | QA Test Manager |  | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 |  | 1058.4 | 0 |  | 0.091875 | 14.7
|  | QA Technical Manager |  | 252 | 252 | 252 | 252 | 252 | 252 |  | 1512 | 0 |  | 0.13125 | 21
|  | QA SDET |  | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 |  | 1058.4 | 0 |  | 0.091875 | 14.7
|  | Security Lead |  | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 |  | 1058.4 | 0 |  | 0.091875 | 14.7
|  | AI Engineers |  | 756 | 756 | 756 | 756 | 756 | 756 |  | 4536 | 0 |  | 0.39375 | 63
[11 empty] | 0 | 0 |  | 0 | 0
| Enhancement and Innovation - QA Subtotal |  |  | 1663.2 | 1663.2 | 1663.2 | 1663.2 | 1663.2 | 1663.2 | 0 | 9979.2 | 0 |  | 0.86625 | 138.6
2.7 | Operations - QA | QA Project Manager |  | 126 | 126 | 126 | 126 | 126 | 126 |  | 756 | 0 |  | 0.065625 | 10.5
|  | QA Test Manager |  | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 |  | 1058.4 | 0 |  | 0.091875 | 14.7
|  | QA Technical Manager |  | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 |  | 1058.4 | 0 |  | 0.091875 | 14.7
|  | QA SDET |  | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 |  | 1058.4 | 0 |  | 0.091875 | 14.7
|  | Security Lead |  | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 |  | 1058.4 | 0 |  | 0.091875 | 14.7
|  | QA Tester 1 |  | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 |  | 1058.4 | 0 |  | 0.091875 | 14.7
|  | QA Tester 2 |  | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 |  | 1058.4 | 0 |  | 0.091875 | 14.7
[11 empty] | 0 | 0 |  | 0 | 0
[11 empty] | 0 | 0 |  | 0 | 0
| Operations - QA Subtotal |  |  | 1184.4 | 1184.4 | 1184.4 | 1184.4 | 1184.4 | 1184.4 | 0 | 7106.4 | 0 |  | 0.61687 | 98.7
2.8 | Security - QA | QA Technical Manager |  | 126 | 126 | 126 | 126 | 126 | 126 |  | 756 | 0 |  | 0.065625 | 10.5
|  | QA SDET |  | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 |  | 1058.4 | 0 |  | 0.091875 | 14.7
|  | Security Lead |  | 252 | 252 | 252 | 252 | 252 | 252 |  | 1512 | 0 |  | 0.13125 | 21
[11 empty] | 0 | 0 |  | 0 | 0
[11 empty] | 0 | 0 |  | 0 | 0
| Security - QA Subtotal |  |  | 554.4 | 554.4 | 554.4 | 554.4 | 554.4 | 554.4 | 0 | 3326.4 | 0 |  | 0.28875 | 46.2
0
| Quality Assurance Subtotal |  |  | 9097.2 | 9097.2 | 9097.2 | 9097.2 | 9097.2 | 9097.2 | 0 | 54583.2 | 0 |  | 3.8719 | 758.1
3 | Independent Test Planning, Executing, and Reporting
3.1 | Independent Test Plan/Management | QA Project Manager |  | 126 | 126 | 126 | 126 | 126 | 126 |  | 756 | 0 |  | 0.065625 | 10.5
|  | QA Test Manager |  | 504 | 504 | 504 | 504 | 504 | 504 |  | 3024 | 0 |  | 0.2625 | 42
|  | QA Technical Manager |  | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 |  | 1058.4 | 0 |  | 0.091875 | 14.7
|  | QA SDET |  | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 |  | 1058.4 | 0 |  | 0.091875 | 14.7
|  | QA Functional Manager |  | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 | 176.4 |  | 1058.4 | 0 |  | 0.091875 | 14.7
|  | QA Tester 1 |  | 230 | 230 | 230 | 230 | 230 | 230 |  | 1380 | 0 |  | 0.11979 | 19.1667
|  | QA Tester 2 |  | 230 | 230 | 230 | 230 | 230 | 230 |  | 1380 | 0 |  | 0.11979 | 19.1667
|  | QA Tester 3 |  | 230 | 230 | 230 | 230 | 230 | 230 |  | 1380 | 0 |  | 0.11979 | 19.1667
|  | QA Tester 4 |  | 230 | 230 | 230 | 230 | 230 | 230 |  | 1380 | 0 |  | 0.11979 | 19.1667
|  | QA Tester 5 |  | 230 | 230 | 230 | 230 | 230 | 230 |  | 1380 | 0 |  | 0.11979 | 19.1667
|  | QA Tester 6 |  | 230 | 230 | 230 | 230 | 230 | 230 |  | 1380 | 0 |  | 0.11979 | 19.1667
|  | AI Engineers |  | 230 | 230 | 230 | 230 | 230 | 230 |  | 1380 | 0 |  | 0.11979 | 19.1667
[11 empty] | 0 | 0 |  | 0 | 0
| Independent Test Plan/Management Subtotal |  |  | 2769.2 | 2769.2 | 2769.2 | 2769.2 | 2769.2 | 2769.2 | 0 | 16615.2 | 0 |  | 1.4423 | 230.7667
3.2 | Independent Test Development | QA Test Manager |  | 1031 | 1031 | 1031 | 1031 | 1031 | 1031 |  | 6186 | 0 |  | 0.53698 | 85.9167
|  | QA SDET |  | 1030 | 1030 | 1030 | 1030 | 1030 | 1030 |  | 6180 | 0 |  | 0.53646 | 85.8333
|  | QA Tester 1 |  | 230 | 230 | 230 | 230 | 230 | 230 |  | 1380 | 0 |  | 0.11979 | 19.1667
|  | QA Tester 2 |  | 230 | 230 | 230 | 230 | 230 | 230 |  | 1380 | 0 |  | 0.11979 | 19.1667
|  | QA Tester 3 |  | 230 | 230 | 230 | 230 | 230 | 230 |  | 1380 | 0 |  | 0.11979 | 19.1667
|  | QA Tester 4 |  | 230 | 230 | 230 | 230 | 230 | 230 |  | 1380 | 0 |  | 0.11979 | 19.1667
|  | QA Tester 5 |  | 550 | 550 | 550 | 550 | 550 | 550 |  | 3300 | 0 |  | 0.28646 | 45.8333
|  | QA Tester 6 |  | 550 | 550 | 550 | 550 | 550 | 550 |  | 3300 | 0 |  | 0.28646 | 45.8333
|  | QA Tester 7 |  | 550 | 550 | 550 | 550 | 550 | 550 |  | 3300 | 0 |  | 0.28646 | 45.8333
|  | AI Engineers |  | 1008 | 1008 | 1008 | 1008 | 1008 | 1008 |  | 6048 | 0 |  | 0.525 | 84
[11 empty] | 0 | 0 |  | 0 | 0
[11 empty] | 0 | 0 |  | 0 | 0
[11 empty] | 0 | 0 |  | 0 | 0
| Independent Test Development Subtotal |  |  | 5639 | 5639 | 5639 | 5639 | 5639 | 5639 | 0 | 33834 | 0 |  | 2.937 | 469.9167
3.3 | Independent Test Execution | QA Test Manager |  | 687 | 687 | 687 | 687 | 687 | 687 |  | 4122 | 0 |  | 0.35781 | 57.25
|  | QA SDET |  | 687 | 687 | 687 | 687 | 687 | 687 |  | 4122 | 0 |  | 0.35781 | 57.25
|  | QA Tester 1 |  | 900 | 900 | 900 | 900 | 900 | 900 |  | 5400 | 0 |  | 0.46875 | 75
|  | QA Tester 2 |  | 900 | 900 | 900 | 900 | 900 | 900 |  | 5400 | 0 |  | 0.46875 | 75
|  | QA Tester 3 |  | 900 | 900 | 900 | 900 | 900 | 900 |  | 5400 | 0 |  | 0.46875 | 75
|  | QA Tester 4 |  | 900 | 900 | 900 | 900 | 900 | 900 |  | 5400 | 0 |  | 0.46875 | 75
|  | QA Tester 5 |  | 600 | 600 | 600 | 600 | 600 | 600 |  | 3600 | 0 |  | 0.3125 | 50
|  | QA Tester 6 |  | 600 | 600 | 600 | 600 | 600 | 600 |  | 3600 | 0 |  | 0.3125 | 50
|  | QA Tester 7 |  | 600 | 600 | 600 | 600 | 600 | 600 |  | 3600 | 0 |  | 0.3125 | 50
|  | QA Tester 8 |  | 1008 | 1008 | 1008 | 1008 | 1008 | 1008 |  | 6048 | 0 |  | 0.525 | 84
|  | AI Engineers |  | 700 | 700 | 700 | 700 | 700 | 700 |  | 4200 | 0 |  | 0.36458 | 58.3333
|  | AI Engineers |  | 504 | 504 | 504 | 504 | 504 | 504 |  | 3024 | 0 |  | 0.2625 | 42
[11 empty] | 0 | 0 |  | 0 | 0
| Independent Test Execution Subtotal |  |  | 8986 | 8986 | 8986 | 8986 | 8986 | 8986 | 0 | 53916 | 0 |  | 4.6802 | 748.8333
| Independent Test Planning, Executing, and Reporting Subtotal |  |  | 17394.2 | 17394.2 | 17394.2 | 17394.2 | 17394.2 | 17394.2 | 0 | 104365.2 | 0 |  | 9.0595 | 1449.5167
| QA Staff Loading Total |  |  | 28507.4 | 28507.4 | 28507.4 | 28507.4 | 28507.4 | 28507.4 | 0 | 171044.4 | 0 |  | 13.9814 | 2375.6167
[9 empty] | Average Hourly Rate |  |  | 0
Assumptions
1 | The proposed delivery follows a blended onshore–offshore model to balance cost efficiency and delivery agility. Staff loading is based on forecasted workload for each base year as per the RFP scope.
2 | Approximately 75% of resources will operate from onsite or remote U.S. locations to ensure alignment with CalSAWS stakeholders, time zones, and program dependencies.
3 | Entire team will be operating in PST hours
4 | Quadrant will maintain a flexible bench to scale up or down by ±15% without cost or schedule impact.
5 | Functional Manager is aligned to one or more CalSAWS program areas (e.g., CalWORKs, Medi-Cal, CalFresh) to ensure subject matter expertise and continuity throughout releases
6 | Quadrant’s Technical Managers possess cloud-agnostic expertise, ensuring seamless integration, testing, and validation across multiple cloud environments (e.g., AWS, Azure, GCP, or hybrid models).
7 | The QA frameworks, automation pipelines, and performance validation tools proposed are platform-independent, supporting scalable and portable deployments across environments.
8
9
10

## 3. Base QA Staff
Schedule 3
Base QA Staff
California State Fiscal Year is July through June
# | Staff Position
Key Roles
1 | QA Project Manager
2 | QA Functional Manager
3 | QA Technical Manager
4 | QA Test Manager
5 | Other Roles
6 | SDET
7 | QA Analysts
8 | Test Lead
9 | AI Engineers
10 | Security Lead
11
12
13
14 | <Add as necessary>
15
Assumptions
1 | Resource mix reflects the proposed QA delivery structure (e.g., Test Manager, Test Lead, QA Engineer, Automation Engineer, etc.).
2 | Staffing ratios are determined based on industry-standard QA models for similar project size and complexity.
3 | Average FTE cost or hours are assumed per standard labor rates (adjust as per commercial bid).
4 | All QA personnel are fully allocated to the project; no shared resources are assumed.
5 | The team supports both manual and automated testing under the defined scope.
6 | Staff experience levels (junior/senior split) are assumed per role standard—no mid-term role changes.
7 | Any specialized tool or environment support is included in the QA staff complement.
8 | State fiscal year runs July through June, aligning resource planning with fiscal reporting.
9 | Headcount assumptions exclude client-side resources; only vendor QA staff are counted.
10